## Sheet1
| Parameter | Category | Sub cat | Impact | TRL | Description | Region Numeric | Region | Project | Year | Month | Cost
0 | Resource | Money | Limitation | 18 | 5 | Did not have sufficient resources and the contingency plan was inadequate | 0 | Americas | IT/Solution | 2010 | October | 700560
1 | Resource | Outsourcing | Delayed start | 17 | 4 | Contractor setup delayed by a week | 0 | Americas | Prod. Dev. | 2002 | May | 347922
2 | Resource | Outsourcing | Late or poor output | 13 | 5 | Contractor did not spend time on the project because his organization used him for other work | 0 | Americas | IT/Solution | 2002 | August | 919828
3 | Resource | Outsourcing | Late or poor output | 13 | 7 | Contractors failed to show up as committed | 1 | Asia | IT/Solution | 2014 | July | 521495
4 | Resource | Outsourcing | Late or poor output | 13 | 3 | Third-party vendor inadvertently introduced a bug during an upgrade | 0 | Americas | IT/Solution | 2010 | November | 322010
5 | Resource | Outsourcing | Late or poor output | 16 | 7 | Outsouced staff lacked the necessary skillset | 3 | Africa | IT/Solution | 2014 | June | 498896
6 | Resource | People | Late start | 15 | 5 | Planning delayed due to staff being still tied up in testing on prior project. | 0 | Americas | Prod. Dev. | 2015 | April | 592785
7 | Resource | People | Loss | 16 | 4 | Chef quit two days before the café was scheduled to open | 3 | Africa | IT/Solution | 2017 | October | 578928
8 | Resource | People | Motivation | 11 | 5 | Work at customer site had to be done by union workers; took 6 days to do what project team could do in 1. | 3 | Africa | IT/Solution | 2003 | July | 318846
9 | Resource | People | Queuing | 16 | 6 | Critical task assigned to a heavily booked expert | 0 | Americas | IT/Solution | 2010 | June | 1109120
10 | Resource | People | Queuing | 11 | 6 | Key packaging engineer was working on a high priority project when needed | 0 | Americas | IT/Solution | 2010 | September | 444774
11 | Resource | People | Queuing | 10 | 7 | No engineer is available or has enough knowledge | 0 | Americas | IT/Solution | 2011 | July | 632070
12 | Resource | People | Queuing | 10 | 3 | People were allocated to too many projects and bottlenecks developed | 0 | Americas | IT/Solution | 2010 | August | 228730
13 | Resource | People | Queuing | 17 | 7 | Key person not available when needed. | 0 | Americas | Prod. Dev. | 2002 | November | 1261689
14 | Resource | People | Queuing | 18 | 5 | US expertise needed for project in Asia. Team member flies to US, but expert is busy. | 3 | Africa | Prod. Dev. | 2002 | June | 1214586
15 | Resource | People | Temp loss | 12 | 4 | Engineer responsible to program the ISDN router called in sick | 0 | Americas | IT/Solution | 2009 | March | 347772
16 | Resource | People | Temp loss | 10 | 4 | Key welding staff are out with flu | 0 | Americas | Prod. Dev. | 2012 | January | 783340
17 | Resource | People | Temp loss | 15 | 3 | Manufacturing volumes spiked and diverted project contributors. | 3 | Africa | Prod. Dev. | 2004 | September | 707610
18 | Resource | People | Temp loss | 10 | 5 | Unannounced audit in mid-project caused delay to prepare and participate. | 0 | Americas | Prod. Dev. | 2010 | January | 453280
19 | Resource | People | Temp loss | 13 | 7 | Key team member grounded in Middle East during a regional war. | 3 | Africa | IT/Solution | 2014 | March | 985595
20 | Resource | People | Temp loss | 13 | 4 | Key contributor out ill at critical time. | 0 | Americas | IT/Solution | 2013 | August | 915798
21 | Schedule | Delay | Decision | 13 | 5 | Client missed the deadline for feedback by several days | 0 | Americas | IT/Solution | 2010 | October | 703092
22 | Schedule | Delay | Decision | 17 | 6 | Document reviews slipped due to conflicts and low priority. | 0 | Americas | Prod. Dev. | 2010 | May | 858432
23 | Schedule | Delay | Hardware | 14 | 4 | Flood shuts down data center. Delay to restore power and clean up. | 0 | Americas | IT/Solution | 2002 | August | 855778
24 | Schedule | Delay | Hardware | 14 | 5 | "Customer supplied" hardware does not work. Replacement required. | 3 | Africa | IT/Solution | 2001 | September | 639310
25 | Schedule | Delay | Hardware | 14 | 4 | System arrives late, then when it does arrive staff is not available to install it. | 0 | Americas | Prod. Dev. | 2002 | July | 958244
26 | Schedule | Delay | Hardware | 10 | 3 | System needed was down for scheduled maintenance not in plan. | 3 | Africa | IT/Solution | 2013 | August | 655540
27 | Schedule | Delay | Hardware | 18 | 5 | Installation of new systems required by project delayed. | 0 | Americas | Prod. Dev. | 2002 | November | 483354
28 | Schedule | Delay | Information | 14 | 4 | Access to required support tools was not established | 0 | Americas | IT/Solution | 2010 | April | 929726
29 | Schedule | Delay | Information | 13 | 3 | Documentation from the researcher lacks crucial information | 0 | Americas | Prod. Dev. | 2001 | June | 381641
30 | Schedule | Delay | Information | 15 | 6 | Customer not showing up for key meeting | 0 | Americas | Prod. Dev. | 2002 | June | 483390
31 | Schedule | Delay | Parts | 13 | 7 | No coordinated shipment of system components; last one delays installation. | 0 | Americas | IT/Solution | 2010 | May | 706953
32 | Schedule | Delay | Parts | 12 | 4 | Lack of supplies and adequate time for printing | 0 | Americas | IT/Solution | 2011 | July | 450660
33 | Schedule | Delay | Parts | 10 | 7 | Out of stock on key parts needed for PC boards. | 0 | Americas | Prod. Dev. | 2010 | February | 311690
34 | Schedule | Delay | Parts | 16 | 3 | Parts delivery delay | 0 | Americas | Prod. Dev. | 2010 | September | 572976
35 | Schedule | Delay | Parts | 13 | 5 | A needed component was not very stable and only available from only one supplier. | 3 | Africa | Prod. Dev. | 2010 | September | 329706
36 | Schedule | Delay | Parts | 13 | 7 | Delivery problems on international shipment--paperwork, customs. | 0 | Americas | IT/Solution | 2002 | August | 510289
37 | Schedule | Delay | Parts | 12 | 3 | Shipping documents not filled in correctly | 3 | Africa | Prod. Dev. | 2012 | April | 321996
38 | Schedule | Dependency | Project | 10 | 3 | Dependency on other project not discovered until project end. | 0 | Americas | IT/Solution | 2010 | February | 260780
39 | Schedule | Dependency | Project | 11 | 5 | Deliverable from one project claimed to be done, but receiving project cannot use it. | 0 | Americas | Prod. Dev. | 2002 | September | 337986
40 | Schedule | Dependency | Project | 17 | 7 | Other group could not deliver on time, soI had to do work myself | 0 | Americas | IT/Solution | 2004 | July | 910095
41 | Schedule | Estimates | Judgment | 15 | 6 | Untried beta software with unknown computer needs required for training | 3 | Africa | IT/Solution | 2001 | October | 964230
42 | Schedule | Estimates | Judgment | 12 | 6 | Underestimated weight of stumps to be removed | 0 | Americas | IT/Solution | 2010 | March | 478692
43 | Scope | Change | Creep | 11 | 7 | Late additional request on a small project delayed completion | 0 | Americas | IT/Solution | 2002 | December | 742346
44 | Scope | Change | Creep | 18 | 3 | Change to the objective when the project was almost finished | 0 | Americas | IT/Solution | 2010 | July | 798372
45 | Scope | Change | Creep | 15 | 6 | Additional enhancements requested at the last minute | 3 | Africa | IT/Solution | 2018 | April | 595065
46 | Scope | Change | Creep | 18 | 5 | Scope continuously changed by client | 0 | Americas | Prod. Dev. | 2010 | May | 774630
47 | Scope | Change | Creep | 14 | 4 | Late changes resulted in expedite charges and delay | 0 | Americas | Prod. Dev. | 2001 | December | 765576
48 | Scope | Change | Creep | 17 | 5 | System move delayed by last minute system changes that delayed and made backups take too long. | 3 | Africa | IT/Solution | 2009 | March | 692257
49 | Scope | Change | Creep | 13 | 6 | Scope changed after writers had completed initial draft | 0 | Americas | Prod. Dev. | 2010 | August | 646412
50 | Scope | Change | Dependency | 13 | 4 | Legal required late changes to a large print run of materials | 3 | Africa | Prod. Dev. | 2003 | September | 926003
51 | Scope | Change | Dependency | 14 | 3 | Policy changes made late in a project requiring additional unplanned work. | 0 | Americas | Prod. Dev. | 2002 | March | 728854
52 | Scope | Change | Dependency | 13 | 3 | Inadequate facilities; had to find alternatives | 0 | Americas | Prod. Dev. | 2002 | October | 900822
53 | Scope | Change | Gap | 12 | 5 | Poor definition of training requirements; had to do much more. | 0 | Americas | IT/Solution | 2010 | January | 480552
54 | Scope | Change | Gap | 13 | 5 | After project "complete" rework required for customer approval | 0 | Americas | IT/Solution | 2002 | February | 721266
55 | Scope | Change | Gap | 11 | 6 | Design team failed to collect the details on what was to be displayed to users | 0 | Americas | IT/Solution | 2010 | January | 362065
56 | Scope | Change | Gap | 13 | 6 | PM did not take the time to determine what the move entailed | 0 | Americas | IT/Solution | 2002 | August | 759174
57 | Scope | Change | Gap | 10 | 6 | Lack of a solid plan, or any formal scoping | 0 | Americas | Prod. Dev. | 2012 | May | 528640
58 | Scope | Defect | Hardware | 12 | 7 | Final burn-in test interrupted by faulty oven. Replacement and retest took extra time. | 3 | Africa | IT/Solution | 2005 | June | 343236
59 | Scope | Defect | Hardware | 12 | 7 | Old equipment failed at the last minute | 3 | Africa | IT/Solution | 2013 | January | 340176
60 | Scope | Defect | Hardware | 11 | 6 | A batch of servers came in with the wrong configurations; had to be fixed | 0 | Americas | IT/Solution | 2010 | December | 252076
61 | Scope | Defect | Hardware | 11 | 6 | Unanticipated fumes form epoxy concrete paint forced a delay in work | 0 | Americas | IT/Solution | 2007 | April | 234102
62 | Scope | Defect | Hardware | 17 | 4 | Miscalculation on a critical task | 0 | Americas | Prod. Dev. | 2015 | July | 468027
63 | Scope | Defect | Hardware | 13 | 3 | Vibration in transit caused the loosing of the nuts and bolts of antennas, which eventually caused the collapse of the antennas | 0 | Americas | Prod. Dev. | 2001 | July | 496938
64 | Scope | Defect | Hardware | 14 | 6 | Cable required had been left off the implementation parts list | 0 | Americas | IT/Solution | 2003 | June | 854266
65 | Scope | Defect | Software | 11 | 5 | Integration testing is incomplete, causing system failures. | 0 | Americas | IT/Solution | 2004 | September | 532818
66 | Scope | Defect | Software | 18 | 5 | No problems in test, but production problems required overtime to fix | 3 | Africa | IT/Solution | 2019 | October | 793818
67 | Scope | Defect | Software | 15 | 7 | Access problems surfaced in production | 3 | Africa | IT/Solution | 2018 | July | 658440
68 | Scope | Defect | Software | 16 | 6 | Engineering overlooked the functional design and did not implement correctly | 0 | Americas | IT/Solution | 2010 | April | 551120
69 | Scope | Defect | Software | 14 | 5 | Bugs were reported by UAT that should have been caught by QA | 3 | Africa | IT/Solution | 2017 | May | 514136
70 | Scope | Defect | Software | 11 | 6 | Performance issues surfaced following migration | 3 | Africa | IT/Solution | 2004 | March | 788689
71 | Schedule | Delay | Hardware | 18 | 6 | Servers got stuck in customs | 0 | Americas | IT/Solution | 2002 | February | 1245294
72 | Scope | Change | Gap | 11 | 5 | New technology, required changes to SW to work | 0 | Americas | Prod. Dev. | 2010 | August | 329758
73 | Resource | Money | Limitation | 10 | 5 | Failed to allocate enough resources and missed important parts of scope | 0 | Americas | IT/Solution | 2002 | May | 708760
74 | Scope | Change | Creep | 11 | 7 | Mid-project feature revisions. Major impact on effort and schedule; product failed (too late to market). | 3 | Africa | Prod. Dev. | 2017 | December | 461835
75 | Scope | Change | Gap | 13 | 7 | Development plans failed to include all of the 23 required applications | 0 | Americas | IT/Solution | 2019 | August | 383578
76 | Resource | Money | Limitation | 15 | 6 | Project budget was dramatically cut | 0 | Americas | IT/Solution | 2009 | May | 832665
77 | Schedule | Delay | Information | 17 | 6 | Merging of multiple standards is needed to support reorganization. Lack of a new, common definition delayed the project to convert data. | 0 | Americas | IT/Solution | 2002 | October | 1216639
78 | Resource | Outsourcing | Late or poor output | 10 | 7 | The other company was unable to stick to needed deadlines | 3 | Africa | Prod. Dev. | 2007 | July | 767350
79 | Resource | Money | Limitation | 12 | 6 | Severe funding cutbacks (66% of project team) | 0 | Americas | IT/Solution | 2002 | September | 425964
80 | Resource | Money | Limitation | 11 | 4 | Project Budget was restricted to the bare minimum estimated | 3 | Africa | Prod. Dev. | 2018 | February | 393745
81 | Scope | Change | Gap | 17 | 5 | Project based on standards still in draft form. Several options are possible, but project is only staffed to pursue one. | 0 | Americas | Prod. Dev. | 2009 | March | 1232313
82 | Resource | People | Loss | 14 | 7 | Due to a re-organization the team lost essential resources | 0 | Americas | Prod. Dev. | 2010 | July | 929544
83 | Resource | People | Late start | 14 | 6 | Staffing was late and inexperienced | 0 | Americas | IT/Solution | 2014 | March | 320334
84 | Resource | People | Loss | 12 | 5 | One of the Senior System Analysts who was fully trained on the application resigned | 0 | Americas | IT/Solution | 2002 | March | 745596
85 | Schedule | Delay | Parts | 10 | 5 | Project experienced shortages in steel rebar and copper electrical wire | 0 | Americas | IT/Solution | 2002 | February | 544260
86 | Schedule | Estimates | Learning | 17 | 6 | Developers on the project were not experienced enough to implement the solution | 0 | Americas | IT/Solution | 2002 | May | 1099798
87 | Scope | Change | Creep | 13 | 3 | Scope not defined well; huge software delays | 0 | Americas | IT/Solution | 2010 | November | 792727
88 | Scope | Change | Creep | 10 | 5 | New requirements were piled on as the project ran | 0 | Americas | IT/Solution | 2010 | December | 389470
89 | Scope | Defect | Hardware | 10 | 5 | Components failure means finding another type of component and redoing tests | 0 | Americas | Prod. Dev. | 2012 | December | 481750
90 | Resource | Money | Limitation | 15 | 3 | Sponsor fails to provide money | 3 | Africa | Prod. Dev. | 2019 | June | 448755
91 | Scope | Change | Gap | 13 | 3 | Management never talked to the test department when creating proposals | 3 | Africa | IT/Solution | 2005 | July | 875537
92 | Schedule | Estimates | Learning | 18 | 5 | Key staff member lacked knowledge, experience and ability | 3 | Africa | IT/Solution | 2011 | May | 1188504
93 | Scope | Change | Gap | 17 | 4 | Lack of understanding by the manager of the system forced the project to replan | 0 | Americas | Prod. Dev. | 2010 | November | 541909
94 | Resource | People | Loss | 15 | 4 | The project manager was assigned to another big project part way through the project | 0 | Americas | IT/Solution | 2010 | August | 404655
95 | Resource | People | Queuing | 15 | 3 | Conflicting priorities. on-going maintenance, and loss of a person led to delay | 3 | Africa | Prod. Dev. | 2013 | April | 1194060
96 | Resource | People | Queuing | 17 | 3 | Lone subject matter expert unavailable when needed during the initial stages | 0 | Americas | Prod. Dev. | 2010 | August | 945506
97 | Schedule | Delay | Hardware | 14 | 4 | New technology not available on time. | 3 | Africa | IT/Solution | 2013 | May | 405902
98 | Schedule | Dependency | Infrastructure | 17 | 7 | Insufficient capacity in the cabling system for needed fiber connection | 3 | Africa | IT/Solution | 2019 | July | 583491
99 | Schedule | Dependency | Legal | 17 | 6 | Iidviduals who must to approve work are unavailable | 0 | Americas | IT/Solution | 2010 | May | 970870
100 | Scope | Change | Creep | 17 | 3 | Project priorities and criteria are unclear through much of the project, causing lots of unneeded work. | 0 | Americas | IT/Solution | 2002 | February | 1218747
101 | Scope | Change | Gap | 11 | 5 | Poor prework led to assumption that project would be simpler than it was | 3 | Africa | IT/Solution | 2016 | February | 668492
102 | Resource | Money | Limitation | 11 | 6 | Project had limited funding and limited staffing | 0 | Americas | IT/Solution | 2012 | April | 717541
103 | Resource | Outsourcing | Late or poor output | 16 | 7 | Work being done more than 3000 miles away was difficult to check | 0 | Americas | Prod. Dev. | 2002 | November | 1211408
104 | Resource | People | Loss | 16 | 3 | Due to contractor layoffs, a Subject Matter Expert had to be replaced | 0 | Americas | IT/Solution | 2014 | February | 355520
105 | Resource | People | Queuing | 18 | 4 | Expert at third party required for work not available when needed | 0 | Americas | IT/Solution | 2002 | June | 1011420
106 | Schedule | Delay | Decision | 14 | 4 | Limited access to management. Decisions and escalations too slow. | 0 | Americas | Prod. Dev. | 2002 | November | 346332
107 | Schedule | Delay | Decision | 15 | 4 | Did not have the signature of the director | 0 | Americas | IT/Solution | 2002 | June | 867165
108 | Schedule | Delay | Hardware | 16 | 7 | Equipment used for data analysis failed and was down for 2 weeks | 3 | Africa | Prod. Dev. | 2007 | December | 758528
109 | Schedule | Dependency | Legal | 16 | 5 | Shipping requirements changed. Some shipments bounce, others get stuck in customs. | 3 | Africa | Prod. Dev. | 2017 | March | 1193280
110 | Scope | Change | Creep | 18 | 5 | Customer reorganization led to new staffing and changed requirements | 0 | Americas | IT/Solution | 2010 | August | 475470
111 | Scope | Change | Creep | 10 | 3 | Scope creep and resource inadequacy | 0 | Americas | IT/Solution | 2015 | January | 481130
112 | Scope | Change | Dependency | 15 | 4 | Operating system release expected slips; project forced to use prior version missing some needed functionality. | 0 | Americas | Prod. Dev. | 2014 | March | 1124475
113 | Scope | Change | Gap | 13 | 7 | Proprietary data needed, but owners unwilling to provide. After delay, partial information shared. | 0 | Americas | Prod. Dev. | 2006 | September | 358709
114 | Resource | People | Queuing | 14 | 4 | Key packaging engineer was working on a high priority project when needed | 0 | Americas | IT/Solution | 2010 | November | 396410
115 | Resource | People | Temp loss | 10 | 6 | Key team member grounded in Middle East during a regional war. | 0 | Americas | IT/Solution | 2004 | March | 469050
116 | Schedule | Delay | Information | 13 | 7 | Customer not showing up for key meeting | 3 | Africa | Prod. Dev. | 2010 | July | 497328
117 | Scope | Change | Dependency | 18 | 4 | Inadequate facilities; had to find alternatives | 0 | Americas | Prod. Dev. | 2010 | July | 1438794
118 | Resource | Money | Limitation | 16 | 4 | Project did not have the buy-in for staffing from other departmens | 0 | Americas | IT/Solution | 2002 | June | 384800
119 | Resource | Money | Limitation | 11 | 6 | Project had limited funding and limited staffing | 3 | Africa | IT/Solution | 2019 | October | 528572
120 | Resource | Money | Limitation | 11 | 5 | lack of staff availability due to company down-sizing | 0 | Americas | IT/Solution | 2017 | December | 450725
121 | Resource | Money | Limitation | 17 | 4 | Lack of money for sufficient equipment | 0 | Americas | Prod. Dev. | 2006 | June | 357748
122 | Resource | Outsourcing | Delayed start | 16 | 3 | Slow start of work outsourced. | 0 | Americas | IT/Solution | 2013 | June | 709056
123 | Resource | Outsourcing | Delayed start | 15 | 3 | Pricing negotiation stalls project work until resolved. | 0 | Americas | IT/Solution | 2010 | October | 590010
124 | Resource | Outsourcing | Delayed start | 12 | 3 | New supplier, extensive start up and coordination issues. | 3 | Africa | Prod. Dev. | 2014 | September | 360852
125 | Resource | Outsourcing | Late or poor output | 17 | 4 | Subcontractor delay causes compression of later work. | 0 | Americas | IT/Solution | 2002 | March | 651423
126 | Resource | Outsourcing | Late or poor output | 11 | 7 | Supplier failure, inputs late and inadequate | 0 | Americas | IT/Solution | 2002 | August | 476069
127 | Resource | Outsourcing | Late or poor output | 17 | 7 | An external part-time consultant wasn't always available when needed | 0 | Americas | IT/Solution | 2008 | June | 870876
128 | Resource | Outsourcing | Late or poor output | 15 | 3 | Outsource partner replaced several key people on team | 3 | Africa | IT/Solution | 2002 | January | 746490
129 | Resource | Outsourcing | Late or poor output | 15 | 3 | Local subcontractors lacked needed technical skills | 0 | Americas | IT/Solution | 2010 | July | 1094355
130 | Resource | Outsourcing | Late or poor output | 18 | 3 | Problems with vendor capacity and performance | 3 | Africa | IT/Solution | 2009 | September | 1340316
131 | Resource | Outsourcing | Late or poor output | 18 | 6 | Outsourcing firm had an incompetent design team | 0 | Americas | IT/Solution | 2003 | May | 1223460
132 | Resource | Outsourcing | Late or poor output | 15 | 7 | Contractors are not close to the business and often overlook requirements | 0 | Americas | IT/Solution | 2002 | April | 797925
133 | Resource | Outsourcing | Late or poor output | 18 | 7 | Slow renewal of contract for consultant; interruption in work | 0 | Americas | Prod. Dev. | 2002 | June | 1300662
134 | Resource | Outsourcing | Late or poor output | 16 | 4 | Task supposed to be done by an outside company was completed late | 0 | Americas | Prod. Dev. | 2002 | February | 708400
135 | Resource | Outsourcing | Late or poor output | 13 | 4 | Work being done more than 3000 miles away was difficult to check | 0 | Americas | Prod. Dev. | 2002 | December | 928395
136 | Resource | Outsourcing | Late or poor output | 16 | 6 | High turnover leads to delays and crisis management. | 0 | Americas | Prod. Dev. | 2010 | March | 402608
137 | Resource | Outsourcing | Late or poor output | 15 | 3 | Contract had no penalties for missing deadlines; 3 weeks taken on 1 week task. | 0 | Americas | IT/Solution | 2004 | March | 434535
138 | Resource | Outsourcing | Late or poor output | 11 | 7 | Outsourced tasks slipped, but not known until too late. | 0 | Americas | IT/Solution | 2002 | November | 355058
139 | Resource | Outsourcing | Late or poor output | 18 | 3 | Work from team in Pakistan failed miserably | 3 | Africa | IT/Solution | 2019 | October | 997362
140 | Resource | Outsourcing | Late or poor output | 10 | 6 | One factory went on labor strike for 2 weeks –Delayed production of 20 pallets | 0 | Americas | Prod. Dev. | 2017 | February | 611870
141 | Resource | Outsourcing | Late or poor output | 16 | 3 | Labor union of subcontractor went on stike | 0 | Americas | Prod. Dev. | 2002 | April | 502848
142 | Resource | People | Late start | 11 | 7 | Insufficient planning and commitment by the committee involved | 0 | Americas | IT/Solution | 2010 | August | 432003
143 | Resource | People | Late start | 10 | 7 | Developer from the database group was not available because of another project | 3 | Africa | IT/Solution | 2015 | January | 770890
144 | Resource | People | Late start | 18 | 6 | Project start delayed; team busy on other work. | 3 | Africa | Prod. Dev. | 2014 | July | 1342476
145 | Resource | People | Late start | 17 | 3 | Project start delayed; staffing and buy-in late, required overtime and extra project management. | 0 | Americas | Prod. Dev. | 2010 | November | 1044871
146 | Resource | People | Loss | 17 | 5 | Toward the end of the development life cycle the original QA lead and trainer quit the firm | 0 | Americas | IT/Solution | 2008 | February | 788766
147 | Resource | People | Loss | 11 | 7 | A key team member was replaced mid-project | 0 | Americas | IT/Solution | 2002 | October | 284262
148 | Resource | People | Loss | 11 | 6 | Due to contractor layoffs, a Subject Matter Expert had to be replaced | 0 | Americas | IT/Solution | 2002 | April | 458876
149 | Resource | People | Loss | 13 | 5 | Expert developer left the company | 3 | Africa | IT/Solution | 2003 | December | 322088
150 | Resource | People | Loss | 13 | 4 | Chief architect quit, and was the only person with critical skills | 0 | Americas | IT/Solution | 2002 | April | 274833
151 | Resource | People | Loss | 16 | 7 | Contributor is leaving due to contract expiration | 0 | Americas | IT/Solution | 2002 | March | 797296
152 | Resource | People | Loss | 16 | 7 | At a critical stage of the project the Medical Director left the company | 0 | Americas | Prod. Dev. | 2002 | September | 649648
153 | Resource | People | Loss | 18 | 7 | Expert developer left the company | 0 | Americas | Prod. Dev. | 2003 | April | 556272
154 | Resource | People | Loss | 14 | 5 | Key people resigned, leaving too few to complete project and training on time | 3 | Africa | IT/Solution | 2018 | February | 1043210
155 | Resource | People | Loss | 12 | 3 | Late in project, the budget and staff are cut leading to delays, forced overtime, and demotivation. | 0 | Americas | Prod. Dev. | 2002 | November | 839652
156 | Resource | People | Motivation | 12 | 4 | Project involved several departments, several of which were uncooperative | 0 | Americas | IT/Solution | 2010 | November | 434184
157 | Resource | People | Motivation | 14 | 5 | On a very long project, enthusiasm and motivation falls; tasks stretch out. | 0 | Americas | Prod. Dev. | 2002 | August | 459368
158 | Resource | People | Queuing | 12 | 6 | Limits on headcount create work backlog | 3 | Africa | IT/Solution | 2017 | March | 456348
159 | Resource | People | Queuing | 14 | 3 | Expert at third party required for work not available when needed | 3 | Africa | IT/Solution | 2017 | September | 760774
160 | Resource | People | Queuing | 11 | 7 | Resources thin and tasks queued in backlogs. | 3 | Africa | IT/Solution | 2003 | May | 685828
161 | Resource | People | Queuing | 16 | 5 | Key people are shared by several projects; lots of queuing. | 0 | Americas | IT/Solution | 2010 | September | 1156464
162 | Resource | People | Queuing | 17 | 4 | A single person was responsible for key reports many wait in queue | 0 | Americas | IT/Solution | 2010 | July | 706265
163 | Resource | People | Queuing | 12 | 7 | The test capabilities constitute a bottleneck late in release cycles. | 0 | Americas | Prod. Dev. | 2010 | June | 636072
164 | Resource | People | Queuing | 13 | 5 | Conflict for resources with a higher priority project | 0 | Americas | Prod. Dev. | 2002 | January | 714259
165 | Resource | People | Queuing | 13 | 7 | Business Operations Analyst was busy with another big project | 0 | Americas | Prod. Dev. | 2002 | March | 689312
166 | Resource | People | Queuing | 12 | 4 | Failure by project manager to communicate the need for architect’s time | 0 | Americas | Prod. Dev. | 2010 | August | 611604
167 | Resource | People | Temp loss | 12 | 3 | Key work in flu season delayed; most of staff out ill. | 0 | Americas | IT/Solution | 2007 | May | 709308
168 | Resource | People | Temp loss | 18 | 3 | Production partner had a personal issue which brought production to a halt | 3 | Africa | IT/Solution | 2008 | March | 1181880
169 | Resource | People | Temp loss | 13 | 4 | Project team frequently diverted to support work. | 0 | Americas | Prod. Dev. | 2010 | March | 620321
170 | Resource | People | Temp loss | 12 | 3 | Staff lost to customer hot site | 0 | Americas | Prod. Dev. | 2009 | April | 802380
171 | Resource | People | Temp loss | 13 | 4 | Key resource was pulled off the project twice to fix bugs in a previous product | 0 | Americas | Prod. Dev. | 2010 | October | 641901
172 | Resource | People | Temp loss | 13 | 3 | Key Designer was out of the office for 2 weeks | 0 | Americas | Prod. Dev. | 2006 | February | 867633
173 | Resource | People | Temp loss | 14 | 6 | Software engineer was lost to a higher priority project | 3 | Africa | Prod. Dev. | 2017 | November | 1026256
174 | Resource | People | Temp loss | 15 | 3 | Staff illness results in use of temporary staff | 0 | Americas | Prod. Dev. | 2002 | September | 942555
175 | Resource | People | Temp loss | 17 | 5 | Key contributor "rounded up" after 9/11 (and later released) | 3 | Africa | Prod. Dev. | 2016 | January | 1225717
176 | Resource | People | Temp loss | 18 | 3 | Reorganization during product ramp creates chaos and ownership problems. | 0 | Americas | Prod. Dev. | 2002 | August | 1083690
177 | Resource | People | Temp loss | 15 | 4 | Lead engineer stuck in Japan for 2 weeks longer than expected | 0 | Americas | Prod. Dev. | 2010 | May | 327540
178 | Resource | People | Temp loss | 13 | 6 | Staff lost to customer Hot Site | 0 | Americas | Prod. Dev. | 2002 | December | 945971
179 | Schedule | Delay | Decision | 18 | 7 | Poor access to decision makers | 0 | Americas | IT/Solution | 2002 | July | 406494
180 | Schedule | Delay | Decision | 14 | 3 | Problems getting timely management decisions. | 3 | Africa | Prod. Dev. | 2013 | February | 602126
181 | Schedule | Delay | Decision | 10 | 4 | Limited access to management. Decisions and escalations too slow. | 0 | Americas | Prod. Dev. | 2014 | November | 513600
182 | Schedule | Delay | Decision | 12 | 6 | System needed to approve requests went down; ordering required parts delayed. | 0 | Americas | Prod. Dev. | 2002 | October | 536352
183 | Schedule | Delay | Decision | 18 | 7 | Requisition required the authorization of CEO who was out of town in Finland | 0 | Americas | Prod. Dev. | 2004 | November | 482094
184 | Schedule | Delay | Decision | 11 | 3 | Code review delayed due to merger | 0 | Americas | Prod. Dev. | 2010 | August | 491524
185 | Schedule | Delay | Decision | 11 | 5 | Required design review delayed. | 0 | Americas | Prod. Dev. | 2004 | July | 331881
186 | Schedule | Delay | Decision | 14 | 7 | Project relocated manufacturing to a contract manufacturer. Required management decisions are frequent and too slow. | 0 | Americas | Prod. Dev. | 2007 | January | 1096676
187 | Schedule | Delay | Decision | 17 | 7 | Decisions are too slow due to distance and lack of face-to-face communication | 0 | Americas | Prod. Dev. | 2002 | December | 943602
188 | Schedule | Delay | Decision | 17 | 4 | Did not have the signature of the director | 0 | Americas | IT/Solution | 2010 | September | 1122782
189 | Schedule | Delay | Decision | 12 | 4 | Scope definition and stakeholder agreement delayed. | 3 | Africa | Prod. Dev. | 2010 | November | 720648
190 | Schedule | Delay | Hardware | 17 | 5 | Disaster recovery tests delayed at project end; hardware needed tied up with an actual customer problem. | 3 | Africa | IT/Solution | 2014 | March | 720511
191 | Schedule | Delay | Hardware | 15 | 3 | Equipment needed for project came from a pool of hardware partly in another country. Critical hardware delayed by customs. | 0 | Americas | IT/Solution | 2010 | December | 684900
192 | Schedule | Delay | Hardware | 12 | 5 | Project work that customer is responsible for slips, causing project slip. | 0 | Americas | IT/Solution | 2002 | March | 592296
193 | Schedule | Delay | Hardware | 11 | 7 | Team relocated with insufficient time to schedule high speed network lines. Rushed, but did not work; team was down until fixed. | 3 | Africa | IT/Solution | 2008 | July | 846395
194 | Schedule | Delay | Hardware | 13 | 6 | Required server was misplaced in shipping | 0 | Americas | IT/Solution | 2003 | October | 687375
195 | Schedule | Delay | Hardware | 15 | 4 | Test systems shared by 6 projects; queuing and delays common. | 0 | Americas | Prod. Dev. | 2002 | March | 763365
196 | Schedule | Delay | Hardware | 18 | 5 | New equipment critical to the success of the product quality was installed late | 3 | Africa | Prod. Dev. | 2004 | April | 1137978
197 | Schedule | Delay | Hardware | 11 | 5 | Equipment used for data analysis failed and was down for 2 weeks | 3 | Africa | Prod. Dev. | 2018 | July | 245245
198 | Schedule | Delay | Information | 11 | 4 | Tests delayed at project end; delayed access to databases | 0 | Americas | IT/Solution | 2002 | October | 494791
199 | Schedule | Delay | Information | 14 | 6 | Delay to reconfigure printer outside firewall | 0 | Americas | IT/Solution | 2010 | October | 451864
200 | Schedule | Delay | Information | 18 | 5 | Orders sometimes get lost in manual routing | 0 | Americas | IT/Solution | 2003 | April | 998622
201 | Schedule | Delay | Information | 13 | 4 | Data submitted by the participating vendors contains errors | 3 | Africa | IT/Solution | 2011 | May | 487344
202 | Schedule | Delay | Information | 18 | 7 | Document transfer to sites takes more time and effort than expected. | 3 | Africa | Prod. Dev. | 2013 | April | 1319580
203 | Schedule | Delay | Information | 16 | 7 | "Overnight" shipping takes extra time in big co. mailrooms | 3 | Africa | Prod. Dev. | 2007 | May | 962512
204 | Schedule | Delay | Information | 18 | 3 | Errors in input data had to be fixed and reports re-generated | 0 | Americas | Prod. Dev. | 2002 | March | 1036692
205 | Schedule | Delay | Information | 14 | 6 | There was a communication lag | 0 | Americas | Prod. Dev. | 2002 | December | 1031590
206 | Schedule | Delay | Information | 18 | 3 | Parts of development team have a 12 hour time difference. Bugs take 2-3 days longer to fix, on average. | 0 | Americas | IT/Solution | 2010 | February | 788202
207 | Schedule | Delay | Parts | 13 | 6 | Defective parts received. Reorder doubled the time required. | 0 | Americas | IT/Solution | 2010 | June | 601809
208 | Schedule | Delay | Parts | 14 | 6 | Equipment / parts not delivered on time or in full by the outside supplier | 0 | Americas | IT/Solution | 2010 | May | 458752
209 | Schedule | Delay | Parts | 18 | 3 | Inventory from vendors could not be secured by the desired transport date | 0 | Americas | IT/Solution | 2010 | August | 897030
210 | Schedule | Delay | Parts | 16 | 7 | Incorrect part shipped. Delay for reshipment. | 0 | Americas | Prod. Dev. | 2002 | May | 448224
211 | Schedule | Delay | Parts | 13 | 4 | Needed parts arrive too late. | 0 | Americas | Prod. Dev. | 2007 | January | 706069
212 | Schedule | Delay | Parts | 11 | 5 | Parts availability and pricing volatile | 3 | Africa | Prod. Dev. | 2011 | February | 567655
213 | Schedule | Delay | Parts | 12 | 7 | Boards would fail incoming quality check due to the specs given to fabrication house not being tight enough | 0 | Americas | Prod. Dev. | 2010 | July | 754596
214 | Schedule | Delay | Parts | 12 | 5 | Production problem with key component | 0 | Americas | Prod. Dev. | 2003 | April | 611328
215 | Schedule | Delay | Parts | 16 | 6 | Key contractors have the flu | 0 | Americas | Prod. Dev. | 2010 | April | 888832
216 | Schedule | Delay | Parts | 10 | 7 | Project manager redesigned the prototype and made inventory invalid | 0 | Americas | Prod. Dev. | 2002 | September | 202730
217 | Schedule | Delay | Parts | 13 | 6 | International shipment of tape was on time, but the tape was bad. | 0 | Americas | IT/Solution | 2006 | May | 623064
218 | Schedule | Delay | Parts | 18 | 4 | Delivery problems on international shipment--paperwork, customs. | 3 | Africa | Prod. Dev. | 2018 | April | 1144782
219 | Schedule | Delay | Parts | 15 | 4 | Component needed in China for prototype not available; had to be shipped from US | 0 | Americas | Prod. Dev. | 2001 | September | 1004100
220 | Schedule | Delay | Parts | 11 | 4 | Lack of spare parts and expertise | 0 | Americas | Prod. Dev. | 2010 | March | 745987
221 | Schedule | Delay | Parts | 12 | 6 | New pumps sent that lacked instructions and spare parts | 0 | Americas | Prod. Dev. | 2002 | December | 396960
222 | Schedule | Dependency | Infrastructure | 18 | 6 | Move out of old location required, but new space is not ready. Interim move to temporary space takes extra time and money. | 0 | Americas | IT/Solution | 2004 | July | 523476
223 | Schedule | Dependency | Infrastructure | 16 | 6 | Operating system selected (LINUX) has inadequate support for timely solution of conversion and delivery problems. | 0 | Americas | IT/Solution | 2011 | January | 820944
224 | Schedule | Dependency | Infrastructure | 16 | 4 | Late facility availability | 3 | Africa | Prod. Dev. | 2009 | June | 757888
225 | Schedule | Dependency | Infrastructure | 14 | 6 | Lack of access to professional translation services | 0 | Americas | Prod. Dev. | 2004 | October | 914900
226 | Schedule | Dependency | Infrastructure | 13 | 3 | Systems needed for project work failed late in the project, and when work was completed installation delayed further to next possible installation window. | 0 | Americas | IT/Solution | 2002 | October | 823940
227 | Schedule | Dependency | Infrastructure | 16 | 3 | Telecom line delays | 3 | Africa | IT/Solution | 2005 | July | 417312
228 | Schedule | Dependency | Legal | 16 | 3 | New requirements that mandated all products that have yet to ship to market to be re-tested | 0 | Americas | IT/Solution | 2011 | June | 328832
229 | Schedule | Dependency | Legal | 15 | 3 | Shipping requirements changed. Some shipments bounce, others get stuck in customs. | 0 | Americas | Prod. Dev. | 2010 | October | 536460
230 | Schedule | Dependency | Project | 16 | 6 | Approvals held up at project completion to wait for delayed support plan. | 0 | Americas | IT/Solution | 2003 | November | 750784
231 | Schedule | Dependency | Project | 11 | 5 | One team in another country missed deadlines on a complex proposal, creating delay and frustration. | 0 | Americas | IT/Solution | 2010 | October | 673376
232 | Schedule | Dependency | Project | 13 | 7 | Lack of coordination between projects causes delays. | 3 | Africa | Prod. Dev. | 2004 | March | 971867
233 | Schedule | Dependency | Project | 12 | 6 | Clear delegation of work done by project team and by customer never done. Confusion led to delays. | 0 | Americas | IT/Solution | 2010 | November | 723060
234 | Schedule | Dependency | Project | 12 | 4 | Installation of new systems scheduled by central team, but local people are not ready. | 0 | Americas | IT/Solution | 2016 | December | 620772
235 | Schedule | Dependency | Project | 10 | 6 | Changes to related systems resulted in wrong/late paychecks | 0 | Americas | IT/Solution | 2008 | March | 484530
236 | Schedule | Estimates | Deadline | 12 | 6 | Firewall changes can take 25 days, estimates are capped at 15 | 3 | Africa | IT/Solution | 2016 | June | 882756
237 | Schedule | Estimates | Judgment | 10 | 7 | Software upgrades take longer each cycle as O/S expands and application list grows. | 0 | Americas | IT/Solution | 2010 | January | 516540
238 | Schedule | Estimates | Judgment | 13 | 6 | Estimates in proposal too short. Testing takes more time and is highly variable. | 0 | Americas | IT/Solution | 2010 | July | 874731
239 | Schedule | Estimates | Judgment | 12 | 6 | Work was underestimated by 40% | 3 | Africa | IT/Solution | 2015 | September | 796908
240 | Schedule | Estimates | Judgment | 16 | 6 | Insufficient time is estimated; the deadline could not be met. | 3 | Africa | Prod. Dev. | 2003 | November | 952432
241 | Schedule | Estimates | Judgment | 11 | 5 | Issues with testing were severly underestimated | 0 | Americas | Prod. Dev. | 2007 | March | 638825
242 | Schedule | Estimates | Judgment | 12 | 3 | Insufficient time was scheduled for testing | 3 | Africa | Prod. Dev. | 2007 | January | 321780
243 | Schedule | Estimates | Judgment | 12 | 7 | Cabling estimates too optimistic. | 0 | Americas | IT/Solution | 2016 | September | 277020
244 | Schedule | Estimates | Judgment | 13 | 4 | Testing time underestimated. | 3 | Africa | Prod. Dev. | 2015 | June | 556569
245 | Schedule | Estimates | Learning | 14 | 3 | Lack of in-house expertise of the source system | 0 | Americas | IT/Solution | 2008 | August | 288624
246 | Schedule | Estimates | Learning | 15 | 7 | Programmer had a lack of experience in the healthcare industry | 0 | Americas | IT/Solution | 2006 | January | 323985
247 | Schedule | Estimates | Learning | 13 | 3 | Software could only be delivered to a certified person | 3 | Africa | Prod. Dev. | 2005 | September | 712842
248 | Schedule | Estimates | Learning | 16 | 7 | Critical technical task was assigned to resource who was a new hire | 0 | Americas | Prod. Dev. | 2008 | January | 918128
249 | Scope | Change | Creep | 16 | 6 | Customer reorganization led to new staffing and changed requirements | 0 | Americas | IT/Solution | 2010 | February | 564928
250 | Scope | Change | Creep | 15 | 6 | Project priorities are unclear and secondary, less important work is done delaying required tasks. | 0 | Americas | IT/Solution | 2006 | August | 409695
251 | Scope | Change | Creep | 10 | 6 | Project end date moved; unrealistic | 0 | Americas | IT/Solution | 2010 | August | 563030
252 | Scope | Change | Creep | 10 | 7 | Scope creep and resource inadequacy | 0 | Americas | IT/Solution | 2005 | January | 262180
253 | Scope | Change | Creep | 10 | 6 | Project benchmarks and requirements were never clearly defined | 0 | Americas | IT/Solution | 2016 | September | 562800
254 | Scope | Change | Creep | 11 | 6 | Project manager added additional customized reporting (for no additional fee) | 0 | Americas | IT/Solution | 2010 | April | 383328
255 | Scope | Change | Creep | 16 | 4 | Client changes her mind every step of the way | 0 | Americas | IT/Solution | 2010 | November | 444416
256 | Scope | Change | Creep | 15 | 7 | Program Manager squeezes in additional functionalities until the very last minute | 3 | Africa | Prod. Dev. | 2008 | February | 903840
257 | Scope | Change | Creep | 16 | 5 | Scope of product categories was broadened significantly | 0 | Americas | Prod. Dev. | 2003 | May | 852624
258 | Scope | Change | Creep | 12 | 3 | Senior management decided to change the core switching platform technology | 0 | Americas | Prod. Dev. | 2019 | June | 561252
259 | Scope | Change | Creep | 11 | 4 | Changes double the work on solution project; no change in funding. | 0 | Americas | IT/Solution | 2010 | February | 229614
260 | Scope | Change | Creep | 15 | 4 | Excessive scope change in ERP project | 0 | Americas | IT/Solution | 2010 | April | 331425
261 | Scope | Change | Creep | 10 | 7 | Translated text was too long | 3 | Africa | IT/Solution | 2011 | October | 499280
262 | Scope | Change | Creep | 14 | 5 | Late in long project, process rigor falls and changes are managed poorly. | 0 | Americas | Prod. Dev. | 2011 | August | 1043224
263 | Scope | Change | Dependency | 13 | 5 | Upgrade to software required. Planning and training caused delays. | 0 | Americas | IT/Solution | 2008 | November | 383253
264 | Scope | Change | Dependency | 11 | 4 | New software release installed by IT, and inconsistencies with older version caused delay and extra work. | 3 | Africa | IT/Solution | 2007 | July | 808500
265 | Scope | Change | Dependency | 17 | 6 | Details of requirements were submitted incorrectly | 0 | Americas | Prod. Dev. | 2016 | January | 494989
266 | Scope | Change | Dependency | 11 | 3 | Patch to software required for project work; extra work required to implement. | 0 | Americas | Prod. Dev. | 2005 | July | 545314
267 | Scope | Change | Dependency | 13 | 6 | New software installed by IT. It does not work, and causes delay to fix. | 0 | Americas | IT/Solution | 2013 | August | 289328
268 | Scope | Change | Dependency | 14 | 7 | Operating system release expected slips; project forced to use prior version missing some needed functionality. | 0 | Americas | Prod. Dev. | 2002 | November | 332752
269 | Scope | Change | Gap | 14 | 3 | Metrics from many sites required. When collected, additional work required to make consistent. | 0 | Americas | IT/Solution | 2011 | December | 794150
270 | Scope | Change | Gap | 16 | 5 | Mismatch in documents and expectations. Adjustments required lots of additional work. | 0 | Americas | IT/Solution | 2003 | April | 344816
271 | Scope | Change | Gap | 16 | 6 | Scanning of text was estimated before it was known text was bound in volumes | 0 | Americas | IT/Solution | 2010 | February | 725664
272 | Scope | Change | Gap | 10 | 3 | Scope was poorly defined | 0 | Americas | IT/Solution | 2012 | January | 678440
273 | Scope | Change | Gap | 17 | 3 | Online badge printing requirement completely missing from scope definition | 0 | Americas | IT/Solution | 2010 | March | 1197055
274 | Scope | Change | Gap | 16 | 6 | The old production machine fails. The new production machine is pressed into production ahead of schedule; takes longer than planned | 0 | Americas | IT/Solution | 2004 | March | 1062336
275 | Scope | Change | Gap | 10 | 4 | Missing important scope at the beginning of the project | 0 | Americas | IT/Solution | 2010 | May | 596730
276 | Scope | Change | Gap | 16 | 5 | IT staff failed to understand the user requirements | 0 | Americas | IT/Solution | 2012 | June | 927488
277 | Scope | Change | Gap | 10 | 5 | Requirements for compiling and formatting data were not clear | 0 | Americas | IT/Solution | 2008 | December | 674550
278 | Scope | Change | Gap | 15 | 6 | Scope of the project was underestimated and only detected during analysis | 3 | Africa | IT/Solution | 2004 | December | 512730
279 | Scope | Change | Gap | 13 | 3 | Scope requirement discovered late in a construction project | 0 | Americas | IT/Solution | 2014 | April | 615173
280 | Scope | Change | Gap | 13 | 7 | Kitchen remodel required a seismic upgrade | 0 | Americas | IT/Solution | 2010 | August | 503737
281 | Scope | Change | Gap | 10 | 5 | Database of components had not been updated to current OSHA standards | 0 | Americas | IT/Solution | 2015 | August | 727380
282 | Scope | Change | Gap | 15 | 4 | IT team did not perform a thorough investigation of the existing infrastructure | 0 | Americas | IT/Solution | 2010 | February | 562275
283 | Scope | Change | Gap | 15 | 5 | Tests not scheduled for working parts, but mandated for project. Added late. | 3 | Africa | Prod. Dev. | 2012 | November | 1188540
284 | Scope | Change | Gap | 17 | 3 | Proprietary data needed, but owners unwilling to provide. After delay, partial information shared. | 3 | Africa | Prod. Dev. | 2007 | October | 539512
285 | Scope | Change | Gap | 12 | 4 | Retrofit project discovered hidden damage that had to be fixed | 0 | Americas | Prod. Dev. | 2019 | May | 616584
286 | Scope | Change | Gap | 15 | 7 | After test, additional requirements surface | 0 | Americas | Prod. Dev. | 2009 | January | 853050
287 | Scope | Change | Gap | 12 | 7 | Iadequate analysis prior to iniitating development efforts | 0 | Americas | Prod. Dev. | 2014 | June | 828828
288 | Scope | Change | Gap | 16 | 3 | Scope was not discussed with the manufacturer before design was completed | 0 | Americas | Prod. Dev. | 2006 | May | 1232752
289 | Scope | Change | Gap | 16 | 3 | Technical requirements communicated to developers too late | 3 | Africa | IT/Solution | 2002 | January | 1063136
290 | Scope | Change | Gap | 16 | 4 | System functions well in Germany, but has no German documentation. Delay for translation. | 0 | Americas | IT/Solution | 2009 | October | 470800
291 | Scope | Defect | Hardware | 15 | 4 | fittings and assemblies were not up to project standards | 0 | Americas | IT/Solution | 2004 | January | 486000
292 | Scope | Defect | Hardware | 18 | 3 | Prototype problems excessive; more time to fix than planned. | 0 | Americas | Prod. Dev. | 2001 | November | 1233954
293 | Scope | Defect | Hardware | 13 | 7 | Process reliability was too low and required a new component to work | 0 | Americas | Prod. Dev. | 2010 | June | 921024
294 | Scope | Defect | Hardware | 12 | 7 | Problem arose that required use of a a novel raw material not in inventory | 0 | Americas | Prod. Dev. | 2009 | November | 745308
295 | Scope | Defect | Hardware | 14 | 7 | Solution project integrated new, untried technology. Difficulty getting it to work. | 0 | Americas | IT/Solution | 2002 | January | 366534
296 | Scope | Defect | Integration | 15 | 6 | Integrating course content that does not comply with LMS specifications | 0 | Americas | IT/Solution | 2016 | November | 963045
297 | Scope | Defect | Integration | 14 | 7 | Software modules in system do not work together as planned. | 0 | Americas | Prod. Dev. | 2010 | November | 536578
298 | Scope | Defect | Integration | 14 | 6 | Following recent upgrade, many bugs were found | 0 | Americas | IT/Solution | 2009 | September | 723828
299 | Scope | Defect | Software | 14 | 3 | Excessive bugs detected late; delayed to fix. | 0 | Americas | IT/Solution | 2017 | January | 769552
300 | Scope | Defect | Software | 14 | 3 | When testing reveals a performance defect which is due to a conflict between two, or more, of the components significant extra work is required | 0 | Americas | IT/Solution | 2010 | September | 799162
301 | Scope | Defect | Software | 16 | 3 | Excessive bugs | 0 | Americas | IT/Solution | 2015 | January | 1226960
302 | Scope | Defect | Software | 10 | 5 | New software release causes problems | 0 | Americas | IT/Solution | 2008 | October | 435680
303 | Scope | Defect | Software | 11 | 6 | Bug could be fixed only by moving to a later version of software | 0 | Americas | IT/Solution | 2010 | August | 731236
304 | Scope | Defect | Software | 10 | 3 | Controlled Document rejected by Approvers | 0 | Americas | IT/Solution | 2010 | October | 576540
305 | Scope | Defect | Software | 15 | 3 | Approvers reject required document | 0 | Americas | Prod. Dev. | 2019 | September | 1134315
306 | Scope | Defect | Software | 18 | 4 | Late quality assurance finds additional translation work is needed | 0 | Americas | Prod. Dev. | 2010 | August | 399546
307 | Scope | Defect | Software | 10 | 4 | Translations are incomplete | 0 | Americas | IT/Solution | 2001 | January | 417550
308 | Scope | Defect | Software | 12 | 3 | Quality problems led to late redesign, extra work and plan changes. | 3 | Africa | Prod. Dev. | 2006 | October | 554772
309 | Schedule | Delay | Decision | 12 | 7 | Delay in patient recruitment for clinical trials | 0 | Americas | Prod. Dev. | 2010 | December | 831156
310 | Scope | Change | Creep | 12 | 7 | Engineering would not stop adding “bell and whistles” to GUI | 0 | Americas | Prod. Dev. | 2003 | November | 643068
311 | Scope | Change | Dependency | 10 | 4 | A full bioequivalent (BE) study was unexpectedly needed even though there was only a minor difference | 0 | Americas | IT/Solution | 2010 | June | 331520
312 | Scope | Change | Gap | 12 | 7 | Due to poor understanding, a redesign and costing effort was neeed | 3 | Africa | IT/Solution | 2017 | December | 389820
313 | Scope | Defect | Hardware | 10 | 6 | Based on testing, performance was insufficient to gain approval to market | 0 | Americas | Prod. Dev. | 2010 | March | 277120
314 | Scope | Change | Gap | 12 | 4 | Requirements are misunderstood or understood differently by multiple parties | 0 | Americas | Prod. Dev. | 2010 | September | 329964
315 | Resource | People | Loss | 18 | 5 | Sudden exit of the primary developer | 3 | Africa | Prod. Dev. | 2007 | March | 1136502
316 | Resource | Outsourcing | Late or poor output | 11 | 4 | Change requested and agreed to, but supplier ships late and it does not work. | 0 | Americas | IT/Solution | 2014 | March | 868879
317 | Resource | People | Loss | 15 | 3 | Lack of head count from a 10% company-wide lay-off. | 0 | Americas | IT/Solution | 2011 | November | 406680
318 | Schedule | Estimates | Learning | 15 | 7 | Neophyte project staff lacked system expertise. | 0 | Americas | IT/Solution | 2010 | May | 1080375
319 | Scope | Defect | Software | 16 | 6 | New technology to be used failed to meet the needs | 0 | Americas | Prod. Dev. | 2010 | June | 924384
320 | Resource | Outsourcing | Late or poor output | 14 | 4 | Changes in contracts and scope not managed well | 3 | Africa | Prod. Dev. | 2005 | April | 768026
321 | Resource | Outsourcing | Late or poor output | 18 | 5 | High turnover. ( 80%) of developer at off shore development unit left, including project lead | 0 | Americas | IT/Solution | 2003 | January | 876600
322 | Resource | People | Temp loss | 17 | 6 | Contributor couldn't work due to injury and back pains | 3 | Africa | Prod. Dev. | 2017 | August | 710957
323 | Scope | Change | Creep | 18 | 6 | Definition changed late in project. | 0 | Americas | Prod. Dev. | 2006 | August | 1360674
324 | Scope | Change | Creep | 17 | 3 | Management did not plan for a requirements gathering phase | 0 | Americas | Prod. Dev. | 2006 | June | 1140581
325 | Scope | Defect | Hardware | 12 | 6 | 1000 hour tests required at project end. Failure half-way (or later) requires fix and restart. | 0 | Americas | Prod. Dev. | 2006 | May | 374808
326 | Scope | Defect | Integration | 10 | 5 | Project was longer than necessary because one team insisted on doing "half" literally, even though the effort resulting was very lopsided. | 3 | Africa | Prod. Dev. | 2005 | September | 683330
327 | Schedule | Dependency | Project | 16 | 6 | Partner software is incompatible with current applications. | 0 | Americas | IT/Solution | 2014 | April | 1135920
328 | Resource | People | Loss | 12 | 4 | Key person gave notice more than a month before leaving, but nothing was done | 0 | Americas | IT/Solution | 2008 | January | 436620
329 | Schedule | Delay | Parts | 10 | 4 | Chip failed and had to be refabricated with changes | 0 | Americas | Prod. Dev. | 2010 | March | 483340
330 | Schedule | Estimates | Deadline | 10 | 7 | Unrealistic deadline set; slips unavoidable. | 0 | Americas | IT/Solution | 2006 | September | 426980
331 | Scope | Change | Gap | 12 | 5 | Contractual obligations set without adequate knowledge of potential hidden issues | 3 | Africa | IT/Solution | 2005 | April | 802296
332 | Schedule | Dependency | Project | 16 | 3 | Server expansion project dependent on delayed tape library decommissioning | 0 | Americas | IT/Solution | 2010 | June | 654304
333 | Schedule | Estimates | Learning | 16 | 5 | 3 week test took 7 due to learning curve and ramp time. | 0 | Americas | Prod. Dev. | 2003 | May | 1088720
334 | Scope | Change | Creep | 12 | 7 | Mid project expansion to include account receivable process | 0 | Americas | IT/Solution | 2013 | January | 405768
335 | Scope | Change | Gap | 13 | 6 | Construction of subdivision was initiated using old maps | 3 | Africa | IT/Solution | 2011 | April | 369486
336 | Scope | Defect | Hardware | 18 | 5 | System with new components fails in final tests. Getting older components difficult. | 0 | Americas | Prod. Dev. | 2010 | April | 382590
337 | Resource | People | Queuing | 14 | 3 | Only one subject matter expert, who was also the PM | 0 | Americas | Prod. Dev. | 2019 | August | 982100
338 | Resource | People | Temp loss | 14 | 6 | Key analyst is scheduled to work on another project | 0 | Americas | IT/Solution | 2010 | April | 814800
339 | Resource | People | Temp loss | 10 | 4 | Architect who knew how to integrate all components fell sick and was hospitalized | 3 | Africa | IT/Solution | 2013 | July | 721080
340 | Schedule | Delay | Hardware | 13 | 6 | One key investigation step failed, and had to be redone | 0 | Americas | Prod. Dev. | 2013 | June | 668486
341 | Schedule | Estimates | Learning | 12 | 3 | None of the developers had experience with the platform the application needed | 3 | Africa | Prod. Dev. | 2019 | August | 540612
342 | Scope | Change | Creep | 15 | 5 | Client made a late change the landscape design, causing overtime, expense and delay | 0 | Americas | IT/Solution | 2007 | September | 594870
343 | Scope | Change | Creep | 13 | 7 | Didn’t explicitly define the scope, and changed part way through | 0 | Americas | Prod. Dev. | 2004 | October | 992927
344 | Resource | People | Loss | 15 | 4 | Late in project, the budget and staff are cut leading to delays, forced overtime, and demotivation. | 0 | Americas | Prod. Dev. | 2016 | May | 774225
345 | Resource | People | Queuing | 16 | 7 | Limits on headcount create work backlog | 0 | Americas | IT/Solution | 2019 | January | 699728
346 | Schedule | Delay | Decision | 16 | 7 | Required design review delayed. | 0 | Americas | Prod. Dev. | 2010 | December | 1000560
347 | Schedule | Delay | Parts | 16 | 3 | Lack of spare parts and expertise | 0 | Americas | Prod. Dev. | 2015 | June | 641328
348 | Schedule | Dependency | Project | 13 | 3 | Approvals held up at project completion to wait for delayed support plan. | 0 | Americas | IT/Solution | 2007 | July | 367094
349 | Scope | Change | Dependency | 15 | 6 | Patch to software required for project work; extra work required to implement. | 0 | Americas | Prod. Dev. | 2007 | November | 337185
350 | Scope | Change | Gap | 10 | 7 | The old production machine fails. The new production machine is pressed into production ahead of schedule; takes longer than planned | 0 | Americas | IT/Solution | 2015 | December | 694110
351 | Scope | Change | Gap | 10 | 5 | Scope of the project was underestimated and only detected during analysis | 3 | Africa | IT/Solution | 2015 | December | 716780
352 | Resource | Outsourcing | Late or poor output | 18 | 5 | Outsouced staff lacked the necessary skillset | 0 | Americas | IT/Solution | 2008 | May | 1374912
353 | Resource | People | Motivation | 17 | 7 | Work at customer site had to be done by union workers; took 6 days to do what project team could do in 1. | 0 | Americas | IT/Solution | 2008 | January | 826948
354 | Scope | Defect | Software | 15 | 3 | Integration testing is incomplete, causing system failures. | 0 | Americas | IT/Solution | 2019 | July | 547710
355 | Resource | Money | Limitation | 13 | 5 | Part of the project team ran of money three months before the project was scheduled to end | 0 | Americas | Prod. Dev. | 2009 | July | 777777
356 | Resource | Money | Limitation | 13 | 5 | Development team had insufficient resources assigned to the project | 0 | Americas | Prod. Dev. | 2005 | September | 779298
357 | Resource | Outsourcing | Delayed start | 16 | 3 | Unexpectedly high demand requires outlisde help | 0 | Americas | IT/Solution | 2001 | July | 479680
358 | Resource | Outsourcing | Delayed start | 11 | 3 | Excessive challenge of initiating a project in different time zones | 0 | Americas | IT/Solution | 2019 | May | 272712
359 | Resource | Outsourcing | Late or poor output | 10 | 6 | Key consultant breaks both arms 3 weeks before project end | 0 | Americas | IT/Solution | 2014 | May | 560640
360 | Resource | Outsourcing | Late or poor output | 11 | 7 | Poor planning for the transition between consultants | 0 | Americas | IT/Solution | 2013 | November | 700590
361 | Resource | Outsourcing | Late or poor output | 17 | 3 | Engineering consultant firm laid off a chief structural engineer late in project | 0 | Americas | IT/Solution | 2001 | October | 1288311
362 | Resource | Outsourcing | Late or poor output | 17 | 6 | Growth pushed work to understaffed contract firms | 0 | Americas | IT/Solution | 2012 | August | 1197650
363 | Resource | Outsourcing | Late or poor output | 13 | 7 | Subcontractor late with a critical component | 3 | Africa | IT/Solution | 2006 | March | 990353
364 | Resource | Outsourcing | Late or poor output | 14 | 6 | Contractor got a bigger project moved most of his team to that | 0 | Americas | IT/Solution | 2019 | August | 891268
365 | Resource | Outsourcing | Late or poor output | 13 | 4 | Designer doesn’t have skills to finish needed work | 3 | Africa | Prod. Dev. | 2007 | December | 307411
366 | Resource | Outsourcing | Late or poor output | 17 | 7 | Usual vendor closed its business and had to be replaced | 0 | Americas | Prod. Dev. | 2011 | October | 1282463
367 | Resource | Outsourcing | Late or poor output | 14 | 6 | Programming object delivered late from India delays integration tests | 3 | Africa | IT/Solution | 2016 | September | 1083054
368 | Resource | Outsourcing | Late or poor output | 11 | 5 | Decision to switch to contract manufacturer near end of project caused delays and cost increases. | 0 | Americas | Prod. Dev. | 2017 | May | 591041
369 | Resource | Outsourcing | Late or poor output | 17 | 4 | Vendor was inexperienced with relevant equipment | 3 | Africa | Prod. Dev. | 2011 | January | 1241714
370 | Resource | Outsourcing | Late start | 10 | 4 | Subcontractor overbooked; not available when needed | 0 | Americas | IT/Solution | 2019 | October | 371400
371 | Resource | People | Late start | 14 | 4 | Finding instructional designers that know how to use specialized software | 0 | Americas | Prod. Dev. | 2014 | December | 376194
372 | Resource | People | Loss | 12 | 6 | Critical person went on maternity leave | 3 | Africa | IT/Solution | 2010 | August | 934788
373 | Resource | People | Loss | 11 | 5 | Key contriobutor quit, and there was insufficient information transfer | 3 | Africa | IT/Solution | 2002 | August | 540254
374 | Resource | People | Loss | 10 | 6 | The key business user assigned to the ITS project was lost while assisting with a manufacturing problem and was no longer available to the project team | 0 | Americas | Prod. Dev. | 2013 | December | 750440
375 | Resource | People | Loss | 12 | 7 | Senior technical writer resigns and another takes a leave | 0 | Americas | Prod. Dev. | 2007 | January | 389196
376 | Resource | People | Loss | 13 | 7 | A senior technical architecte quit | 3 | Africa | Prod. Dev. | 2005 | October | 914836
377 | Resource | People | Loss | 15 | 5 | The key person responsible for major marketing activities resigned | 3 | Africa | Prod. Dev. | 2013 | March | 517725
378 | Resource | People | Loss | 13 | 5 | Resources committed to projects reassigned to new projects and not replaced. | 0 | Americas | Prod. Dev. | 2018 | December | 740051
379 | Resource | People | Motivation | 12 | 5 | Too little management interest and support | 0 | Americas | Prod. Dev. | 2012 | September | 738528
380 | Resource | People | Queuing | 15 | 4 | People who require training miss classes; more classes required. | 3 | Africa | IT/Solution | 2005 | October | 1081455
381 | Resource | People | Queuing | 17 | 4 | All students did not complete training as scheduled, so the project is completed late | 0 | Americas | IT/Solution | 2011 | December | 813569
382 | Resource | People | Queuing | 11 | 5 | Two projects depended on one resource for completion and this one had lower priority | 0 | Americas | IT/Solution | 2001 | July | 407143
383 | Resource | People | Queuing | 12 | 4 | There was only on one experienced consultant who knew the tool | 0 | Americas | IT/Solution | 2009 | July | 396588
384 | Resource | People | Queuing | 14 | 7 | Only one subject matter expert, who was also the PM | 0 | Americas | Prod. Dev. | 2011 | June | 688814
385 | Resource | People | Queuing | 14 | 5 | "50%" resources are not aligned, resulting in activity delays | 3 | Africa | Prod. Dev. | 2019 | March | 751660
386 | Resource | People | Queuing | 17 | 7 | Two of the developers were able to work on the project only 60% of their time, not full time | 3 | Africa | Prod. Dev. | 2011 | March | 605999
387 | Resource | People | Queuing | 15 | 3 | Reduction in work force affects the % commitment of team members | 0 | Americas | Prod. Dev. | 2003 | May | 657570
388 | Resource | People | Queuing | 15 | 3 | Expert worked on at least 4-5 projects at a time | 0 | Americas | Prod. Dev. | 2017 | March | 317310
389 | Resource | People | Queuing | 10 | 3 | CMO analyzing output developed a severe backup | 3 | Africa | Prod. Dev. | 2017 | January | 661620
390 | Resource | People | Queuing | 13 | 6 | During testing phase, resource availability was indaequate due to other priorities | 0 | Americas | Prod. Dev. | 2010 | December | 396071
391 | Resource | People | Queuing | 10 | 6 | Multiple projects depend on lone expert scientist | 0 | Americas | Prod. Dev. | 2018 | October | 499360
392 | Resource | People | Temp loss | 18 | 5 | 2 key team members lost for a time because of illness | 0 | Americas | IT/Solution | 2013 | November | 877536
393 | Resource | People | Temp loss | 18 | 6 | Key analyst is scheduled to work on another project | 3 | Africa | IT/Solution | 2008 | April | 472878
394 | Resource | People | Temp loss | 17 | 7 | Key IT resources scheduled extensive vacations | 3 | Africa | IT/Solution | 2004 | June | 1317755
395 | Resource | People | Temp loss | 16 | 6 | Study timeline set before staff vacation dates were known | 0 | Americas | IT/Solution | 2017 | August | 854192
396 | Resource | People | Temp loss | 16 | 6 | Loss of key members of a project team in an already constrained project. | 3 | Africa | Prod. Dev. | 2013 | June | 1017104
397 | Resource | People | Temp loss | 17 | 4 | Architect who knew how to integrate all components fell sick and was hospitalized | 3 | Africa | IT/Solution | 2009 | December | 437835
398 | Resource | People | Temp loss | 12 | 6 | Earthquake in Taiwan makes part of the project team unavailable for work. | 0 | Americas | Prod. Dev. | 2009 | August | 698100
399 | Resource | People | Temp loss | 12 | 7 | Only 2 people understood the new system, and neither was available | 3 | Africa | IT/Solution | 2006 | June | 813120
400 | Resource | People | Temp loss | 16 | 5 | At year-end, engineer in Germenay had to take accrued vacation time | 0 | Americas | Prod. Dev. | 2002 | October | 990496
401 | Schedule | Delay | Decision | 12 | 6 | Senior management approval for software licenses delayed | 0 | Americas | Prod. Dev. | 2006 | August | 335856
402 | Schedule | Delay | Hardware | 15 | 4 | A component needed for necropsy data analysis failed | 0 | Americas | IT/Solution | 2009 | December | 510420
403 | Schedule | Delay | Hardware | 11 | 7 | One key investigation step failed, and had to be redone | 0 | Americas | Prod. Dev. | 2001 | January | 307736
404 | Schedule | Delay | Hardware | 16 | 7 | Needed system delivered to wrong building; lost for weeks. | 3 | Africa | IT/Solution | 2014 | December | 335648
405 | Schedule | Delay | Information | 12 | 4 | Metrics required by process improvement project collected and delivered late. | 3 | Africa | IT/Solution | 2010 | December | 939972
406 | Schedule | Delay | Information | 12 | 3 | With 12 hour time difference and dependence on E-mail, even simple questions take 2-4 days to resolve. | 3 | Africa | Prod. Dev. | 2001 | July | 501708
407 | Schedule | Delay | Information | 14 | 4 | Some tasks assigned only by function; no one actually working on them. | 0 | Americas | Prod. Dev. | 2004 | November | 885206
408 | Schedule | Delay | Parts | 11 | 7 | Servers stuck in customs | 0 | Americas | IT/Solution | 2012 | July | 303061
409 | Schedule | Delay | Parts | 13 | 7 | Had only 1/3 of the units needed on time | 0 | Americas | IT/Solution | 2009 | December | 440206
410 | Schedule | Delay | Parts | 11 | 6 | Key supplier lost in the middle of a project | 0 | Americas | IT/Solution | 2003 | March | 421355
411 | Schedule | Delay | Parts | 13 | 5 | Parts unavailable; backordered. | 0 | Americas | Prod. Dev. | 2012 | December | 659373
412 | Schedule | Delay | Parts | 10 | 5 | ASIC delays | 3 | Africa | Prod. Dev. | 2002 | January | 651280
413 | Schedule | Delay | Parts | 14 | 3 | Change to US sourcing created demand and delays | 0 | Americas | Prod. Dev. | 2005 | April | 684782
414 | Schedule | Delay | Parts | 13 | 6 | Manufacturing problem with key component | 3 | Africa | Prod. Dev. | 2006 | June | 840814
415 | Schedule | Delay | Parts | 11 | 6 | Parts shipped by sea from Asia, not air. | 0 | Americas | Prod. Dev. | 2006 | July | 465179
416 | Schedule | Delay | Parts | 13 | 6 | International shipment of parts supposed to take 6 weeks, actually averages 9. | 0 | Americas | Prod. Dev. | 2002 | October | 715741
417 | Schedule | Delay | Parts | 14 | 4 | Some parts are damaged in shipping and must be reordered. | 3 | Africa | Prod. Dev. | 2006 | September | 776440
418 | Schedule | Delay | Parts | 10 | 4 | Samples needed in Spain were late | 3 | Africa | IT/Solution | 2009 | March | 630490
419 | Schedule | Delay | Parts | 11 | 4 | Needed concrete wasn’t delivered on time | 3 | Africa | IT/Solution | 2006 | April | 324203
420 | Schedule | Delay | Parts | 18 | 4 | Component delivery late. Causes ramp delays. | 0 | Americas | Prod. Dev. | 2011 | September | 1032930
421 | Schedule | Dependency | Infrastructure | 16 | 5 | Needed wiring not available on time | 0 | Americas | IT/Solution | 2013 | October | 529152
422 | Schedule | Dependency | Infrastructure | 18 | 6 | the infrastructure changes needed (network, microwave, etc) were not budgeted for the project | 3 | Africa | IT/Solution | 2004 | June | 692514
423 | Schedule | Dependency | Infrastructure | 10 | 5 | Space unavailable; needed to implement in old space | 0 | Americas | Prod. Dev. | 2015 | May | 243320
424 | Schedule | Dependency | Infrastructure | 17 | 6 | Problems due to last minute infrastructure changes | 0 | Americas | Prod. Dev. | 2009 | April | 1227927
425 | Schedule | Dependency | Legal | 13 | 3 | Delay in approval to proceed in France and German | 0 | Americas | Prod. Dev. | 2018 | August | 445185
426 | Schedule | Dependency | Project | 10 | 6 | Commitment given, but deliverables were late. | 0 | Americas | IT/Solution | 2001 | February | 531700
427 | Schedule | Dependency | Project | 15 | 4 | Localization of the web contents delivery is delayed | 0 | Americas | IT/Solution | 2003 | June | 810255
428 | Schedule | Dependency | Project | 15 | 3 | ASIC supplier (only source) was fine for low volume, but at lower cost and high volume had quality problems and created delays. | 0 | Americas | Prod. Dev. | 2006 | July | 878175
429 | Schedule | Estimates | Deadline | 11 | 6 | Unrealistic compressed timeline | 0 | Americas | Prod. Dev. | 2005 | April | 300333
430 | Schedule | Estimates | Deadline | 16 | 6 | Unrealistic deadline set | 0 | Americas | Prod. Dev. | 2010 | May | 466720
431 | Schedule | Estimates | Judgment | 10 | 5 | Recertification of updated applications took longer than hoped | 0 | Americas | IT/Solution | 2005 | February | 777220
432 | Schedule | Estimates | Judgment | 12 | 3 | Components that could have been purchased were developed by team, taking longer than expected. | 0 | Americas | Prod. Dev. | 2010 | November | 626160
433 | Schedule | Estimates | Judgment | 17 | 3 | The integration task was not defined and broken down to sufficiently small pieces in the project plan. | 0 | Americas | Prod. Dev. | 2012 | October | 982770
434 | Schedule | Estimates | Learning | 16 | 6 | Due to organizational change new person was assigned the work | 0 | Americas | IT/Solution | 2016 | June | 388688
435 | Schedule | Estimates | Learning | 11 | 4 | Team was staffed by 3 successive new hires in a six-month period | 3 | Africa | Prod. Dev. | 2012 | August | 380655
436 | Schedule | Estimates | Learning | 14 | 6 | None of the developers had experience with the platform the application needed | 3 | Africa | Prod. Dev. | 2002 | September | 904274
437 | Schedule | Estimates | Learning | 14 | 7 | Oversea engineering team was inexperienced | 3 | Africa | Prod. Dev. | 2001 | February | 688856
438 | Schedule | Estimates | Learning | 10 | 7 | Lack of skills with recent university hires | 0 | Americas | IT/Solution | 2016 | October | 679540
439 | Scope | Change | Creep | 17 | 4 | Client requested "15 minute" change accepted and led to delay and loss on project | 0 | Americas | IT/Solution | 2018 | April | 496553
440 | Scope | Change | Creep | 17 | 6 | Revision to the story board is required | 0 | Americas | IT/Solution | 2016 | December | 1229899
441 | Scope | Change | Creep | 14 | 5 | Project delayed due to recent/last minute changes to portal interface design | 3 | Africa | IT/Solution | 2004 | April | 603274
442 | Scope | Change | Creep | 18 | 6 | Client made a late change the landscape design, causing overtime, expense and delay | 0 | Americas | IT/Solution | 2003 | August | 1164258
443 | Scope | Change | Creep | 18 | 4 | Power configuration change was requested too late in the schedule | 0 | Americas | IT/Solution | 2001 | January | 632610
444 | Scope | Change | Creep | 11 | 3 | 6 sister organizations with an additional 250 users added to the project late | 0 | Americas | IT/Solution | 2013 | October | 519838
445 | Scope | Change | Creep | 12 | 3 | Complex feature added that was not requested by the customer | 0 | Americas | IT/Solution | 2008 | November | 611220
446 | Scope | Change | Creep | 17 | 3 | Additional deliverable added late | 0 | Americas | IT/Solution | 2011 | May | 1226312
447 | Scope | Change | Creep | 13 | 6 | Late design changes required manufacturing retooling at the last minute. | 0 | Americas | Prod. Dev. | 2003 | June | 606918
448 | Scope | Change | Creep | 16 | 3 | Didn’t explicitly define the scope, and changed part way through | 0 | Americas | Prod. Dev. | 2016 | May | 570432
449 | Scope | Change | Creep | 11 | 5 | Escalated late changes from Sponsor | 0 | Americas | Prod. Dev. | 2011 | May | 433697
450 | Scope | Change | Creep | 10 | 7 | Project schedule was revised user interface requirements which increased project scope | 0 | Americas | Prod. Dev. | 2013 | December | 239380
451 | Scope | Change | Creep | 11 | 5 | Integrating late features meant that the existing architecture had to be modified | 0 | Americas | Prod. Dev. | 2002 | October | 824560
452 | Scope | Change | Creep | 17 | 5 | No proper change control process resulted in unnecessary new requirements | 3 | Africa | Prod. Dev. | 2019 | December | 1180140
453 | Scope | Change | Creep | 14 | 6 | "Minor" changes added and accepted late in project. Phase work doubled and delayed project end. | 0 | Americas | IT/Solution | 2011 | March | 682164
454 | Scope | Change | Creep | 15 | 4 | Customer driven late changes | 0 | Americas | IT/Solution | 2013 | November | 1079865
455 | Scope | Change | Creep | 13 | 4 | Customer requirements continually shift; lots of extra work. | 0 | Americas | IT/Solution | 2009 | May | 771004
456 | Scope | Change | Dependency | 10 | 6 | Server technology chage was necessitated to support application | 0 | Americas | IT/Solution | 2012 | April | 656430
457 | Scope | Change | Dependency | 13 | 7 | Corporate merger delayed project | 0 | Americas | IT/Solution | 2008 | December | 416091
458 | Scope | Change | Gap | 17 | 3 | Lack of testing of older WWW browser versions led to custom coding being written before application could be used. | 0 | Americas | IT/Solution | 2007 | December | 1318860
459 | Scope | Change | Gap | 12 | 7 | Incorrect input data provided | 0 | Americas | IT/Solution | 2017 | November | 569784
460 | Scope | Change | Gap | 13 | 5 | Failure to collect the details about the interfaces and links to the third party websites | 0 | Americas | IT/Solution | 2011 | September | 1022788
461 | Scope | Change | Gap | 10 | 7 | The database assigned for the client did not have sufficient free space for their growing accounts | 0 | Americas | IT/Solution | 2006 | December | 276890
462 | Scope | Change | Gap | 10 | 6 | Changes were approved by the business users without proper testing | 0 | Americas | IT/Solution | 2018 | May | 497350
463 | Scope | Change | Gap | 12 | 3 | Deliverable requirements were discovered during the execution phase | 0 | Americas | IT/Solution | 2007 | April | 243972
464 | Scope | Change | Gap | 16 | 3 | One week’s analysis is insufficient to capture needed requirements | 0 | Americas | IT/Solution | 2017 | April | 668224
465 | Scope | Change | Gap | 14 | 7 | Legacy systems and processes were not well documented | 0 | Americas | IT/Solution | 2011 | February | 403592
466 | Scope | Change | Gap | 15 | 3 | Requireemnts sent via email were never formally documented | 0 | Americas | IT/Solution | 2002 | November | 679200
467 | Scope | Change | Gap | 14 | 6 | Sponsor failed to communicate his requirements at the start of the project | 0 | Americas | IT/Solution | 2005 | June | 954716
468 | Scope | Change | Gap | 13 | 7 | Not enough timewas spent to identify all the requirements for the process | 0 | Americas | IT/Solution | 2013 | July | 398996
469 | Scope | Change | Gap | 11 | 7 | Lack of communication between the teams | 0 | Americas | IT/Solution | 2003 | April | 471779
470 | Scope | Change | Gap | 17 | 6 | Programmer didn’t understand what data was needed or why | 0 | Americas | IT/Solution | 2019 | January | 1098897
471 | Scope | Change | Gap | 16 | 3 | Specifications incomplete and late. Delayed project start. | 3 | Africa | Prod. Dev. | 2019 | March | 944272
472 | Scope | Change | Gap | 18 | 6 | Insufficient initial project scope was defined when the estimate given to the client | 0 | Americas | Prod. Dev. | 2005 | June | 772758
473 | Scope | Change | Gap | 10 | 3 | In testing, it is discovered that 50K words were left untranslated due to updates and changes | 0 | Americas | Prod. Dev. | 2004 | November | 692040
474 | Scope | Change | Gap | 13 | 6 | Failure to understand the scope of the project | 3 | Africa | Prod. Dev. | 2013 | June | 762931
475 | Scope | Change | Gap | 12 | 4 | Resistance of the business stakeholders to reach consensus on the project’s scope | 3 | Africa | Prod. Dev. | 2002 | May | 444468
476 | Scope | Change | Gap | 14 | 3 | Lack of research and analysis on a key compoent of the deliverable | 3 | Africa | Prod. Dev. | 2007 | May | 805770
477 | Scope | Change | Gap | 15 | 4 | Analysis group not involved in planning meetings | 0 | Americas | Prod. Dev. | 2005 | May | 864075
478 | Scope | Change | Gap | 12 | 6 | Instructions provided to the testing facility were too vague, necessitating re-tests | 0 | Americas | Prod. Dev. | 2016 | November | 657876
479 | Scope | Change | Gap | 16 | 3 | Scoping was much more complex then originally thought | 0 | Americas | Prod. Dev. | 2018 | March | 348064
480 | Scope | Change | Gap | 12 | 6 | Lack of data and knowledge for the new product | 0 | Americas | Prod. Dev. | 2002 | November | 282072
481 | Scope | Change | Gap | 16 | 7 | The development team in Pakistan misinterpreted a number of req'ts | 0 | Americas | IT/Solution | 2008 | February | 1174560
482 | Scope | Change | Gap | 17 | 6 | Documentation provided in only one of two required languages. Delay for translation. | 3 | Africa | IT/Solution | 2007 | January | 639540
483 | Scope | Change | Gap | 12 | 5 | Documentation needed in French was entirely overlooked | 3 | Africa | Prod. Dev. | 2011 | January | 812820
484 | Scope | Defect | Hardware | 17 | 5 | Network configuration sometimes causes the backups to fail intermittently; troubleshooting is hard. | 3 | Africa | IT/Solution | 2013 | April | 913920
485 | Scope | Defect | Hardware | 14 | 7 | Components were incorrectly measured | 0 | Americas | IT/Solution | 2001 | August | 594118
486 | Scope | Defect | Hardware | 14 | 3 | PC board failure requires redesign and fabrication. | 0 | Americas | Prod. Dev. | 2004 | October | 681142
487 | Scope | Defect | Hardware | 10 | 7 | Poor quality control and record keeping on the field installation side resulted in many openings being installed incorrectly | 3 | Africa | Prod. Dev. | 2002 | July | 379210
488 | Scope | Defect | Hardware | 15 | 7 | Revisions required after review | 0 | Americas | Prod. Dev. | 2016 | July | 1178745
489 | Scope | Defect | Software | 18 | 7 | There was not enough time to redo the programming to fix the errors identified | 3 | Africa | IT/Solution | 2012 | April | 679788
490 | Scope | Defect | Software | 10 | 3 | Editing text worsened product quality and necessitated retranslation | 3 | Africa | Prod. Dev. | 2002 | September | 282090
491 | Scope | Defect | Software | 17 | 4 | Errors found in data and critrical reports | 0 | Americas | Prod. Dev. | 2018 | December | 1222028
492 | Scope | Defect | Software | 13 | 7 | Legacy system (COBOL) fails during system upgrade project. Extra effort required to fix. | 0 | Americas | IT/Solution | 2003 | January | 288275
493 | Resource | Outsourcing | Late or poor output | 15 | 5 | Key supplier purchased by other company and reorganized. Forced to find new supplier. | 0 | Americas | Prod. Dev. | 2005 | December | 332745
494 | Scope | Change | Creep | 11 | 5 | Scoping for a wiring project increased substantially after awarding the business | 0 | Americas | IT/Solution | 2006 | April | 288662
495 | Scope | Defect | Software | 15 | 4 | The software had around 20 major defects and 80 problems that prevented us from moving forward | 0 | Americas | IT/Solution | 2014 | January | 830370
496 | Scope | Defect | Software | 18 | 4 | During unit testing, discovered performance issue with bulk loads | 0 | Americas | IT/Solution | 2005 | September | 556830
497 | Scope | Change | Gap | 13 | 5 | There was a very large mismatch between stakeholder expectations and given scope | 0 | Americas | IT/Solution | 2014 | September | 657670
498 | Resource | People | Loss | 18 | 6 | Lack of people resources (designers, requirement/business analysts, data modelers and QA/Testing) | 3 | Africa | Prod. Dev. | 2019 | February | 445176
499 | Scope | Change | Dependency | 18 | 4 | Market change due to Improvements in technology became an ‘urgent’ requirement | 0 | Americas | IT/Solution | 2009 | March | 1196622
500 | Resource | Money | Limitation | 13 | 6 | Due to a layoff no writer was immediately available, so approval was delayed | 3 | Africa | Prod. Dev. | 2007 | November | 577239
501 | Scope | Defect | Hardware | 16 | 3 | New chips caused the mother board to perform poorly | 3 | Africa | Prod. Dev. | 2008 | May | 992048
502 | Resource | People | Loss | 13 | 4 | Product owner having unique knowledge left the company | 0 | Americas | Prod. Dev. | 2009 | June | 875095
503 | Scope | Change | Gap | 18 | 5 | Poor communications resulted in never truly understanding customer needs | 3 | Africa | IT/Solution | 2003 | July | 668052
504 | Schedule | Estimates | Learning | 17 | 7 | High attrition in positions requiring unique technical training | 0 | Americas | IT/Solution | 2011 | March | 967895
505 | Schedule | Delay | Information | 14 | 4 | Data for key tables not available when needed | 3 | Africa | IT/Solution | 2012 | January | 566594
506 | Schedule | Delay | Parts | 13 | 7 | Manufacutring group did not have the capcity to produce a critical new enzyme | 0 | Americas | Prod. Dev. | 2001 | June | 1033474
507 | Scope | Change | Creep | 16 | 3 | Functionality for email added late to a document retrieval project | 0 | Americas | IT/Solution | 2017 | August | 1264688
508 | Schedule | Dependency | Project | 11 | 3 | Project delayed to work on higher profit margin work | 0 | Americas | IT/Solution | 2017 | May | 653103
509 | Resource | People | Loss | 10 | 3 | The contractor half-way through the electrical job had a heart attack | 0 | Americas | Prod. Dev. | 2015 | February | 387560
510 | Scope | Change | Gap | 15 | 6 | Real-life data used did not test every scenario possible, so had to be replaced | 0 | Americas | Prod. Dev. | 2007 | January | 1005705
511 | Scope | Change | Gap | 18 | 5 | Lack of communication between the customer and all vendors involved | 3 | Africa | IT/Solution | 2004 | November | 1189746
512 | Resource | Outsourcing | Delayed start | 11 | 3 | Delays due to bidding issues and protests | 3 | Africa | IT/Solution | 2007 | September | 361383
513 | Scope | Defect | Software | 10 | 7 | Issues discovered late in testing | 0 | Americas | IT/Solution | 2006 | December | 700250
514 | Resource | People | Temp loss | 17 | 4 | Staff lost to customer Hot Site | 3 | Africa | Prod. Dev. | 2004 | April | 912509
515 | Schedule | Delay | Decision | 16 | 7 | International leased line order delayed (management approval) and then only ran at half the desired . | 0 | Americas | IT/Solution | 2007 | June | 873728
516 | Schedule | Dependency | Project | 18 | 4 | Other organizations are late with promised work, then deliverables do not work as expected. | 0 | Americas | Prod. Dev. | 2014 | July | 619506
517 | Schedule | Estimates | Deadline | 14 | 3 | Schedule set without first doing a project feasibility and capacity analysis | 3 | Africa | IT/Solution | 2014 | March | 429520
518 | Resource | People | Loss | 12 | 7 | A senior technical architecte quit | 0 | Americas | Prod. Dev. | 2003 | August | 700116
519 | Resource | People | Queuing | 13 | 7 | During testing phase, resource availability was indaequate due to other priorities | 0 | Americas | Prod. Dev. | 2002 | September | 299039
520 | Resource | People | Loss | 12 | 3 | A key team member was replaced mid-project | 3 | Africa | IT/Solution | 2017 | July | 610668
521 | Schedule | Delay | Parts | 16 | 3 | International shipment of tape was on time, but the tape was bad. | 0 | Americas | IT/Solution | 2002 | August | 374032
522 | Scope | Change | Creep | 18 | 4 | Project benchmarks and requirements were never clearly defined | 0 | Americas | IT/Solution | 2011 | October | 958032
523 | Scope | Change | Dependency | 15 | 7 | Details of requirements were submitted incorrectly | 3 | Africa | Prod. Dev. | 2017 | April | 884895
524 | Schedule | Estimates | Judgment | 10 | 6 | Underestimated weight of stumps to be removed | 3 | Africa | IT/Solution | 2008 | January | 668480
525 | Scope | Change | Creep | 12 | 4 | Additional enhancements requested at the last minute | 0 | Americas | IT/Solution | 2008 | October | 703812
526 | Scope | Change | Gap | 11 | 5 | Design team failed to collect the details on what was to be displayed to users | 0 | Americas | IT/Solution | 2014 | September | 647031
527 | Scope | Defect | Hardware | 18 | 7 | Vibration in transit caused the loosing of the nuts and bolts of antennas, which eventually caused the collapse of the antennas | 0 | Americas | Prod. Dev. | 2007 | February | 871128
528 | Scope | Defect | Hardware | 14 | 5 | Cable required had been left off the implementation parts list | 0 | Americas | IT/Solution | 2015 | August | 892612
529 | Scope | Defect | Software | 10 | 5 | Engineering overlooked the functional design and did not implement correctly | 3 | Africa | IT/Solution | 2007 | October | 781980
530 | Resource | Money | Limitation | 18 | 6 | Key consultant was let go at a critical time for coat reasons | 0 | Americas | IT/Solution | 2001 | March | 561078
531 | Resource | Money | Limitation | 15 | 6 | Lack of funds for travel at launch | 0 | Americas | Prod. Dev. | 2014 | September | 1160100
532 | Resource | Outsourcing | Delayed start | 13 | 6 | Contract negotiations delayed by 20 days | 0 | Americas | IT/Solution | 2010 | September | 613496
533 | Resource | Outsourcing | Delayed start | 18 | 4 | Vendor currently has limited capacity and could not hire quickly enough to support this product | 0 | Americas | IT/Solution | 2017 | August | 1211562
534 | Resource | Outsourcing | Delayed start | 10 | 3 | For cost reasons, Asian supplier chosen. Qualification and paperwork caused delays. | 0 | Americas | Prod. Dev. | 2003 | June | 432660
535 | Resource | Outsourcing | Late or poor output | 16 | 3 | Initial stages were outsourced to a professor who started late and lacked needed information | 3 | Africa | IT/Solution | 2007 | April | 1118960
536 | Resource | Outsourcing | Late or poor output | 15 | 6 | Incompetent subcontractor led to delay and unhappy clients | 0 | Americas | IT/Solution | 2001 | May | 1172550
537 | Resource | Outsourcing | Late or poor output | 18 | 5 | Subcontractor did not build stairs according to the drawings and had to redo them | 0 | Americas | IT/Solution | 2012 | April | 392922
538 | Resource | Outsourcing | Late or poor output | 11 | 6 | Lack of clear definition of the contractor and Lead Tech roles and responsibilities | 3 | Africa | IT/Solution | 2012 | June | 671561
539 | Resource | Outsourcing | Late or poor output | 16 | 4 | Vendor made a promise on something they could not deliver | 0 | Americas | IT/Solution | 2011 | April | 832192
540 | Resource | Outsourcing | Late or poor output | 10 | 6 | Vendor missed validation due date delaying Clinical Trials | 0 | Americas | Prod. Dev. | 2013 | September | 747930
541 | Resource | Outsourcing | Late or poor output | 13 | 6 | Contract lab failed to inform us that they had trouble with a genotyping assay | 0 | Americas | Prod. Dev. | 2009 | November | 632970
542 | Resource | Outsourcing | Late or poor output | 15 | 5 | Contractor provided inadequate survey data | 0 | Americas | Prod. Dev. | 2004 | January | 372780
543 | Resource | Outsourcing | Late or poor output | 18 | 5 | Chinese IT company to guarantee the quality of their work | 0 | Americas | IT/Solution | 2016 | July | 1011672
544 | Resource | Outsourcing | Late or poor output | 12 | 7 | Abnormally high turnover and shortage of capable developers in India | 3 | Africa | Prod. Dev. | 2007 | June | 256008
545 | Resource | People | Late start | 12 | 7 | Delay in hiring more engineers due to cost cutting | 0 | Americas | IT/Solution | 2001 | October | 881628
546 | Resource | People | Late start | 13 | 5 | "Rolling Sledgehammer" Last project ties up (and exhausts) staff; next project starts late and slow. | 0 | Americas | Prod. Dev. | 2019 | August | 665873
547 | Resource | People | Loss | 17 | 7 | Key person lost mid-project | 3 | Africa | IT/Solution | 2001 | February | 582743
548 | Resource | People | Loss | 12 | 5 | Turnover on staff 100% in year, leading to delays and training. | 0 | Americas | IT/Solution | 2018 | April | 347352
549 | Resource | People | Loss | 10 | 5 | The project manager was assigned to another big project part way through the project | 3 | Africa | IT/Solution | 2018 | January | 752260
550 | Resource | People | Loss | 12 | 5 | Layoffs in the company | 3 | Africa | Prod. Dev. | 2013 | March | 855264
551 | Resource | People | Loss | 15 | 5 | Loss of a key person | 0 | Americas | Prod. Dev. | 2011 | November | 701055
552 | Resource | People | Loss | 15 | 4 | Key resource pulled from a high priority project | 0 | Americas | IT/Solution | 2001 | July | 369420
553 | Resource | People | Loss | 14 | 7 | Key engineer on project leaves the company | 0 | Americas | IT/Solution | 2003 | December | 1099182
554 | Resource | People | Loss | 14 | 6 | Project team members reassigned. Not replaced; led to overtime, quality problems, missed deadlines. | 0 | Americas | Prod. Dev. | 2018 | October | 888594
555 | Resource | People | Loss | 18 | 7 | Team members reassigned to other, higher priority projects. | 3 | Africa | Prod. Dev. | 2008 | January | 928944
556 | Resource | People | Queuing | 11 | 5 | Only one employee with other commitments had both the Cobol and relational database data conversion experience | 0 | Americas | IT/Solution | 2019 | April | 864292
557 | Resource | People | Queuing | 16 | 7 | Lack of key SME resource availability when needed | 0 | Americas | IT/Solution | 2010 | November | 946592
558 | Resource | People | Queuing | 18 | 5 | Key contributor unavailable when needed. | 0 | Americas | Prod. Dev. | 2013 | February | 1055214
559 | Resource | People | Queuing | 17 | 7 | The trained resource was tied up in other work | 0 | Americas | Prod. Dev. | 2005 | July | 706010
560 | Resource | People | Queuing | 18 | 4 | Conflicting priorities. on-going maintenance, and loss of a person led to delay | 0 | Americas | Prod. Dev. | 2018 | May | 561780
561 | Resource | People | Queuing | 11 | 7 | Lone subject matter expert unavailable when needed during the initial stages | 0 | Americas | Prod. Dev. | 2016 | April | 442640
562 | Resource | People | Temp loss | 13 | 7 | Unexpected shutdown at year end delays work and rescheduling it is difficult. | 0 | Americas | IT/Solution | 2011 | August | 976469
563 | Resource | People | Temp loss | 10 | 3 | A valuable resource gets pulled off of project to work on a larger, higher profile project | 0 | Americas | IT/Solution | 2010 | October | 546250
564 | Resource | People | Temp loss | 14 | 7 | Key resource tied to a previous project for two weeks | 0 | Americas | IT/Solution | 2001 | November | 900634
565 | Resource | People | Temp loss | 12 | 7 | No vacation/time-off estimate planning was done | 0 | Americas | IT/Solution | 2005 | June | 778776
566 | Resource | People | Temp loss | 14 | 4 | Change Management Lead took unexpected medical leave | 0 | Americas | IT/Solution | 2009 | January | 1118208
567 | Resource | People | Temp loss | 17 | 4 | Contributor has lengthy, unannounced vacation | 0 | Americas | IT/Solution | 2015 | April | 1313641
568 | Resource | People | Temp loss | 12 | 6 | Staff lost to customer Hot Site | 0 | Americas | Prod. Dev. | 2013 | April | 452160
569 | Resource | People | Temp loss | 13 | 6 | Multiple projects competing for a limited staff to do the work leads to interruptions and delays | 0 | Americas | Prod. Dev. | 2010 | February | 995605
570 | Resource | People | Temp loss | 18 | 5 | Key code developer had a family emergency | 0 | Americas | IT/Solution | 2012 | April | 754974
571 | Resource | People | Temp loss | 11 | 4 | Staff lost to customer Hot Site | 0 | Americas | Prod. Dev. | 2003 | April | 409662
572 | Schedule | Delay | Decision | 17 | 7 | All stakeholders approve project individually, but at meeting together for final approval, disagreements changed and delayed the project. | 3 | Africa | IT/Solution | 2004 | November | 780096
573 | Schedule | Delay | Decision | 11 | 4 | Decisions are being delayed without apparent reason | 0 | Americas | Prod. Dev. | 2002 | May | 631994
574 | Schedule | Delay | Decision | 18 | 3 | International leased line order delayed (management approval) and then only ran at half the desired . | 3 | Africa | IT/Solution | 2018 | July | 1038150
575 | Schedule | Delay | Hardware | 15 | 7 | Systems required backordered (6 months). Forced to use competitor's system. | 0 | Americas | IT/Solution | 2006 | December | 855570
576 | Schedule | Delay | Hardware | 14 | 7 | Multiple phase roll out paused near the end, systems temporarily out of stock. | 0 | Americas | IT/Solution | 2013 | June | 814184
577 | Schedule | Delay | Hardware | 11 | 3 | New technology not available on time. | 0 | Americas | IT/Solution | 2001 | August | 355003
578 | Schedule | Delay | Hardware | 14 | 7 | Equipment was unreliable and caused slips | 3 | Africa | IT/Solution | 2006 | September | 403690
579 | Schedule | Delay | Hardware | 12 | 5 | Key parts would be delivered late | 0 | Americas | IT/Solution | 2011 | July | 494340
580 | Schedule | Delay | Information | 15 | 4 | Key stakeholders were not identified during requirements gathering | 0 | Americas | IT/Solution | 2006 | October | 961290
581 | Schedule | Delay | Information | 10 | 3 | The business counterparts were not in agreement with which option to choose and went back and forth on the decision | 0 | Americas | Prod. Dev. | 2012 | May | 273720
582 | Schedule | Delay | Information | 12 | 7 | Communications problems and misinterpretation of the requirements in India | 0 | Americas | IT/Solution | 2004 | May | 757992
583 | Schedule | Delay | Information | 14 | 7 | Documents could not be translated promptly | 0 | Americas | IT/Solution | 2010 | September | 821338
584 | Schedule | Delay | Parts | 18 | 5 | A special peripheral used for the project deliverable was discontinued | 3 | Africa | IT/Solution | 2015 | October | 893610
585 | Schedule | Delay | Parts | 13 | 3 | Solar panels arrived late and were not what was ordered | 3 | Africa | IT/Solution | 2018 | December | 561132
586 | Schedule | Delay | Parts | 18 | 3 | Supplier was unable to make a sample correctly | 0 | Americas | Prod. Dev. | 2002 | February | 1374084
587 | Schedule | Delay | Parts | 14 | 5 | There was a delay in the delivery of test samples | 0 | Americas | Prod. Dev. | 2005 | May | 896420
588 | Schedule | Delay | Parts | 10 | 3 | Granite countertops had incorrect measurements | 0 | Americas | Prod. Dev. | 2018 | October | 268180
589 | Schedule | Dependency | Infrastructure | 13 | 5 | Insufficient capacity in the cabling system for needed fiber connection | 0 | Americas | IT/Solution | 2014 | June | 559039
590 | Schedule | Dependency | Infrastructure | 13 | 7 | Scheduling based on small pilot installation, but full roll out backed up the help desk and project was delayed. | 0 | Americas | IT/Solution | 2014 | April | 282633
591 | Schedule | Dependency | Infrastructure | 15 | 3 | During required short visits, the network was sometimes down for an indefinite amount of time, requiring a second trip | 0 | Americas | IT/Solution | 2018 | May | 591615
592 | Schedule | Dependency | Infrastructure | 14 | 7 | Last minute infrastructure changes and conflict with another deployment | 0 | Americas | IT/Solution | 2005 | June | 591010
593 | Schedule | Dependency | Infrastructure | 17 | 5 | Current processes did not scale as needed by project, requiring redesign | 0 | Americas | Prod. Dev. | 2005 | October | 704684
594 | Schedule | Dependency | Infrastructure | 10 | 6 | Infrasturcture changes made mid-project | 0 | Americas | Prod. Dev. | 2009 | September | 673110
595 | Schedule | Dependency | Infrastructure | 12 | 7 | Compilers and open source libraries needed were not available | 0 | Americas | IT/Solution | 2016 | April | 316152
596 | Schedule | Dependency | Legal | 17 | 5 | Iidviduals who must to approve work are unavailable | 0 | Americas | IT/Solution | 2015 | July | 1139884
597 | Schedule | Dependency | Project | 18 | 3 | Other organizations are late with promised work, then deliverables do not work as expected. | 3 | Africa | Prod. Dev. | 2002 | July | 624150
598 | Schedule | Estimates | Deadline | 12 | 3 | Customer insists on deadline shorter than plan. Attempted, but not possible. | 0 | Americas | IT/Solution | 2016 | September | 699300
599 | Schedule | Estimates | Deadline | 18 | 6 | Schedule set without first doing a project feasibility and capacity analysis | 0 | Americas | IT/Solution | 2004 | January | 853056
600 | Schedule | Estimates | Judgment | 18 | 6 | Plans for project for new customer based on similar work for existing customer. Relationships, infrastructure, jargon and other differences took 50% more effort. | 0 | Americas | IT/Solution | 2014 | September | 711216
601 | Schedule | Estimates | Judgment | 18 | 4 | Estimated level of effort for project was way too optimistic | 0 | Americas | IT/Solution | 2009 | December | 1374516
602 | Schedule | Estimates | Judgment | 12 | 4 | Development scheduled in parallel leads to frequent rework. | 0 | Americas | Prod. Dev. | 2010 | January | 249828
603 | Schedule | Estimates | Judgment | 11 | 4 | Headcount required for document management was grossly underestimated | 0 | Americas | IT/Solution | 2003 | December | 705562
604 | Schedule | Estimates | Learning | 15 | 6 | Unavailability of skilled resources | 0 | Americas | IT/Solution | 2007 | August | 776220
605 | Schedule | Estimates | Learning | 16 | 4 | The team member lacked the right skills for a development job | 0 | Americas | Prod. Dev. | 2015 | October | 753376
606 | Schedule | Estimates | Learning | 11 | 6 | 3 week test took 7 due to learning curve and ramp time. | 0 | Americas | Prod. Dev. | 2009 | December | 860893
607 | Schedule | Estimates | Learning | 18 | 3 | New hires used; time for training. | 3 | Africa | Prod. Dev. | 2015 | June | 669132
608 | Schedule | Estimates | Learning | 10 | 7 | Field Engineers experience a long learning curve | 0 | Americas | Prod. Dev. | 2003 | December | 692230
609 | Scope | Change | Creep | 11 | 5 | People who would deliver training seeking perfection; required extra work and was late. | 0 | Americas | IT/Solution | 2005 | March | 734701
610 | Scope | Change | Creep | 13 | 6 | One patch was almost completely tested when it was decided to fix another bug | 3 | Africa | IT/Solution | 2005 | June | 327587
611 | Scope | Change | Creep | 18 | 5 | Half way through the project the client changed the scope by adding additional work | 0 | Americas | IT/Solution | 2011 | March | 1280340
612 | Scope | Change | Creep | 18 | 6 | Several applications were changed due to change in project requirements | 3 | Africa | IT/Solution | 2013 | October | 848646
613 | Scope | Change | Creep | 10 | 3 | Mid project expansion to include account receivable process | 0 | Americas | IT/Solution | 2013 | May | 788130
614 | Scope | Change | Creep | 13 | 3 | Executives added a new requirement late | 3 | Africa | IT/Solution | 2002 | April | 302913
615 | Scope | Change | Creep | 17 | 5 | Late change to motorized door led to redesign, parts delay, and conflict with other work | 0 | Americas | IT/Solution | 2010 | October | 488138
616 | Scope | Change | Creep | 10 | 7 | Requested scope expansion took a month to assess and was ultimately rejected | 0 | Americas | IT/Solution | 2010 | August | 559240
617 | Scope | Change | Creep | 11 | 3 | Twelve additional design and construction tasks were added late | 0 | Americas | IT/Solution | 2005 | September | 277222
618 | Scope | Change | Creep | 12 | 7 | Client's insisted on the use of "the latest technology | 0 | Americas | IT/Solution | 2007 | December | 431772
619 | Scope | Change | Creep | 14 | 6 | Project priorities and criteria are unclear through much of the project, causing lots of unneeded work. | 0 | Americas | Prod. Dev. | 2016 | May | 366436
620 | Scope | Change | Creep | 18 | 4 | Changing product definition and poor estimation of effort | 0 | Americas | Prod. Dev. | 2019 | December | 417150
621 | Scope | Change | Creep | 17 | 4 | Project priorities and criteria are unclear through much of the project, causing lots of unneeded work. | 0 | Americas | IT/Solution | 2016 | July | 475864
622 | Scope | Change | Creep | 17 | 7 | Database used for system changed in mid project; more resources used and delay. | 0 | Americas | IT/Solution | 2017 | June | 1342456
623 | Scope | Change | Creep | 12 | 3 | Design stability poor, requiring rework and late changes for manufacturing. | 0 | Americas | Prod. Dev. | 2005 | April | 877020
624 | Scope | Change | Creep | 15 | 4 | Specifications poorly defined until late in the project. | 3 | Africa | Prod. Dev. | 2007 | March | 458670
625 | Scope | Change | Creep | 16 | 4 | Modifying requirements in the middle of a phase | 0 | Americas | Prod. Dev. | 2015 | February | 812896
626 | Scope | Change | Dependency | 18 | 7 | Operating system release expected canceled; project forced to use prior version. | 0 | Americas | Prod. Dev. | 2012 | June | 820728
627 | Scope | Change | Dependency | 18 | 4 | New CPU chip to be used in product assumed same as old, but requires additional heat sink and mechanical design work. | 0 | Americas | Prod. Dev. | 2013 | November | 602982
628 | Scope | Change | Dependency | 10 | 6 | As product increases, new packaging and unexpected shielding needed. | 0 | Americas | Prod. Dev. | 2016 | July | 383740
629 | Scope | Change | Gap | 11 | 4 | User specifications not defined until late in the project. | 0 | Americas | IT/Solution | 2010 | June | 748220
630 | Scope | Change | Gap | 10 | 4 | Work done by contractors with too little information; components require rework. | 0 | Americas | IT/Solution | 2005 | February | 269920
631 | Scope | Change | Gap | 16 | 6 | The programmer hadn’t understood how certain parts of the program date-logic worked and hadn’t asked for any assistance. | 0 | Americas | IT/Solution | 2015 | February | 871072
632 | Scope | Change | Gap | 16 | 5 | Original scope missed supply chain issues; could not be used without changes | 3 | Africa | IT/Solution | 2017 | February | 542048
633 | Scope | Change | Gap | 14 | 3 | Scope change adding new categories and fees | 0 | Americas | IT/Solution | 2011 | May | 700560
634 | Scope | Change | Gap | 11 | 3 | Enterprise Portal improperly specified | 0 | Americas | IT/Solution | 2017 | January | 467093
635 | Scope | Change | Gap | 10 | 5 | Major Scope change during the design phase due to the complex processes involved | 0 | Americas | IT/Solution | 2002 | November | 692100
636 | Scope | Change | Gap | 14 | 5 | Poor project planning and missed end-user requirements | 0 | Americas | IT/Solution | 2015 | August | 631064
637 | Scope | Change | Gap | 18 | 3 | Project had aggressive timeline and due to rush details were poorly defined | 0 | Americas | IT/Solution | 2008 | June | 518112
638 | Scope | Change | Gap | 10 | 4 | Inexperience of the leader resulted in overcommitment and little planning | 0 | Americas | IT/Solution | 2005 | July | 664760
639 | Scope | Change | Gap | 18 | 7 | Design documentation was signed off by users, but had fatal flaws | 0 | Americas | IT/Solution | 2012 | August | 1423044
640 | Scope | Change | Gap | 13 | 7 | Substrate material was initially specified incorrectly and had to be reordered | 0 | Americas | IT/Solution | 2016 | April | 1015482
641 | Scope | Change | Gap | 17 | 3 | Customer did not describe in detail what exactly was needed | 0 | Americas | IT/Solution | 2007 | March | 1307759
642 | Scope | Change | Gap | 15 | 4 | Construction of subdivision was initiated using old maps | 0 | Americas | IT/Solution | 2007 | June | 956715
643 | Scope | Change | Gap | 17 | 6 | Requested requirement proved impossible, but was not actually needed | 0 | Americas | Prod. Dev. | 2007 | May | 815269
644 | Scope | Change | Gap | 10 | 3 | Multiple team program with some work not clearly delegated. Assigned and added late. | 0 | Americas | Prod. Dev. | 2007 | November | 619480
645 | Scope | Change | Gap | 11 | 6 | Scoping set and estimated based on just one set of data from one customer | 3 | Africa | Prod. Dev. | 2008 | October | 337370
646 | Scope | Change | Gap | 13 | 4 | The business analyst failed to fully understand the scientist’s requirements | 0 | Americas | Prod. Dev. | 2007 | September | 857532
647 | Scope | Change | Gap | 12 | 3 | Flaw was found in the functional design | 0 | Americas | Prod. Dev. | 2010 | February | 696792
648 | Scope | Change | Gap | 12 | 4 | System only partly specified until near the end of the project. | 0 | Americas | IT/Solution | 2016 | May | 337896
649 | Scope | Change | Gap | 12 | 6 | Poor prework led to assumption that project would be simpler than it was | 0 | Americas | IT/Solution | 2016 | February | 769944
650 | Scope | Change | Gap | 12 | 3 | Complexity not understood or documented. Required work added. | 0 | Americas | Prod. Dev. | 2017 | March | 801084
651 | Scope | Change | Gap | 14 | 7 | Product developed for multiple platforms, but works only on 2. Delayed to fix some, but others dropped at project end. | 3 | Africa | Prod. Dev. | 2010 | August | 1075536
652 | Scope | Change | Gap | 16 | 7 | Faulty market & competitive analysis information discovered late; led to changes | 0 | Americas | Prod. Dev. | 2012 | May | 1246656
653 | Scope | Change | Gap | 17 | 7 | Lack of initial consensus on the scope | 0 | Americas | Prod. Dev. | 2011 | April | 1339991
654 | Scope | Defect | Hardware | 17 | 6 | New technology used, seeking faster results. It does not work and leads to redesign and rework. | 3 | Africa | IT/Solution | 2019 | July | 1176196
655 | Scope | Defect | Hardware | 18 | 3 | Instrument system for customer based on Intel PC. New system released; fails to work as older model did. Finally installed with salvaged older PC. | 0 | Americas | IT/Solution | 2007 | September | 530532
656 | Scope | Defect | Hardware | 11 | 7 | Testing facilities were too low-tech to verify automated systems | 0 | Americas | IT/Solution | 2019 | February | 508827
657 | Scope | Defect | Hardware | 18 | 5 | Components do not work as documented. Replacements and software workarounds required. | 0 | Americas | Prod. Dev. | 2007 | March | 422964
658 | Scope | Defect | Hardware | 11 | 6 | System with new components fails in final tests. Getting older components difficult. | 2 | Eur/ME | Prod. Dev. | 2018 | February | 474617
659 | Scope | Defect | Hardware | 17 | 7 | Late test results came back negative | 2 | Eur/ME | Prod. Dev. | 2006 | June | 412148
660 | Scope | Defect | Hardware | 15 | 7 | Insufficient length of anchor bolts protruding from the concrete foundation to allow the base plate nuts to fully engage | 0 | Americas | Prod. Dev. | 2009 | November | 961395
661 | Scope | Defect | Hardware | 18 | 3 | During the feedback/review phase it was noticed that the numbers were incorrect | 0 | Americas | Prod. Dev. | 2007 | June | 1165806
662 | Scope | Defect | Hardware | 10 | 4 | After the first run was lost, a third run was added | 0 | Americas | Prod. Dev. | 2010 | October | 489660
663 | Scope | Defect | Hardware | 12 | 7 | First production run problems necessitated adding a third run | 0 | Americas | Prod. Dev. | 2014 | May | 364704
664 | Scope | Defect | Hardware | 10 | 5 | Deliverable fails final test; rework to fix. | 0 | Americas | Prod. Dev. | 2019 | August | 328020
665 | Scope | Defect | Integration | 14 | 6 | All components pass tests, but assembled system fails. Rework causes delay. | 0 | Americas | Prod. Dev. | 2001 | September | 824334
666 | Scope | Defect | Integration | 13 | 6 | Failure to not carefully proofread the documents to be produced before printing | 3 | Africa | Prod. Dev. | 2015 | April | 474526
667 | Scope | Defect | Integration | 13 | 5 | Process does not scale to production; changes required. | 0 | Americas | Prod. Dev. | 2007 | November | 542958
668 | Scope | Defect | Software | 18 | 7 | Problem detected in production due to transaction volume not detected in test | 0 | Americas | IT/Solution | 2010 | February | 786762
669 | Scope | Defect | Software | 16 | 3 | Bug surfaced one day after implementation | 0 | Americas | IT/Solution | 2007 | January | 822784
670 | Scope | Defect | Software | 17 | 4 | Purchased software is limited and inflexible. Workarounds and additional software required. | 3 | Africa | IT/Solution | 2004 | January | 704191
671 | Scope | Defect | Software | 12 | 4 | Late testing failure | 0 | Americas | IT/Solution | 2006 | March | 506400
672 | Resource | Outsourcing | Late or poor output | 18 | 4 | Vendor was unable to control the environment: work had to be repeated | 3 | Africa | Prod. Dev. | 2003 | September | 484362
673 | Schedule | Estimates | Judgment | 12 | 7 | Complexity of the investigation was badly underestimated | 2 | Eur/ME | Prod. Dev. | 2001 | February | 893412
674 | Schedule | Estimates | Learning | 14 | 6 | Inexperienced staff | 2 | Eur/ME | Prod. Dev. | 2019 | March | 453362
675 | Schedule | Estimates | Learning | 13 | 3 | The team in Germany did not have the resources or expertise to do testing in key intermediate step | 2 | Eur/ME | Prod. Dev. | 2015 | June | 907543
676 | Schedule | Dependency | Infrastructure | 12 | 4 | Support offering requires more overhead to span several OS versions | 0 | Americas | Prod. Dev. | 2007 | February | 251532
677 | Scope | Change | Gap | 17 | 3 | Testing requierments poorly defined, so functionality deferred to phase 2 | 3 | Africa | IT/Solution | 2019 | June | 481202
678 | Resource | Outsourcing | Late or poor output | 10 | 3 | Contaminated specimen for cell culture had to be replaced by the contract organization | 3 | Africa | Prod. Dev. | 2016 | April | 758190
679 | Resource | Outsourcing | Late or poor output | 16 | 6 | Subcontractor failed to understand technology and requirements | 0 | Americas | IT/Solution | 2008 | November | 1232720
680 | Scope | Change | Creep | 11 | 5 | Late change required new hardware and 2 phase delivery | 3 | Africa | Prod. Dev. | 2008 | July | 511610
681 | Scope | Defect | Hardware | 18 | 6 | Defective component--Bugs had to be fixed | 0 | Americas | Prod. Dev. | 2015 | February | 362520
682 | Resource | People | Loss | 13 | 5 | Project lost irreplaceable experts | 0 | Americas | IT/Solution | 2008 | August | 482508
683 | Schedule | Dependency | Infrastructure | 16 | 7 | Too few disc drives, and insufficient "owned" space | 2 | Eur/ME | Prod. Dev. | 2005 | July | 1090080
684 | Schedule | Delay | Hardware | 12 | 3 | There was a high fluctuation of pressure that nobody could explain | 2 | Eur/ME | Prod. Dev. | 2013 | February | 839724
685 | Resource | Outsourcing | Delayed start | 16 | 6 | Contractors late and unreliable | 0 | Americas | Prod. Dev. | 2011 | June | 1245488
686 | Scope | Defect | Hardware | 10 | 4 | Needed plants were set too far apart to fertilize initially | 2 | Eur/ME | Prod. Dev. | 2009 | July | 548660
687 | Resource | People | Loss | 13 | 6 | Workforce reduction left only 3 developers were remaining on the project | 2 | Eur/ME | Prod. Dev. | 2001 | November | 994942
688 | Schedule | Delay | Parts | 11 | 3 | Materials did not pass quality inspection | 3 | Africa | Prod. Dev. | 2008 | June | 811338
689 | Schedule | Estimates | Learning | 13 | 7 | Developer had limited experience | 3 | Africa | Prod. Dev. | 2002 | August | 914771
690 | Scope | Change | Creep | 12 | 6 | Late requirement changes and shifting priorities | 0 | Americas | Prod. Dev. | 2007 | July | 368232
691 | Scope | Change | Creep | 18 | 6 | New Requirement addition during the middle of the project | 3 | Africa | Prod. Dev. | 2002 | March | 907416
692 | Resource | Outsourcing | Late or poor output | 11 | 3 | Contract lab failed to inform us that they had trouble with a genotyping assay | 0 | Americas | Prod. Dev. | 2007 | August | 763884
693 | Resource | Outsourcing | Late or poor output | 10 | 6 | Chinese IT company to guarantee the quality of their work | 2 | Eur/ME | IT/Solution | 2017 | December | 538990
694 | Resource | People | Late start | 10 | 7 | "Rolling Sledgehammer" Last project ties up (and exhausts) staff; next project starts late and slow. | 0 | Americas | Prod. Dev. | 2007 | October | 586830
695 | Schedule | Delay | Decision | 11 | 5 | All stakeholders approve project individually, but at meeting together for final approval, disagreements changed and delayed the project. | 3 | Africa | IT/Solution | 2002 | March | 488906
696 | Schedule | Delay | Information | 14 | 6 | Communications problems and misinterpretation of the requirements in India | 0 | Americas | IT/Solution | 2007 | August | 656362
697 | Schedule | Delay | Parts | 11 | 3 | Supplier was unable to make a sample correctly | 3 | Africa | Prod. Dev. | 2009 | September | 515801
698 | Schedule | Estimates | Judgment | 14 | 5 | Estimated level of effort for project was way too optimistic | 2 | Eur/ME | IT/Solution | 2012 | October | 531510
699 | Scope | Change | Creep | 13 | 7 | Late change to motorized door led to redesign, parts delay, and conflict with other work | 0 | Americas | IT/Solution | 2007 | November | 812331
700 | Scope | Change | Dependency | 11 | 4 | New CPU chip to be used in product assumed same as old, but requires additional heat sink and mechanical design work. | 2 | Eur/ME | Prod. Dev. | 2019 | December | 681065
701 | Scope | Defect | Hardware | 18 | 4 | Late test results came back negative | 3 | Africa | Prod. Dev. | 2007 | December | 1327446
702 | Scope | Defect | Software | 15 | 5 | Problem detected in production due to transaction volume not detected in test | 2 | Eur/ME | IT/Solution | 2003 | December | 343515
703 | Resource | People | Loss | 10 | 7 | Resources committed to projects reassigned to new projects and not replaced. | 0 | Americas | Prod. Dev. | 2007 | November | 429570
704 | Schedule | Delay | Parts | 14 | 5 | Manufacturing problem with key component | 2 | Eur/ME | Prod. Dev. | 2003 | July | 331562
705 | Scope | Change | Gap | 16 | 7 | Lack of research and analysis on a key compoent of the deliverable | 0 | Americas | Prod. Dev. | 2012 | August | 1188096
706 | Scope | Defect | Hardware | 13 | 5 | Components were incorrectly measured | 0 | Americas | IT/Solution | 2016 | December | 983866
707 | Resource | People | Queuing | 10 | 3 | A single person was responsible for key reports many wait in queue | 2 | Eur/ME | IT/Solution | 2018 | June | 538350
708 | Resource | People | Temp loss | 10 | 5 | Key resource was pulled off the project twice to fix bugs in a previous product | 2 | Eur/ME | Prod. Dev. | 2015 | May | 684970
709 | Schedule | Estimates | Judgment | 12 | 5 | Estimates in proposal too short. Testing takes more time and is highly variable. | 0 | Americas | IT/Solution | 2013 | November | 489048
710 | Scope | Change | Creep | 15 | 7 | Project end date moved; unrealistic | 0 | Americas | IT/Solution | 2007 | March | 448485
711 | Resource | People | Queuing | 12 | 4 | People were allocated to too many projects and bottlenecks developed | 0 | Americas | IT/Solution | 2007 | December | 793392
712 | Resource | People | Queuing | 17 | 7 | Key person not available when needed. | 0 | Americas | Prod. Dev. | 2016 | April | 579343
713 | Resource | People | Temp loss | 12 | 5 | Unannounced audit in mid-project caused delay to prepare and participate. | 0 | Americas | Prod. Dev. | 2007 | March | 649176
714 | Schedule | Delay | Hardware | 13 | 4 | Flood shuts down data center. Delay to restore power and clean up. | 2 | Eur/ME | IT/Solution | 2014 | December | 333411
715 | Schedule | Delay | Parts | 12 | 3 | Parts delivery delay | 3 | Africa | Prod. Dev. | 2010 | November | 414768
716 | Scope | Change | Gap | 10 | 4 | Lack of a solid plan, or any formal scoping | 2 | Eur/ME | Prod. Dev. | 2019 | December | 606550
717 | Scope | Defect | Software | 15 | 6 | No problems in test, but production problems required overtime to fix | 0 | Americas | IT/Solution | 2007 | January | 600510
718 | Resource | Money | Limitation | 11 | 3 | Layoffs in mid-project | 3 | Africa | IT/Solution | 2016 | May | 780945
719 | Resource | Money | Limitation | 11 | 4 | Client slashed the original budget | 0 | Americas | IT/Solution | 2014 | December | 673464
720 | Resource | Money | Limitation | 11 | 3 | Inadequate staffing | 3 | Africa | Prod. Dev. | 2010 | March | 487124
721 | Resource | Outsourcing | Delayed start | 14 | 3 | Delays due to bidding issues and protests | 0 | Americas | IT/Solution | 2007 | June | 592886
722 | Resource | Outsourcing | Delayed start | 12 | 7 | Vendor failed to confirm start date, resulting in delay | 0 | Americas | Prod. Dev. | 2007 | March | 395868
723 | Resource | Outsourcing | Delayed start | 17 | 7 | Failed to get client sign-off for work done in India | 2 | Eur/ME | IT/Solution | 2012 | August | 1272501
724 | Resource | Outsourcing | Late or poor output | 17 | 4 | Consultant who worked on benefits was taken off the project | 2 | Eur/ME | IT/Solution | 2002 | February | 526133
725 | Resource | Outsourcing | Late or poor output | 16 | 4 | Freelancer hired was a nutjob, and lacked the correct skills | 2 | Eur/ME | IT/Solution | 2011 | April | 789840
726 | Resource | Outsourcing | Late or poor output | 17 | 7 | Management pushed plans to outsource printing operations, causing problems | 2 | Eur/ME | IT/Solution | 2018 | January | 1268540
727 | Resource | Outsourcing | Late or poor output | 14 | 3 | Contractor was uncooperative and late | 0 | Americas | IT/Solution | 2007 | June | 930216
728 | Resource | Outsourcing | Late or poor output | 16 | 5 | Consulting agency had not fulfilled its obligations under the terms of the contract | 2 | Eur/ME | IT/Solution | 2010 | July | 1205712
729 | Resource | Outsourcing | Late or poor output | 13 | 3 | Outsourcing delayed the order entry process for all U.S. Based customers | 2 | Eur/ME | IT/Solution | 2005 | May | 1019707
730 | Resource | People | Late start | 13 | 5 | Legacy systems not retired as planned; project team tied up in unplanned support. | 3 | Africa | IT/Solution | 2006 | May | 347126
731 | Resource | People | Late start | 17 | 6 | Delay in getting a firewall PM and a firewall engineer assigned | 3 | Africa | IT/Solution | 2011 | September | 840956
732 | Resource | People | Late start | 14 | 5 | Resources were not available at the time the project started | 0 | Americas | IT/Solution | 2007 | May | 999866
733 | Resource | People | Late start | 10 | 7 | Project has funding, but limited staff delays start. | 2 | Eur/ME | Prod. Dev. | 2012 | October | 352570
734 | Resource | People | Loss | 15 | 4 | Critical skills unique in the head of a 62-yearl old programmer who had a heart attack | 0 | Americas | IT/Solution | 2017 | August | 430185
735 | Resource | People | Loss | 18 | 6 | Lost a key programmer | 0 | Americas | IT/Solution | 2007 | June | 966870
736 | Resource | People | Loss | 12 | 5 | Workforce reduction left only 3 developers were remaining on the project | 3 | Africa | Prod. Dev. | 2011 | January | 464556
737 | Resource | People | Loss | 10 | 6 | Key contributor left the company | 0 | Americas | Prod. Dev. | 2007 | November | 727030
738 | Resource | People | Motivation | 12 | 7 | Technical lead had a “command and control" style that caused animosity | 3 | Africa | IT/Solution | 2012 | August | 601740
739 | Resource | People | Queuing | 14 | 6 | Parallel tasks require resources beyond what is available | 0 | Americas | IT/Solution | 2017 | October | 680554
740 | Resource | People | Queuing | 10 | 4 | There were not enough study directors to conduct all the studies needed | 3 | Africa | Prod. Dev. | 2013 | April | 787300
741 | Resource | People | Queuing | 15 | 6 | Six other projects required time and effort from our assigned engineer | 0 | Americas | Prod. Dev. | 2007 | August | 650085
742 | Resource | People | Queuing | 14 | 7 | Project was dependent on onekey resource and had to wait | 2 | Eur/ME | Prod. Dev. | 2001 | July | 731528
743 | Resource | People | Temp loss | 14 | 6 | Critical training had to be postponed because of a last minute emergency leave by the lead designer | 3 | Africa | Prod. Dev. | 2011 | September | 1028230
744 | Resource | People | Temp loss | 12 | 3 | Feedback from South Korea delayed due to a few months of sick leave by product manager | 0 | Americas | Prod. Dev. | 2007 | December | 364176
745 | Schedule | Delay | Hardware | 12 | 7 | There were not enough vendors who had the capacity to manufacture specialized tools | 0 | Americas | IT/Solution | 2007 | April | 659124
746 | Schedule | Delay | Information | 16 | 7 | The Project Lead did not hold the customer/business line accountable for their delay | 3 | Africa | Prod. Dev. | 2006 | May | 692048
747 | Schedule | Delay | Parts | 11 | 7 | Internal supplier problem; needed components delayed. | 3 | Africa | Prod. Dev. | 2002 | July | 561429
748 | Schedule | Delay | Parts | 16 | 5 | Materials did not pass quality inspection | 3 | Africa | Prod. Dev. | 2002 | February | 884592
749 | Schedule | Delay | Parts | 14 | 7 | New technology was analyzed and didn’t meet the needs | 0 | Americas | Prod. Dev. | 2011 | July | 662578
750 | Schedule | Dependency | Infrastructure | 11 | 4 | Foundation was inadaquate and needed upgrading | 0 | Americas | IT/Solution | 2013 | April | 651222
751 | Schedule | Dependency | Legal | 14 | 3 | Issues found with the SOX documents provided by the legal team | 2 | Eur/ME | IT/Solution | 2002 | December | 1049594
752 | Schedule | Dependency | Project | 11 | 5 | Reviews delayed on complex program, waiting for last team to finish phase work. | 0 | Americas | Prod. Dev. | 2010 | July | 667084
753 | Schedule | Dependency | Project | 17 | 6 | Server expansion project dependent on delayed tape library decommissioning | 2 | Eur/ME | IT/Solution | 2006 | June | 899861
754 | Schedule | Estimates | Deadline | 17 | 3 | Work was intentionally underestimatged to win the contract | 3 | Africa | IT/Solution | 2017 | October | 672452
755 | Schedule | Estimates | Judgment | 16 | 6 | Chronic optimism on completion dates for work | 0 | Americas | Prod. Dev. | 2006 | September | 657504
756 | Schedule | Estimates | Learning | 11 | 4 | Key staff member lacked knowledge, experience and ability | 0 | Americas | IT/Solution | 2007 | January | 750365
757 | Schedule | Estimates | Learning | 11 | 6 | Software engineers, not technicians skilled in the work, were used to complete product testing | 0 | Americas | Prod. Dev. | 2007 | May | 285703
758 | Schedule | Estimates | Learning | 11 | 7 | Developer had limited experience | 3 | Africa | Prod. Dev. | 2007 | June | 691526
759 | Scope | Change | Creep | 16 | 7 | Big scope change in the middle of the project | 3 | Africa | Prod. Dev. | 2017 | September | 833648
760 | Scope | Change | Creep | 10 | 7 | Late requirement changes and shifting priorities | 3 | Africa | Prod. Dev. | 2015 | June | 650100
761 | Scope | Change | Creep | 12 | 4 | New Requirement addition during the middle of the project | 3 | Africa | Prod. Dev. | 2004 | November | 359304
762 | Scope | Change | Creep | 16 | 5 | Extra release added just a month before a major upgrade go live date | 0 | Americas | Prod. Dev. | 2004 | March | 393872
763 | Scope | Change | Creep | 12 | 3 | Two new Features were introduced midway during development | 2 | Eur/ME | Prod. Dev. | 2008 | July | 265320
764 | Scope | Change | Gap | 14 | 7 | Problems associated with confidential patient information in transit without a tracking mechanism surfaced during the project | 2 | Eur/ME | IT/Solution | 2004 | April | 887950
765 | Scope | Change | Gap | 11 | 5 | Late change required to meet code | 0 | Americas | IT/Solution | 2007 | March | 223938
766 | Scope | Change | Gap | 11 | 3 | Project required a change to the current website technology | 0 | Americas | IT/Solution | 2013 | April | 266420
767 | Scope | Change | Gap | 17 | 5 | Responsibilities not defined well for project | 0 | Americas | Prod. Dev. | 2007 | March | 915705
768 | Scope | Change | Gap | 12 | 6 | Lack of understanding by the manager of the system forced the project to replan | 2 | Eur/ME | Prod. Dev. | 2008 | June | 927696
769 | Scope | Change | Gap | 11 | 5 | A critical issue was neglected resulting in a significant scope gap | 0 | Americas | Prod. Dev. | 2009 | September | 796114
770 | Scope | Change | Gap | 10 | 3 | Scope gaps became apparent when legal department was consulted too late | 0 | Americas | Prod. Dev. | 2012 | July | 390980
771 | Scope | Change | Gap | 13 | 3 | Instructions to contract testing facility were too vague and tests had to be repeated | 0 | Americas | Prod. Dev. | 2019 | December | 631670
772 | Scope | Change | Gap | 14 | 3 | Flaw found in functional design specifications | 0 | Americas | Prod. Dev. | 2007 | June | 677292
773 | Scope | Change | Gap | 17 | 4 | Some of the cross functional teams were not involved early enough | 0 | Americas | Prod. Dev. | 2007 | July | 1318554
774 | Scope | Change | Gap | 13 | 4 | Functional design was not properly done, due to limited access to users; led to changes | 0 | Americas | Prod. Dev. | 2009 | March | 806767
775 | Scope | Change | Gap | 15 | 3 | Development team in France was unable to convey their requests, issues and concerns | 0 | Americas | IT/Solution | 2018 | June | 558060
776 | Scope | Defect | Hardware | 11 | 3 | Half way through the upgrade; the new processor failed | 0 | Americas | IT/Solution | 2007 | August | 354981
777 | Scope | Defect | Integration | 14 | 5 | In large system conversion, new applications cannot find and work with existing data as expected. Lots of redirecting and conversion is required. | 0 | Americas | IT/Solution | 2006 | May | 535360
778 | Scope | Defect | Software | 15 | 7 | Memory problems not detected in test caused server crashes; backed out for more than a month | 0 | Americas | IT/Solution | 2007 | August | 300045
779 | Scope | Defect | Software | 16 | 4 | Issues discovered late in testing | 2 | Eur/ME | IT/Solution | 2005 | March | 1273392
780 | Scope | Defect | Software | 14 | 6 | Errors were discovered in reports that had to be fixed following release | 0 | Americas | IT/Solution | 2014 | December | 962402
781 | Schedule | Delay | Information | 12 | 3 | Software is developed in Israel. In a week, there was less than one working day for teleconference and war made it impractical to travel. Needed info was always late. | 0 | Americas | IT/Solution | 2007 | May | 580512
782 | Scope | Change | Creep | 13 | 3 | Scope definition was poor and change was rampant | 0 | Americas | IT/Solution | 2007 | April | 833495
783 | Resource | Outsourcing | Late or poor output | 11 | 3 | Research and development were outsourced, but the relationship was not managed well, and all work was ultimately redone | 0 | Americas | Prod. Dev. | 2014 | October | 510378
784 | Scope | Change | Creep | 16 | 3 | System for expense analysis expanded into redesign of most major internal systems | 2 | Eur/ME | Prod. Dev. | 2016 | August | 638592
785 | Resource | Outsourcing | Late or poor output | 18 | 4 | Deliverable received was inadequate | 0 | Americas | IT/Solution | 2007 | February | 1124082
786 | Scope | Change | Gap | 17 | 4 | There was a design flaw in the roof detail | 2 | Eur/ME | IT/Solution | 2015 | September | 617202
787 | Schedule | Estimates | Deadline | 13 | 4 | Apartments were sold before construction begins with commitments based on requests, not planning | 2 | Eur/ME | IT/Solution | 2004 | May | 940082
788 | Scope | Change | Creep | 13 | 5 | Project specifications had changed and the material needed during the design phase had to be imported from overseas | 2 | Eur/ME | Prod. Dev. | 2005 | October | 620919
789 | Scope | Change | Gap | 16 | 6 | Scope initially consisted only of general objectives | 0 | Americas | IT/Solution | 2007 | July | 878384
790 | Resource | People | Loss | 13 | 7 | Manager quit his job because of his mother's illness | 2 | Eur/ME | IT/Solution | 2007 | July | 1026792
791 | Scope | Change | Gap | 18 | 3 | Delay due to testing requirements uncovered late and shifting priorities | 0 | Americas | IT/Solution | 2007 | January | 748134
792 | Resource | People | Late start | 16 | 6 | Project was new to the company and needed to hire people and develop a team | 0 | Americas | Prod. Dev. | 2007 | October | 608080
793 | Scope | Change | Creep | 11 | 3 | Initial scoping for a minor upgrade was not sufficient | 2 | Eur/ME | Prod. Dev. | 2018 | August | 234146
794 | Scope | Change | Creep | 15 | 7 | Migration project (to NT from UNIX) saddled with increasing list of changes. | 0 | Americas | IT/Solution | 2015 | May | 1094730
795 | Scope | Defect | Software | 14 | 7 | After the upgrade was released, issues with the software were discovered | 0 | Americas | IT/Solution | 2007 | March | 880460
796 | Scope | Change | Creep | 11 | 4 | Additional scope added; slipped project | 2 | Eur/ME | IT/Solution | 2017 | March | 341781
797 | Resource | People | Temp loss | 10 | 7 | Product manager was out due to sick leave (a few months long) | 0 | Americas | Prod. Dev. | 2012 | November | 389100
798 | Resource | People | Motivation | 13 | 5 | Technical lead had a “command and control" style that caused animosity | 2 | Eur/ME | IT/Solution | 2014 | August | 272207
799 | Resource | People | Temp loss | 15 | 3 | Critical training had to be postponed because of a last minute emergency leave by the lead designer | 0 | Americas | Prod. Dev. | 2014 | September | 846780
800 | Scope | Change | Creep | 10 | 7 | Extra release added just a month before a major upgrade go live date | 0 | Americas | Prod. Dev. | 2019 | October | 552580
801 | Scope | Change | Gap | 17 | 5 | Development team in France was unable to convey their requests, issues and concerns | 0 | Americas | IT/Solution | 2003 | June | 689452
802 | Scope | Defect | Software | 15 | 3 | Errors were discovered in reports that had to be fixed following release | 0 | Americas | IT/Solution | 2007 | June | 836175
803 | Schedule | Estimates | Learning | 12 | 5 | Field Engineers experience a long learning curve | 0 | Americas | Prod. Dev. | 2010 | April | 855888
804 | Scope | Change | Creep | 18 | 4 | People who would deliver training seeking perfection; required extra work and was late. | 0 | Americas | IT/Solution | 2001 | March | 1337220
805 | Scope | Change | Creep | 15 | 4 | Executives added a new requirement late | 0 | Americas | IT/Solution | 2010 | November | 819240
806 | Resource | Outsourcing | Delayed start | 18 | 5 | Unexpectedly high demand requires outlisde help | 2 | Eur/ME | IT/Solution | 2010 | October | 453708
807 | Schedule | Estimates | Judgment | 15 | 7 | Recertification of updated applications took longer than hoped | 0 | Americas | IT/Solution | 2007 | August | 995250
808 | Scope | Change | Creep | 18 | 4 | Project schedule was revised user interface requirements which increased project scope | 0 | Americas | Prod. Dev. | 2006 | May | 477180
809 | Scope | Change | Gap | 18 | 5 | Lack of testing of older WWW browser versions led to custom coding being written before application could be used. | 0 | Americas | IT/Solution | 2007 | May | 1073322
810 | Scope | Change | Gap | 15 | 6 | Incorrect input data provided | 2 | Eur/ME | IT/Solution | 2008 | March | 417915
811 | Scope | Change | Gap | 11 | 6 | The database assigned for the client did not have sufficient free space for their growing accounts | 0 | Americas | IT/Solution | 2005 | January | 854216
812 | Scope | Change | Gap | 11 | 3 | In testing, it is discovered that 50K words were left untranslated due to updates and changes | 2 | Eur/ME | Prod. Dev. | 2010 | December | 334675
813 | Resource | Money | Limitation | 18 | 6 | lack of staff availability due to company down-sizing | 0 | Americas | IT/Solution | 2007 | February | 917766
814 | Resource | Outsourcing | Delayed start | 13 | 6 | Pricing negotiation stalls project work until resolved. | 2 | Eur/ME | IT/Solution | 2016 | March | 655200
815 | Resource | Outsourcing | Late or poor output | 10 | 3 | Outsourced tasks slipped, but not known until too late. | 0 | Americas | IT/Solution | 2015 | April | 429290
816 | Schedule | Delay | Hardware | 14 | 7 | Equipment needed for project came from a pool of hardware partly in another country. Critical hardware delayed by customs. | 0 | Americas | IT/Solution | 2007 | July | 791672
817 | Schedule | Delay | Parts | 10 | 5 | Parts availability and pricing volatile | 0 | Americas | Prod. Dev. | 2007 | July | 487890
818 | Schedule | Delay | Parts | 13 | 3 | Production problem with key component | 0 | Americas | Prod. Dev. | 2007 | March | 588913
819 | Scope | Change | Gap | 11 | 4 | Scope requirement discovered late in a construction project | 2 | Eur/ME | IT/Solution | 2012 | June | 347094
820 | Scope | Change | Gap | 17 | 4 | After test, additional requirements surface | 0 | Americas | Prod. Dev. | 2007 | November | 971057
821 | Scope | Defect | Software | 16 | 4 | Approvers reject required document | 2 | Eur/ME | Prod. Dev. | 2001 | August | 951040
822 | Schedule | Delay | Parts | 17 | 5 | A needed component was not very stable and only available from only one supplier. | 0 | Americas | Prod. Dev. | 2008 | October | 590070
823 | Scope | Defect | Hardware | 10 | 3 | A batch of servers came in with the wrong configurations; had to be fixed | 0 | Americas | IT/Solution | 2005 | December | 767900
824 | Resource | Outsourcing | Delayed start | 11 | 3 | Delayed start of work due to negotiation of contract. | 0 | Americas | Prod. Dev. | 2010 | April | 566357
825 | Resource | Outsourcing | Delayed start | 18 | 5 | Contractors late and unreliable | 2 | Eur/ME | Prod. Dev. | 2019 | June | 1144188
826 | Resource | Outsourcing | Late or poor output | 12 | 6 | Unrelaible and incopentent contractors | 0 | Americas | IT/Solution | 2007 | February | 896796
827 | Resource | Outsourcing | Late or poor output | 15 | 7 | Contractor installed smaller wire sizes than specified causing rework (after a fire) | 0 | Americas | IT/Solution | 2012 | December | 916050
828 | Resource | Outsourcing | Late or poor output | 14 | 7 | At start of project, insufficient research on the level of local expertise | 0 | Americas | IT/Solution | 2015 | October | 695002
829 | Resource | Outsourcing | Late or poor output | 13 | 6 | Outsourcing partner in Switzerland did unneeded work, delaying their inputs | 0 | Americas | Prod. Dev. | 2007 | August | 702858
830 | Resource | People | Late start | 12 | 7 | Supply chain expert needed was hard to find and engage. | 0 | Americas | Prod. Dev. | 2005 | August | 856380
831 | Resource | People | Loss | 10 | 7 | Key person gave notice more than a month before leaving, but nothing was done | 2 | Eur/ME | IT/Solution | 2003 | July | 376380
832 | Resource | People | Loss | 16 | 4 | The contractor half-way through the electrical job had a heart attack | 2 | Eur/ME | Prod. Dev. | 2010 | July | 394480
833 | Resource | People | Loss | 11 | 7 | Lead Engineer’s resignation | 0 | Americas | Prod. Dev. | 2018 | March | 665038
834 | Resource | People | Loss | 10 | 5 | Project leader resigns and is not replaced promptly | 0 | Americas | IT/Solution | 2007 | June | 278010
835 | Resource | People | Temp loss | 12 | 5 | The business analyst was unavailable for project work due to her backup role for a higher priority project | 0 | Americas | IT/Solution | 2007 | June | 457872
836 | Resource | People | Temp loss | 10 | 7 | Product manager was out due to sick leave (a few months long) | 2 | Eur/ME | Prod. Dev. | 2013 | January | 758340
837 | Schedule | Delay | Decision | 18 | 5 | Negotiation and training on a new tool took more time than planned | 2 | Eur/ME | IT/Solution | 2014 | November | 1024128
838 | Schedule | Delay | Hardware | 12 | 3 | It took a over month to get the custom designed equipment | 0 | Americas | IT/Solution | 2007 | July | 706812
839 | Schedule | Delay | Hardware | 11 | 5 | The vendor sent equipment to a wrong location in Michigan instead of the Bay Area | 0 | Americas | Prod. Dev. | 2009 | December | 790515
840 | Schedule | Delay | Information | 11 | 3 | Need to get input from one of the external group for specific info; late | 0 | Americas | IT/Solution | 2003 | March | 754809
841 | Schedule | Delay | Information | 10 | 3 | Lack of communication and trust between locations | 0 | Americas | IT/Solution | 2003 | July | 369500
842 | Schedule | Delay | Parts | 13 | 4 | Ship sinks with critical part; forced to replace with remanufactured old component | 0 | Americas | Prod. Dev. | 2007 | April | 1022801
843 | Schedule | Delay | Parts | 11 | 5 | Delay in getting material when a fermentation run crashes | 0 | Americas | Prod. Dev. | 2007 | November | 235312
844 | Schedule | Delay | Parts | 11 | 4 | Chip failed and had to be refabricated with changes | 0 | Americas | Prod. Dev. | 2018 | November | 726803
845 | Schedule | Delay | Parts | 12 | 6 | Inadequate water supply available to complete project, needed to be trucked in | 2 | Eur/ME | Prod. Dev. | 2017 | June | 730788
846 | Schedule | Dependency | Project | 12 | 3 | Lack of communication with the project team in Germany | 0 | Americas | Prod. Dev. | 2016 | November | 706296
847 | Schedule | Estimates | Deadline | 16 | 7 | Unrealistic deadline set; slips unavoidable. | 0 | Americas | IT/Solution | 2003 | May | 585600
848 | Schedule | Estimates | Judgment | 18 | 6 | Company underestimated the scope of the project | 2 | Eur/ME | IT/Solution | 2007 | December | 1140264
849 | Schedule | Estimates | Judgment | 13 | 6 | Expert opinion was 2 weeks; work took 8. | 2 | Eur/ME | Prod. Dev. | 2015 | February | 315406
850 | Schedule | Estimates | Judgment | 15 | 4 | Problems using trainers and training materials from Germany | 0 | Americas | Prod. Dev. | 2012 | December | 867525
851 | Schedule | Estimates | Learning | 15 | 6 | Inexperienced staff | 0 | Americas | IT/Solution | 2007 | May | 1061820
852 | Schedule | Estimates | Learning | 13 | 6 | Entry level employees lacked needed skill and experience | 0 | Americas | Prod. Dev. | 2008 | November | 632593
853 | Schedule | Estimates | Learning | 11 | 4 | No cross training within the team to make more knowledgeable resources available | 2 | Eur/ME | Prod. Dev. | 2009 | July | 437789
854 | Scope | Change | Creep | 15 | 7 | Late features were added | 0 | Americas | IT/Solution | 2006 | April | 877320
855 | Scope | Change | Creep | 14 | 3 | Late stakeholders redefine requiremnts | 2 | Eur/ME | IT/Solution | 2011 | September | 683928
856 | Scope | Change | Creep | 18 | 5 | Conflicting design attributes and an unfocused process resulted in confusion and changes | 0 | Americas | Prod. Dev. | 2014 | May | 1014048
857 | Scope | Change | Creep | 10 | 7 | Late addition of a USB port to a recharging adapter | 0 | Americas | Prod. Dev. | 2011 | March | 336400
858 | Scope | Change | Creep | 17 | 7 | Sponsor agreed to specifications on door, loading docks, structural supports etc that impeded efficient work flows | 2 | Eur/ME | Prod. Dev. | 2001 | December | 984521
859 | Scope | Change | Creep | 10 | 6 | Constant design changes occurred and parts had to be scrapped and replaced | 2 | Eur/ME | Prod. Dev. | 2007 | October | 215700
860 | Scope | Change | Creep | 13 | 3 | The scope of the project was poorly defined | 2 | Eur/ME | Prod. Dev. | 2002 | April | 361634
861 | Scope | Change | Creep | 11 | 3 | Client added new web pages to showcase the European site | 0 | Americas | IT/Solution | 2019 | January | 306163
862 | Scope | Change | Dependency | 10 | 4 | Old hardware became unavailable and product had to be tested on the new series | 0 | Americas | IT/Solution | 2007 | October | 274850
863 | Scope | Change | Gap | 12 | 4 | The statement of work did not indicate clearly the responsibilities of the outsourced programmers | 0 | Americas | IT/Solution | 2001 | December | 829740
864 | Scope | Change | Gap | 13 | 3 | The statement of work was not as specific as the authors thought and the deliverable from the vendor did not function as expected | 2 | Eur/ME | IT/Solution | 2012 | November | 936845
865 | Scope | Change | Gap | 18 | 7 | Contractual obligations set without adequate knowledge of potential hidden issues | 0 | Americas | IT/Solution | 2013 | September | 759798
866 | Scope | Change | Gap | 10 | 7 | The delivery of the content started without the content being finalized | 0 | Americas | Prod. Dev. | 2007 | February | 740490
867 | Scope | Change | Gap | 12 | 3 | Manufacturing process was not scalable and had to be redesigned | 0 | Americas | Prod. Dev. | 2013 | September | 730416
868 | Scope | Change | Gap | 13 | 5 | Real-life data used did not test every scenario possible, so had to be replaced | 2 | Eur/ME | Prod. Dev. | 2001 | November | 789581
869 | Scope | Change | Gap | 11 | 6 | Lack of communication between the customer and all vendors involved | 0 | Americas | IT/Solution | 2007 | November | 739607
870 | Scope | Change | Gap | 15 | 3 | Management never talked to the test department when creating proposals | 0 | Americas | IT/Solution | 2006 | September | 494370
871 | Scope | Defect | Hardware | 16 | 5 | Needed plants were set too far apart to fertilize initially | 0 | Americas | Prod. Dev. | 2005 | September | 1195872
872 | Scope | Defect | Hardware | 14 | 6 | Chp failed due to a hardware design issue and had to be redesigned and refabricated | 0 | Americas | Prod. Dev. | 2007 | September | 334642
873 | Scope | Defect | Integration | 14 | 3 | New application works, but data collected is not accessible. | 0 | Americas | IT/Solution | 2015 | December | 670628
874 | Scope | Defect | Software | 15 | 6 | Defects discovered in late testing | 0 | Americas | IT/Solution | 2004 | December | 1086315
875 | Scope | Defect | Software | 14 | 5 | Application required its own server, delay for installation | 0 | Americas | IT/Solution | 2006 | April | 364042
876 | Scope | Defect | Software | 16 | 6 | Excessive defects in Web Page translations | 0 | Americas | IT/Solution | 2009 | February | 1085008
877 | Resource | Money | Limitation | 17 | 3 | Understaffing causes overtime and leads to loss of staff | 0 | Americas | IT/Solution | 2002 | February | 382602
878 | Resource | Money | Limitation | 18 | 7 | Money for needed software was not in the budget; project was delayed to push expense into next quarter | 2 | Eur/ME | Prod. Dev. | 2007 | December | 479142
879 | Scope | Change | Gap | 10 | 4 | Project manager thought the solution was only one task, but there were four | 0 | Americas | Prod. Dev. | 2013 | March | 647670
880 | Scope | Change | Gap | 16 | 3 | Lack of consensus on the spec resulted in modifications during the second phase of the project | 2 | Eur/ME | IT/Solution | 2014 | July | 393264
881 | Schedule | Delay | Parts | 15 | 5 | Critical application delivery late | 0 | Americas | Prod. Dev. | 2003 | April | 1032990
882 | Schedule | Dependency | Project | 14 | 6 | Prior work was completed late | 0 | Americas | IT/Solution | 2007 | August | 661262
883 | Resource | Money | Limitation | 15 | 6 | Insufficient resources and little change control | 0 | Americas | Prod. Dev. | 2008 | July | 595515
884 | Scope | Change | Gap | 14 | 3 | Unique and specific requirements were poorly understood | 2 | Eur/ME | IT/Solution | 2005 | December | 1054718
885 | Resource | Outsourcing | Late or poor output | 18 | 5 | Subcontracted work failed to meet client's criteria | 0 | Americas | IT/Solution | 2018 | September | 758592
886 | Resource | Outsourcing | Delayed start | 16 | 5 | Planning the terms of the agreement and negotiating the contracts took time, making the project begin late | 2 | Eur/ME | Prod. Dev. | 2019 | October | 1035040
887 | Schedule | Delay | Information | 17 | 7 | Old application to be modified for Y2K had no documentation, and finding original code took weeks. | 0 | Americas | Prod. Dev. | 2007 | November | 788103
888 | Scope | Change | Gap | 17 | 3 | Peak season begun earlier than expected and Higher Freight Volume than usual | 0 | Americas | IT/Solution | 2015 | October | 1068994
889 | Scope | Change | Gap | 10 | 5 | Key requirements were uncovered late | 2 | Eur/ME | Prod. Dev. | 2011 | September | 402760
890 | Scope | Defect | Software | 14 | 7 | Initial code release was a major failure | 0 | Americas | IT/Solution | 2007 | February | 1069040
891 | Resource | Outsourcing | Late or poor output | 13 | 7 | High turnover led to training and low productivity throughout project. | 0 | Americas | IT/Solution | 2012 | February | 891436
892 | Schedule | Delay | Information | 12 | 6 | Initial ubjects for tests did not meet project requirements | 2 | Eur/ME | Prod. Dev. | 2001 | December | 913296
893 | Resource | Outsourcing | Late or poor output | 16 | 5 | Subcontractor goes out of business and it took 2 months to replace them. | 0 | Americas | Prod. Dev. | 2002 | April | 853600
894 | Resource | People | Loss | 10 | 4 | Key contributor on jury duty | 2 | Eur/ME | IT/Solution | 2006 | December | 517650
895 | Schedule | Estimates | Deadline | 11 | 7 | To expand business, unrealistic commitments were made to win the project | 0 | Americas | IT/Solution | 2007 | February | 743479
896 | Scope | Change | Gap | 15 | 5 | Completion criteria were not documented well | 0 | Americas | IT/Solution | 2005 | November | 937770
897 | Scope | Defect | Integration | 16 | 6 | Complex system designed in pieces, and integration fails. Redesign is required. | 0 | Americas | IT/Solution | 2019 | May | 475648
898 | Resource | Outsourcing | Late or poor output | 16 | 5 | Freelancer hired was a nutjob, and lacked the correct skills | 0 | Americas | IT/Solution | 2007 | August | 584096
899 | Resource | People | Late start | 18 | 5 | Resources were not available at the time the project started | 0 | Americas | IT/Solution | 2007 | February | 591390
900 | Resource | People | Temp loss | 11 | 4 | Unexpected shutdown at year end delays work and rescheduling it is difficult. | 0 | Americas | IT/Solution | 2007 | May | 373934
901 | Schedule | Dependency | Infrastructure | 11 | 4 | Infrasturcture changes made mid-project | 0 | Americas | Prod. Dev. | 2007 | December | 778360
902 | Schedule | Estimates | Judgment | 10 | 6 | Plans for project for new customer based on similar work for existing customer. Relationships, infrastructure, jargon and other differences took 50% more effort. | 0 | Americas | IT/Solution | 2012 | October | 760560
903 | Scope | Change | Creep | 17 | 6 | One patch was almost completely tested when it was decided to fix another bug | 0 | Americas | IT/Solution | 2007 | November | 402696
904 | Scope | Change | Creep | 12 | 6 | Design stability poor, requiring rework and late changes for manufacturing. | 0 | Americas | Prod. Dev. | 2004 | November | 312120
905 | Scope | Change | Gap | 11 | 6 | Poor project planning and missed end-user requirements | 0 | Americas | IT/Solution | 2003 | September | 341132
906 | Scope | Defect | Hardware | 17 | 7 | First production run problems necessitated adding a third run | 0 | Americas | Prod. Dev. | 2010 | July | 1000365
907 | Scope | Defect | Software | 11 | 6 | Purchased software is limited and inflexible. Workarounds and additional software required. | 2 | Eur/ME | IT/Solution | 2007 | April | 666314
908 | Resource | People | Loss | 17 | 5 | Senior technical writer resigns and another takes a leave | 0 | Americas | Prod. Dev. | 2011 | January | 1134019
909 | Schedule | Delay | Parts | 13 | 7 | Servers stuck in customs | 2 | Eur/ME | IT/Solution | 2013 | November | 813579
910 | Scope | Change | Gap | 13 | 4 | Legacy systems and processes were not well documented | 0 | Americas | IT/Solution | 2007 | October | 777452
911 | Scope | Defect | Software | 11 | 5 | Legacy system (COBOL) fails during system upgrade project. Extra effort required to fix. | 0 | Americas | IT/Solution | 2014 | March | 678392
912 | Resource | Outsourcing | Late or poor output | 18 | 4 | Contractors are not close to the business and often overlook requirements | 0 | Americas | IT/Solution | 2009 | March | 1302300
913 | Schedule | Delay | Decision | 15 | 7 | Requisition required the authorization of CEO who was out of town in Finland | 0 | Americas | Prod. Dev. | 2007 | May | 602730
914 | Schedule | Delay | Parts | 18 | 6 | Key contractors have the flu | 0 | Americas | Prod. Dev. | 2011 | January | 538884
915 | Schedule | Estimates | Judgment | 13 | 5 | Work was underestimated by 40% | 0 | Americas | IT/Solution | 2007 | July | 653497
916 | Scope | Change | Creep | 10 | 7 | Project manager added additional customized reporting (for no additional fee) | 2 | Eur/ME | IT/Solution | 2002 | March | 553760
917 | Scope | Change | Gap | 11 | 7 | Scanning of text was estimated before it was known text was bound in volumes | 2 | Eur/ME | IT/Solution | 2001 | December | 700150
918 | Schedule | Delay | Parts | 17 | 3 | Lack of supplies and adequate time for printing | 0 | Americas | IT/Solution | 2007 | July | 566729
919 | Scope | Change | Creep | 16 | 6 | Late additional request on a small project delayed completion | 0 | Americas | IT/Solution | 2007 | November | 1276752
920 | Scope | Change | Gap | 17 | 3 | Poor definition of training requirements; had to do much more. | 2 | Eur/ME | IT/Solution | 2017 | October | 353243
921 | Scope | Change | Gap | 16 | 3 | After project "complete" rework required for customer approval | 2 | Eur/ME | IT/Solution | 2010 | July | 427520
922 | Scope | Defect | Software | 16 | 6 | Access problems surfaced in production | 2 | Eur/ME | IT/Solution | 2010 | December | 600784
923 | Resource | Outsourcing | Late or poor output | 11 | 7 | Outsource company’s abilities were poor and they had to be replaced | 0 | Americas | IT/Solution | 2003 | April | 699314
924 | Resource | Outsourcing | Late or poor output | 13 | 5 | Vendor had a poor resource plan | 0 | Americas | IT/Solution | 2007 | June | 899652
925 | Schedule | Delay | Hardware | 14 | 7 | There was a high fluctuation of pressure that nobody could explain | 0 | Americas | Prod. Dev. | 2010 | April | 965734
926 | Schedule | Dependency | Project | 10 | 4 | Partner software is incompatible with current applications. | 0 | Americas | IT/Solution | 2009 | February | 647280
927 | Schedule | Dependency | Project | 10 | 3 | Project delayed to work on higher profit margin work | 0 | Americas | IT/Solution | 2007 | July | 547570
928 | Scope | Change | Creep | 17 | 6 | Additional scope added; slipped project | 0 | Americas | IT/Solution | 2017 | December | 508402
929 | Scope | Change | Creep | 11 | 4 | New specs provided and priorities changed in the middle of the project | 0 | Americas | Prod. Dev. | 2014 | February | 410245
930 | Scope | Change | Gap | 16 | 6 | Did not have the correct people validate requirements | 0 | Americas | IT/Solution | 2001 | January | 1204960
931 | Scope | Change | Gap | 13 | 6 | No understanding of the scope and not enough system resources | 0 | Americas | IT/Solution | 2019 | August | 552370
932 | Scope | Change | Gap | 11 | 3 | Additional localization requirements will cost significant extra effort and time | 0 | Americas | Prod. Dev. | 2007 | March | 848386
933 | Scope | Defect | Hardware | 18 | 7 | Purchased electronic component failed with a very high rate of 30% and had to be replaced with a designed one | 2 | Eur/ME | Prod. Dev. | 2007 | September | 562788
934 | Resource | People | Loss | 16 | 3 | Indefinite loss of key staff member | 0 | Americas | IT/Solution | 2005 | July | 672320
935 | Schedule | Estimates | Learning | 14 | 4 | Incompetent developer | 0 | Americas | Prod. Dev. | 2017 | July | 484400
936 | Scope | Change | Creep | 15 | 6 | Product was scoped with unnecessary requirements and was late | 0 | Americas | Prod. Dev. | 2015 | September | 693090
937 | Resource | Money | Limitation | 15 | 5 | Without funding, all work ceased, contracts were effectively terminated with no prospect of renewal | 0 | Americas | Prod. Dev. | 2001 | March | 1124565
938 | Scope | Change | Gap | 12 | 5 | Inaccurate comparison between our requirements and the software | 0 | Americas | IT/Solution | 2011 | September | 421548
939 | Scope | Change | Gap | 16 | 4 | New application was slow and some initial requirements were missed | 2 | Eur/ME | IT/Solution | 2005 | November | 788384
940 | Schedule | Estimates | Learning | 15 | 4 | Project manager had very few skills in this field | 0 | Americas | IT/Solution | 2007 | May | 1029615
941 | Scope | Change | Creep | 16 | 6 | One company expands scope in web design project without communicating or getting approval from others | 0 | Americas | IT/Solution | 2014 | November | 912496
942 | Resource | Money | Limitation | 13 | 4 | Subject matter experts were let go to save money | 2 | Eur/ME | Prod. Dev. | 2009 | August | 682240
943 | Resource | People | Loss | 18 | 4 | Loss of a programmer | 0 | Americas | Prod. Dev. | 2007 | September | 511488
944 | Schedule | Estimates | Judgment | 17 | 7 | Work was significantly underestimated for the project | 0 | Americas | IT/Solution | 2002 | January | 998393
945 | Schedule | Estimates | Learning | 14 | 5 | Lacked expertise needed for project (SOW too high level | 0 | Americas | Prod. Dev. | 2014 | August | 413868
946 | Scope | Defect | Software | 11 | 5 | “Off the shelf” software package was to support migration from mainframe to client-server application. Lots of unexpected customization required. | 0 | Americas | IT/Solution | 2003 | February | 221991
947 | Resource | People | Temp loss | 17 | 4 | PM unavailable due to Jury Duty | 0 | Americas | Prod. Dev. | 2008 | June | 883932
948 | Schedule | Estimates | Judgment | 12 | 7 | Combining two features into one project release created unexpected complexity | 2 | Eur/ME | IT/Solution | 2002 | July | 920904
949 | Scope | Change | Creep | 16 | 4 | Kitchen remodel expanded to renovating the bathrooms | 0 | Americas | IT/Solution | 2017 | July | 766304
950 | Resource | Outsourcing | Late or poor output | 18 | 4 | At start of project, insufficient research on the level of local expertise | 2 | Eur/ME | IT/Solution | 2014 | February | 590076
951 | Scope | Change | Creep | 18 | 7 | Client added new web pages to showcase the European site | 0 | Americas | IT/Solution | 2007 | May | 574452
952 | Scope | Change | Gap | 17 | 3 | Responsibilities not defined well for project | 0 | Americas | Prod. Dev. | 2014 | December | 841126
953 | Scope | Change | Gap | 15 | 5 | Instructions to contract testing facility were too vague and tests had to be repeated | 2 | Eur/ME | Prod. Dev. | 2019 | September | 645195
954 | Schedule | Delay | Hardware | 12 | 6 | Systems required backordered (6 months). Forced to use competitor's system. | 0 | Americas | IT/Solution | 2003 | October | 428004
955 | Schedule | Delay | Information | 12 | 7 | Documents could not be translated promptly | 0 | Americas | IT/Solution | 2007 | December | 410544
956 | Scope | Change | Gap | 18 | 3 | The business analyst failed to fully understand the scientist’s requirements | 0 | Americas | Prod. Dev. | 2008 | August | 1138428
957 | Resource | Outsourcing | Late or poor output | 13 | 3 | Contractor got a bigger project moved most of his team to that | 0 | Americas | IT/Solution | 2009 | August | 627029
958 | Resource | Outsourcing | Late or poor output | 18 | 3 | Programming object delivered late from India delays integration tests | 0 | Americas | IT/Solution | 2007 | April | 846648
959 | Resource | Outsourcing | Late or poor output | 11 | 4 | Decision to switch to contract manufacturer near end of project caused delays and cost increases. | 0 | Americas | Prod. Dev. | 2014 | June | 744128
960 | Resource | People | Loss | 12 | 4 | The key business user assigned to the ITS project was lost while assisting with a manufacturing problem and was no longer available to the project team | 0 | Americas | Prod. Dev. | 2011 | May | 898536
961 | Schedule | Dependency | Infrastructure | 14 | 6 | Needed wiring not available on time | 2 | Eur/ME | IT/Solution | 2006 | February | 610526
962 | Scope | Change | Creep | 18 | 4 | Escalated late changes from Sponsor | 2 | Eur/ME | Prod. Dev. | 2011 | April | 1079874
963 | Scope | Change | Creep | 17 | 3 | Customer requirements continually shift; lots of extra work. | 0 | Americas | IT/Solution | 2010 | October | 883847
964 | Resource | Outsourcing | Late or poor output | 12 | 6 | An external part-time consultant wasn't always available when needed | 0 | Americas | IT/Solution | 2004 | June | 321144
965 | Resource | People | Queuing | 10 | 7 | Resources thin and tasks queued in backlogs. | 0 | Americas | IT/Solution | 2008 | July | 696430
966 | Schedule | Dependency | Infrastructure | 12 | 4 | Move out of old location required, but new space is not ready. Interim move to temporary space takes extra time and money. | 0 | Americas | IT/Solution | 2007 | January | 663828
967 | Schedule | Dependency | Infrastructure | 12 | 4 | Late facility availability | 2 | Eur/ME | Prod. Dev. | 2011 | April | 731256
968 | Schedule | Dependency | Project | 17 | 6 | Installation of new systems scheduled by central team, but local people are not ready. | 0 | Americas | IT/Solution | 2004 | July | 729861
969 | Schedule | Dependency | Project | 14 | 4 | Changes to related systems resulted in wrong/late paychecks | 0 | Americas | IT/Solution | 2001 | February | 725830
970 | Schedule | Estimates | Learning | 17 | 7 | Software could only be delivered to a certified person | 2 | Eur/ME | Prod. Dev. | 2013 | August | 491776
971 | Scope | Change | Gap | 14 | 7 | IT team did not perform a thorough investigation of the existing infrastructure | 0 | Americas | IT/Solution | 2006 | March | 706048
972 | Scope | Defect | Software | 15 | 7 | New software release causes problems | 0 | Americas | IT/Solution | 2005 | July | 618840
973 | Resource | Outsourcing | Delayed start | 17 | 6 | Contractor setup delayed by a week | 0 | Americas | Prod. Dev. | 2007 | June | 654942
974 | Resource | Outsourcing | Late or poor output | 15 | 3 | Contractors failed to show up as committed | 0 | Americas | IT/Solution | 2007 | July | 558000
975 | Scope | Change | Creep | 13 | 7 | Late changes resulted in expedite charges and delay | 0 | Americas | Prod. Dev. | 2007 | October | 593775
976 | Resource | Outsourcing | Delayed start | 11 | 4 | Consultants failed to secure required resources in timely manner | 0 | Americas | IT/Solution | 2005 | February | 682011
977 | Resource | Outsourcing | Late or poor output | 17 | 3 | WWW code supplied by third party late and poor quality; major delay and rework. | 0 | Americas | IT/Solution | 2007 | March | 757350
978 | Resource | Outsourcing | Late or poor output | 18 | 4 | Subcontractor refused to follow the core vendor’s processes | 0 | Americas | IT/Solution | 2007 | October | 1088532
979 | Resource | Outsourcing | Late or poor output | 10 | 4 | Because of incopetence, a second consultant was hired to redo the work | 0 | Americas | IT/Solution | 2012 | December | 625540
980 | Resource | Outsourcing | Late or poor output | 14 | 3 | Contracted with a small outside firm that didn’t understand the business | 0 | Americas | Prod. Dev. | 2007 | August | 368046
981 | Resource | Outsourcing | Late or poor output | 14 | 4 | High turnover. ( 80%) of developer at off shore development unit left, including project lead | 0 | Americas | IT/Solution | 2007 | January | 958076
982 | Resource | Outsourcing | Late or poor output | 11 | 6 | Subcontractor goes out of business and it took 2 months to replace them. | 2 | Eur/ME | Prod. Dev. | 2008 | July | 868406
983 | Resource | People | Late start | 13 | 7 | Government contract required only US born nationals; company had too few | 0 | Americas | IT/Solution | 2008 | March | 926718
984 | Resource | People | Late start | 10 | 7 | Project was new to the company and needed to hire people and develop a team | 0 | Americas | Prod. Dev. | 2011 | February | 744990
985 | Resource | People | Late start | 12 | 3 | Staffing was late and inexperienced | 0 | Americas | IT/Solution | 2009 | September | 802296
986 | Resource | People | Loss | 18 | 4 | The only experienced programmer gave notice and left the company | 0 | Americas | IT/Solution | 2011 | June | 1412280
987 | Resource | People | Loss | 15 | 4 | One of the Senior System Analysts who was fully trained on the application resigned | 0 | Americas | IT/Solution | 2002 | January | 534450
988 | Resource | People | Loss | 14 | 5 | Team leader reassigned to another project and a new leader was assigned | 2 | Eur/ME | IT/Solution | 2018 | May | 1052450
989 | Resource | People | Loss | 15 | 6 | Lack of IT subject matter experts | 0 | Americas | IT/Solution | 2007 | August | 643770
990 | Resource | People | Loss | 17 | 7 | Key contributor on jury duty | 2 | Eur/ME | IT/Solution | 2008 | January | 643620
991 | Resource | People | Loss | 12 | 6 | Project lost irreplaceable experts | 0 | Americas | IT/Solution | 2012 | January | 416100
992 | Resource | People | Loss | 16 | 3 | Executive director stayed two months and then left | 0 | Americas | Prod. Dev. | 2009 | September | 669776
993 | Resource | People | Loss | 10 | 5 | A company-wide reduction in force let go some of the people who were supposed to lead the next phase | 0 | Americas | Prod. Dev. | 2007 | August | 763940
994 | Resource | People | Loss | 16 | 5 | Applications Engineer found another job and left the company | 0 | Americas | Prod. Dev. | 2010 | June | 621168
995 | Resource | People | Loss | 11 | 4 | Both the full time developers assigned to the project quit the company | 0 | Americas | Prod. Dev. | 2015 | August | 359502
996 | Resource | People | Loss | 16 | 7 | Project leader was transferred to another project | 2 | Eur/ME | IT/Solution | 2009 | April | 1104800
997 | Resource | People | Loss | 15 | 5 | Half way through the project three of the engineers had to return to China due to visa issues | 0 | Americas | Prod. Dev. | 2002 | May | 1015560
998 | Resource | People | Loss | 21 | 6 | Project work estimated to take 1 month took 3 due to loss of staff to do the work. | 0 | Americas | Prod. Dev. | 2007 | April | 684159
999 | Resource | People | Motivation | 7 | 3 | Projects with similar objectives taken on centrally and locally at the same time. Lots of overlap, redundancy and arguing. | 0 | Americas | IT/Solution | 2019 | November | 361025
1000 | Resource | People | Queuing | 22 | 6 | Project is not complete until all users are trained. Coordinating schedules requires 4 months, not 2. | 0 | Americas | IT/Solution | 2010 | September | 646118
1001 | Resource | People | Queuing | 5 | 7 | Specialist was busy with a lot of work | 2 | Eur/ME | Prod. Dev. | 2018 | September | 163175
1002 | Resource | People | Temp loss | 12 | 7 | Mid-way in design stage, a key Engineer had a family emergency and had to leave the country for a month | 0 | Americas | IT/Solution | 2011 | September | 675072
1003 | Resource | People | Temp loss | 5 | 3 | Key engineer was pulled out of the team to work on another project. | 2 | Eur/ME | IT/Solution | 2017 | December | 115725
1004 | Resource | People | Temp loss | 7 | 3 | Two of the SAP technicians were reassigned to a more “business critical” project midway through the system development phase. | 0 | Americas | IT/Solution | 2009 | September | 362117
1005 | Resource | People | Temp loss | 6 | 3 | PM unavailable due to Jury Duty | 0 | Americas | Prod. Dev. | 2013 | December | 426210
1006 | Resource | People | Temp loss | 5 | 7 | Contributor couldn't work due to injury and back pains | 0 | Americas | Prod. Dev. | 2007 | May | 245555
1007 | Schedule | Delay | Decision | 12 | 6 | Sponsorship not sustained and decisions and resources are problematic. | 0 | Americas | IT/Solution | 2007 | September | 846300
1008 | Schedule | Delay | Decision | 7 | 6 | Endless debate over choice of three possible approaches for project work | 0 | Americas | Prod. Dev. | 2005 | August | 254366
1009 | Schedule | Delay | Hardware | 22 | 4 | Color printer version of app fails on WAN | 0 | Americas | IT/Solution | 2007 | October | 1278200
1010 | Schedule | Delay | Hardware | 16 | 5 | Vendor merger caused interruption in hardware availability; had to recertify | 0 | Americas | IT/Solution | 2010 | August | 1166096
1011 | Schedule | Delay | Information | 5 | 7 | Data for key tables not available when needed | 2 | Eur/ME | IT/Solution | 2009 | January | 380905
1012 | Schedule | Delay | Information | 9 | 5 | Old application to be modified had no one left who knew it and no documentation. | 0 | Americas | IT/Solution | 2008 | September | 409905
1013 | Schedule | Delay | Parts | 6 | 7 | Quantity of Intel CPU processors needed not available | 2 | Eur/ME | Prod. Dev. | 2012 | May | 479112
1014 | Schedule | Delay | Parts | 11 | 3 | Existing systems were removed from market, requiring changes for new model | 0 | Americas | Prod. Dev. | 2007 | June | 420662
1015 | Schedule | Delay | Parts | 12 | 3 | Partner misses bimaontly shipping deadline | 0 | Americas | Prod. Dev. | 2009 | December | 760236
1016 | Schedule | Delay | Parts | 11 | 4 | Manufacutring group did not have the capcity to produce a critical new enzyme | 0 | Americas | Prod. Dev. | 2001 | November | 767041
1017 | Schedule | Delay | Parts | 6 | 3 | Project experienced shortages in steel rebar and copper electrical wire | 2 | Eur/ME | IT/Solution | 2003 | January | 321528
1018 | Schedule | Dependency | Infrastructure | 13 | 3 | Too few disc drives, and insufficient "owned" space | 0 | Americas | Prod. Dev. | 2011 | February | 363935
1019 | Schedule | Dependency | Legal | 11 | 5 | Sponsors who knew the system well didn't bother to analyze the impact of rolling out sensitive data to global users without security in place | 0 | Americas | IT/Solution | 2008 | January | 342056
1020 | Schedule | Estimates | Deadline | 14 | 6 | A six month conversion period from the date a contract is signed is the norm, but project goal is four months | 0 | Americas | IT/Solution | 2003 | August | 962262
1021 | Schedule | Estimates | Deadline | 5 | 7 | To expand business, unrealistic commitments were made to win the project | 2 | Eur/ME | IT/Solution | 2005 | June | 261640
1022 | Schedule | Estimates | Deadline | 7 | 3 | Unrealistic deadline set; slips unavoidable. | 0 | Americas | IT/Solution | 2017 | August | 256515
1023 | Schedule | Estimates | Judgment | 15 | 3 | Combining two features into one project release created unexpected complexity | 0 | Americas | IT/Solution | 2009 | June | 746280
1024 | Schedule | Estimates | Judgment | 21 | 7 | Software development underestimated by a factor of three. | 2 | Eur/ME | Prod. Dev. | 2008 | February | 597555
1025 | Schedule | Estimates | Learning | 19 | 4 | Few of the administrators and developers hired for executing this project had the right skill sets to execute the project | 0 | Americas | IT/Solution | 2016 | January | 690992
1026 | Schedule | Estimates | Learning | 14 | 6 | Developers on the project were not experienced enough to implement the solution | 2 | Eur/ME | IT/Solution | 2016 | July | 392252
1027 | Schedule | Estimates | Learning | 16 | 5 | No staff that was knowledgeable in the technology | 0 | Americas | Prod. Dev. | 2010 | July | 612704
1028 | Scope | Change | Creep | 18 | 7 | Redesign added late in maintenance project for legacy system. Major slip. | 0 | Americas | IT/Solution | 2011 | July | 864036
1029 | Scope | Change | Creep | 17 | 5 | Scope not defined well; huge software delays | 0 | Americas | IT/Solution | 2011 | July | 860234
1030 | Scope | Change | Creep | 13 | 7 | Functionality for email added late to a document retrieval project | 2 | Eur/ME | IT/Solution | 2009 | April | 583583
1031 | Scope | Change | Creep | 8 | 6 | Continuous revisions to the specifications for a building remodel | 0 | Americas | IT/Solution | 2016 | October | 513952
1032 | Scope | Change | Creep | 18 | 6 | Kitchen remodel expanded to renovating the bathrooms | 0 | Americas | IT/Solution | 2007 | November | 1343088
1033 | Scope | Change | Creep | 16 | 7 | Additional three manufacturing sites meant using another server for this project | 0 | Americas | IT/Solution | 2003 | February | 1121968
1034 | Scope | Change | Creep | 9 | 3 | New requirements were piled on as the project ran | 0 | Americas | IT/Solution | 2011 | May | 291546
1035 | Scope | Change | Creep | 12 | 3 | Requirements were unclear at the beginning of the project | 0 | Americas | IT/Solution | 2007 | October | 388812
1036 | Scope | Change | Creep | 10 | 4 | Definition changed late in project. | 2 | Eur/ME | Prod. Dev. | 2016 | October | 638600
1037 | Scope | Change | Creep | 11 | 7 | After more than 2/3 of the original budget had been expended, a major design change resulted in major requirement modifications and additions | 0 | Americas | Prod. Dev. | 2012 | July | 309947
1038 | Scope | Change | Creep | 11 | 7 | Processes were changed and made more complex late in the project | 2 | Eur/ME | Prod. Dev. | 2018 | August | 840686
1039 | Scope | Change | Creep | 19 | 3 | Additional renovations added late that were not in the original plan | 0 | Americas | Prod. Dev. | 2004 | July | 1505313
1040 | Scope | Change | Creep | 7 | 3 | Initial scoping for a minor upgrade was not sufficient | 0 | Americas | Prod. Dev. | 2013 | October | 292201
1041 | Scope | Change | Creep | 18 | 3 | Management did not plan for a requirements gathering phase | 0 | Americas | Prod. Dev. | 2005 | June | 1327572
1042 | Scope | Change | Creep | 10 | 3 | Solution project priced "to win" and had few details on work; led to big losses and delays. | 2 | Eur/ME | IT/Solution | 2015 | August | 699260
1043 | Scope | Change | Creep | 5 | 5 | Migration project (to NT from UNIX) saddled with increasing list of changes. | 2 | Eur/ME | IT/Solution | 2012 | March | 315085
1044 | Scope | Change | Creep | 12 | 6 | Sponsor demanded specification changes late in the project | 2 | Eur/ME | Prod. Dev. | 2014 | January | 537216
1045 | Scope | Change | Gap | 20 | 3 | Sales reps did not clearly understand the client’s request | 0 | Americas | IT/Solution | 2007 | September | 952300
1046 | Scope | Change | Gap | 10 | 5 | Requirements document for a new database system were not specific enough regarding user interface details | 0 | Americas | IT/Solution | 2015 | June | 424400
1047 | Scope | Change | Gap | 19 | 7 | Incorrect decimal pay rate did not reflect the true and accurate pay | 0 | Americas | IT/Solution | 2007 | December | 1384511
1048 | Scope | Change | Gap | 8 | 7 | Procurement is done based on out-of date drawings | 2 | Eur/ME | IT/Solution | 2015 | July | 477096
1049 | Scope | Change | Gap | 18 | 6 | Completion criteria were not documented well | 0 | Americas | IT/Solution | 2003 | July | 1346184
1050 | Scope | Change | Gap | 9 | 6 | Sufficient time was not allocated to understand client needs and assumptions | 0 | Americas | IT/Solution | 2007 | March | 230184
1051 | Scope | Change | Gap | 17 | 7 | No clear requirements from management | 0 | Americas | IT/Solution | 2002 | September | 343723
1052 | Scope | Change | Gap | 13 | 5 | Unique data in each region prevented information flow | 0 | Americas | IT/Solution | 2010 | January | 496067
1053 | Scope | Change | Gap | 21 | 5 | Website wasn't as simple as it iniitally seemed | 0 | Americas | IT/Solution | 2002 | July | 631554
1054 | Scope | Change | Gap | 15 | 4 | Lead engineer thought he had a good ‘understanding’ of what needed to be done | 2 | Eur/ME | Prod. Dev. | 2003 | January | 1120080
1055 | Scope | Change | Gap | 10 | 4 | Partner company introduced a changed requirement late in development | 0 | Americas | Prod. Dev. | 2007 | January | 572670
1056 | Scope | Change | Gap | 9 | 6 | Key telecom requirement detected late | 0 | Americas | IT/Solution | 2007 | January | 318366
1057 | Scope | Change | Gap | 10 | 3 | Need to upgrade detected only at project end | 2 | Eur/ME | IT/Solution | 2013 | November | 348350
1058 | Scope | Change | Gap | 22 | 7 | The students in a new course had insufficient knowledge of reading and math | 0 | Americas | IT/Solution | 2007 | October | 502436
1059 | Scope | Defect | Hardware | 13 | 5 | Redesign required late in printer project to meet paper speed goals. OT and delays. | 0 | Americas | Prod. Dev. | 2007 | February | 543816
1060 | Scope | Defect | Hardware | 15 | 5 | Components failure means finding another type of component and redoing tests | 2 | Eur/ME | Prod. Dev. | 2016 | June | 730620
1061 | Scope | Defect | Hardware | 13 | 5 | To reduce costs and speed time to market there were too few pre-launch product builds performed | 0 | Americas | Prod. Dev. | 2005 | July | 812955
1062 | Scope | Defect | Hardware | 9 | 5 | 1000 hour tests required at project end. Failure half-way (or later) requires fix and restart. | 2 | Eur/ME | Prod. Dev. | 2017 | March | 652860
1063 | Scope | Defect | Hardware | 8 | 4 | Packaging for a critical white board component was too flimsy to withstand standard shipping stress | 0 | Americas | Prod. Dev. | 2006 | March | 504136
1064 | Scope | Defect | Hardware | 8 | 5 | Test hardware does not work. All tests done manually using extra time and effort. | 0 | Americas | Prod. Dev. | 2002 | August | 290728
1065 | Scope | Defect | Integration | 13 | 5 | Complex system designed in pieces, and integration fails. Redesign is required. | 0 | Americas | IT/Solution | 2001 | September | 849563
1066 | Scope | Defect | Integration | 12 | 4 | Unusual usage caused problems in the integration process | 0 | Americas | IT/Solution | 2007 | October | 589440
1067 | Scope | Defect | Integration | 6 | 5 | Two related projects failed to successfully synchronize and missed a release | 2 | Eur/ME | IT/Solution | 2013 | May | 237888
1068 | Scope | Defect | Integration | 19 | 3 | Project was longer than necessary because one team insisted on doing "half" literally, even though the effort resulting was very lopsided. | 0 | Americas | Prod. Dev. | 2007 | July | 979203
1069 | Scope | Defect | Software | 6 | 3 | Major failure in the Validation tests | 0 | Americas | IT/Solution | 2006 | May | 301272
1070 | Scope | Defect | Software | 11 | 7 | After the upgrade was released, issues with the software were discovered | 0 | Americas | IT/Solution | 2005 | July | 833921
1071 | Scope | Defect | Software | 13 | 4 | A patch breaks other functionality in the system and is backed out until the next maintenance window | 0 | Americas | IT/Solution | 2007 | January | 881686
1072 | Scope | Defect | Software | 17 | 4 | Poorly implemented web tool causes ongoing support issues | 2 | Eur/ME | IT/Solution | 2019 | August | 755837
1073 | Scope | Defect | Software | 9 | 3 | Problems detected and solution developed based on presumed root cause. Cause was actually something else and led to major slip. | 0 | Americas | Prod. Dev. | 2006 | November | 222579
1074 | Scope | Defect | Software | 11 | 3 | During the printing test, the printer couldn’t interpret the incoming file | 0 | Americas | Prod. Dev. | 2009 | June | 226710
1075 | Resource | Money | Limitation | 9 | 3 | insufficient staff to carry out the implementation plan | 0 | Americas | IT/Solution | 2009 | April | 644310
1076 | Resource | Money | Limitation | 8 | 6 | Reduced staff with a bare minimum budget was assigned to the project | 0 | Americas | IT/Solution | 2007 | May | 193528
1077 | Resource | Money | Limitation | 21 | 6 | Sponsor fails to provide money | 0 | Americas | Prod. Dev. | 2007 | November | 1646505
1078 | Resource | Money | Limitation | 22 | 4 | Project needs $150K per month in supplies but limit is $100K, which delayed progress. | 0 | Americas | Prod. Dev. | 2007 | August | 1105742
1079 | Resource | Money | Limitation | 20 | 7 | The travel budget for the project was cut and led to inefficient long-distance collaboration | 2 | Eur/ME | Prod. Dev. | 2008 | March | 1225860
1080 | Resource | Money | Limitation | 16 | 6 | Chronically understaffed business environment | 2 | Eur/ME | Prod. Dev. | 2005 | April | 672736
1081 | Schedule | Estimates | Learning | 8 | 6 | Severe learning curve of somestaff slowed progress | 0 | Americas | IT/Solution | 2017 | April | 402152
1082 | Resource | Money | Limitation | 11 | 4 | Not enough staff to cover the load and failure to prioritize | 0 | Americas | Prod. Dev. | 2016 | February | 345103
1083 | Schedule | Dependency | Legal | 15 | 6 | Process change led to recertification requirements and delay | 2 | Eur/ME | Prod. Dev. | 2003 | February | 1032255
1084 | Scope | Change | Creep | 11 | 4 | Developer added a new routine that was not fully tested, and release window passed | 0 | Americas | IT/Solution | 2007 | June | 680273
1085 | Resource | Money | Limitation | 16 | 7 | A team of 5 contract engineers were let go | 2 | Eur/ME | IT/Solution | 2007 | May | 1258880
1086 | Schedule | Delay | Parts | 9 | 7 | Insufficient amount of test material was sent to the contract lab | 0 | Americas | Prod. Dev. | 2007 | June | 718281
1087 | Scope | Change | Creep | 10 | 4 | System expanded to into include two more cities for political reasons | 0 | Americas | IT/Solution | 2007 | March | 561150
1088 | Scope | Change | Creep | 15 | 4 | Poor scoping led to scope creep | 0 | Americas | Prod. Dev. | 2011 | December | 939600
1089 | Resource | Money | Limitation | 21 | 6 | Insufficient resources assigned to the project | 0 | Americas | Prod. Dev. | 2011 | September | 528696
1090 | Resource | Money | Limitation | 21 | 7 | For cost reasons, critical work was transferred out of Japan | 2 | Eur/ME | Prod. Dev. | 2018 | November | 1303386
1091 | Scope | Defect | Hardware | 5 | 4 | Mixture given to test animals caused too many side-effects | 0 | Americas | Prod. Dev. | 2015 | August | 255445
1092 | Schedule | Delay | Parts | 12 | 6 | Existing systems were removed from market, requiring changes for new model | 2 | Eur/ME | Prod. Dev. | 2001 | August | 627876
1093 | Scope | Change | Creep | 12 | 4 | Additional three manufacturing sites meant using another server for this project | 0 | Americas | IT/Solution | 2004 | March | 942456
1094 | Scope | Change | Gap | 6 | 4 | Procurement is done based on out-of date drawings | 2 | Eur/ME | IT/Solution | 2008 | August | 168912
1095 | Resource | Money | Limitation | 14 | 3 | insufficient staff to carry out the implementation plan | 0 | Americas | IT/Solution | 2017 | October | 632786
1096 | Schedule | Delay | Information | 12 | 3 | Lack of communication and trust between locations | 0 | Americas | IT/Solution | 2015 | October | 773736
1097 | Scope | Change | Gap | 11 | 7 | The statement of work was not as specific as the authors thought and the deliverable from the vendor did not function as expected | 0 | Americas | IT/Solution | 2007 | March | 344036
1098 | Schedule | Delay | Hardware | 6 | 5 | Equipment was unreliable and caused slips | 0 | Americas | IT/Solution | 2016 | September | 430812
1099 | Scope | Defect | Hardware | 16 | 7 | Testing facilities were too low-tech to verify automated systems | 0 | Americas | IT/Solution | 2007 | December | 698224
1100 | Resource | Money | Limitation | 20 | 6 | Development team had insufficient resources assigned to the project | 0 | Americas | Prod. Dev. | 2017 | August | 1342380
1101 | Resource | People | Temp loss | 16 | 6 | At year-end, engineer in Germenay had to take accrued vacation time | 2 | Eur/ME | Prod. Dev. | 2014 | September | 632672
1102 | Schedule | Delay | Hardware | 18 | 4 | A component needed for necropsy data analysis failed | 0 | Americas | IT/Solution | 2010 | July | 1109142
1103 | Schedule | Delay | Information | 18 | 7 | Some tasks assigned only by function; no one actually working on them. | 0 | Americas | Prod. Dev. | 2013 | October | 781200
1104 | Scope | Change | Creep | 13 | 3 | Complex feature added that was not requested by the customer | 0 | Americas | IT/Solution | 2005 | October | 819299
1105 | Scope | Change | Creep | 5 | 6 | Additional deliverable added late | 0 | Americas | IT/Solution | 2006 | January | 354720
1106 | Scope | Defect | Software | 8 | 5 | Editing text worsened product quality and necessitated retranslation | 0 | Americas | Prod. Dev. | 2019 | August | 181920
1107 | Resource | Money | Limitation | 7 | 3 | Project did not have the buy-in for staffing from other departmens | 2 | Eur/ME | IT/Solution | 2018 | February | 449428
1108 | Resource | Outsourcing | Late or poor output | 14 | 3 | Task supposed to be done by an outside company was completed late | 2 | Eur/ME | Prod. Dev. | 2008 | December | 359072
1109 | Resource | People | Temp loss | 9 | 4 | Staff lost to customer hot site | 0 | Americas | Prod. Dev. | 2014 | February | 456228
1110 | Schedule | Delay | Hardware | 17 | 4 | Disaster recovery tests delayed at project end; hardware needed tied up with an actual customer problem. | 0 | Americas | IT/Solution | 2006 | February | 1200795
1111 | Schedule | Delay | Hardware | 18 | 7 | Test systems shared by 6 projects; queuing and delays common. | 0 | Americas | Prod. Dev. | 2007 | June | 1244376
1112 | Schedule | Delay | Hardware | 10 | 7 | New equipment critical to the success of the product quality was installed late | 0 | Americas | Prod. Dev. | 2004 | October | 709590
1113 | Schedule | Dependency | Legal | 8 | 3 | New requirements that mandated all products that have yet to ship to market to be re-tested | 0 | Americas | IT/Solution | 2001 | November | 343200
1114 | Schedule | Dependency | Project | 14 | 6 | Clear delegation of work done by project team and by customer never done. Confusion led to delays. | 0 | Americas | IT/Solution | 2007 | October | 679000
1115 | Schedule | Estimates | Deadline | 18 | 3 | Firewall changes can take 25 days, estimates are capped at 15 | 2 | Eur/ME | IT/Solution | 2016 | June | 719568
1116 | Scope | Change | Gap | 22 | 5 | Mismatch in documents and expectations. Adjustments required lots of additional work. | 2 | Eur/ME | IT/Solution | 2005 | December | 1611192
1117 | Scope | Defect | Integration | 7 | 3 | Integrating course content that does not comply with LMS specifications | 0 | Americas | IT/Solution | 2007 | February | 326669
1118 | Resource | People | Temp loss | 16 | 7 | Engineer responsible to program the ISDN router called in sick | 2 | Eur/ME | IT/Solution | 2006 | May | 1062672
1119 | Schedule | Delay | Information | 14 | 6 | Documentation from the researcher lacks crucial information | 0 | Americas | Prod. Dev. | 2007 | March | 593810
1120 | Scope | Defect | Software | 19 | 4 | Performance issues surfaced following migration | 2 | Eur/ME | IT/Solution | 2015 | November | 1449928
1121 | Resource | Outsourcing | Delayed start | 6 | 6 | Delay in contract signing because legal had a higher priority contract to review | 0 | Americas | Prod. Dev. | 2005 | May | 457002
1122 | Resource | Outsourcing | Late or poor output | 16 | 5 | Contractors are not sufficiently skilled nor motivated | 0 | Americas | Prod. Dev. | 2013 | March | 963408
1123 | Resource | People | Loss | 5 | 6 | Key contributor injured in a car accident | 0 | Americas | IT/Solution | 2007 | August | 272240
1124 | Resource | People | Loss | 13 | 7 | Employees terminated for sexual harassment | 0 | Americas | Prod. Dev. | 2010 | June | 554073
1125 | Resource | People | Loss | 13 | 5 | Key staff member assigned to project was changed 3 times during the project | 0 | Americas | Prod. Dev. | 2007 | October | 266240
1126 | Resource | People | Loss | 17 | 3 | Due to a re-organization the team lost essential resources | 2 | Eur/ME | Prod. Dev. | 2003 | January | 905080
1127 | Schedule | Delay | Information | 9 | 5 | Initial ubjects for tests did not meet project requirements | 0 | Americas | Prod. Dev. | 2007 | July | 599922
1128 | Schedule | Delay | Parts | 6 | 6 | Manufacutring group did not have the capcity to produce a critical new enzyme | 0 | Americas | Prod. Dev. | 2007 | May | 385878
1129 | Schedule | Dependency | Legal | 21 | 6 | State government overtime and holiday compensation rules just before a new payroll application goes live | 0 | Americas | IT/Solution | 2001 | January | 703353
1130 | Scope | Defect | Hardware | 6 | 3 | Mixture given to test animals caused too many side-effects | 0 | Americas | Prod. Dev. | 2009 | November | 473832
1131 | Scope | Defect | Software | 14 | 3 | Data conversion problems made the implementation of a new system dependent on manual reentry of data | 0 | Americas | IT/Solution | 2018 | August | 782194
1132 | Resource | Money | Limitation | 22 | 3 | IT department was underfunded and had insuffient staff | 0 | Americas | IT/Solution | 2019 | January | 1594516
1133 | Resource | Money | Limitation | 10 | 5 | Staffing was not sufficient to complete all assigned tasks with deadlines | 0 | Americas | Prod. Dev. | 2011 | August | 585710
1134 | Resource | People | Loss | 10 | 3 | Staff cutbacks (and dropped scope as well) | 0 | Americas | IT/Solution | 2007 | November | 672290
1135 | Scope | Defect | Hardware | 6 | 3 | Defect discovered after delivery to customer | 0 | Americas | IT/Solution | 2009 | April | 223704
1136 | Schedule | Delay | Decision | 18 | 5 | Approvals were late so campaign could be pushed out of the Sales Team | 0 | Americas | IT/Solution | 2010 | August | 887220
1137 | Schedule | Dependency | Legal | 20 | 6 | State government overtime and holiday compensation rules just before a new payroll application goes live | 2 | Eur/ME | IT/Solution | 2002 | April | 881680
1138 | Resource | Money | Limitation | 21 | 5 | Staffing was not sufficient to complete all assigned tasks with deadlines | 0 | Americas | Prod. Dev. | 2019 | July | 1464645
1139 | Resource | People | Temp loss | 15 | 7 | Key engineer was pulled out of the team to work on another project. | 0 | Americas | IT/Solution | 2016 | January | 451050
1140 | Schedule | Delay | Parts | 10 | 5 | Partner misses bimaontly shipping deadline | 0 | Americas | Prod. Dev. | 2005 | July | 295090
1141 | Scope | Change | Creep | 16 | 6 | Continuous revisions to the specifications for a building remodel | 2 | Eur/ME | IT/Solution | 2006 | December | 822784
1142 | Scope | Change | Gap | 10 | 3 | Website wasn't as simple as it iniitally seemed | 0 | Americas | IT/Solution | 2016 | October | 280460
1143 | Scope | Defect | Hardware | 21 | 4 | Redesign required late in printer project to meet paper speed goals. OT and delays. | 0 | Americas | Prod. Dev. | 2007 | November | 628446
1144 | Scope | Change | Creep | 13 | 4 | New specs provided and priorities changed in the middle of the project | 0 | Americas | Prod. Dev. | 2007 | January | 893282
1145 | Scope | Defect | Hardware | 5 | 7 | Purchased electronic component failed with a very high rate of 30% and had to be replaced with a designed one | 2 | Eur/ME | Prod. Dev. | 2006 | October | 229415
1146 | Schedule | Dependency | Project | 21 | 4 | Lack of communication with the project team in Germany | 0 | Americas | Prod. Dev. | 2004 | June | 1203090
1147 | Scope | Defect | Hardware | 21 | 3 | Chp failed due to a hardware design issue and had to be redesigned and refabricated | 0 | Americas | Prod. Dev. | 2013 | May | 764022
1148 | Scope | Defect | Software | 10 | 6 | Defects discovered in late testing | 2 | Eur/ME | IT/Solution | 2001 | March | 746750
1149 | Resource | People | Temp loss | 14 | 6 | Feedback from South Korea delayed due to a few months of sick leave by product manager | 0 | Americas | Prod. Dev. | 2007 | February | 748384
1150 | Resource | People | Temp loss | 15 | 7 | Multiple projects competing for a limited staff to do the work leads to interruptions and delays | 0 | Americas | Prod. Dev. | 2004 | October | 796305
1151 | Scope | Change | Gap | 21 | 5 | System only partly specified until near the end of the project. | 0 | Americas | IT/Solution | 2019 | October | 553539
1152 | Resource | People | Loss | 10 | 7 | Key contriobutor quit, and there was insufficient information transfer | 0 | Americas | IT/Solution | 2019 | July | 544680
1153 | Resource | People | Queuing | 7 | 4 | People who require training miss classes; more classes required. | 0 | Americas | IT/Solution | 2014 | April | 550123
1154 | Schedule | Dependency | Infrastructure | 15 | 5 | Space unavailable; needed to implement in old space | 0 | Americas | Prod. Dev. | 2012 | March | 347205
1155 | Scope | Change | Creep | 13 | 7 | Revision to the story board is required | 0 | Americas | IT/Solution | 2010 | May | 293449
1156 | Scope | Defect | Hardware | 17 | 3 | Revisions required after review | 0 | Americas | Prod. Dev. | 2012 | June | 1299650
1157 | Resource | People | Loss | 15 | 5 | Expert developer left the company | 0 | Americas | Prod. Dev. | 2007 | October | 969765
1158 | Schedule | Delay | Information | 21 | 6 | "Overnight" shipping takes extra time in big co. mailrooms | 0 | Americas | Prod. Dev. | 2004 | November | 497595
1159 | Schedule | Dependency | Infrastructure | 16 | 3 | Operating system selected (LINUX) has inadequate support for timely solution of conversion and delivery problems. | 0 | Americas | IT/Solution | 2010 | January | 1279328
1160 | Scope | Change | Gap | 6 | 3 | Iadequate analysis prior to iniitating development efforts | 2 | Eur/ME | Prod. Dev. | 2019 | November | 259446
1161 | Scope | Defect | Hardware | 7 | 3 | Final burn-in test interrupted by faulty oven. Replacement and retest took extra time. | 0 | Americas | IT/Solution | 2018 | February | 311234
1162 | Resource | Outsourcing | Delayed start | 9 | 5 | RFP Process was flawed and created delays | 0 | Americas | IT/Solution | 2002 | August | 588663
1163 | Resource | Outsourcing | Late or poor output | 18 | 6 | High turnover led to training and low productivity throughout project. | 2 | Eur/ME | IT/Solution | 2019 | December | 365922
1164 | Resource | Outsourcing | Late or poor output | 15 | 4 | Changes in contracts and scope not managed well | 0 | Americas | Prod. Dev. | 2016 | February | 541320
1165 | Resource | People | Loss | 20 | 7 | On this long project, turnover was high on project team and at customer. | 0 | Americas | IT/Solution | 2013 | July | 730860
1166 | Resource | People | Loss | 15 | 5 | Process improvement project has low priority and high turnover. | 0 | Americas | Prod. Dev. | 2007 | August | 928995
1167 | Resource | People | Loss | 5 | 4 | Cardiologist on the project team resigned and had to be replaced | 2 | Eur/ME | Prod. Dev. | 2008 | December | 229310
1168 | Resource | People | Loss | 21 | 7 | Key programmer resigned | 2 | Eur/ME | Prod. Dev. | 2012 | November | 860538
1169 | Schedule | Delay | Decision | 5 | 4 | Approvals were late so campaign could be pushed out of the Sales Team | 0 | Americas | IT/Solution | 2007 | March | 319775
1170 | Schedule | Delay | Information | 20 | 7 | Project has customer info, but also needs supplier data. Project to provide this is delayed. | 0 | Americas | IT/Solution | 2004 | April | 1225880
1171 | Schedule | Delay | Information | 22 | 6 | Project had to wait until all data collection was finished before starting analysis | 0 | Americas | IT/Solution | 2007 | June | 1674156
1172 | Schedule | Delay | Parts | 18 | 4 | Test run is rejected or lost | 0 | Americas | Prod. Dev. | 2007 | August | 1195902
1173 | Schedule | Dependency | Infrastructure | 11 | 4 | Adopting the selected system required several new pieces of major software | 0 | Americas | IT/Solution | 2007 | June | 225280
1174 | Schedule | Estimates | Learning | 17 | 3 | High attrition in positions requiring unique technical training | 0 | Americas | IT/Solution | 2016 | January | 733499
1175 | Schedule | Estimates | Learning | 12 | 6 | Development team didn’t have the expertise to implement the modules | 0 | Americas | IT/Solution | 2007 | September | 945636
1176 | Scope | Change | Creep | 22 | 4 | Late inclusions resulted in change orders and delay | 2 | Eur/ME | IT/Solution | 2017 | July | 973676
1177 | Scope | Change | Creep | 15 | 3 | New product features were added at every weekly meeting and stage review | 0 | Americas | Prod. Dev. | 2007 | August | 1064640
1178 | Scope | Change | Dependency | 7 | 6 | Business environment shifts forcing project changes, | 2 | Eur/ME | Prod. Dev. | 2008 | June | 234535
1179 | Scope | Change | Gap | 13 | 6 | The scope was not clearly defined | 0 | Americas | IT/Solution | 2001 | February | 781885
1180 | Scope | Change | Gap | 15 | 6 | Requesters failed to understand the complexity and did not make their wishes clear | 0 | Americas | IT/Solution | 2001 | December | 911655
1181 | Scope | Change | Gap | 19 | 5 | Project based on standards still in draft form. Several options are possible, but project is only staffed to pursue one. | 0 | Americas | Prod. Dev. | 2005 | March | 462422
1182 | Scope | Change | Gap | 21 | 6 | The Product Manager never told the team what the customer was asking for | 2 | Eur/ME | Prod. Dev. | 2013 | June | 1053948
1183 | Scope | Change | Gap | 9 | 3 | Project team was not aware that the new release would have a new UI | 0 | Americas | Prod. Dev. | 2007 | June | 527715
1184 | Scope | Change | Gap | 6 | 4 | Delay due to testing requirements uncovered late and shifting priorities | 0 | Americas | IT/Solution | 2008 | November | 235032
1185 | Scope | Change | Gap | 10 | 6 | Supplier code changes resulted in major backlog | 2 | Eur/ME | IT/Solution | 2009 | October | 474210
1186 | Scope | Defect | Integration | 22 | 7 | Technology used for design is unstable | 0 | Americas | Prod. Dev. | 2007 | November | 1209934
1187 | Scope | Defect | Software | 7 | 3 | Conversion from legacy system to SAP has multiple modules that cause unanticipated problems leading to delays of 3 to 10 days each to fix. | 0 | Americas | IT/Solution | 2007 | May | 475559
1188 | Scope | Defect | Software | 12 | 5 | “Off the shelf” software package was to support migration from mainframe to client-server application. Lots of unexpected customization required. | 0 | Americas | IT/Solution | 2019 | March | 473568
1189 | Resource | Money | Limitation | 12 | 3 | Too few staff members | 0 | Americas | IT/Solution | 2003 | February | 346164
1190 | Resource | Money | Limitation | 15 | 3 | For cost reasons, critical work was transferred out of Japan | 0 | Americas | Prod. Dev. | 2007 | April | 342735
1191 | Scope | Change | Creep | 6 | 5 | The contract indicated state of the art retrofit materials; differing meaning over 2 years | 0 | Americas | Prod. Dev. | 2006 | April | 304626
1192 | Scope | Change | Creep | 20 | 3 | Extension of scope in Japan was not managed or controlled well | 0 | Americas | IT/Solution | 2004 | May | 877560
1193 | Scope | Defect | Hardware | 15 | 7 | Redesign required late in printer project to meet print quality goals. Major slip. | 2 | Eur/ME | Prod. Dev. | 2006 | May | 1022910
1194 | Scope | Change | Creep | 16 | 6 | Failure to finalize Product Definition Document requirements | 0 | Americas | Prod. Dev. | 2006 | February | 982400
1195 | Scope | Change | Gap | 17 | 4 | Scope of the project increased following final requirements review | 0 | Americas | Prod. Dev. | 2019 | August | 1216894
1196 | Scope | Change | Gap | 12 | 6 | There were gaps in the functional document | 0 | Americas | Prod. Dev. | 2009 | March | 719844
1197 | Scope | Defect | Software | 19 | 7 | Virus destroys interface software in two required languages, requiring rework to replace them. | 0 | Americas | Prod. Dev. | 2007 | January | 748600
1198 | Resource | Outsourcing | Late or poor output | 17 | 4 | Components delayed, and contractors were committed to other work and were only able to work part-time | 2 | Eur/ME | Prod. Dev. | 2009 | July | 798252
1199 | Resource | People | Loss | 7 | 4 | Process improvement project has low priority and high turnover. | 0 | Americas | Prod. Dev. | 2005 | March | 246281
1200 | Scope | Change | Creep | 5 | 4 | Processes were changed and made more complex late in the project | 0 | Americas | Prod. Dev. | 2016 | March | 124465
1201 | Scope | Change | Gap | 12 | 3 | Incorrect decimal pay rate did not reflect the true and accurate pay | 2 | Eur/ME | IT/Solution | 2011 | February | 951720
1202 | Scope | Defect | Hardware | 7 | 6 | Test hardware does not work. All tests done manually using extra time and effort. | 2 | Eur/ME | Prod. Dev. | 2016 | November | 459347
1203 | Scope | Defect | Software | 7 | 5 | During the printing test, the printer couldn’t interpret the incoming file | 0 | Americas | Prod. Dev. | 2007 | May | 489580
1204 | Resource | Outsourcing | Delayed start | 14 | 5 | Delayed start of work due to negotiation of contract. | 0 | Americas | Prod. Dev. | 2003 | July | 452592
1205 | Schedule | Estimates | Judgment | 19 | 7 | Company underestimated the scope of the project | 0 | Americas | IT/Solution | 2013 | November | 1111405
1206 | Resource | Money | Limitation | 13 | 5 | Inadequate staffing | 0 | Americas | Prod. Dev. | 2016 | June | 630201
1207 | Resource | People | Queuing | 16 | 4 | There were not enough study directors to conduct all the studies needed | 0 | Americas | Prod. Dev. | 2007 | July | 423392
1208 | Schedule | Estimates | Learning | 15 | 5 | Software engineers, not technicians skilled in the work, were used to complete product testing | 2 | Eur/ME | Prod. Dev. | 2012 | January | 414585
1209 | Resource | People | Loss | 9 | 7 | Key engineer on project leaves the company | 0 | Americas | IT/Solution | 2007 | September | 495144
1210 | Scope | Change | Creep | 7 | 6 | Specifications poorly defined until late in the project. | 0 | Americas | Prod. Dev. | 2014 | June | 363440
1211 | Scope | Change | Gap | 18 | 4 | Scope change adding new categories and fees | 2 | Eur/ME | IT/Solution | 2013 | December | 1384146
1212 | Scope | Defect | Hardware | 10 | 4 | Components do not work as documented. Replacements and software workarounds required. | 0 | Americas | Prod. Dev. | 2019 | June | 477710
1213 | Schedule | Delay | Parts | 10 | 4 | Key supplier lost in the middle of a project | 2 | Eur/ME | IT/Solution | 2004 | May | 739820
1214 | Schedule | Delay | Parts | 12 | 4 | Parts shipped by sea from Asia, not air. | 0 | Americas | Prod. Dev. | 2007 | September | 297828
1215 | Schedule | Dependency | Project | 19 | 6 | Commitment given, but deliverables were late. | 0 | Americas | IT/Solution | 2001 | October | 543381
1216 | Schedule | Estimates | Deadline | 8 | 7 | Unrealistic compressed timeline | 0 | Americas | Prod. Dev. | 2018 | August | 320928
1217 | Scope | Change | Gap | 12 | 6 | Specifications incomplete and late. Delayed project start. | 2 | Eur/ME | Prod. Dev. | 2010 | December | 609192
1218 | Scope | Change | Gap | 7 | 5 | Resistance of the business stakeholders to reach consensus on the project’s scope | 0 | Americas | Prod. Dev. | 2015 | July | 203854
1219 | Resource | Outsourcing | Late or poor output | 5 | 3 | Outsource partner replaced several key people on team | 0 | Americas | IT/Solution | 2015 | September | 320030
1220 | Resource | Outsourcing | Late or poor output | 19 | 4 | High turnover leads to delays and crisis management. | 0 | Americas | Prod. Dev. | 2007 | February | 1301994
1221 | Resource | People | Queuing | 21 | 4 | Conflict for resources with a higher priority project | 0 | Americas | Prod. Dev. | 2017 | June | 1551942
1222 | Resource | People | Temp loss | 6 | 7 | Software engineer was lost to a higher priority project | 2 | Eur/ME | Prod. Dev. | 2004 | December | 452604
1223 | Schedule | Delay | Hardware | 16 | 7 | Required server was misplaced in shipping | 2 | Eur/ME | IT/Solution | 2006 | September | 872464
1224 | Scope | Change | Gap | 10 | 3 | Kitchen remodel required a seismic upgrade | 2 | Eur/ME | IT/Solution | 2008 | May | 262250
1225 | Scope | Change | Gap | 9 | 4 | System functions well in Germany, but has no German documentation. Delay for translation. | 0 | Americas | IT/Solution | 2017 | June | 525600
1226 | Resource | People | Queuing | 8 | 4 | Critical task assigned to a heavily booked expert | 0 | Americas | IT/Solution | 2007 | January | 334264
1227 | Resource | Outsourcing | Late or poor output | 16 | 5 | Components delayed, and contractors were committed to other work and were only able to work part-time | 0 | Americas | Prod. Dev. | 2006 | March | 913488
1228 | Resource | People | Loss | 9 | 3 | Manager quit his job because of his mother's illness | 2 | Eur/ME | IT/Solution | 2004 | January | 548433
1229 | Scope | Defect | Software | 11 | 6 | Purchased component never delivered (vaporware). Workaround developed by brute force (not high-tech and difficult to support). | 2 | Eur/ME | IT/Solution | 2009 | December | 803220
1230 | Schedule | Dependency | Project | 12 | 6 | Coordination of the scopes of work between several projects | 0 | Americas | Prod. Dev. | 2019 | January | 395244
1231 | Resource | Money | Limitation | 14 | 4 | Insufficient budget and Staff Resources allocated | 0 | Americas | Prod. Dev. | 2003 | August | 515228
1232 | Scope | Change | Gap | 7 | 4 | Poor scoping and missed end-user requirements | 0 | Americas | IT/Solution | 2007 | February | 539210
1233 | Schedule | Delay | Decision | 13 | 7 | PM had insufficient decision-making authority | 0 | Americas | IT/Solution | 2013 | June | 635167
1234 | Scope | Change | Dependency | 6 | 3 | Homeland security has changed Import requirements late | 0 | Americas | IT/Solution | 2019 | January | 172410
1235 | Scope | Change | Gap | 12 | 6 | There was no detailed description of the software deliverable in the project plan | 0 | Americas | IT/Solution | 2012 | January | 314088
1236 | Schedule | Estimates | Learning | 12 | 6 | Development team didn’t have the expertise to implement the modules | 0 | Americas | IT/Solution | 2010 | May | 711696
1237 | Resource | People | Loss | 13 | 5 | Key contributor injured in a car accident | 0 | Americas | IT/Solution | 2008 | May | 579397
1238 | Resource | People | Loss | 10 | 5 | Project leader was transferred to another project | 0 | Americas | IT/Solution | 2009 | December | 368340
1239 | Schedule | Delay | Decision | 12 | 6 | Endless debate over choice of three possible approaches for project work | 2 | Eur/ME | Prod. Dev. | 2008 | May | 787056
1240 | Schedule | Dependency | Legal | 22 | 3 | Sponsors who knew the system well didn't bother to analyze the impact of rolling out sensitive data to global users without security in place | 0 | Americas | IT/Solution | 2002 | January | 1667622
1241 | Schedule | Estimates | Deadline | 22 | 5 | A six month conversion period from the date a contract is signed is the norm, but project goal is four months | 0 | Americas | IT/Solution | 2001 | October | 884400
1242 | Scope | Change | Gap | 22 | 6 | Unique data in each region prevented information flow | 2 | Eur/ME | IT/Solution | 2006 | July | 1397198
1243 | Scope | Defect | Hardware | 19 | 4 | Packaging for a critical white board component was too flimsy to withstand standard shipping stress | 0 | Americas | Prod. Dev. | 2007 | July | 924768
1244 | Scope | Change | Gap | 21 | 4 | Manufacturing process was not scalable and had to be redesigned | 2 | Eur/ME | Prod. Dev. | 2009 | March | 1476993
1245 | Resource | People | Late start | 6 | 4 | Project has funding, but limited staff delays start. | 0 | Americas | Prod. Dev. | 2005 | February | 288480
1246 | Resource | Money | Limitation | 15 | 5 | Lack of funds for travel at launch | 0 | Americas | Prod. Dev. | 2007 | October | 619545
1247 | Resource | Outsourcing | Delayed start | 12 | 5 | Vendor currently has limited capacity and could not hire quickly enough to support this product | 2 | Eur/ME | IT/Solution | 2009 | May | 612168
1248 | Resource | People | Loss | 6 | 6 | Key resource pulled from a high priority project | 0 | Americas | IT/Solution | 2016 | November | 441324
1249 | Resource | People | Temp loss | 15 | 6 | No vacation/time-off estimate planning was done | 0 | Americas | IT/Solution | 2019 | January | 760335
1250 | Scope | Change | Creep | 15 | 5 | Changing product definition and poor estimation of effort | 0 | Americas | Prod. Dev. | 2007 | February | 1072560
1251 | Scope | Change | Gap | 21 | 4 | User specifications not defined until late in the project. | 0 | Americas | IT/Solution | 2004 | January | 1255296
1252 | Scope | Change | Gap | 8 | 5 | Multiple team program with some work not clearly delegated. Assigned and added late. | 0 | Americas | Prod. Dev. | 2014 | March | 413808
1253 | Scope | Change | Gap | 9 | 5 | Product developed for multiple platforms, but works only on 2. Delayed to fix some, but others dropped at project end. | 0 | Americas | Prod. Dev. | 2017 | April | 197604
1254 | Scope | Change | Gap | 10 | 5 | Lack of initial consensus on the scope | 2 | Eur/ME | Prod. Dev. | 2002 | February | 572570
1255 | Resource | Outsourcing | Late or poor output | 17 | 4 | Vendor was inexperienced with relevant equipment | 0 | Americas | Prod. Dev. | 2009 | April | 1302098
1256 | Schedule | Delay | Information | 18 | 3 | Metrics required by process improvement project collected and delivered late. | 0 | Americas | IT/Solution | 2006 | January | 559098
1257 | Scope | Change | Gap | 17 | 6 | Changes were approved by the business users without proper testing | 0 | Americas | IT/Solution | 2007 | August | 1193621
1258 | Scope | Change | Gap | 14 | 7 | One week’s analysis is insufficient to capture needed requirements | 0 | Americas | IT/Solution | 2002 | March | 1029168
1259 | Scope | Change | Gap | 22 | 5 | Analysis group not involved in planning meetings | 0 | Americas | Prod. Dev. | 2007 | June | 943206
1260 | Resource | Outsourcing | Delayed start | 11 | 5 | New supplier, extensive start up and coordination issues. | 0 | Americas | Prod. Dev. | 2018 | August | 283899
1261 | Resource | Outsourcing | Late or poor output | 18 | 6 | Work from team in Pakistan failed miserably | 0 | Americas | IT/Solution | 2007 | January | 1004004
1262 | Resource | Outsourcing | Late or poor output | 7 | 7 | Labor union of subcontractor went on stike | 0 | Americas | Prod. Dev. | 2011 | February | 330442
1263 | Resource | People | Loss | 19 | 3 | Expert developer left the company | 0 | Americas | IT/Solution | 2005 | March | 488984
1264 | Resource | People | Loss | 21 | 6 | Chief architect quit, and was the only person with critical skills | 0 | Americas | IT/Solution | 2013 | January | 1468425
1265 | Resource | People | Temp loss | 13 | 6 | Production partner had a personal issue which brought production to a halt | 0 | Americas | IT/Solution | 2004 | August | 508417
1266 | Schedule | Delay | Information | 7 | 6 | Tests delayed at project end; delayed access to databases | 0 | Americas | IT/Solution | 2018 | November | 497119
1267 | Schedule | Delay | Information | 8 | 7 | Parts of development team have a 12 hour time difference. Bugs take 2-3 days longer to fix, on average. | 0 | Americas | IT/Solution | 2015 | June | 327192
1268 | Schedule | Estimates | Judgment | 10 | 5 | Cabling estimates too optimistic. | 0 | Americas | IT/Solution | 2009 | April | 635530
1269 | Schedule | Estimates | Learning | 12 | 4 | Lack of in-house expertise of the source system | 0 | Americas | IT/Solution | 2015 | May | 736752
1270 | Scope | Change | Gap | 14 | 6 | Database of components had not been updated to current OSHA standards | 0 | Americas | IT/Solution | 2009 | June | 1039500
1271 | Scope | Defect | Hardware | 20 | 3 | Prototype problems excessive; more time to fix than planned. | 0 | Americas | Prod. Dev. | 2018 | December | 1049060
1272 | Scope | Change | Creep | 5 | 7 | Scope continuously changed by client | 0 | Americas | Prod. Dev. | 2003 | March | 352965
1273 | Resource | Outsourcing | Delayed start | 6 | 4 | Planning the terms of the agreement and negotiating the contracts took time, making the project begin late | 0 | Americas | Prod. Dev. | 2009 | October | 477366
1274 | Resource | Outsourcing | Late or poor output | 5 | 4 | Change requested and agreed to, but supplier ships late and it does not work. | 0 | Americas | IT/Solution | 2015 | February | 373370
1275 | Resource | Outsourcing | Late or poor output | 17 | 4 | Contaminated specimen for cell culture had to be replaced by the contract organization | 0 | Americas | Prod. Dev. | 2002 | October | 861900
1276 | Resource | Outsourcing | Late or poor output | 10 | 6 | Subcontractor failed to understand technology and requirements | 0 | Americas | IT/Solution | 2004 | February | 380990
1277 | Resource | Outsourcing | Late or poor output | 13 | 3 | Partner on project defaults. | 0 | Americas | Prod. Dev. | 2017 | February | 346775
1278 | Resource | Outsourcing | Late or poor output | 17 | 3 | The other company was unable to stick to needed deadlines | 0 | Americas | Prod. Dev. | 2007 | September | 477462
1279 | Resource | People | Late start | 10 | 3 | People still on prior project | 0 | Americas | IT/Solution | 2013 | May | 665960
1280 | Resource | People | Loss | 12 | 6 | Loss of a programmer | 0 | Americas | Prod. Dev. | 2010 | May | 281484
1281 | Resource | People | Loss | 17 | 4 | Lack of head count from a 10% company-wide lay-off. | 0 | Americas | IT/Solution | 2018 | February | 858364
1282 | Resource | People | Motivation | 16 | 6 | Project manger and the Product Manager didn’t get along on an interpersonal level | 0 | Americas | Prod. Dev. | 2007 | March | 873184
1283 | Resource | People | Queuing | 19 | 7 | Key decisions stalled when system architect not available. | 0 | Americas | Prod. Dev. | 2007 | October | 834613
1284 | Resource | People | Queuing | 10 | 4 | One SME for several projects | 0 | Americas | Prod. Dev. | 2018 | January | 420720
1285 | Resource | People | Temp loss | 22 | 7 | Peak season begins earlier than expected and impedes project progress | 0 | Americas | IT/Solution | 2007 | January | 1172842
1286 | Schedule | Delay | Decision | 13 | 5 | PM had insufficient decision-making authority | 0 | Americas | IT/Solution | 2009 | December | 290498
1287 | Schedule | Delay | Information | 17 | 5 | Old application to be modified for Y2K had no documentation, and finding original code took weeks. | 0 | Americas | Prod. Dev. | 2013 | April | 972196
1288 | Schedule | Delay | Parts | 15 | 6 | Delay in the delivery of the test samples | 0 | Americas | Prod. Dev. | 2004 | October | 1073625
1289 | Schedule | Dependency | Infrastructure | 5 | 6 | Building permit was issued late due to roof damages | 0 | Americas | IT/Solution | 2007 | September | 338145
1290 | Schedule | Dependency | Project | 15 | 7 | Fix for critical bug was delayed | 0 | Americas | Prod. Dev. | 2009 | April | 1151730
1291 | Schedule | Estimates | Deadline | 11 | 7 | Apartments were sold before construction begins with commitments based on requests, not planning | 0 | Americas | IT/Solution | 2015 | December | 366993
1292 | Schedule | Estimates | Judgment | 21 | 6 | Work was significantly underestimated for the project | 0 | Americas | IT/Solution | 2013 | August | 778176
1293 | Schedule | Estimates | Judgment | 9 | 7 | Effort estimate was significantly under-estimated | 0 | Americas | Prod. Dev. | 2018 | January | 540306
1294 | Schedule | Estimates | Learning | 18 | 7 | Neophyte project staff lacked system expertise. | 0 | Americas | IT/Solution | 2019 | May | 807606
1295 | Schedule | Estimates | Learning | 8 | 5 | Lack of expertise, experience and inadequate training | 0 | Americas | IT/Solution | 2007 | January | 415960
1296 | Schedule | Estimates | Learning | 6 | 4 | Lacked expertise needed for project (SOW too high level | 0 | Americas | Prod. Dev. | 2009 | April | 462378
1297 | Scope | Change | Creep | 20 | 5 | Scope expanded during the course of the project | 0 | Americas | IT/Solution | 2006 | November | 761080
1298 | Scope | Change | Creep | 5 | 5 | System expanded to into include two more cities for political reasons | 0 | Americas | IT/Solution | 2001 | June | 262545
1299 | Scope | Change | Creep | 21 | 7 | Poor scoping led to scope creep | 0 | Americas | Prod. Dev. | 2017 | September | 1346163
1300 | Scope | Change | Creep | 8 | 6 | Project specifications had changed and the material needed during the design phase had to be imported from overseas | 0 | Americas | Prod. Dev. | 2018 | January | 543744
1301 | Scope | Change | Creep | 13 | 3 | Adding two more configurations tripled the scope with the same staff | 0 | Americas | Prod. Dev. | 2014 | March | 899886
1302 | Scope | Change | Creep | 15 | 7 | Significant growth of scope in renovation project | 0 | Americas | IT/Solution | 2017 | September | 1194690
1303 | Scope | Change | Creep | 11 | 7 | Late change required new hardware and 2 phase delivery | 0 | Americas | Prod. Dev. | 2004 | January | 825275
1304 | Scope | Change | Creep | 19 | 5 | Application changed for prospective Chinese customer (who did not buy) | 0 | Americas | Prod. Dev. | 2019 | November | 382299
1305 | Scope | Change | Dependency | 17 | 5 | Homeland security has changed Import requirements late | 0 | Americas | IT/Solution | 2008 | June | 1089615
1306 | Scope | Change | Gap | 11 | 3 | There was no detailed description of the software deliverable in the project plan | 0 | Americas | IT/Solution | 2005 | July | 569932
1307 | Scope | Change | Gap | 21 | 6 | A mid-project review turned up numerous regulations that were not implemented | 0 | Americas | IT/Solution | 2015 | July | 696171
1308 | Scope | Change | Gap | 14 | 3 | Significant additional testing required; discovered late | 0 | Americas | IT/Solution | 2007 | April | 542822
1309 | Scope | Change | Gap | 22 | 3 | Peak season begun earlier than expected and Higher Freight Volume than usual | 0 | Americas | IT/Solution | 2018 | June | 1273118
1310 | Scope | Change | Gap | 16 | 4 | Bad choice of billing threshold problems forced system redesign | 0 | Americas | IT/Solution | 2007 | May | 969968
1311 | Scope | Change | Gap | 8 | 3 | Scope initially consisted only of general objectives | 0 | Americas | IT/Solution | 2007 | May | 291096
1312 | Scope | Change | Gap | 5 | 7 | There were gaps in the functional document | 0 | Americas | Prod. Dev. | 2019 | April | 250610
1313 | Scope | Change | Gap | 13 | 7 | Problems with manufacturing arose that were not seen in the original analysis | 0 | Americas | Prod. Dev. | 2006 | June | 544050
1314 | Scope | Change | Gap | 9 | 6 | Key requirements were uncovered late | 0 | Americas | Prod. Dev. | 2007 | March | 244026
1315 | Scope | Change | Gap | 16 | 7 | Poor stakeholder buy-in | 0 | Americas | Prod. Dev. | 2014 | June | 566608
1316 | Scope | Change | Gap | 6 | 3 | Module 1 team did not involve other developers during the initial scoping | 0 | Americas | IT/Solution | 2003 | June | 256794
1317 | Scope | Defect | Hardware | 19 | 4 | Defect discovered after delivery to customer | 0 | Americas | IT/Solution | 2009 | September | 1416374
1318 | Scope | Defect | Hardware | 7 | 5 | Late ramp problem. Quadrupled resources and caused major slip. | 0 | Americas | Prod. Dev. | 2007 | January | 362173
1319 | Scope | Defect | Hardware | 7 | 6 | Defective component--Bugs had to be fixed | 0 | Americas | Prod. Dev. | 2011 | March | 303639
1320 | Scope | Defect | Software | 9 | 6 | System tool could not be scaled to a huge web application | 0 | Americas | IT/Solution | 2007 | July | 190953
1321 | Scope | Defect | Software | 21 | 3 | Database contains incorrect information and the QA environment is unstable | 0 | Americas | IT/Solution | 2003 | August | 565341
1322 | Scope | Defect | Software | 21 | 7 | Initial code release was a major failure | 0 | Americas | IT/Solution | 2004 | August | 1573824
1323 | Scope | Defect | Software | 6 | 5 | Virus destroys interface software in two required languages, requiring rework to replace them. | 0 | Americas | Prod. Dev. | 2016 | August | 275898
1324 | Scope | Defect | Software | 5 | 3 | New technology to be used failed to meet the needs | 0 | Americas | Prod. Dev. | 2016 | January | 353425
1325 | Scope | Defect | Software | 20 | 5 | Purchased application led to performance problems. | 0 | Americas | IT/Solution | 2007 | October | 1354960
1326 | Resource | Money | Limitation | 5 | 6 | Internal resources were not available on a full time basis | 0 | Americas | IT/Solution | 2018 | September | 350185
1327 | Resource | Money | Limitation | 7 | 5 | Severe funding cutbacks (66% of project team) | 0 | Americas | IT/Solution | 2013 | July | 327943
1328 | Resource | Money | Limitation | 20 | 6 | Insufficient resources assigned to the project | 0 | Americas | Prod. Dev. | 2007 | September | 930900
1329 | Resource | Money | Limitation | 11 | 7 | Project Budget was restricted to the bare minimum estimated | 0 | Americas | Prod. Dev. | 2009 | June | 785147
1330 | Scope | Change | Creep | 13 | 6 | Contract had no input from project team and few defined specs. Changes poorly managed and project was very late. | 0 | Americas | IT/Solution | 2002 | September | 530361
1331 | Scope | Change | Creep | 7 | 3 | The project team agreed to new requirements; unfortunately, some of the changes promised were not even possible | 0 | Americas | Prod. Dev. | 2005 | September | 288239
1332 | Scope | Defect | Software | 20 | 3 | In UAT testing, a fatal flaw sent the deliverable back to development | 0 | Americas | IT/Solution | 2002 | February | 890480
1333 | Schedule | Estimates | Judgment | 21 | 4 | Goal of 90% participation in study is proved infeasible | 0 | Americas | IT/Solution | 2012 | September | 616140
1334 | Scope | Change | Gap | 22 | 3 | 75% of the requirements were unknowninitially to the project staff | 0 | Americas | IT/Solution | 2007 | October | 1678842
1335 | Resource | Outsourcing | Late or poor output | 6 | 4 | Serbian Developers took longer than expected to complete the project | 0 | Americas | IT/Solution | 2007 | July | 197820
1336 | Schedule | Estimates | Judgment | 5 | 4 | Effort estimate was significantly under-estimated | 0 | Americas | Prod. Dev. | 2006 | April | 108045
1337 | Resource | People | Loss | 5 | 3 | Cardiologist on the project team resigned and had to be replaced | 0 | Americas | Prod. Dev. | 2005 | September | 230120
1338 | Resource | People | Loss | 7 | 7 | Key programmer resigned | 0 | Americas | Prod. Dev. | 2006 | August | 526617
1339 | Scope | Change | Creep | 19 | 3 | Late inclusions resulted in change orders and delay | 0 | Americas | IT/Solution | 2012 | May | 773167
1340 | Schedule | Delay | Parts | 7 | 3 | Manufacutring group did not have the capcity to produce a critical new enzyme | 0 | Americas | Prod. Dev. | 2006 | October | 230104
1341 | Resource | People | Loss | 17 | 3 | Executive director stayed two months and then left | 0 | Americas | Prod. Dev. | 2007 | April | 873188
1342 | Resource | People | Loss | 20 | 5 | Half way through the project three of the engineers had to return to China due to visa issues | 0 | Americas | Prod. Dev. | 2008 | August | 526000
1343 | Scope | Change | Creep | 18 | 3 | Solution project priced "to win" and had few details on work; led to big losses and delays. | 0 | Americas | IT/Solution | 2015 | July | 1148058
1344 | Scope | Change | Gap | 14 | 3 | Requirements document for a new database system were not specific enough regarding user interface details | 0 | Americas | IT/Solution | 2003 | January | 346696
1345 | Scope | Change | Gap | 11 | 7 | Key telecom requirement detected late | 0 | Americas | IT/Solution | 2007 | February | 570339
1346 | Scope | Change | Gap | 17 | 6 | Need to upgrade detected only at project end | 0 | Americas | IT/Solution | 2011 | February | 855100
1347 | Schedule | Delay | Decision | 14 | 6 | Negotiation and training on a new tool took more time than planned | 0 | Americas | IT/Solution | 2007 | April | 292026
1348 | Scope | Change | Creep | 22 | 4 | Sponsor agreed to specifications on door, loading docks, structural supports etc that impeded efficient work flows | 0 | Americas | Prod. Dev. | 2003 | March | 1714482
1349 | Scope | Defect | Hardware | 20 | 7 | Half way through the upgrade; the new processor failed | 0 | Americas | IT/Solution | 2012 | June | 1485540
1350 | Resource | People | Loss | 10 | 4 | Loss of a key person | 0 | Americas | Prod. Dev. | 2007 | October | 629780
1351 | Schedule | Dependency | Infrastructure | 18 | 5 | Last minute infrastructure changes and conflict with another deployment | 0 | Americas | IT/Solution | 2010 | June | 552708
1352 | Resource | Outsourcing | Delayed start | 21 | 7 | Excessive challenge of initiating a project in different time zones | 0 | Americas | IT/Solution | 2003 | August | 1399377
1353 | Resource | Outsourcing | Late start | 20 | 4 | Subcontractor overbooked; not available when needed | 0 | Americas | IT/Solution | 2013 | August | 997880
1354 | Resource | People | Temp loss | 14 | 4 | 2 key team members lost for a time because of illness | 0 | Americas | IT/Solution | 2007 | January | 988834
1355 | Resource | People | Temp loss | 8 | 4 | Loss of key members of a project team in an already constrained project. | 0 | Americas | Prod. Dev. | 2003 | March | 284992
1356 | Scope | Change | Gap | 21 | 4 | The development team in Pakistan misinterpreted a number of req'ts | 0 | Americas | IT/Solution | 2001 | November | 1532433
1357 | Resource | Outsourcing | Late or poor output | 6 | 7 | Supplier failure, inputs late and inadequate | 0 | Americas | IT/Solution | 2007 | April | 160032
1358 | Resource | People | Loss | 20 | 5 | Key people resigned, leaving too few to complete project and training on time | 0 | Americas | IT/Solution | 2004 | February | 852900
1359 | Resource | People | Queuing | 18 | 5 | The test capabilities constitute a bottleneck late in release cycles. | 0 | Americas | Prod. Dev. | 2017 | July | 834552
1360 | Resource | People | Temp loss | 19 | 7 | Reorganization during product ramp creates chaos and ownership problems. | 0 | Americas | Prod. Dev. | 2011 | March | 547884
1361 | Schedule | Delay | Decision | 17 | 3 | Problems getting timely management decisions. | 0 | Americas | Prod. Dev. | 2016 | June | 937346
1362 | Scope | Defect | Hardware | 9 | 4 | fittings and assemblies were not up to project standards | 0 | Americas | IT/Solution | 2007 | September | 374571
1363 | Scope | Defect | Hardware | 14 | 7 | Process reliability was too low and required a new component to work | 0 | Americas | Prod. Dev. | 2001 | June | 442232
1364 | Resource | People | Loss | 16 | 3 | Chef quit two days before the café was scheduled to open | 0 | Americas | IT/Solution | 2001 | July | 620368
1365 | Resource | People | Temp loss | 22 | 4 | Key contributor out ill at critical time. | 0 | Americas | IT/Solution | 2007 | April | 1108492
1366 | Schedule | Delay | Parts | 11 | 4 | Shipping documents not filled in correctly | 0 | Americas | Prod. Dev. | 2003 | August | 317229
1367 | Scope | Change | Gap | 15 | 3 | PM did not take the time to determine what the move entailed | 0 | Americas | IT/Solution | 2012 | September | 846660
1368 | Resource | Outsourcing | Late or poor output | 7 | 3 | Subcontracted work failed to meet client's criteria | 0 | Americas | IT/Solution | 2009 | February | 192724
1369 | Resource | Outsourcing | Late or poor output | 14 | 4 | Serbian Developers took longer than expected to complete the project | 0 | Americas | IT/Solution | 2012 | November | 283374
1370 | Resource | People | Loss | 11 | 3 | Expert Cardiologist no longer available | 0 | Americas | Prod. Dev. | 2008 | April | 578380
1371 | Resource | People | Loss | 16 | 4 | Sudden exit of the primary developer | 0 | Americas | Prod. Dev. | 2008 | April | 1212832
1372 | Resource | People | Loss | 22 | 7 | Product owner having unique knowledge left the company | 0 | Americas | Prod. Dev. | 2007 | December | 1081256
1373 | Resource | People | Temp loss | 15 | 3 | Several employees had to take a leave of absence due to a family emergency | 0 | Americas | IT/Solution | 2008 | February | 679200
1374 | Schedule | Delay | Decision | 9 | 7 | Stakeholders were numerous and unable to come to a timely decision | 0 | Americas | IT/Solution | 2007 | March | 246663
1375 | Schedule | Delay | Information | 9 | 4 | Merging of multiple standards is needed to support reorganization. Lack of a new, common definition delayed the project to convert data. | 0 | Americas | IT/Solution | 2009 | June | 344304
1376 | Schedule | Delay | Parts | 15 | 6 | Insufficient amount of test material was sent to the contract lab | 0 | Americas | Prod. Dev. | 2007 | June | 638445
1377 | Schedule | Estimates | Judgment | 19 | 3 | Team did not break down the processes enough to clearly identify each step | 0 | Americas | Prod. Dev. | 2006 | September | 394174
1378 | Scope | Change | Gap | 14 | 4 | Poor scoping and missed end-user requirements | 0 | Americas | IT/Solution | 2006 | March | 923062
1379 | Scope | Change | Gap | 22 | 4 | Some countries provided incomplete requirements | 0 | Americas | IT/Solution | 2016 | November | 1379664
1380 | Scope | Change | Gap | 6 | 7 | Testing requierments poorly defined, so functionality deferred to phase 2 | 0 | Americas | IT/Solution | 2001 | August | 152244
1381 | Scope | Change | Gap | 9 | 7 | Poor communications resulted in never truly understanding customer needs | 0 | Americas | IT/Solution | 2007 | September | 203517
1382 | Scope | Change | Gap | 7 | 6 | Poor communications and assumptions were not backed by written agreements | 0 | Americas | IT/Solution | 2007 | May | 400407
1383 | Scope | Change | Gap | 12 | 5 | There was a design flaw in the roof detail | 0 | Americas | IT/Solution | 2007 | June | 495000
1384 | Scope | Change | Gap | 14 | 7 | Scope of the project increased following final requirements review | 0 | Americas | Prod. Dev. | 2007 | January | 578340
1385 | Scope | Change | Gap | 5 | 7 | Original product requirements document was incomplete | 0 | Americas | Prod. Dev. | 2015 | October | 112265
1386 | Scope | Defect | Software | 9 | 7 | Tests revealed a fatal issue, deferring release to next quartely update | 0 | Americas | IT/Solution | 2015 | June | 212157
1387 | Scope | Change | Gap | 9 | 5 | Clinical evidence was insufficient for European market | 0 | Americas | Prod. Dev. | 2007 | March | 665226
1388 | Scope | Change | Gap | 19 | 7 | Lack of understanding the business processes used to develop manual reports and insufficient relevant experience | 0 | Americas | IT/Solution | 2010 | July | 679896
1389 | Schedule | Delay | Decision | 17 | 7 | Stakeholders were numerous and unable to come to a timely decision | 0 | Americas | IT/Solution | 2011 | November | 350965
1390 | Resource | People | Late start | 5 | 7 | People still on prior project | 0 | Americas | IT/Solution | 2005 | March | 289105
1391 | Scope | Change | Creep | 22 | 6 | Adding two more configurations tripled the scope with the same staff | 0 | Americas | Prod. Dev. | 2001 | December | 1413984
1392 | Resource | People | Loss | 10 | 6 | On this long project, turnover was high on project team and at customer. | 0 | Americas | IT/Solution | 2007 | March | 659170
1393 | Scope | Defect | Integration | 11 | 6 | Technology used for design is unstable | 0 | Americas | Prod. Dev. | 2019 | September | 507254
1394 | Scope | Defect | Software | 6 | 6 | Data conversion problems made the implementation of a new system dependent on manual reentry of data | 0 | Americas | IT/Solution | 2018 | May | 181374
1395 | Resource | Outsourcing | Late or poor output | 10 | 6 | Contracted with a small outside firm that didn’t understand the business | 0 | Americas | Prod. Dev. | 2007 | March | 506950
1396 | Resource | People | Loss | 18 | 7 | The only experienced programmer gave notice and left the company | 0 | Americas | IT/Solution | 2012 | June | 1259820
1397 | Resource | People | Loss | 7 | 6 | Both the full time developers assigned to the project quit the company | 0 | Americas | Prod. Dev. | 2008 | November | 438480
1398 | Resource | People | Queuing | 17 | 3 | Project is not complete until all users are trained. Coordinating schedules requires 4 months, not 2. | 0 | Americas | IT/Solution | 2007 | September | 590597
1399 | Scope | Defect | Software | 17 | 7 | A patch breaks other functionality in the system and is backed out until the next maintenance window | 0 | Americas | IT/Solution | 2018 | June | 1276309
1400 | Resource | Money | Limitation | 16 | 3 | The travel budget for the project was cut and led to inefficient long-distance collaboration | 0 | Americas | Prod. Dev. | 2003 | March | 849680
1401 | Resource | Outsourcing | Late or poor output | 20 | 4 | Management pushed plans to outsource printing operations, causing problems | 0 | Americas | IT/Solution | 2006 | June | 1485860
1402 | Resource | Outsourcing | Late or poor output | 16 | 5 | Consulting agency had not fulfilled its obligations under the terms of the contract | 0 | Americas | IT/Solution | 2002 | September | 636912
1403 | Scope | Change | Creep | 12 | 3 | Two new Features were introduced midway during development | 0 | Americas | Prod. Dev. | 2018 | February | 579492
1404 | Scope | Defect | Software | 13 | 5 | Memory problems not detected in test caused server crashes; backed out for more than a month | 0 | Americas | IT/Solution | 2007 | July | 1000467
1405 | Resource | Money | Limitation | 15 | 4 | Key consultant was let go at a critical time for coat reasons | 0 | Americas | IT/Solution | 2014 | February | 664230
1406 | Resource | Outsourcing | Late or poor output | 16 | 6 | Contractor provided inadequate survey data | 0 | Americas | Prod. Dev. | 2007 | November | 384096
1407 | Schedule | Delay | Hardware | 15 | 3 | Multiple phase roll out paused near the end, systems temporarily out of stock. | 0 | Americas | IT/Solution | 2009 | February | 632235
1408 | Scope | Change | Creep | 11 | 4 | Twelve additional design and construction tasks were added late | 0 | Americas | IT/Solution | 2009 | April | 663080
1409 | Scope | Change | Creep | 10 | 7 | Database used for system changed in mid project; more resources used and delay. | 0 | Americas | IT/Solution | 2017 | January | 734250
1410 | Scope | Defect | Hardware | 20 | 6 | Instrument system for customer based on Intel PC. New system released; fails to work as older model did. Finally installed with salvaged older PC. | 0 | Americas | IT/Solution | 2019 | December | 1424580
1411 | Scope | Defect | Software | 9 | 3 | Late testing failure | 0 | Americas | IT/Solution | 2003 | August | 689850
1412 | Schedule | Delay | Parts | 11 | 7 | Samples needed in Spain were late | 0 | Americas | IT/Solution | 2003 | April | 675048
1413 | Schedule | Delay | Parts | 20 | 3 | Component delivery late. Causes ramp delays. | 0 | Americas | Prod. Dev. | 2012 | October | 1501460
1414 | Scope | Change | Creep | 5 | 7 | Late design changes required manufacturing retooling at the last minute. | 0 | Americas | Prod. Dev. | 2015 | April | 130785
1415 | Scope | Change | Gap | 10 | 4 | Programmer didn’t understand what data was needed or why | 0 | Americas | IT/Solution | 2013 | January | 370190
1416 | Resource | Outsourcing | Delayed start | 15 | 7 | Slow start of work outsourced. | 0 | Americas | IT/Solution | 2012 | June | 390105
1417 | Resource | Outsourcing | Late or poor output | 13 | 3 | Slow renewal of contract for consultant; interruption in work | 0 | Americas | Prod. Dev. | 2007 | September | 789191
1418 | Resource | People | Late start | 22 | 7 | Project start delayed; team busy on other work. | 0 | Americas | Prod. Dev. | 2015 | March | 786368
1419 | Resource | People | Queuing | 7 | 3 | Business Operations Analyst was busy with another big project | 0 | Americas | Prod. Dev. | 2010 | June | 175742
1420 | Schedule | Delay | Parts | 10 | 5 | Boards would fail incoming quality check due to the specs given to fabrication house not being tight enough | 0 | Americas | Prod. Dev. | 2011 | July | 474310
1421 | Scope | Change | Creep | 10 | 4 | Program Manager squeezes in additional functionalities until the very last minute | 0 | Americas | Prod. Dev. | 2007 | April | 798150
1422 | Scope | Defect | Hardware | 20 | 7 | Problem arose that required use of a a novel raw material not in inventory | 0 | Americas | Prod. Dev. | 2009 | January | 1244440
1423 | Resource | People | Queuing | 19 | 6 | No engineer is available or has enough knowledge | 0 | Americas | IT/Solution | 2012 | July | 1491576
1424 | Schedule | Delay | Decision | 19 | 4 | Document reviews slipped due to conflicts and low priority. | 0 | Americas | Prod. Dev. | 2007 | August | 591812
1425 | Schedule | Delay | Information | 12 | 7 | Access to required support tools was not established | 0 | Americas | IT/Solution | 2005 | June | 537540
1426 | Resource | Outsourcing | Late or poor output | 8 | 4 | Lack of oversight and quality assurance led to short cuts being taken | 0 | Americas | Prod. Dev. | 2017 | September | 574080
1427 | Scope | Change | Creep | 11 | 3 | Failure to finalize Product Definition Document requirements | 0 | Americas | Prod. Dev. | 2007 | November | 723712
1428 | Scope | Change | Gap | 22 | 4 | Deficiency in the scope due to cutting corners | 0 | Americas | Prod. Dev. | 2007 | October | 1687114
1429 | Scope | Defect | Hardware | 18 | 4 | New chips caused the mother board to perform poorly | 0 | Americas | Prod. Dev. | 2005 | August | 617400
1430 | Resource | Money | Limitation | 16 | 6 | A team of 5 contract engineers were let go | 0 | Americas | IT/Solution | 2005 | April | 540432
1431 | Scope | Change | Creep | 9 | 6 | Late rescoping of 2-year project led to half-year slip. | 0 | Americas | IT/Solution | 2002 | April | 430452
1432 | Scope | Change | Creep | 11 | 4 | Excessive late changes | 0 | Americas | IT/Solution | 2007 | March | 421278
1433 | Resource | People | Loss | 22 | 5 | A company-wide reduction in force let go some of the people who were supposed to lead the next phase | 0 | Americas | Prod. Dev. | 2006 | February | 1499828
1434 | Resource | People | Temp loss | 18 | 4 | Mid-way in design stage, a key Engineer had a family emergency and had to leave the country for a month | 0 | Americas | IT/Solution | 2003 | July | 757944
1435 | Schedule | Delay | Information | 14 | 7 | Old application to be modified had no one left who knew it and no documentation. | 0 | Americas | IT/Solution | 2001 | October | 612808
1436 | Schedule | Delay | Parts | 16 | 4 | Quantity of Intel CPU processors needed not available | 0 | Americas | Prod. Dev. | 2007 | August | 491264
1437 | Schedule | Estimates | Learning | 7 | 4 | No staff that was knowledgeable in the technology | 0 | Americas | Prod. Dev. | 2007 | March | 490483
1438 | Resource | Money | Limitation | 10 | 7 | Project needs $150K per month in supplies but limit is $100K, which delayed progress. | 0 | Americas | Prod. Dev. | 2006 | November | 363850
1439 | Schedule | Delay | Hardware | 12 | 4 | The vendor sent equipment to a wrong location in Michigan instead of the Bay Area | 0 | Americas | Prod. Dev. | 2002 | November | 245436
1440 | Schedule | Estimates | Judgment | 11 | 4 | Problems using trainers and training materials from Germany | 0 | Americas | Prod. Dev. | 2012 | November | 447678
1441 | Scope | Change | Gap | 10 | 7 | Some of the cross functional teams were not involved early enough | 0 | Americas | Prod. Dev. | 2007 | November | 684030
1442 | Resource | Outsourcing | Late or poor output | 20 | 6 | Subcontractor did not build stairs according to the drawings and had to redo them | 0 | Americas | IT/Solution | 2017 | April | 865380
1443 | Resource | People | Queuing | 20 | 6 | Key contributor unavailable when needed. | 0 | Americas | Prod. Dev. | 2009 | May | 1206800
1444 | Scope | Change | Creep | 22 | 7 | Half way through the project the client changed the scope by adding additional work | 0 | Americas | IT/Solution | 2003 | October | 968066
1445 | Resource | People | Loss | 22 | 4 | The key person responsible for major marketing activities resigned | 0 | Americas | Prod. Dev. | 2001 | February | 773058
1446 | Resource | People | Temp loss | 11 | 7 | Earthquake in Taiwan makes part of the project team unavailable for work. | 0 | Americas | Prod. Dev. | 2016 | July | 801977
1447 | Schedule | Dependency | Legal | 6 | 4 | Delay in approval to proceed in France and German | 0 | Americas | Prod. Dev. | 2016 | March | 310944
1448 | Schedule | Estimates | Deadline | 17 | 4 | Unrealistic deadline set | 0 | Americas | Prod. Dev. | 2014 | November | 631635
1449 | Scope | Change | Creep | 8 | 3 | Power configuration change was requested too late in the schedule | 0 | Americas | IT/Solution | 2002 | September | 184648
1450 | Scope | Change | Creep | 21 | 3 | 6 sister organizations with an additional 250 users added to the project late | 0 | Americas | IT/Solution | 2019 | November | 449526
1451 | Scope | Change | Creep | 16 | 5 | "Minor" changes added and accepted late in project. Phase work doubled and delayed project end. | 0 | Americas | IT/Solution | 2008 | December | 509184
1452 | Scope | Change | Gap | 16 | 3 | Sponsor failed to communicate his requirements at the start of the project | 0 | Americas | IT/Solution | 2003 | September | 1049328
1453 | Resource | Money | Limitation | 12 | 4 | Lack of money for sufficient equipment | 0 | Americas | Prod. Dev. | 2007 | August | 701112
1454 | Resource | Outsourcing | Late or poor output | 12 | 7 | Local subcontractors lacked needed technical skills | 0 | Americas | IT/Solution | 2016 | March | 484548
1455 | Resource | Outsourcing | Late or poor output | 12 | 5 | Problems with vendor capacity and performance | 0 | Americas | IT/Solution | 2007 | March | 522048
1456 | Resource | People | Loss | 9 | 4 | At a critical stage of the project the Medical Director left the company | 0 | Americas | Prod. Dev. | 2006 | March | 228510
1457 | Resource | People | Temp loss | 8 | 5 | Key work in flu season delayed; most of staff out ill. | 0 | Americas | IT/Solution | 2004 | March | 231096
1458 | Schedule | Delay | Information | 17 | 5 | Errors in input data had to be fixed and reports re-generated | 0 | Americas | Prod. Dev. | 2007 | September | 603007
1459 | Scope | Change | Creep | 12 | 4 | Changes double the work on solution project; no change in funding. | 0 | Americas | IT/Solution | 2007 | June | 908808
1460 | Scope | Change | Gap | 10 | 3 | IT staff failed to understand the user requirements | 0 | Americas | IT/Solution | 2007 | September | 328730
1461 | Schedule | Delay | Decision | 22 | 4 | Client missed the deadline for feedback by several days | 0 | Americas | IT/Solution | 2006 | March | 475222
1462 | Schedule | Delay | Parts | 12 | 3 | Delivery problems on international shipment--paperwork, customs. | 0 | Americas | IT/Solution | 2007 | April | 244632
1463 | Schedule | Dependency | Project | 18 | 3 | Other group could not deliver on time, soI had to do work myself | 0 | Americas | IT/Solution | 2007 | August | 441882
1464 | Resource | Outsourcing | Late or poor output | 20 | 6 | Vendor was just starting out and didn’t have the equipment necessary | 0 | Americas | IT/Solution | 2016 | June | 1347540
1465 | Schedule | Dependency | Project | 13 | 5 | Firmware needed for an add-on paper handler dropped from printer project. | 0 | Americas | IT/Solution | 2007 | November | 824616
1466 | Scope | Change | Gap | 9 | 7 | Scope initially proposed for the project was not signed off by the upper management | 0 | Americas | IT/Solution | 2010 | September | 435150
1467 | Resource | Money | Limitation | 12 | 3 | Subject matter experts were let go to save money | 0 | Americas | Prod. Dev. | 2004 | February | 445212
1468 | Resource | People | Queuing | 16 | 4 | Insufficient QA resources to cover the auditing tasks and training tasks. | 0 | Americas | Prod. Dev. | 2012 | October | 775424
1469 | Scope | Change | Creep | 8 | 3 | Volume requirements increased late in project, requiring extensive rework | 0 | Americas | Prod. Dev. | 2001 | July | 576544
1470 | Scope | Change | Gap | 17 | 3 | Poor Fit/Gap analysis | 0 | Americas | Prod. Dev. | 2009 | April | 1211063
1471 | Scope | Change | Gap | 17 | 4 | Architect determined that the new design plan for the medical clinic would be considerably more complex than a simple remodeling job | 0 | Americas | Prod. Dev. | 2007 | December | 917558
1472 | Schedule | Dependency | Project | 20 | 5 | The manager of a related project allowed stakeholders to change the scope, driving continual changes | 0 | Americas | IT/Solution | 2017 | November | 763820
1473 | Scope | Change | Creep | 19 | 5 | Code freeze not done until the release date, making training and documentation late | 0 | Americas | Prod. Dev. | 2018 | March | 883519
1474 | Resource | Outsourcing | Late or poor output | 6 | 3 | Vendor was just starting out and didn’t have the equipment necessary | 0 | Americas | IT/Solution | 2011 | February | 379950
1475 | Resource | People | Temp loss | 8 | 7 | Several employees had to take a leave of absence due to a family emergency | 0 | Americas | IT/Solution | 2001 | April | 471224
1476 | Scope | Change | Gap | 7 | 6 | Poor communications and assumptions were not backed by written agreements | 0 | Americas | IT/Solution | 2012 | November | 186095
1477 | Resource | People | Temp loss | 6 | 7 | Peak season begins earlier than expected and impedes project progress | 0 | Americas | IT/Solution | 2007 | August | 249462
1478 | Scope | Change | Creep | 6 | 4 | Scope expanded during the course of the project | 0 | Americas | IT/Solution | 2015 | February | 173898
1479 | Scope | Defect | Hardware | 14 | 5 | Late ramp problem. Quadrupled resources and caused major slip. | 0 | Americas | Prod. Dev. | 2016 | April | 642348
1480 | Resource | Money | Limitation | 21 | 6 | Internal resources were not available on a full time basis | 0 | Americas | IT/Solution | 2007 | December | 1486023
1481 | Resource | Outsourcing | Late or poor output | 20 | 3 | Contractors are not sufficiently skilled nor motivated | 0 | Americas | Prod. Dev. | 2001 | September | 539600
1482 | Resource | Outsourcing | Late or poor output | 5 | 6 | Contractor installed smaller wire sizes than specified causing rework (after a fire) | 0 | Americas | IT/Solution | 2019 | October | 130895
1483 | Scope | Change | Gap | 17 | 7 | The delivery of the content started without the content being finalized | 0 | Americas | Prod. Dev. | 2007 | August | 791571
1484 | Resource | Outsourcing | Delayed start | 18 | 7 | For cost reasons, Asian supplier chosen. Qualification and paperwork caused delays. | 0 | Americas | Prod. Dev. | 2017 | August | 1132758
1485 | Resource | People | Queuing | 17 | 5 | Only one employee with other commitments had both the Cobol and relational database data conversion experience | 0 | Americas | IT/Solution | 2011 | July | 1125417
1486 | Resource | People | Queuing | 8 | 6 | The trained resource was tied up in other work | 0 | Americas | Prod. Dev. | 2007 | September | 271632
1487 | Schedule | Delay | Information | 19 | 3 | The business counterparts were not in agreement with which option to choose and went back and forth on the decision | 0 | Americas | Prod. Dev. | 2014 | August | 780767
1488 | Schedule | Dependency | Infrastructure | 14 | 3 | Current processes did not scale as needed by project, requiring redesign | 0 | Americas | Prod. Dev. | 2007 | January | 357952
1489 | Scope | Change | Creep | 22 | 6 | Project priorities and criteria are unclear through much of the project, causing lots of unneeded work. | 0 | Americas | Prod. Dev. | 2007 | October | 924418
1490 | Scope | Change | Gap | 17 | 6 | Original scope missed supply chain issues; could not be used without changes | 0 | Americas | IT/Solution | 2007 | August | 815150
1491 | Scope | Change | Gap | 20 | 5 | Faulty market & competitive analysis information discovered late; led to changes | 0 | Americas | Prod. Dev. | 2018 | March | 1258660
1492 | Scope | Defect | Hardware | 8 | 3 | During the feedback/review phase it was noticed that the numbers were incorrect | 0 | Americas | Prod. Dev. | 2007 | July | 444776
1493 | Resource | People | Queuing | 8 | 7 | There was only on one experienced consultant who knew the tool | 0 | Americas | IT/Solution | 2010 | February | 260344
1494 | Schedule | Dependency | Infrastructure | 15 | 7 | the infrastructure changes needed (network, microwave, etc) were not budgeted for the project | 0 | Americas | IT/Solution | 2011 | August | 1053795
1495 | Resource | Outsourcing | Late or poor output | 16 | 6 | Subcontractor delay causes compression of later work. | 0 | Americas | IT/Solution | 2019 | December | 706480
1496 | Resource | Outsourcing | Late or poor output | 22 | 7 | One factory went on labor strike for 2 weeks –Delayed production of 20 pallets | 0 | Americas | Prod. Dev. | 2014 | January | 1402302
1497 | Schedule | Delay | Hardware | 14 | 6 | Project work that customer is responsible for slips, causing project slip. | 0 | Americas | IT/Solution | 2009 | December | 922656
1498 | Schedule | Delay | Parts | 19 | 6 | Delivery problems on international shipment--paperwork, customs. | 0 | Americas | Prod. Dev. | 2007 | August | 826367
1499 | Schedule | Delay | Parts | 15 | 7 | Component needed in China for prototype not available; had to be shipped from US | 0 | Americas | Prod. Dev. | 2018 | October | 980310
1500 | Scope | Change | Gap | 20 | 7 | Retrofit project discovered hidden damage that had to be fixed | 0 | Americas | Prod. Dev. | 2001 | May | 593240
1501 | Scope | Defect | Software | 18 | 7 | When testing reveals a performance defect which is due to a conflict between two, or more, of the components significant extra work is required | 0 | Americas | IT/Solution | 2018 | November | 1357632
1502 | Scope | Defect | Software | 21 | 6 | Late quality assurance finds additional translation work is needed | 0 | Americas | Prod. Dev. | 2010 | April | 444801
1503 | Scope | Defect | Software | 14 | 6 | Translations are incomplete | 0 | Americas | IT/Solution | 2007 | March | 981792
1504 | Scope | Defect | Hardware | 5 | 7 | Old equipment failed at the last minute | 0 | Americas | IT/Solution | 2016 | September | 107070
1505 | Resource | Outsourcing | Late or poor output | 14 | 7 | A key component of the system was outsourced | 0 | Americas | IT/Solution | 2008 | April | 316596
1506 | Resource | Outsourcing | Late or poor output | 6 | 3 | Contract manufacturer failed to deliver a new drug | 0 | Americas | Prod. Dev. | 2002 | March | 350898
1507 | Resource | Outsourcing | Late or poor output | 10 | 3 | Deliverable received was inadequate | 0 | Americas | IT/Solution | 2007 | July | 717360
1508 | Resource | People | Motivation | 6 | 3 | A pool of unqualified, poorly performing, marginal staff to work with | 0 | Americas | IT/Solution | 2006 | December | 221100
1509 | Schedule | Delay | Information | 11 | 5 | Inadequate procedures for acceptance, quality, and communications with development in India | 0 | Americas | IT/Solution | 2014 | July | 799634
1510 | Schedule | Estimates | Learning | 11 | 3 | Ramp-up required 40 new test engineers | 0 | Americas | Prod. Dev. | 2007 | May | 457578
1511 | Scope | Change | Creep | 12 | 4 | One company expands scope in web design project without communicating or getting approval from others | 0 | Americas | IT/Solution | 2007 | January | 400956
1512 | Scope | Change | Creep | 12 | 7 | Six weeks in, a redesign to the most fundamental part of the research was done | 0 | Americas | Prod. Dev. | 2007 | February | 709644
1513 | Scope | Change | Dependency | 20 | 6 | Market change due to Improvements in technology became an ‘urgent’ requirement | 0 | Americas | IT/Solution | 2018 | August | 1264540
1514 | Scope | Change | Gap | 12 | 5 | Customer requirement discovered late in project | 0 | Americas | Prod. Dev. | 2003 | February | 559980
1515 | Scope | Change | Gap | 17 | 7 | Requirements are misunderstood or understood differently by multiple parties | 0 | Americas | Prod. Dev. | 2003 | January | 723248
1516 | Scope | Change | Gap | 7 | 5 | Problem was not fully understood, leading to many changes | 0 | Americas | Prod. Dev. | 2009 | September | 511616
1517 | Scope | Defect | Hardware | 13 | 6 | Our server crashed, which contains 4 months worth of info. No backup, had to be reentered. | 0 | Americas | Prod. Dev. | 2007 | March | 977106
1518 | Scope | Defect | Hardware | 7 | 7 | Hardware fails near the end of a three-month final test. Refabrication and retest required. | 0 | Americas | Prod. Dev. | 2007 | February | 277536
1519 | Scope | Defect | Software | 14 | 6 | Some users couldn't login because of mixed case passwords | 0 | Americas | IT/Solution | 2007 | April | 957222
1520 | Scope | Defect | Software | 20 | 4 | Software in use casused unacceptable image distortion | 0 | Americas | Prod. Dev. | 2019 | April | 1200540
1521 | Resource | Money | Limitation | 15 | 4 | Due to a layoff no writer was immediately available, so approval was delayed | 0 | Americas | Prod. Dev. | 2009 | January | 1028115
1522 | Resource | Money | Limitation | 8 | 7 | Insufficient budget and Staff Resources allocated | 0 | Americas | Prod. Dev. | 2003 | June | 633928
1523 | Scope | Change | Gap | 12 | 6 | Major system was begun with insufficient internal resources and without good requirements information | 0 | Americas | IT/Solution | 2017 | March | 343656
1524 | Schedule | Dependency | Project | 10 | 5 | Interdependencies in complex program underestimated and detected late. | 0 | Americas | IT/Solution | 2018 | October | 427220
1525 | Schedule | Delay | Information | 6 | 7 | Complexities of solution not understood, even well into project | 0 | Americas | IT/Solution | 2006 | May | 184164
1526 | Scope | Change | Gap | 21 | 6 | In creating a new system, there was too little involvement from the end users | 0 | Americas | Prod. Dev. | 2010 | August | 1027404
1527 | Schedule | Dependency | Infrastructure | 21 | 6 | Building permit was issued late due to roof damages | 0 | Americas | IT/Solution | 2014 | July | 683340
1528 | Scope | Change | Dependency | 16 | 5 | Business environment shifts forcing project changes, | 0 | Americas | Prod. Dev. | 2001 | April | 771616
1529 | Scope | Change | Gap | 16 | 7 | Project team was not aware that the new release would have a new UI | 0 | Americas | Prod. Dev. | 2013 | May | 588144
1530 | Scope | Defect | Software | 16 | 5 | Conversion from legacy system to SAP has multiple modules that cause unanticipated problems leading to delays of 3 to 10 days each to fix. | 0 | Americas | IT/Solution | 2007 | April | 1229120
1531 | Resource | Outsourcing | Delayed start | 11 | 3 | Delay in contract signing because legal had a higher priority contract to review | 0 | Americas | Prod. Dev. | 2019 | July | 466939
1532 | Resource | People | Loss | 11 | 4 | Team leader reassigned to another project and a new leader was assigned | 0 | Americas | IT/Solution | 2010 | June | 472791
1533 | Resource | People | Loss | 9 | 4 | Applications Engineer found another job and left the company | 0 | Americas | Prod. Dev. | 2007 | February | 390870
1534 | Schedule | Delay | Decision | 14 | 3 | Sponsorship not sustained and decisions and resources are problematic. | 0 | Americas | IT/Solution | 2007 | July | 986440
1535 | Scope | Change | Creep | 5 | 6 | Redesign added late in maintenance project for legacy system. Major slip. | 0 | Americas | IT/Solution | 2013 | November | 270760
1536 | Scope | Change | Gap | 18 | 5 | Sufficient time was not allocated to understand client needs and assumptions | 0 | Americas | IT/Solution | 2007 | December | 1416168
1537 | Resource | Outsourcing | Late or poor output | 21 | 7 | Vendor had a poor resource plan | 0 | Americas | IT/Solution | 2003 | May | 979986
1538 | Resource | People | Late start | 17 | 6 | Supply chain expert needed was hard to find and engage. | 0 | Americas | Prod. Dev. | 2005 | January | 1224204
1539 | Schedule | Delay | Parts | 14 | 7 | Inadequate water supply available to complete project, needed to be trucked in | 0 | Americas | Prod. Dev. | 2016 | January | 463120
1540 | Scope | Change | Creep | 14 | 3 | Late features were added | 0 | Americas | IT/Solution | 2013 | October | 1016778
1541 | Scope | Change | Creep | 15 | 7 | Conflicting design attributes and an unfocused process resulted in confusion and changes | 0 | Americas | Prod. Dev. | 2018 | April | 1161990
1542 | Scope | Change | Gap | 14 | 3 | Functional design was not properly done, due to limited access to users; led to changes | 0 | Americas | Prod. Dev. | 2007 | February | 850892
1543 | Resource | Outsourcing | Late or poor output | 13 | 7 | Vendor made a promise on something they could not deliver | 0 | Americas | IT/Solution | 2007 | November | 934713
1544 | Resource | People | Temp loss | 9 | 3 | Key code developer had a family emergency | 0 | Americas | IT/Solution | 2014 | October | 479097
1545 | Schedule | Estimates | Learning | 7 | 6 | Unavailability of skilled resources | 0 | Americas | IT/Solution | 2009 | January | 426755
1546 | Scope | Change | Dependency | 21 | 5 | Operating system release expected canceled; project forced to use prior version. | 0 | Americas | Prod. Dev. | 2008 | July | 1674351
1547 | Scope | Defect | Hardware | 6 | 5 | Deliverable fails final test; rework to fix. | 0 | Americas | Prod. Dev. | 2010 | November | 378624
1548 | Resource | Outsourcing | Late or poor output | 8 | 6 | Key consultant breaks both arms 3 weeks before project end | 0 | Americas | IT/Solution | 2003 | April | 401768
1549 | Resource | Outsourcing | Late or poor output | 13 | 5 | Usual vendor closed its business and had to be replaced | 0 | Americas | Prod. Dev. | 2005 | February | 391625
1550 | Schedule | Dependency | Infrastructure | 21 | 5 | Problems due to last minute infrastructure changes | 0 | Americas | Prod. Dev. | 2007 | September | 569100
1551 | Schedule | Estimates | Learning | 17 | 6 | Lack of skills with recent university hires | 0 | Americas | IT/Solution | 2007 | May | 459374
1552 | Scope | Change | Dependency | 10 | 3 | Server technology chage was necessitated to support application | 0 | Americas | IT/Solution | 2007 | April | 501750
1553 | Resource | People | Temp loss | 22 | 6 | Project team frequently diverted to support work. | 0 | Americas | Prod. Dev. | 2004 | October | 1408132
1554 | Schedule | Delay | Decision | 6 | 5 | System needed to approve requests went down; ordering required parts delayed. | 0 | Americas | Prod. Dev. | 2015 | November | 191982
1555 | Schedule | Delay | Hardware | 14 | 4 | Team relocated with insufficient time to schedule high speed network lines. Rushed, but did not work; team was down until fixed. | 0 | Americas | IT/Solution | 2001 | August | 892206
1556 | Schedule | Delay | Parts | 12 | 4 | Equipment / parts not delivered on time or in full by the outside supplier | 0 | Americas | IT/Solution | 2003 | April | 727020
1557 | Schedule | Dependency | Infrastructure | 22 | 4 | Lack of access to professional translation services | 0 | Americas | Prod. Dev. | 2007 | July | 1207272
1558 | Schedule | Dependency | Project | 18 | 4 | One team in another country missed deadlines on a complex proposal, creating delay and frustration. | 0 | Americas | IT/Solution | 2013 | January | 939294
1559 | Schedule | Estimates | Judgment | 21 | 6 | Issues with testing were severly underestimated | 0 | Americas | Prod. Dev. | 2004 | November | 834897
1560 | Scope | Change | Creep | 17 | 7 | Excessive scope change in ERP project | 0 | Americas | IT/Solution | 2013 | October | 514692
1561 | Scope | Change | Gap | 15 | 4 | Tests not scheduled for working parts, but mandated for project. Added late. | 0 | Americas | Prod. Dev. | 2010 | September | 563955
1562 | Scope | Defect | Integration | 8 | 4 | Following recent upgrade, many bugs were found | 0 | Americas | IT/Solution | 2017 | June | 517544
1563 | Scope | Change | Creep | 8 | 7 | Scope changed after writers had completed initial draft | 0 | Americas | Prod. Dev. | 2017 | June | 594080
1564 | Schedule | Estimates | Deadline | 6 | 6 | Unrealistic commit made in order to win the business | 0 | Americas | IT/Solution | 2015 | November | 466452
1565 | Schedule | Estimates | Learning | 15 | 4 | Project manager had very few skills in this field | 0 | Americas | IT/Solution | 2017 | June | 864390
1566 | Scope | Change | Creep | 15 | 7 | Excessive late changes | 0 | Americas | IT/Solution | 2016 | July | 1059765
1567 | Scope | Change | Creep | 16 | 7 | Developer added a new routine that was not fully tested, and release window passed | 0 | Americas | IT/Solution | 2013 | July | 733744
1568 | Scope | Change | Creep | 20 | 4 | Company wasted time developing functionality that was ultimately unimportant | 0 | Americas | Prod. Dev. | 2001 | August | 1585180
1569 | Scope | Change | Gap | 7 | 6 | New database wouldn’t work with the proposed platform | 0 | Americas | IT/Solution | 2002 | October | 142352
1570 | Resource | Money | Limitation | 5 | 3 | Project budget was dramatically cut | 0 | Americas | IT/Solution | 2012 | April | 355820
1571 | Scope | Change | Creep | 15 | 4 | Late scope change added customer choice in subscription ticket selection | 0 | Americas | IT/Solution | 2002 | April | 716820
1572 | Scope | Change | Gap | 12 | 6 | Poor requirements definition | 0 | Americas | Prod. Dev. | 2013 | November | 301668
1573 | Resource | People | Motivation | 19 | 3 | Project manger and the Product Manager didn’t get along on an interpersonal level | 0 | Americas | Prod. Dev. | 2015 | May | 899118
1574 | Scope | Change | Gap | 17 | 5 | Poor stakeholder buy-in | 0 | Americas | Prod. Dev. | 2015 | August | 818295
1575 | Schedule | Delay | Parts | 21 | 5 | Test run is rejected or lost | 0 | Americas | Prod. Dev. | 2011 | December | 859845
1576 | Resource | People | Loss | 8 | 5 | Employees terminated for sexual harassment | 0 | Americas | Prod. Dev. | 2001 | May | 192240
1577 | Resource | People | Loss | 21 | 7 | Key staff member assigned to project was changed 3 times during the project | 0 | Americas | Prod. Dev. | 2011 | June | 699951
1578 | Resource | People | Motivation | 7 | 6 | Projects with similar objectives taken on centrally and locally at the same time. Lots of overlap, redundancy and arguing. | 0 | Americas | IT/Solution | 2004 | August | 482209
1579 | Scope | Change | Creep | 13 | 3 | Sponsor demanded specification changes late in the project | 0 | Americas | Prod. Dev. | 2019 | April | 693446
1580 | Resource | Money | Limitation | 14 | 4 | Reduced staff with a bare minimum budget was assigned to the project | 0 | Americas | IT/Solution | 2008 | October | 578144
1581 | Resource | People | Loss | 15 | 4 | Project leader resigns and is not replaced promptly | 0 | Americas | IT/Solution | 2019 | August | 993450
1582 | Schedule | Delay | Parts | 21 | 5 | Ship sinks with critical part; forced to replace with remanufactured old component | 0 | Americas | Prod. Dev. | 2014 | March | 1482390
1583 | Schedule | Estimates | Learning | 10 | 6 | Inexperienced staff | 0 | Americas | IT/Solution | 2013 | August | 634290
1584 | Scope | Defect | Software | 6 | 6 | Application required its own server, delay for installation | 0 | Americas | IT/Solution | 2009 | January | 150900
1585 | Resource | Outsourcing | Delayed start | 19 | 4 | Vendor failed to confirm start date, resulting in delay | 0 | Americas | Prod. Dev. | 2009 | March | 453492
1586 | Resource | People | Loss | 11 | 3 | Critical skills unique in the head of a 62-yearl old programmer who had a heart attack | 0 | Americas | IT/Solution | 2018 | October | 717596
1587 | Scope | Change | Gap | 12 | 7 | A critical issue was neglected resulting in a significant scope gap | 0 | Americas | Prod. Dev. | 2019 | April | 256284
1588 | Scope | Change | Gap | 18 | 3 | Scope gaps became apparent when legal department was consulted too late | 0 | Americas | Prod. Dev. | 2003 | November | 439434
1589 | Scope | Change | Gap | 11 | 4 | Complexity not understood or documented. Required work added. | 0 | Americas | Prod. Dev. | 2004 | January | 631686
1590 | Scope | Defect | Hardware | 7 | 5 | After the first run was lost, a third run was added | 0 | Americas | Prod. Dev. | 2010 | August | 518035
1591 | Resource | Outsourcing | Late or poor output | 6 | 6 | Subcontractor late with a critical component | 0 | Americas | IT/Solution | 2009 | July | 420510
1592 | Resource | People | Queuing | 9 | 5 | CMO analyzing output developed a severe backup | 0 | Americas | Prod. Dev. | 2012 | November | 189873
1593 | Scope | Change | Creep | 5 | 7 | Integrating late features meant that the existing architecture had to be modified | 0 | Americas | Prod. Dev. | 2008 | September | 216975
1594 | Scope | Change | Gap | 16 | 6 | Not enough timewas spent to identify all the requirements for the process | 0 | Americas | IT/Solution | 2019 | January | 572736
1595 | Resource | People | Temp loss | 13 | 3 | Key contributor "rounded up" after 9/11 (and later released) | 0 | Americas | Prod. Dev. | 2012 | March | 987090
1596 | Schedule | Delay | Information | 19 | 7 | Delay to reconfigure printer outside firewall | 0 | Americas | IT/Solution | 2018 | September | 1138385
1597 | Schedule | Delay | Parts | 5 | 7 | Inventory from vendors could not be secured by the desired transport date | 0 | Americas | IT/Solution | 2017 | March | 161450
1598 | Schedule | Estimates | Judgment | 17 | 5 | Insufficient time is estimated; the deadline could not be met. | 0 | Americas | Prod. Dev. | 2016 | June | 1173799
1599 | Scope | Change | Gap | 6 | 4 | Requirements for compiling and formatting data were not clear | 0 | Americas | IT/Solution | 2011 | September | 219054
1600 | Schedule | Delay | Hardware | 8 | 5 | System arrives late, then when it does arrive staff is not available to install it. | 0 | Americas | Prod. Dev. | 2010 | March | 267448
1601 | Schedule | Dependency | Infrastructure | 9 | 4 | Support offering requires more overhead to span several OS versions | 0 | Americas | Prod. Dev. | 2001 | May | 366930
1602 | Schedule | Dependency | Project | 13 | 3 | Coordination of the scopes of work between several projects | 0 | Americas | Prod. Dev. | 2004 | November | 611663
1603 | Schedule | Estimates | Deadline | 20 | 6 | Added resources failed to cut the schedule in half | 0 | Americas | Prod. Dev. | 2007 | June | 1452080
1604 | Scope | Change | Creep | 13 | 5 | Excessive changes made | 0 | Americas | Prod. Dev. | 2005 | January | 589485
1605 | Scope | Change | Gap | 12 | 7 | Unique and specific requirements were poorly understood | 0 | Americas | IT/Solution | 2001 | December | 608952
1606 | Scope | Change | Gap | 22 | 7 | 75% of the requirements were unknowninitially to the project staff | 0 | Americas | IT/Solution | 2005 | December | 1284932
1607 | Scope | Defect | Hardware | 14 | 3 | Found some strange and unusual contamination of an entire batch of petri plates | 0 | Americas | IT/Solution | 2002 | February | 727020
1608 | Resource | People | Late start | 22 | 6 | Significant delay in patient recruitment | 0 | Americas | Prod. Dev. | 2007 | April | 527934
1609 | Scope | Change | Creep | 12 | 4 | An extra specialty service to the hospital was added | 0 | Americas | IT/Solution | 2018 | July | 556728
1610 | Scope | Change | Gap | 14 | 5 | Team failed to engage the critical “power-users” early enough | 0 | Americas | IT/Solution | 2012 | May | 1026368
1611 | Scope | Change | Gap | 10 | 7 | Incomplete design was a result of not considering the particular country needs | 0 | Americas | IT/Solution | 2017 | April | 627870
1612 | Scope | Change | Gap | 9 | 4 | Survey data required for project assigned to several people in some countries; each assumes others will do work | 0 | Americas | IT/Solution | 2019 | May | 313965
1613 | Scope | Change | Creep | 9 | 6 | During a company-wide OS refresh of all desktops and laptops, a merger occurred. Complexity added. | 0 | Americas | IT/Solution | 2019 | August | 259434
1614 | Scope | Defect | Hardware | 6 | 3 | Selected motor was not able to operate reliably requiring redesign | 0 | Americas | Prod. Dev. | 2010 | January | 349122
1615 | Scope | Change | Gap | 8 | 4 | New database wouldn’t work with the proposed platform | 0 | Americas | IT/Solution | 2008 | November | 448384
1616 | Scope | Change | Gap | 12 | 3 | Deficiency in the scope due to cutting corners | 0 | Americas | Prod. Dev. | 2015 | August | 772284
1617 | Schedule | Delay | Parts | 21 | 5 | Delay in the delivery of the test samples | 0 | Americas | Prod. Dev. | 2004 | March | 852768
1618 | Scope | Change | Gap | 14 | 5 | Bad choice of billing threshold problems forced system redesign | 0 | Americas | IT/Solution | 2016 | December | 1078462
1619 | Scope | Defect | Software | 22 | 6 | Purchased application led to performance problems. | 0 | Americas | IT/Solution | 2006 | January | 769450
1620 | Resource | Outsourcing | Delayed start | 21 | 5 | RFP Process was flawed and created delays | 0 | Americas | IT/Solution | 2015 | July | 570990
1621 | Scope | Change | Creep | 15 | 4 | New product features were added at every weekly meeting and stage review | 0 | Americas | Prod. Dev. | 2018 | January | 1150440
1622 | Scope | Change | Gap | 11 | 3 | Sales reps did not clearly understand the client’s request | 0 | Americas | IT/Solution | 2008 | February | 276067
1623 | Scope | Change | Gap | 21 | 6 | The students in a new course had insufficient knowledge of reading and math | 0 | Americas | IT/Solution | 2012 | July | 613872
1624 | Scope | Defect | Hardware | 5 | 3 | To reduce costs and speed time to market there were too few pre-launch product builds performed | 0 | Americas | Prod. Dev. | 2012 | April | 229760
1625 | Scope | Change | Gap | 21 | 3 | No understanding of the scope and not enough system resources | 0 | Americas | IT/Solution | 2009 | November | 703479
1626 | Resource | Money | Limitation | 7 | 6 | Money for needed software was not in the budget; project was delayed to push expense into next quarter | 0 | Americas | Prod. Dev. | 2005 | July | 238091
1627 | Resource | Outsourcing | Late or poor output | 5 | 6 | Incompetent subcontractor led to delay and unhappy clients | 0 | Americas | IT/Solution | 2013 | September | 268570
1628 | Resource | People | Temp loss | 16 | 7 | A valuable resource gets pulled off of project to work on a larger, higher profile project | 0 | Americas | IT/Solution | 2009 | February | 572176
1629 | Schedule | Delay | Parts | 6 | 6 | A special peripheral used for the project deliverable was discontinued | 0 | Americas | IT/Solution | 2011 | September | 379230
1630 | Schedule | Estimates | Learning | 8 | 4 | The team member lacked the right skills for a development job | 0 | Americas | Prod. Dev. | 2006 | February | 208432
1631 | Scope | Change | Gap | 17 | 6 | Inexperience of the leader resulted in overcommitment and little planning | 0 | Americas | IT/Solution | 2006 | November | 678521
1632 | Scope | Change | Gap | 7 | 3 | Substrate material was initially specified incorrectly and had to be reordered | 0 | Americas | IT/Solution | 2003 | April | 195881
1633 | Resource | People | Queuing | 14 | 3 | Reduction in work force affects the % commitment of team members | 0 | Americas | Prod. Dev. | 2019 | January | 587944
1634 | Schedule | Delay | Parts | 6 | 7 | Parts unavailable; backordered. | 0 | Americas | Prod. Dev. | 2005 | February | 372984
1635 | Scope | Change | Creep | 16 | 5 | Customer driven late changes | 0 | Americas | IT/Solution | 2009 | May | 668416
1636 | Scope | Change | Dependency | 13 | 4 | Corporate merger delayed project | 0 | Americas | IT/Solution | 2010 | September | 593060
1637 | Scope | Change | Gap | 18 | 3 | Requireemnts sent via email were never formally documented | 0 | Americas | IT/Solution | 2005 | June | 538056
1638 | Scope | Defect | Hardware | 13 | 3 | Poor quality control and record keeping on the field installation side resulted in many openings being installed incorrectly | 0 | Americas | Prod. Dev. | 2003 | April | 961454
1639 | Resource | People | Temp loss | 10 | 7 | Key Designer was out of the office for 2 weeks | 0 | Americas | Prod. Dev. | 2013 | January | 444750
1640 | Schedule | Delay | Decision | 9 | 3 | Scope definition and stakeholder agreement delayed. | 0 | Americas | Prod. Dev. | 2006 | February | 529488
1641 | Schedule | Delay | Information | 6 | 4 | Data submitted by the participating vendors contains errors | 0 | Americas | IT/Solution | 2013 | October | 149208
1642 | Schedule | Delay | Parts | 12 | 4 | Defective parts received. Reorder doubled the time required. | 0 | Americas | IT/Solution | 2008 | June | 815424
1643 | Schedule | Delay | Parts | 8 | 4 | Needed parts arrive too late. | 0 | Americas | Prod. Dev. | 2016 | November | 624152
1644 | Schedule | Estimates | Judgment | 9 | 7 | Software upgrades take longer each cycle as O/S expands and application list grows. | 0 | Americas | IT/Solution | 2003 | November | 348255
1645 | Scope | Change | Gap | 5 | 7 | Missing important scope at the beginning of the project | 0 | Americas | IT/Solution | 2015 | October | 322870
1646 | Scope | Defect | Software | 13 | 6 | Controlled Document rejected by Approvers | 0 | Americas | IT/Solution | 2010 | January | 684970
1647 | Schedule | Dependency | Project | 22 | 3 | Deliverable from one project claimed to be done, but receiving project cannot use it. | 0 | Americas | Prod. Dev. | 2009 | August | 661452
1648 | Resource | Money | Limitation | 10 | 4 | Major infrastructure project cut back; delayed fixes cost a lot of money, and resources needed were assigned to other work. | 0 | Americas | IT/Solution | 2006 | June | 241210
1649 | Resource | People | Motivation | 7 | 4 | Programmers were volunteers, and ultimately all of them quit | 0 | Americas | IT/Solution | 2001 | November | 524986
1650 | Schedule | Estimates | Learning | 21 | 4 | Complexity of new software was underestimated | 0 | Americas | Prod. Dev. | 2002 | August | 1639407
1651 | Schedule | Estimates | Deadline | 6 | 4 | Unrealistic commit made in order to win the business | 0 | Americas | IT/Solution | 2008 | February | 407352
1652 | Scope | Defect | Hardware | 12 | 5 | Hardware fails near the end of a three-month final test. Refabrication and retest required. | 0 | Americas | Prod. Dev. | 2002 | May | 303792
1653 | Schedule | Dependency | Project | 20 | 7 | Firmware needed for an add-on paper handler dropped from printer project. | 0 | Americas | IT/Solution | 2006 | March | 888020
1654 | Scope | Change | Gap | 13 | 7 | Some countries provided incomplete requirements | 0 | Americas | IT/Solution | 2016 | September | 766441
1655 | Scope | Change | Gap | 9 | 4 | Original product requirements document was incomplete | 0 | Americas | Prod. Dev. | 2019 | November | 544572
1656 | Schedule | Estimates | Learning | 20 | 5 | Lack of expertise, experience and inadequate training | 0 | Americas | IT/Solution | 2010 | April | 1544820
1657 | Schedule | Delay | Information | 17 | 6 | Project had to wait until all data collection was finished before starting analysis | 0 | Americas | IT/Solution | 2003 | April | 850119
1658 | Resource | Money | Limitation | 7 | 5 | IT department was underfunded and had insuffient staff | 0 | Americas | IT/Solution | 2018 | August | 504147
1659 | Schedule | Estimates | Learning | 9 | 5 | Few of the administrators and developers hired for executing this project had the right skill sets to execute the project | 0 | Americas | IT/Solution | 2013 | September | 632718
1660 | Scope | Defect | Integration | 13 | 4 | Unusual usage caused problems in the integration process | 0 | Americas | IT/Solution | 2013 | July | 826449
1661 | Scope | Defect | Integration | 7 | 3 | Two related projects failed to successfully synchronize and missed a release | 0 | Americas | IT/Solution | 2014 | May | 210490
1662 | Scope | Defect | Software | 11 | 3 | Poorly implemented web tool causes ongoing support issues | 0 | Americas | IT/Solution | 2010 | October | 807807
1663 | Schedule | Estimates | Learning | 18 | 3 | Entry level employees lacked needed skill and experience | 0 | Americas | Prod. Dev. | 2011 | July | 783432
1664 | Scope | Change | Gap | 19 | 7 | The statement of work did not indicate clearly the responsibilities of the outsourced programmers | 0 | Americas | IT/Solution | 2010 | February | 1483596
1665 | Scope | Defect | Software | 12 | 7 | Excessive defects in Web Page translations | 0 | Americas | IT/Solution | 2002 | July | 522780
1666 | Schedule | Delay | Parts | 21 | 3 | New technology was analyzed and didn’t meet the needs | 0 | Americas | Prod. Dev. | 2019 | May | 1217790
1667 | Resource | Outsourcing | Delayed start | 21 | 7 | Contract negotiations delayed by 20 days | 0 | Americas | IT/Solution | 2009 | February | 1261365
1668 | Resource | Outsourcing | Late or poor output | 12 | 4 | Lack of clear definition of the contractor and Lead Tech roles and responsibilities | 0 | Americas | IT/Solution | 2003 | November | 406548
1669 | Schedule | Delay | Parts | 9 | 5 | Solar panels arrived late and were not what was ordered | 0 | Americas | IT/Solution | 2009 | November | 665757
1670 | Schedule | Delay | Parts | 19 | 6 | Granite countertops had incorrect measurements | 0 | Americas | Prod. Dev. | 2002 | May | 1475141
1671 | Scope | Change | Creep | 6 | 4 | Requested scope expansion took a month to assess and was ultimately rejected | 0 | Americas | IT/Solution | 2016 | November | 201978
1672 | Scope | Change | Gap | 21 | 5 | Enterprise Portal improperly specified | 0 | Americas | IT/Solution | 2007 | December | 851277
1673 | Scope | Change | Gap | 21 | 6 | Major Scope change during the design phase due to the complex processes involved | 0 | Americas | IT/Solution | 2015 | January | 464541
1674 | Scope | Change | Gap | 10 | 5 | Customer did not describe in detail what exactly was needed | 0 | Americas | IT/Solution | 2002 | August | 208220
1675 | Schedule | Delay | Hardware | 17 | 6 | Needed system delivered to wrong building; lost for weeks. | 0 | Americas | IT/Solution | 2008 | November | 352070
1676 | Scope | Change | Gap | 15 | 4 | Scoping was much more complex then originally thought | 0 | Americas | Prod. Dev. | 2015 | May | 355395
1677 | Scope | Defect | Hardware | 15 | 5 | PC board failure requires redesign and fabrication. | 0 | Americas | Prod. Dev. | 2002 | September | 476880
1678 | Resource | People | Late start | 5 | 7 | Project start delayed; staffing and buy-in late, required overtime and extra project management. | 0 | Americas | Prod. Dev. | 2001 | October | 248790
1679 | Resource | People | Queuing | 7 | 4 | Failure by project manager to communicate the need for architect’s time | 0 | Americas | Prod. Dev. | 2006 | December | 290619
1680 | Schedule | Estimates | Learning | 10 | 3 | Critical technical task was assigned to resource who was a new hire | 0 | Americas | Prod. Dev. | 2009 | September | 775380
1681 | Scope | Change | Gap | 11 | 7 | Technical requirements communicated to developers too late | 0 | Americas | IT/Solution | 2002 | January | 774884
1682 | Resource | People | Late start | 15 | 6 | Planning delayed due to staff being still tied up in testing on prior project. | 0 | Americas | Prod. Dev. | 2017 | February | 427500
1683 | Schedule | Estimates | Judgment | 17 | 5 | Untried beta software with unknown computer needs required for training | 0 | Americas | IT/Solution | 2009 | May | 1305600
1684 | Scope | Defect | Hardware | 22 | 3 | Unanticipated fumes form epoxy concrete paint forced a delay in work | 0 | Americas | IT/Solution | 2013 | August | 440792
1685 | Resource | People | Late start | 18 | 5 | Lack of specialized labor to perform the task | 0 | Americas | Prod. Dev. | 2016 | January | 448398
1686 | Resource | People | Motivation | 11 | 3 | Programmers were volunteers, and ultimately all of them quit | 0 | Americas | IT/Solution | 2008 | December | 609235
1687 | Schedule | Dependency | Project | 9 | 5 | Prior work was completed late | 0 | Americas | IT/Solution | 2017 | September | 641880
1688 | Schedule | Estimates | Judgment | 9 | 3 | Goal of 90% participation in study is proved infeasible | 0 | Americas | IT/Solution | 2014 | January | 543348
1689 | Schedule | Estimates | Learning | 6 | 3 | The team in Germany did not have the resources or expertise to do testing in key intermediate step | 0 | Americas | Prod. Dev. | 2014 | July | 251322
1690 | Schedule | Estimates | Learning | 21 | 7 | Complexity of new software was underestimated | 0 | Americas | Prod. Dev. | 2019 | May | 820197
1691 | Scope | Change | Gap | 20 | 5 | New application was slow and some initial requirements were missed | 0 | Americas | IT/Solution | 2002 | February | 1586860
1692 | Scope | Change | Gap | 16 | 6 | Development plans failed to include all of the 23 required applications | 0 | Americas | IT/Solution | 2014 | January | 394928
1693 | Scope | Change | Gap | 8 | 4 | Lack of understanding the business processes used to develop manual reports and insufficient relevant experience | 0 | Americas | IT/Solution | 2019 | June | 568552
1694 | Scope | Change | Gap | 8 | 4 | In creating a new system, there was too little involvement from the end users | 0 | Americas | Prod. Dev. | 2011 | February | 434504
1695 | Scope | Defect | Hardware | 6 | 3 | Selected motor was not able to operate reliably requiring redesign | 0 | Americas | Prod. Dev. | 2010 | July | 259608
1696 | Resource | Money | Limitation | 8 | 6 | Insufficient resources and little change control | 0 | Americas | Prod. Dev. | 2015 | April | 603632
1697 | Scope | Change | Creep | 10 | 5 | Insufficient analysis of new technology introduced late | 0 | Americas | Prod. Dev. | 2018 | September | 669590
1698 | Schedule | Dependency | Infrastructure | 15 | 5 | Development methods have limited (6-month) validation; if project slips, must be recertified | 0 | Americas | IT/Solution | 2015 | January | 706635
1699 | Scope | Change | Gap | 17 | 6 | Databases were not built to share information across systems | 0 | Americas | IT/Solution | 2006 | January | 503744
1700 | Resource | People | Late start | 10 | 7 | Lack of specialized labor to perform the task | 0 | Americas | Prod. Dev. | 2019 | November | 273900
1701 | Scope | Change | Gap | 10 | 7 | Problem was not fully understood, leading to many changes | 0 | Americas | Prod. Dev. | 2001 | January | 213790
1702 | Scope | Change | Gap | 10 | 4 | Module 1 team did not involve other developers during the initial scoping | 0 | Americas | IT/Solution | 2011 | May | 298310
1703 | Scope | Change | Gap | 18 | 5 | Requesters failed to understand the complexity and did not make their wishes clear | 0 | Americas | IT/Solution | 2016 | May | 1011582
1704 | Scope | Change | Gap | 9 | 5 | Supplier code changes resulted in major backlog | 0 | Americas | IT/Solution | 2005 | November | 216585
1705 | Resource | Outsourcing | Delayed start | 22 | 6 | Consultants failed to secure required resources in timely manner | 0 | Americas | IT/Solution | 2004 | February | 731082
1706 | Resource | Outsourcing | Late or poor output | 18 | 3 | WWW code supplied by third party late and poor quality; major delay and rework. | 0 | Americas | IT/Solution | 2016 | January | 568386
1707 | Resource | Outsourcing | Late or poor output | 5 | 4 | Subcontractor refused to follow the core vendor’s processes | 0 | Americas | IT/Solution | 2016 | January | 390570
1708 | Schedule | Delay | Hardware | 22 | 7 | Color printer version of app fails on WAN | 0 | Americas | IT/Solution | 2004 | February | 824296
1709 | Resource | Money | Limitation | 17 | 6 | Chronically understaffed business environment | 0 | Americas | Prod. Dev. | 2016 | September | 1339753
1710 | Resource | Money | Limitation | 7 | 7 | Client slashed the original budget | 0 | Americas | IT/Solution | 2006 | November | 443282
1711 | Resource | People | Late start | 21 | 5 | Legacy systems not retired as planned; project team tied up in unplanned support. | 0 | Americas | IT/Solution | 2012 | January | 1118544
1712 | Resource | People | Late start | 21 | 5 | Delay in getting a firewall PM and a firewall engineer assigned | 0 | Americas | IT/Solution | 2009 | February | 545454
1713 | Resource | People | Queuing | 6 | 7 | Parallel tasks require resources beyond what is available | 0 | Americas | IT/Solution | 2019 | June | 473382
1714 | Schedule | Delay | Hardware | 7 | 7 | There were not enough vendors who had the capacity to manufacture specialized tools | 0 | Americas | IT/Solution | 2003 | April | 155778
1715 | Schedule | Delay | Parts | 20 | 5 | Internal supplier problem; needed components delayed. | 0 | Americas | Prod. Dev. | 2009 | October | 1262160
1716 | Schedule | Dependency | Legal | 19 | 5 | Issues found with the SOX documents provided by the legal team | 0 | Americas | IT/Solution | 2004 | April | 480282
1717 | Schedule | Dependency | Project | 19 | 5 | Reviews delayed on complex program, waiting for last team to finish phase work. | 0 | Americas | Prod. Dev. | 2003 | July | 825797
1718 | Resource | Outsourcing | Late or poor output | 9 | 7 | Abnormally high turnover and shortage of capable developers in India | 0 | Americas | Prod. Dev. | 2015 | April | 392220
1719 | Resource | People | Late start | 10 | 4 | Delay in hiring more engineers due to cost cutting | 0 | Americas | IT/Solution | 2011 | January | 476330
1720 | Resource | People | Loss | 15 | 7 | Turnover on staff 100% in year, leading to delays and training. | 0 | Americas | IT/Solution | 2001 | March | 630750
1721 | Schedule | Delay | Parts | 20 | 3 | There was a delay in the delivery of test samples | 0 | Americas | Prod. Dev. | 2005 | April | 1349680
1722 | Schedule | Estimates | Judgment | 13 | 7 | Headcount required for document management was grossly underestimated | 0 | Americas | IT/Solution | 2013 | May | 415935
1723 | Scope | Change | Gap | 6 | 5 | Flaw was found in the functional design | 0 | Americas | Prod. Dev. | 2008 | October | 130596
1724 | Resource | People | Motivation | 5 | 7 | Too little management interest and support | 0 | Americas | Prod. Dev. | 2006 | October | 362230
1725 | Resource | People | Queuing | 18 | 6 | Two projects depended on one resource for completion and this one had lower priority | 0 | Americas | IT/Solution | 2006 | November | 1421550
1726 | Schedule | Delay | Parts | 14 | 5 | Change to US sourcing created demand and delays | 0 | Americas | Prod. Dev. | 2014 | February | 604394
1727 | Schedule | Delay | Parts | 17 | 5 | Some parts are damaged in shipping and must be reordered. | 0 | Americas | Prod. Dev. | 2019 | April | 1217200
1728 | Scope | Change | Gap | 22 | 5 | Failure to collect the details about the interfaces and links to the third party websites | 0 | Americas | IT/Solution | 2008 | January | 1372338
1729 | Resource | People | Late start | 17 | 6 | Developer from the database group was not available because of another project | 0 | Americas | IT/Solution | 2016 | January | 996965
1730 | Resource | People | Loss | 7 | 3 | Toward the end of the development life cycle the original QA lead and trainer quit the firm | 0 | Americas | IT/Solution | 2011 | September | 372162
1731 | Resource | People | Loss | 12 | 7 | Contributor is leaving due to contract expiration | 0 | Americas | IT/Solution | 2017 | May | 943716
1732 | Resource | People | Motivation | 7 | 4 | On a very long project, enthusiasm and motivation falls; tasks stretch out. | 0 | Americas | Prod. Dev. | 2009 | February | 245217
1733 | Resource | People | Temp loss | 10 | 3 | Staff lost to customer Hot Site | 0 | Americas | Prod. Dev. | 2016 | October | 369700
1734 | Schedule | Delay | Decision | 13 | 3 | Poor access to decision makers | 0 | Americas | IT/Solution | 2015 | November | 426530
1735 | Schedule | Delay | Information | 12 | 4 | Document transfer to sites takes more time and effort than expected. | 0 | Americas | Prod. Dev. | 2006 | July | 397968
1736 | Schedule | Delay | Parts | 7 | 5 | New pumps sent that lacked instructions and spare parts | 0 | Americas | Prod. Dev. | 2018 | July | 460082
1737 | Schedule | Dependency | Project | 17 | 4 | Lack of coordination between projects causes delays. | 0 | Americas | Prod. Dev. | 2012 | July | 423402
1738 | Scope | Change | Creep | 5 | 4 | Translated text was too long | 0 | Americas | IT/Solution | 2017 | November | 330980
1739 | Scope | Change | Gap | 5 | 6 | Scope was poorly defined | 0 | Americas | IT/Solution | 2001 | November | 107185
1740 | Scope | Defect | Integration | 21 | 3 | Software modules in system do not work together as planned. | 0 | Americas | Prod. Dev. | 2006 | September | 580125
1741 | Scope | Defect | Software | 5 | 7 | Quality problems led to late redesign, extra work and plan changes. | 0 | Americas | Prod. Dev. | 2014 | March | 333665
1742 | Scope | Change | Creep | 12 | 7 | System move delayed by last minute system changes that delayed and made backups take too long. | 0 | Americas | IT/Solution | 2014 | October | 608964
1743 | Scope | Defect | Hardware | 5 | 4 | Miscalculation on a critical task | 0 | Americas | Prod. Dev. | 2005 | June | 134665
1744 | Scope | Defect | Software | 15 | 3 | Bugs were reported by UAT that should have been caught by QA | 0 | Americas | IT/Solution | 2019 | November | 339915
1745 | Scope | Change | Gap | 11 | 5 | Databases were not built to share information across systems | 0 | Americas | IT/Solution | 2006 | October | 719796
1746 | Schedule | Estimates | Deadline | 7 | 6 | Added resources failed to cut the schedule in half | 0 | Americas | Prod. Dev. | 2018 | September | 223986
1747 | Scope | Change | Creep | 16 | 3 | Company wasted time developing functionality that was ultimately unimportant | 0 | Americas | Prod. Dev. | 2003 | August | 818192
1748 | Scope | Change | Creep | 16 | 3 | Six weeks in, a redesign to the most fundamental part of the research was done | 0 | Americas | Prod. Dev. | 2016 | February | 406336
1749 | Resource | Outsourcing | Late or poor output | 6 | 5 | Partner on project defaults. | 0 | Americas | Prod. Dev. | 2013 | July | 352752
1750 | Scope | Change | Creep | 7 | 3 | Significant growth of scope in renovation project | 0 | Americas | IT/Solution | 2007 | October | 388696
1751 | Scope | Change | Gap | 11 | 6 | No clear requirements from management | 0 | Americas | IT/Solution | 2009 | October | 835043
1752 | Scope | Change | Gap | 22 | 5 | Did not have the correct people validate requirements | 0 | Americas | IT/Solution | 2019 | March | 630168
1753 | Schedule | Estimates | Judgment | 21 | 6 | Expert opinion was 2 weeks; work took 8. | 0 | Americas | Prod. Dev. | 2003 | September | 1317351
1754 | Resource | People | Queuing | 7 | 7 | Six other projects required time and effort from our assigned engineer | 0 | Americas | Prod. Dev. | 2012 | November | 327992
1755 | Scope | Change | Creep | 22 | 6 | Big scope change in the middle of the project | 0 | Americas | Prod. Dev. | 2014 | September | 1517164
1756 | Resource | People | Queuing | 15 | 7 | Lack of key SME resource availability when needed | 0 | Americas | IT/Solution | 2002 | December | 1143555
1757 | Resource | People | Temp loss | 17 | 5 | Key resource tied to a previous project for two weeks | 0 | Americas | IT/Solution | 2013 | November | 1205419
1758 | Scope | Change | Dependency | 15 | 6 | As product increases, new packaging and unexpected shielding needed. | 0 | Americas | Prod. Dev. | 2013 | September | 1045875
1759 | Scope | Change | Gap | 16 | 6 | Requested requirement proved impossible, but was not actually needed | 0 | Americas | Prod. Dev. | 2007 | September | 659296
1760 | Scope | Defect | Hardware | 19 | 6 | New technology used, seeking faster results. It does not work and leads to redesign and rework. | 0 | Americas | IT/Solution | 2019 | December | 693538
1761 | Scope | Defect | Integration | 7 | 6 | Process does not scale to production; changes required. | 0 | Americas | Prod. Dev. | 2013 | December | 419804
1762 | Resource | Outsourcing | Late or poor output | 20 | 7 | Designer doesn’t have skills to finish needed work | 0 | Americas | Prod. Dev. | 2019 | February | 1302840
1763 | Scope | Defect | Software | 19 | 7 | There was not enough time to redo the programming to fix the errors identified | 0 | Americas | IT/Solution | 2007 | November | 647083
1764 | Schedule | Estimates | Learning | 9 | 6 | Programmer had a lack of experience in the healthcare industry | 0 | Americas | IT/Solution | 2014 | March | 256122
1765 | Scope | Change | Creep | 13 | 7 | Project priorities are unclear and secondary, less important work is done delaying required tasks. | 0 | Americas | IT/Solution | 2015 | July | 644540
1766 | Resource | Outsourcing | Late or poor output | 11 | 6 | Third-party vendor inadvertently introduced a bug during an upgrade | 0 | Americas | IT/Solution | 2005 | January | 551573
1767 | Resource | People | Temp loss | 15 | 6 | Manufacturing volumes spiked and diverted project contributors. | 0 | Americas | Prod. Dev. | 2011 | September | 1146615
1768 | Schedule | Delay | Hardware | 13 | 4 | System needed was down for scheduled maintenance not in plan. | 0 | Americas | IT/Solution | 2009 | April | 571181
1769 | Scope | Change | Dependency | 13 | 4 | Policy changes made late in a project requiring additional unplanned work. | 0 | Americas | Prod. Dev. | 2004 | January | 385320
1770 | Schedule | Estimates | Learning | 17 | 6 | Development team members were hired regardless of the lack of business knowledge | 0 | Americas | IT/Solution | 2003 | December | 980033
1771 | Schedule | Delay | Parts | 22 | 5 | Part was too long to ship, so it was cut. Result was useful only as raw material. | 0 | Americas | Prod. Dev. | 2010 | April | 1413324
1772 | Schedule | Delay | Parts | 8 | 3 | Volume of new IC chip required for ramp not available. Major backlog on product delivery. | 0 | Americas | Prod. Dev. | 2006 | September | 467168
1773 | Schedule | Delay | Information | 19 | 7 | Inadequate procedures for acceptance, quality, and communications with development in India | 0 | Americas | IT/Solution | 2003 | December | 1069453
1774 | Scope | Defect | Software | 22 | 4 | Some users couldn't login because of mixed case passwords | 0 | Americas | IT/Solution | 2005 | December | 1655896
1775 | Resource | People | Queuing | 10 | 4 | Key decisions stalled when system architect not available. | 0 | Americas | Prod. Dev. | 2018 | July | 202990
1776 | Resource | People | Queuing | 9 | 7 | One SME for several projects | 0 | Americas | Prod. Dev. | 2001 | November | 611721
1777 | Schedule | Dependency | Project | 14 | 6 | Fix for critical bug was delayed | 0 | Americas | Prod. Dev. | 2004 | November | 422240
1778 | Scope | Change | Gap | 12 | 5 | Problems with manufacturing arose that were not seen in the original analysis | 0 | Americas | Prod. Dev. | 2004 | April | 892152
1779 | Schedule | Dependency | Infrastructure | 12 | 6 | Adopting the selected system required several new pieces of major software | 0 | Americas | IT/Solution | 2013 | January | 530508
1780 | Scope | Change | Gap | 14 | 6 | The Product Manager never told the team what the customer was asking for | 0 | Americas | Prod. Dev. | 2004 | February | 742154
1781 | Resource | Outsourcing | Late or poor output | 13 | 7 | Because of incopetence, a second consultant was hired to redo the work | 0 | Americas | IT/Solution | 2001 | June | 424970
1782 | Schedule | Estimates | Deadline | 21 | 6 | Unrealistic deadline set; slips unavoidable. | 0 | Americas | IT/Solution | 2007 | May | 1050042
1783 | Scope | Change | Creep | 21 | 6 | After more than 2/3 of the original budget had been expended, a major design change resulted in major requirement modifications and additions | 2 | Eur/ME | Prod. Dev. | 2005 | May | 1288476
1784 | Resource | Outsourcing | Late or poor output | 17 | 7 | Outsource company’s abilities were poor and they had to be replaced | 0 | Americas | IT/Solution | 2009 | January | 991066
1785 | Resource | Outsourcing | Late or poor output | 13 | 6 | Outsourcing partner in Switzerland did unneeded work, delaying their inputs | 2 | Eur/ME | Prod. Dev. | 2003 | April | 814905
1786 | Resource | People | Loss | 21 | 4 | Lead Engineer’s resignation | 2 | Eur/ME | Prod. Dev. | 2007 | March | 553560
1787 | Resource | People | Temp loss | 14 | 3 | The business analyst was unavailable for project work due to her backup role for a higher priority project | 2 | Eur/ME | IT/Solution | 2003 | February | 748902
1788 | Schedule | Delay | Information | 7 | 4 | Need to get input from one of the external group for specific info; late | 2 | Eur/ME | IT/Solution | 2001 | January | 517909
1789 | Scope | Change | Creep | 21 | 5 | The scope of the project was poorly defined | 0 | Americas | Prod. Dev. | 2012 | August | 665574
1790 | Scope | Defect | Integration | 5 | 5 | New application works, but data collected is not accessible. | 2 | Eur/ME | IT/Solution | 2002 | February | 135720
1791 | Resource | People | Loss | 10 | 3 | Lost a key programmer | 0 | Americas | IT/Solution | 2019 | September | 527430
1792 | Resource | People | Loss | 10 | 7 | Key contributor left the company | 0 | Americas | Prod. Dev. | 2019 | June | 583620
1793 | Scope | Change | Gap | 13 | 6 | Problems associated with confidential patient information in transit without a tracking mechanism surfaced during the project | 0 | Americas | IT/Solution | 2019 | December | 966329
1794 | Resource | People | Temp loss | 21 | 5 | Change Management Lead took unexpected medical leave | 0 | Americas | IT/Solution | 2013 | January | 1293075
1795 | Schedule | Delay | Decision | 6 | 7 | Decisions are being delayed without apparent reason | 0 | Americas | Prod. Dev. | 2012 | September | 430758
1796 | Schedule | Dependency | Infrastructure | 14 | 5 | During required short visits, the network was sometimes down for an indefinite amount of time, requiring a second trip | 0 | Americas | IT/Solution | 2013 | November | 1083460
1797 | Schedule | Dependency | Infrastructure | 22 | 4 | Compilers and open source libraries needed were not available | 2 | Eur/ME | IT/Solution | 2012 | May | 522896
1798 | Scope | Change | Gap | 20 | 6 | Project had aggressive timeline and due to rush details were poorly defined | 0 | Americas | IT/Solution | 2013 | March | 434920
1799 | Scope | Change | Gap | 5 | 7 | Design documentation was signed off by users, but had fatal flaws | 0 | Americas | IT/Solution | 2014 | December | 306430
1800 | Scope | Defect | Integration | 10 | 3 | Failure to not carefully proofread the documents to be produced before printing | 0 | Americas | Prod. Dev. | 2019 | August | 715680
1801 | Scope | Defect | Software | 22 | 4 | Bug surfaced one day after implementation | 0 | Americas | IT/Solution | 2005 | November | 705540
1802 | Resource | People | Loss | 10 | 7 | Critical person went on maternity leave | 2 | Eur/ME | IT/Solution | 2011 | October | 305210
1803 | Resource | People | Queuing | 12 | 7 | "50%" resources are not aligned, resulting in activity delays | 0 | Americas | Prod. Dev. | 2010 | March | 808752
1804 | Resource | People | Queuing | 12 | 4 | Two of the developers were able to work on the project only 60% of their time, not full time | 2 | Eur/ME | Prod. Dev. | 2018 | July | 749508
1805 | Resource | People | Temp loss | 19 | 7 | Key IT resources scheduled extensive vacations | 2 | Eur/ME | IT/Solution | 2014 | November | 984485
1806 | Resource | People | Temp loss | 16 | 3 | Study timeline set before staff vacation dates were known | 2 | Eur/ME | IT/Solution | 2004 | September | 719888
1807 | Schedule | Delay | Information | 12 | 4 | With 12 hour time difference and dependence on E-mail, even simple questions take 2-4 days to resolve. | 0 | Americas | Prod. Dev. | 2019 | October | 836064
1808 | Schedule | Delay | Parts | 19 | 5 | Had only 1/3 of the units needed on time | 2 | Eur/ME | IT/Solution | 2005 | May | 903887
1809 | Schedule | Estimates | Learning | 15 | 5 | Team was staffed by 3 successive new hires in a six-month period | 0 | Americas | Prod. Dev. | 2019 | April | 682755
1810 | Scope | Change | Gap | 12 | 7 | Deliverable requirements were discovered during the execution phase | 0 | Americas | IT/Solution | 2010 | May | 777600
1811 | Schedule | Delay | Decision | 11 | 4 | Project relocated manufacturing to a contract manufacturer. Required management decisions are frequent and too slow. | 0 | Americas | Prod. Dev. | 2019 | January | 505164
1812 | Schedule | Dependency | Infrastructure | 7 | 7 | Telecom line delays | 0 | Americas | IT/Solution | 2006 | July | 275688
1813 | Schedule | Estimates | Judgment | 19 | 4 | Insufficient time was scheduled for testing | 0 | Americas | Prod. Dev. | 2019 | May | 1323863
1814 | Scope | Change | Creep | 16 | 3 | Scope of product categories was broadened significantly | 0 | Americas | Prod. Dev. | 2017 | September | 562944
1815 | Scope | Change | Dependency | 8 | 5 | New software installed by IT. It does not work, and causes delay to fix. | 0 | Americas | IT/Solution | 2015 | March | 382632
1816 | Schedule | Dependency | Project | 9 | 3 | Dependency on other project not discovered until project end. | 0 | Americas | IT/Solution | 2015 | April | 531468
1817 | Scope | Change | Dependency | 20 | 3 | Legal required late changes to a large print run of materials | 0 | Americas | Prod. Dev. | 2014 | September | 1256760
1818 | Schedule | Dependency | Legal | 15 | 7 | Unexpectedly, the FDA requires a long-term toxicity study | 0 | Americas | Prod. Dev. | 2007 | August | 879030
1819 | Scope | Defect | Integration | 19 | 6 | SumTotal LMS user interface is significantly more complex than the Docent LMS user interface it is to replace | 2 | Eur/ME | IT/Solution | 2001 | September | 740392
1820 | Scope | Change | Gap | 16 | 4 | Unrealistic scope in very short timeframe. | 0 | Americas | IT/Solution | 2019 | October | 371072
1821 | Scope | Change | Gap | 22 | 7 | Scope initially proposed for the project was not signed off by the upper management | 0 | Americas | IT/Solution | 2008 | August | 906664
1822 | Resource | Outsourcing | Late or poor output | 5 | 4 | Lack of oversight and quality assurance led to short cuts being taken | 0 | Americas | Prod. Dev. | 2006 | July | 295680
1823 | Scope | Defect | Software | 17 | 4 | Tests revealed a fatal issue, deferring release to next quartely update | 3 | Africa | IT/Solution | 2014 | March | 1106173
1824 | Scope | Change | Creep | 14 | 3 | Application changed for prospective Chinese customer (who did not buy) | 2 | Eur/ME | Prod. Dev. | 2017 | January | 965930
1825 | Schedule | Estimates | Judgment | 18 | 7 | Software development underestimated by a factor of three. | 0 | Americas | Prod. Dev. | 2019 | March | 1390680
1826 | Scope | Defect | Software | 10 | 3 | Major failure in the Validation tests | 3 | Africa | IT/Solution | 2013 | May | 319610
1827 | Resource | Outsourcing | Late or poor output | 22 | 4 | Unrelaible and incopentent contractors | 0 | Americas | IT/Solution | 2019 | July | 632544
1828 | Schedule | Delay | Hardware | 7 | 6 | It took a over month to get the custom designed equipment | 2 | Eur/ME | IT/Solution | 2015 | January | 161504
1829 | Schedule | Estimates | Learning | 10 | 5 | No cross training within the team to make more knowledgeable resources available | 0 | Americas | Prod. Dev. | 2019 | July | 593740
1830 | Scope | Change | Creep | 7 | 4 | Late stakeholders redefine requiremnts | 0 | Americas | IT/Solution | 2019 | November | 549206
1831 | Scope | Change | Creep | 11 | 7 | Constant design changes occurred and parts had to be scrapped and replaced | 3 | Africa | Prod. Dev. | 2002 | March | 426580
1832 | Resource | Outsourcing | Late or poor output | 19 | 6 | Contractor was uncooperative and late | 0 | Americas | IT/Solution | 2019 | August | 1491405
1833 | Resource | Outsourcing | Late or poor output | 20 | 5 | Outsourcing delayed the order entry process for all U.S. Based customers | 2 | Eur/ME | IT/Solution | 2005 | July | 553960
1834 | Schedule | Dependency | Infrastructure | 18 | 6 | Foundation was inadaquate and needed upgrading | 3 | Africa | IT/Solution | 2015 | September | 555552
1835 | Schedule | Estimates | Deadline | 9 | 4 | Work was intentionally underestimatged to win the contract | 2 | Eur/ME | IT/Solution | 2011 | August | 341064
1836 | Scope | Change | Gap | 12 | 3 | Project required a change to the current website technology | 2 | Eur/ME | IT/Solution | 2004 | August | 633996
1837 | Scope | Defect | Integration | 13 | 4 | In large system conversion, new applications cannot find and work with existing data as expected. Lots of redirecting and conversion is required. | 0 | Americas | IT/Solution | 2012 | October | 674648
1838 | Resource | Outsourcing | Late or poor output | 17 | 4 | Initial stages were outsourced to a professor who started late and lacked needed information | 0 | Americas | IT/Solution | 2019 | December | 529669
1839 | Resource | Outsourcing | Late or poor output | 14 | 6 | Vendor missed validation due date delaying Clinical Trials | 0 | Americas | Prod. Dev. | 2019 | June | 822458
1840 | Resource | People | Loss | 18 | 5 | Layoffs in the company | 3 | Africa | Prod. Dev. | 2005 | June | 1237338
1841 | Resource | People | Loss | 15 | 3 | Project team members reassigned. Not replaced; led to overtime, quality problems, missed deadlines. | 0 | Americas | Prod. Dev. | 2002 | May | 698175
1842 | Resource | People | Temp loss | 16 | 3 | Staff lost to customer Hot Site | 3 | Africa | Prod. Dev. | 2003 | September | 336192
1843 | Schedule | Delay | Information | 20 | 6 | Key stakeholders were not identified during requirements gathering | 0 | Americas | IT/Solution | 2019 | February | 985720
1844 | Scope | Defect | Integration | 16 | 4 | All components pass tests, but assembled system fails. Rework causes delay. | 2 | Eur/ME | Prod. Dev. | 2004 | November | 378400
1845 | Resource | Outsourcing | Late or poor output | 17 | 7 | Poor planning for the transition between consultants | 3 | Africa | IT/Solution | 2009 | August | 736525
1846 | Resource | Outsourcing | Late or poor output | 8 | 3 | Engineering consultant firm laid off a chief structural engineer late in project | 0 | Americas | IT/Solution | 2019 | August | 473384
1847 | Resource | People | Queuing | 9 | 7 | All students did not complete training as scheduled, so the project is completed late | 0 | Americas | IT/Solution | 2019 | February | 555606
1848 | Resource | People | Queuing | 21 | 5 | Expert worked on at least 4-5 projects at a time | 0 | Americas | Prod. Dev. | 2019 | September | 449421
1849 | Resource | People | Queuing | 14 | 5 | Multiple projects depend on lone expert scientist | 0 | Americas | Prod. Dev. | 2019 | June | 667674
1850 | Scope | Defect | Software | 9 | 3 | Errors found in data and critrical reports | 3 | Africa | Prod. Dev. | 2012 | October | 539010
1851 | Schedule | Delay | Information | 13 | 7 | There was a communication lag | 3 | Africa | Prod. Dev. | 2012 | April | 374582
1852 | Schedule | Estimates | Judgment | 17 | 6 | Testing time underestimated. | 0 | Americas | Prod. Dev. | 2019 | January | 608328
1853 | Scope | Change | Gap | 17 | 4 | Metrics from many sites required. When collected, additional work required to make consistent. | 3 | Africa | IT/Solution | 2007 | August | 479264
1854 | Scope | Defect | Software | 18 | 4 | Bug could be fixed only by moving to a later version of software | 0 | Americas | IT/Solution | 2019 | August | 1129212
1855 | Schedule | Delay | Parts | 14 | 6 | Out of stock on key parts needed for PC boards. | 3 | Africa | Prod. Dev. | 2012 | January | 648844
1856 | Resource | Outsourcing | Late or poor output | 20 | 3 | Research and development were outsourced, but the relationship was not managed well, and all work was ultimately redone | 2 | Eur/ME | Prod. Dev. | 2004 | September | 1123180
1857 | Resource | People | Loss | 13 | 5 | Lack of people resources (designers, requirement/business analysts, data modelers and QA/Testing) | 0 | Americas | Prod. Dev. | 2008 | July | 308789
1858 | Schedule | Delay | Information | 13 | 7 | Complexities of solution not understood, even well into project | 0 | Americas | IT/Solution | 2019 | July | 582959
1859 | Schedule | Delay | Parts | 12 | 3 | Critical application delivery late | 0 | Americas | Prod. Dev. | 2005 | September | 770220
1860 | Schedule | Dependency | Infrastructure | 14 | 4 | Development methods have limited (6-month) validation; if project slips, must be recertified | 0 | Americas | IT/Solution | 2019 | April | 641410
1861 | Schedule | Dependency | Legal | 7 | 6 | Process change led to recertification requirements and delay | 2 | Eur/ME | Prod. Dev. | 2005 | May | 222033
1862 | Schedule | Dependency | Project | 20 | 3 | The manager of a related project allowed stakeholders to change the scope, driving continual changes | 3 | Africa | IT/Solution | 2013 | April | 1295280
1863 | Scope | Change | Creep | 20 | 7 | During a company-wide OS refresh of all desktops and laptops, a merger occurred. Complexity added. | 3 | Africa | IT/Solution | 2003 | November | 575260
1864 | Scope | Change | Creep | 13 | 5 | System for expense analysis expanded into redesign of most major internal systems | 3 | Africa | Prod. Dev. | 2003 | May | 804440
1865 | Scope | Change | Creep | 21 | 7 | Code freeze not done until the release date, making training and documentation late | 0 | Americas | Prod. Dev. | 2017 | September | 800037
1866 | Scope | Change | Gap | 13 | 3 | Unrealistic scope in very short timeframe. | 0 | Americas | IT/Solution | 2007 | January | 267501
1867 | Scope | Change | Gap | 15 | 6 | Inaccurate comparison between our requirements and the software | 0 | Americas | IT/Solution | 2019 | December | 988515
1868 | Resource | Money | Limitation | 14 | 6 | Lack of Stakeholder commitment and oversight | 0 | Americas | IT/Solution | 2019 | May | 477176
1869 | Schedule | Delay | Parts | 17 | 6 | Changes to outside providers resulted in major delays | 0 | Americas | Prod. Dev. | 2011 | May | 1225173
1870 | Schedule | Estimates | Learning | 18 | 3 | Development team members were hired regardless of the lack of business knowledge | 2 | Eur/ME | IT/Solution | 2019 | September | 1241388
1871 | Scope | Change | Gap | 11 | 6 | Customer requirement discovered late in project | 3 | Africa | Prod. Dev. | 2005 | December | 234696
1872 | Scope | Change | Gap | 7 | 4 | Significant additional testing required; discovered late | 0 | Americas | IT/Solution | 2009 | March | 404635
1873 | Resource | People | Temp loss | 22 | 5 | Two of the SAP technicians were reassigned to a more “business critical” project midway through the system development phase. | 3 | Africa | IT/Solution | 2018 | August | 606408
1874 | Schedule | Delay | Hardware | 14 | 4 | Vendor merger caused interruption in hardware availability; had to recertify | 2 | Eur/ME | IT/Solution | 2009 | February | 413238
1875 | Scope | Change | Creep | 13 | 7 | Requirements were unclear at the beginning of the project | 2 | Eur/ME | IT/Solution | 2006 | February | 755469
1876 | Resource | Money | Limitation | 15 | 6 | Layoffs in mid-project | 0 | Americas | IT/Solution | 2013 | March | 758550
1877 | Resource | Outsourcing | Delayed start | 17 | 3 | Failed to get client sign-off for work done in India | 2 | Eur/ME | IT/Solution | 2013 | December | 1265905
1878 | Resource | Outsourcing | Late or poor output | 14 | 3 | Consultant who worked on benefits was taken off the project | 0 | Americas | IT/Solution | 2008 | December | 1107288
1879 | Schedule | Estimates | Judgment | 22 | 3 | Chronic optimism on completion dates for work | 2 | Eur/ME | Prod. Dev. | 2015 | August | 1649824
1880 | Scope | Change | Gap | 7 | 5 | Late change required to meet code | 0 | Americas | IT/Solution | 2019 | November | 553679
1881 | Schedule | Delay | Hardware | 22 | 7 | Key parts would be delivered late | 0 | Americas | IT/Solution | 2011 | May | 656546
1882 | Schedule | Estimates | Deadline | 20 | 5 | Customer insists on deadline shorter than plan. Attempted, but not possible. | 0 | Americas | IT/Solution | 2019 | May | 1110280
1883 | Scope | Change | Gap | 6 | 3 | Work done by contractors with too little information; components require rework. | 2 | Eur/ME | IT/Solution | 2010 | January | 282756
1884 | Scope | Change | Gap | 9 | 7 | The programmer hadn’t understood how certain parts of the program date-logic worked and hadn’t asked for any assistance. | 0 | Americas | IT/Solution | 2019 | January | 597375
1885 | Schedule | Dependency | Project | 21 | 6 | Localization of the web contents delivery is delayed | 3 | Africa | IT/Solution | 2001 | April | 947415
1886 | Schedule | Dependency | Project | 13 | 5 | ASIC supplier (only source) was fine for low volume, but at lower cost and high volume had quality problems and created delays. | 3 | Africa | Prod. Dev. | 2003 | September | 843193
1887 | Schedule | Estimates | Judgment | 7 | 5 | The integration task was not defined and broken down to sufficiently small pieces in the project plan. | 2 | Eur/ME | Prod. Dev. | 2019 | December | 532308
1888 | Schedule | Estimates | Learning | 21 | 5 | Oversea engineering team was inexperienced | 3 | Africa | Prod. Dev. | 2004 | December | 1350321
1889 | Scope | Change | Creep | 11 | 3 | No proper change control process resulted in unnecessary new requirements | 3 | Africa | Prod. Dev. | 2006 | October | 879802
1890 | Scope | Change | Gap | 7 | 5 | Lack of communication between the teams | 0 | Americas | IT/Solution | 2019 | July | 232372
1891 | Scope | Change | Gap | 5 | 7 | Failure to understand the scope of the project | 2 | Eur/ME | Prod. Dev. | 2007 | February | 176140
1892 | Scope | Change | Gap | 10 | 4 | Instructions provided to the testing facility were too vague, necessitating re-tests | 0 | Americas | Prod. Dev. | 2019 | January | 474560
1893 | Scope | Defect | Hardware | 7 | 7 | Network configuration sometimes causes the backups to fail intermittently; troubleshooting is hard. | 3 | Africa | IT/Solution | 2007 | January | 172060
1894 | Resource | People | Temp loss | 15 | 3 | Lead engineer stuck in Japan for 2 weeks longer than expected | 2 | Eur/ME | Prod. Dev. | 2003 | February | 365565
1895 | Schedule | Delay | Decision | 18 | 4 | Code review delayed due to merger | 3 | Africa | Prod. Dev. | 2007 | March | 1216206
1896 | Schedule | Delay | Information | 18 | 6 | Orders sometimes get lost in manual routing | 0 | Americas | IT/Solution | 2019 | March | 802494
1897 | Scope | Change | Creep | 6 | 5 | Client changes her mind every step of the way | 0 | Americas | IT/Solution | 2019 | September | 215742
1898 | Scope | Change | Gap | 17 | 3 | Online badge printing requirement completely missing from scope definition | 2 | Eur/ME | IT/Solution | 2005 | December | 897923
1899 | Scope | Change | Gap | 10 | 3 | Scope was not discussed with the manufacturer before design was completed | 3 | Africa | Prod. Dev. | 2008 | November | 776720
1900 | Scope | Defect | Hardware | 18 | 3 | Solution project integrated new, untried technology. Difficulty getting it to work. | 3 | Africa | IT/Solution | 2015 | July | 1396620
1901 | Scope | Defect | Software | 15 | 6 | Excessive bugs detected late; delayed to fix. | 3 | Africa | IT/Solution | 2013 | November | 629115
1902 | Resource | People | Queuing | 12 | 5 | US expertise needed for project in Asia. Team member flies to US, but expert is busy. | 3 | Africa | Prod. Dev. | 2008 | March | 440640
1903 | Resource | People | Temp loss | 15 | 7 | Key welding staff are out with flu | 0 | Americas | Prod. Dev. | 2012 | November | 415500
1904 | Schedule | Delay | Parts | 18 | 6 | No coordinated shipment of system components; last one delays installation. | 0 | Americas | IT/Solution | 2011 | May | 510228
1905 | Resource | People | Motivation | 19 | 7 | Project wanted by management but never gets team buy-in. Even with heavy monitoring, project work is slow. | 2 | Eur/ME | Prod. Dev. | 2018 | March | 1479720
1906 | Schedule | Delay | Parts | 18 | 4 | Volume of new IC chip required for ramp not available. Major backlog on product delivery. | 3 | Africa | Prod. Dev. | 2003 | September | 849294
1907 | Schedule | Delay | Parts | 20 | 3 | Changes to outside providers resulted in major delays | 0 | Americas | Prod. Dev. | 2017 | June | 754220
1908 | Schedule | Dependency | Project | 19 | 5 | Interdependencies in complex program underestimated and detected late. | 3 | Africa | IT/Solution | 2008 | November | 896781
1909 | Scope | Change | Creep | 18 | 4 | Late rescoping of 2-year project led to half-year slip. | 0 | Americas | IT/Solution | 2019 | September | 530640
1910 | Scope | Change | Creep | 21 | 5 | Extension of scope in Japan was not managed or controlled well | 3 | Africa | IT/Solution | 2015 | April | 1164282
1911 | Scope | Change | Creep | 6 | 6 | Mid-project feature revisions. Major impact on effort and schedule; product failed (too late to market). | 0 | Americas | Prod. Dev. | 2010 | February | 214866
1912 | Scope | Change | Gap | 18 | 6 | Survey data required for project assigned to several people in some countries; each assumes others will do work | 2 | Eur/ME | IT/Solution | 2006 | May | 956664
1913 | Scope | Change | Gap | 9 | 7 | There was a very large mismatch between stakeholder expectations and given scope | 3 | Africa | IT/Solution | 2006 | December | 453294
1914 | Scope | Defect | Hardware | 20 | 3 | Redesign required late in printer project to meet print quality goals. Major slip. | 0 | Americas | Prod. Dev. | 2002 | November | 1393280
1915 | Scope | Defect | Software | 9 | 5 | Purchased component never delivered (vaporware). Workaround developed by brute force (not high-tech and difficult to support). | 2 | Eur/ME | IT/Solution | 2015 | June | 608553
1916 | Schedule | Dependency | Project | 15 | 6 | Project was constantly having resources pulled for higher priority work | 0 | Americas | IT/Solution | 2005 | January | 408300
1917 | Resource | People | Motivation | 17 | 5 | Project wanted by management but never gets team buy-in. Even with heavy monitoring, project work is slow. | 0 | Americas | Prod. Dev. | 2019 | July | 782901
1918 | Scope | Change | Creep | 12 | 6 | Excessive changes made | 0 | Americas | Prod. Dev. | 2004 | March | 615240
1919 | Resource | Outsourcing | Late or poor output | 18 | 6 | Contract manufacturer failed to deliver a new drug | 0 | Americas | Prod. Dev. | 2009 | January | 1283958
1920 | Schedule | Estimates | Learning | 5 | 7 | Ramp-up required 40 new test engineers | 3 | Africa | Prod. Dev. | 2005 | February | 364635
1921 | Scope | Defect | Hardware | 7 | 3 | Our server crashed, which contains 4 months worth of info. No backup, had to be reentered. | 2 | Eur/ME | Prod. Dev. | 2014 | July | 155309
1922 | Scope | Defect | Software | 13 | 5 | Software in use casused unacceptable image distortion | 2 | Eur/ME | Prod. Dev. | 2007 | September | 938145
1923 | Schedule | Estimates | Judgment | 20 | 4 | Team did not break down the processes enough to clearly identify each step | 3 | Africa | Prod. Dev. | 2014 | January | 733220
1924 | Scope | Change | Gap | 22 | 7 | A mid-project review turned up numerous regulations that were not implemented | 3 | Africa | IT/Solution | 2018 | July | 700480
1925 | Scope | Defect | Software | 11 | 6 | System tool could not be scaled to a huge web application | 3 | Africa | IT/Solution | 2009 | August | 257785
1926 | Scope | Defect | Software | 18 | 6 | Database contains incorrect information and the QA environment is unstable | 0 | Americas | IT/Solution | 2002 | July | 442152
1927 | Schedule | Delay | Information | 16 | 3 | Project has customer info, but also needs supplier data. Project to provide this is delayed. | 3 | Africa | IT/Solution | 2015 | June | 1215456
1928 | Resource | People | Loss | 10 | 5 | Lack of IT subject matter experts | 0 | Americas | IT/Solution | 2019 | May | 298960
1929 | Resource | People | Loss | 8 | 5 | Project work estimated to take 1 month took 3 due to loss of staff to do the work. | 2 | Eur/ME | Prod. Dev. | 2004 | June | 526656
1930 | Resource | People | Queuing | 18 | 7 | Specialist was busy with a lot of work | 0 | Americas | Prod. Dev. | 2002 | May | 1188990
1931 | Scope | Change | Creep | 12 | 3 | Additional renovations added late that were not in the original plan | 0 | Americas | Prod. Dev. | 2019 | September | 440892
1932 | Scope | Change | Gap | 9 | 7 | Lead engineer thought he had a good ‘understanding’ of what needed to be done | 0 | Americas | Prod. Dev. | 2019 | June | 518724
1933 | Scope | Change | Gap | 21 | 5 | Partner company introduced a changed requirement late in development | 3 | Africa | Prod. Dev. | 2015 | September | 1362144
1934 | Scope | Change | Gap | 11 | 7 | Additional localization requirements will cost significant extra effort and time | 3 | Africa | Prod. Dev. | 2013 | May | 533423
1935 | Scope | Change | Creep | 9 | 6 | Late addition of a USB port to a recharging adapter | 0 | Americas | Prod. Dev. | 2019 | July | 519624
1936 | Scope | Change | Dependency | 6 | 3 | Old hardware became unavailable and product had to be tested on the new series | 3 | Africa | IT/Solution | 2017 | March | 292944
1937 | Resource | Money | Limitation | 11 | 7 | Understaffing causes overtime and leads to loss of staff | 2 | Eur/ME | IT/Solution | 2008 | May | 465333
1938 | Schedule | Delay | Information | 10 | 6 | The Project Lead did not hold the customer/business line accountable for their delay | 2 | Eur/ME | Prod. Dev. | 2018 | September | 371420
1939 | Resource | People | Loss | 12 | 6 | Key person lost mid-project | 0 | Americas | IT/Solution | 2019 | September | 952092
1940 | Resource | People | Loss | 21 | 6 | Team members reassigned to other, higher priority projects. | 2 | Eur/ME | Prod. Dev. | 2007 | April | 478149
1941 | Resource | People | Temp loss | 6 | 6 | Contributor has lengthy, unannounced vacation | 3 | Africa | IT/Solution | 2016 | June | 468780
1942 | Schedule | Estimates | Judgment | 11 | 5 | Development scheduled in parallel leads to frequent rework. | 3 | Africa | Prod. Dev. | 2005 | April | 643610
1943 | Scope | Change | Creep | 21 | 3 | Several applications were changed due to change in project requirements | 0 | Americas | IT/Solution | 2009 | June | 1530333
1944 | Scope | Defect | Hardware | 7 | 4 | Insufficient length of anchor bolts protruding from the concrete foundation to allow the base plate nuts to fully engage | 0 | Americas | Prod. Dev. | 2019 | February | 216209
1945 | Resource | Money | Limitation | 17 | 4 | Part of the project team ran of money three months before the project was scheduled to end | 0 | Americas | Prod. Dev. | 2005 | November | 560898
1946 | Resource | Outsourcing | Late or poor output | 17 | 4 | Growth pushed work to understaffed contract firms | 0 | Americas | IT/Solution | 2010 | December | 682584
1947 | Resource | People | Late start | 20 | 3 | Finding instructional designers that know how to use specialized software | 0 | Americas | Prod. Dev. | 2019 | June | 1089680
1948 | Resource | People | Temp loss | 7 | 5 | Only 2 people understood the new system, and neither was available | 0 | Americas | IT/Solution | 2019 | June | 186109
1949 | Schedule | Delay | Parts | 11 | 3 | ASIC delays | 2 | Eur/ME | Prod. Dev. | 2008 | November | 793540
1950 | Schedule | Delay | Parts | 8 | 3 | International shipment of parts supposed to take 6 weeks, actually averages 9. | 0 | Americas | Prod. Dev. | 2010 | January | 341488
1951 | Schedule | Estimates | Learning | 12 | 3 | Due to organizational change new person was assigned the work | 2 | Eur/ME | IT/Solution | 2005 | December | 883620
1952 | Scope | Change | Creep | 18 | 3 | Client requested "15 minute" change accepted and led to delay and loss on project | 3 | Africa | IT/Solution | 2018 | February | 1306782
1953 | Scope | Change | Gap | 16 | 3 | Lack of data and knowledge for the new product | 0 | Americas | Prod. Dev. | 2019 | July | 577408
1954 | Scope | Change | Gap | 8 | 7 | Documentation provided in only one of two required languages. Delay for translation. | 0 | Americas | IT/Solution | 2004 | November | 415056
1955 | Resource | Outsourcing | Late or poor output | 18 | 4 | Outsourcing firm had an incompetent design team | 2 | Eur/ME | IT/Solution | 2002 | August | 1103490
1956 | Resource | Outsourcing | Late or poor output | 9 | 4 | Contract had no penalties for missing deadlines; 3 weeks taken on 1 week task. | 0 | Americas | IT/Solution | 2019 | September | 512100
1957 | Resource | People | Late start | 21 | 6 | Insufficient planning and commitment by the committee involved | 2 | Eur/ME | IT/Solution | 2004 | July | 542850
1958 | Resource | People | Motivation | 10 | 5 | Project involved several departments, several of which were uncooperative | 0 | Americas | IT/Solution | 2011 | June | 373000
1959 | Schedule | Delay | Parts | 19 | 6 | Incorrect part shipped. Delay for reshipment. | 3 | Africa | Prod. Dev. | 2014 | April | 1200496
1960 | Scope | Change | Creep | 22 | 3 | Late in long project, process rigor falls and changes are managed poorly. | 0 | Americas | Prod. Dev. | 2019 | June | 1166858
1961 | Scope | Change | Dependency | 7 | 5 | Upgrade to software required. Planning and training caused delays. | 2 | Eur/ME | IT/Solution | 2017 | September | 525357
1962 | Scope | Defect | Software | 10 | 5 | Excessive bugs | 0 | Americas | IT/Solution | 2019 | August | 717770
1963 | Resource | Money | Limitation | 22 | 5 | Did not have sufficient resources and the contingency plan was inadequate | 0 | Americas | IT/Solution | 2019 | January | 1005026
1964 | Schedule | Delay | Hardware | 15 | 7 | "Customer supplied" hardware does not work. Replacement required. | 3 | Africa | IT/Solution | 2003 | December | 830385
1965 | Resource | Outsourcing | Late or poor output | 20 | 4 | Vendor was unable to control the environment: work had to be repeated | 0 | Americas | Prod. Dev. | 2019 | August | 1453520
1966 | Resource | Outsourcing | Late or poor output | 5 | 3 | Key supplier purchased by other company and reorganized. Forced to find new supplier. | 3 | Africa | Prod. Dev. | 2002 | June | 289910
1967 | Resource | People | Late start | 14 | 5 | Significant delay in patient recruitment | 0 | Americas | Prod. Dev. | 2019 | February | 740390
1968 | Resource | People | Loss | 9 | 7 | Indefinite loss of key staff member | 3 | Africa | IT/Solution | 2004 | May | 249543
1969 | Resource | People | Loss | 18 | 5 | Staff cutbacks (and dropped scope as well) | 3 | Africa | IT/Solution | 2013 | November | 817722
1970 | Resource | People | Queuing | 10 | 4 | Insufficient QA resources to cover the auditing tasks and training tasks. | 0 | Americas | Prod. Dev. | 2002 | March | 578190
1971 | Schedule | Delay | Decision | 13 | 4 | Delay in patient recruitment for clinical trials | 3 | Africa | Prod. Dev. | 2005 | July | 464997
1972 | Schedule | Delay | Hardware | 19 | 7 | Servers got stuck in customs | 0 | Americas | IT/Solution | 2017 | May | 503766
1973 | Schedule | Delay | Information | 10 | 6 | Software is developed in Israel. In a week, there was less than one working day for teleconference and war made it impractical to travel. Needed info was always late. | 2 | Eur/ME | IT/Solution | 2010 | February | 466980
1974 | Schedule | Delay | Parts | 17 | 6 | Part was too long to ship, so it was cut. Result was useful only as raw material. | 3 | Africa | Prod. Dev. | 2012 | February | 1357433
1975 | Schedule | Dependency | Legal | 20 | 5 | Unexpectedly, the FDA requires a long-term toxicity study | 2 | Eur/ME | Prod. Dev. | 2013 | January | 1191780
1976 | Schedule | Dependency | Project | 22 | 5 | Project was constantly having resources pulled for higher priority work | 0 | Americas | IT/Solution | 2019 | November | 955856
1977 | Schedule | Estimates | Judgment | 13 | 6 | Complexity of the investigation was badly underestimated | 3 | Africa | Prod. Dev. | 2008 | May | 304408
1978 | Schedule | Estimates | Learning | 14 | 3 | Severe learning curve of somestaff slowed progress | 2 | Eur/ME | IT/Solution | 2017 | February | 923496
1979 | Schedule | Estimates | Learning | 8 | 7 | Inexperienced staff | 3 | Africa | Prod. Dev. | 2013 | February | 384376
1980 | Schedule | Estimates | Learning | 22 | 5 | Incompetent developer | 0 | Americas | Prod. Dev. | 2019 | June | 1219372
1981 | Scope | Change | Creep | 11 | 5 | Contract had no input from project team and few defined specs. Changes poorly managed and project was very late. | 2 | Eur/ME | IT/Solution | 2018 | July | 474496
1982 | Scope | Change | Creep | 6 | 5 | Scoping for a wiring project increased substantially after awarding the business | 2 | Eur/ME | IT/Solution | 2005 | February | 418818
1983 | Scope | Change | Creep | 16 | 3 | Late scope change added customer choice in subscription ticket selection | 0 | Americas | IT/Solution | 2001 | January | 967840
1984 | Scope | Change | Creep | 12 | 5 | An extra specialty service to the hospital was added | 0 | Americas | IT/Solution | 2001 | March | 715668
1985 | Scope | Change | Creep | 9 | 5 | Insufficient analysis of new technology introduced late | 3 | Africa | Prod. Dev. | 2005 | July | 712485
1986 | Scope | Change | Creep | 22 | 3 | The contract indicated state of the art retrofit materials; differing meaning over 2 years | 2 | Eur/ME | Prod. Dev. | 2006 | November | 1723942
1987 | Scope | Change | Creep | 11 | 4 | The project team agreed to new requirements; unfortunately, some of the changes promised were not even possible | 2 | Eur/ME | Prod. Dev. | 2013 | August | 608509
1988 | Scope | Change | Creep | 18 | 6 | Volume requirements increased late in project, requiring extensive rework | 3 | Africa | Prod. Dev. | 2011 | January | 739602
1989 | Scope | Change | Creep | 21 | 6 | Product was scoped with unnecessary requirements and was late | 0 | Americas | Prod. Dev. | 2010 | October | 676242
1990 | Scope | Change | Creep | 22 | 6 | Engineering would not stop adding “bell and whistles” to GUI | 0 | Americas | Prod. Dev. | 2019 | November | 856438
1991 | Scope | Change | Creep | 16 | 5 | Scope definition was poor and change was rampant | 2 | Eur/ME | IT/Solution | 2017 | January | 408048
1992 | Scope | Change | Dependency | 12 | 6 | A full bioequivalent (BE) study was unexpectedly needed even though there was only a minor difference | 2 | Eur/ME | IT/Solution | 2017 | December | 509616
1993 | Scope | Change | Gap | 15 | 6 | Major system was begun with insufficient internal resources and without good requirements information | 0 | Americas | IT/Solution | 2019 | August | 584220
1994 | Scope | Change | Gap | 10 | 7 | Due to poor understanding, a redesign and costing effort was neeed | 2 | Eur/ME | IT/Solution | 2004 | November | 720310
1995 | Scope | Change | Gap | 18 | 6 | Team failed to engage the critical “power-users” early enough | 0 | Americas | IT/Solution | 2010 | January | 468144
1996 | Scope | Change | Gap | 17 | 6 | Project manager thought the solution was only one task, but there were four | 0 | Americas | Prod. Dev. | 2012 | September | 1242122
1997 | Scope | Change | Gap | 8 | 5 | New technology, required changes to SW to work | 2 | Eur/ME | Prod. Dev. | 2013 | October | 364512
1998 | Scope | Change | Gap | 5 | 7 | Poor Fit/Gap analysis | 0 | Americas | Prod. Dev. | 2019 | April | 390755
1999 | Scope | Change | Gap | 16 | 4 | Poor requirements definition | 0 | Americas | Prod. Dev. | 2019 | November | 967840
2000 | Scope | Change | Gap | 18 | 6 | Incomplete design was a result of not considering the particular country needs | 2 | Eur/ME | IT/Solution | 2006 | November | 1006938
2001 | Scope | Change | Gap | 9 | 3 | Architect determined that the new design plan for the medical clinic would be considerably more complex than a simple remodeling job | 0 | Americas | Prod. Dev. | 2019 | March | 488682
2002 | Scope | Change | Gap | 8 | 3 | Lack of consensus on the spec resulted in modifications during the second phase of the project | 0 | Americas | IT/Solution | 2011 | December | 297480
2003 | Scope | Change | Gap | 15 | 4 | Clinical evidence was insufficient for European market | 0 | Americas | Prod. Dev. | 2019 | March | 543930
2004 | Scope | Defect | Hardware | 15 | 6 | Based on testing, performance was insufficient to gain approval to market | 2 | Eur/ME | Prod. Dev. | 2014 | March | 611655
2005 | Scope | Defect | Integration | 21 | 6 | SumTotal LMS user interface is significantly more complex than the Docent LMS user interface it is to replace | 2 | Eur/ME | IT/Solution | 2004 | February | 1323147
2006 | Scope | Defect | Software | 10 | 7 | The software had around 20 major defects and 80 problems that prevented us from moving forward | 2 | Eur/ME | IT/Solution | 2013 | May | 503170
2007 | Scope | Defect | Software | 18 | 3 | In UAT testing, a fatal flaw sent the deliverable back to development | 0 | Americas | IT/Solution | 2016 | December | 1387224
2008 | Scope | Defect | Software | 20 | 4 | During unit testing, discovered performance issue with bulk loads | 0 | Americas | IT/Solution | 2019 | January | 516420
2009 | Scope | Defect | Software | 7 | 6 | Serious issues arose with large loads of data, causing performance problems | 3 | Africa | Prod. Dev. | 2007 | November | 483630
2010 | Resource | Money | Limitation | 15 | 4 | Lack of Stakeholder commitment and oversight | 2 | Eur/ME | IT/Solution | 2009 | September | 730710
2011 | Resource | Money | Limitation | 8 | 3 | Failed to allocate enough resources and missed important parts of scope | 0 | Americas | IT/Solution | 2013 | August | 367792
2012 | Resource | Money | Limitation | 6 | 6 | Without funding, all work ceased, contracts were effectively terminated with no prospect of renewal | 3 | Africa | Prod. Dev. | 2011 | April | 150564
2013 | Resource | Money | Limitation | 6 | 5 | Not enough staff to cover the load and failure to prioritize | 2 | Eur/ME | Prod. Dev. | 2006 | May | 396396
2014 | Resource | Money | Limitation | 13 | 6 | Major infrastructure project cut back; delayed fixes cost a lot of money, and resources needed were assigned to other work. | 0 | Americas | IT/Solution | 2007 | July | 883350
2015 | Scope | Defect | Software | 18 | 5 | Serious issues arose with large loads of data, causing performance problems | 3 | Africa | Prod. Dev. | 2015 | December | 1142118
2016 | Scope | Defect | Hardware | 13 | 6 | Found some strange and unusual contamination of an entire batch of petri plates | 2 | Eur/ME | IT/Solution | 2004 | August | 458172
2017 | Resource | Outsourcing | Late or poor output | 5 | 6 | A key component of the system was outsourced | 2 | Eur/ME | IT/Solution | 2018 | June | 262625
2018 | Resource | People | Motivation | 10 | 7 | A pool of unqualified, poorly performing, marginal staff to work with | 0 | Americas | IT/Solution | 2019 | October | 448490
2019 | Resource | People | Loss | 21 | 5 | Expert Cardiologist no longer available | 0 | Americas | Prod. Dev. | 2019 | December | 1244943
2020 | Scope | Change | Gap | 7 | 4 | The scope was not clearly defined | 2 | Eur/ME | IT/Solution | 2016 | September | 414526
2021 | Resource | Money | Limitation | 6 | 6 | Too few staff members | 3 | Africa | IT/Solution | 2006 | May | 212310
2022 | Resource | People | Late start | 7 | 5 | Government contract required only US born nationals; company had too few | 3 | Africa | IT/Solution | 2001 | July | 537691
2023 | Scope | Defect | Software | 13 | 4 | Problems detected and solution developed based on presumed root cause. Cause was actually something else and led to major slip. | 0 | Americas | Prod. Dev. | 2011 | October | 483509
2024 | Schedule | Delay | Parts | 22 | 4 | Delay in getting material when a fermentation run crashes | 0 | Americas | Prod. Dev. | 2019 | October | 463782
2025 | Resource | People | Queuing | 5 | 7 | Project was dependent on onekey resource and had to wait | 0 | Americas | Prod. Dev. | 2019 | November | 158410
2026 | Scope | Change | Gap | 16 | 3 | Flaw found in functional design specifications | 0 | Americas | Prod. Dev. | 2009 | November | 1177872
2027 | Schedule | Dependency | Infrastructure | 9 | 3 | Scheduling based on small pilot installation, but full roll out backed up the help desk and project was delayed. | 3 | Africa | IT/Solution | 2015 | December | 642618
2028 | Schedule | Estimates | Learning | 20 | 6 | New hires used; time for training. | 2 | Eur/ME | Prod. Dev. | 2013 | November | 1157000
2029 | Scope | Change | Creep | 17 | 4 | Client's insisted on the use of "the latest technology | 2 | Eur/ME | IT/Solution | 2015 | May | 837437
2030 | Scope | Change | Creep | 15 | 6 | Modifying requirements in the middle of a phase | 2 | Eur/ME | Prod. Dev. | 2006 | August | 515340
2031 | Scope | Change | Gap | 17 | 7 | Scoping set and estimated based on just one set of data from one customer | 0 | Americas | Prod. Dev. | 2019 | July | 471019
2032 | Schedule | Delay | Decision | 17 | 3 | Senior management approval for software licenses delayed | 0 | Americas | Prod. Dev. | 2019 | October | 1214905
2033 | Schedule | Delay | Parts | 13 | 7 | Needed concrete wasn’t delivered on time | 2 | Eur/ME | IT/Solution | 2006 | July | 607399
2034 | Schedule | Estimates | Judgment | 9 | 4 | Components that could have been purchased were developed by team, taking longer than expected. | 0 | Americas | Prod. Dev. | 2019 | February | 644868
2035 | Scope | Change | Creep | 15 | 3 | Project delayed due to recent/last minute changes to portal interface design | 0 | Americas | IT/Solution | 2003 | April | 452760
2036 | Scope | Change | Gap | 10 | 3 | Insufficient initial project scope was defined when the estimate given to the client | 1 | Asia | Prod. Dev. | 2004 | August | 212070
2037 | Scope | Change | Gap | 11 | 4 | Documentation needed in French was entirely overlooked | 0 | Americas | Prod. Dev. | 2019 | February | 282458
2038 | Resource | People | Queuing | 21 | 4 | Key people are shared by several projects; lots of queuing. | 0 | Americas | IT/Solution | 2019 | February | 1274973
2039 | Resource | People | Temp loss | 18 | 6 | Staff illness results in use of temporary staff | 3 | Africa | Prod. Dev. | 2012 | May | 599274
2040 | Schedule | Delay | Decision | 7 | 5 | Decisions are too slow due to distance and lack of face-to-face communication | 3 | Africa | Prod. Dev. | 2016 | February | 253946
2041 | Schedule | Delay | Parts | 21 | 3 | Project manager redesigned the prototype and made inventory invalid | 3 | Africa | Prod. Dev. | 2010 | May | 1558158
2042 | Schedule | Dependency | Infrastructure | 18 | 5 | Systems needed for project work failed late in the project, and when work was completed installation delayed further to next possible installation window. | 1 | Asia | IT/Solution | 2016 | January | 705996
2043 | Scope | Change | Creep | 15 | 6 | Senior management decided to change the core switching platform technology | 2 | Eur/ME | Prod. Dev. | 2019 | September | 560520
2044 | Scope | Change | Dependency | 10 | 4 | New software release installed by IT, and inconsistencies with older version caused delay and extra work. | 1 | Asia | IT/Solution | 2008 | April | 728930
2045 | Resource | Outsourcing | Late or poor output | 10 | 7 | Contractor did not spend time on the project because his organization used him for other work | 2 | Eur/ME | IT/Solution | 2013 | April | 568880
2046 | Schedule | Delay | Hardware | 22 | 5 | Installation of new systems required by project delayed. | 2 | Eur/ME | Prod. Dev. | 2005 | July | 597410
2047 | Scope | Change | Creep | 18 | 3 | Change to the objective when the project was almost finished | 1 | Asia | IT/Solution | 2009 | January | 1012122
2048 | Resource | Money | Limitation | 22 | 7 | Did not have sufficient resources and the contingency plan was inadequate | 0 | Americas | IT/Solution | 2019 | April | 804584
2049 | Resource | Money | Limitation | 20 | 4 | Contractor setup delayed by a week | 0 | Americas | Prod. Dev. | 2019 | August | 1229220
2050 | Resource | Outsourcing | Delayed start | 14 | 3 | Contractor did not spend time on the project because his organization used him for other work | 3 | Africa | IT/Solution | 2014 | November | 433776
2051 | Resource | Outsourcing | Late or poor output | 8 | 4 | Contractors failed to show up as committed | 2 | Eur/ME | IT/Solution | 2001 | April | 216816
2052 | Resource | Outsourcing | Late or poor output | 14 | 3 | Third-party vendor inadvertently introduced a bug during an upgrade | 3 | Africa | IT/Solution | 2018 | April | 1042720
2053 | Resource | Outsourcing | Late or poor output | 17 | 3 | Outsouced staff lacked the necessary skillset | 2 | Eur/ME | IT/Solution | 2006 | December | 674237
2054 | Resource | Outsourcing | Late or poor output | 7 | 5 | Planning delayed due to staff being still tied up in testing on prior project. | 2 | Eur/ME | Prod. Dev. | 2002 | February | 260148
2055 | Resource | People | Late start | 22 | 3 | Chef quit two days before the café was scheduled to open | 2 | Eur/ME | IT/Solution | 2018 | February | 903518
2056 | Resource | People | Loss | 21 | 4 | Work at customer site had to be done by union workers; took 6 days to do what project team could do in 1. | 1 | Asia | IT/Solution | 2019 | June | 944202
2057 | Resource | People | Motivation | 5 | 7 | Critical task assigned to a heavily booked expert | 3 | Africa | IT/Solution | 2009 | August | 396255
2058 | Resource | People | Queuing | 10 | 3 | Key packaging engineer was working on a high priority project when needed | 3 | Africa | IT/Solution | 2003 | August | 696800
2059 | Resource | People | Queuing | 11 | 4 | No engineer is available or has enough knowledge | 2 | Eur/ME | IT/Solution | 2013 | November | 475893
2060 | Resource | People | Queuing | 14 | 5 | People were allocated to too many projects and bottlenecks developed | 3 | Africa | IT/Solution | 2007 | November | 692020
2061 | Resource | People | Queuing | 16 | 6 | Key person not available when needed. | 0 | Americas | Prod. Dev. | 2019 | May | 498944
2062 | Resource | People | Queuing | 12 | 7 | US expertise needed for project in Asia. Team member flies to US, but expert is busy. | 2 | Eur/ME | Prod. Dev. | 2019 | July | 417144
2063 | Resource | People | Queuing | 13 | 3 | Engineer responsible to program the ISDN router called in sick | 1 | Asia | IT/Solution | 2017 | November | 821548
2064 | Resource | People | Temp loss | 9 | 5 | Key welding staff are out with flu | 0 | Americas | Prod. Dev. | 2019 | December | 578097
2065 | Resource | People | Temp loss | 8 | 5 | Manufacturing volumes spiked and diverted project contributors. | 0 | Americas | Prod. Dev. | 2019 | February | 441304
2066 | Resource | People | Temp loss | 6 | 7 | Unannounced audit in mid-project caused delay to prepare and participate. | 1 | Asia | Prod. Dev. | 2019 | July | 326772
2067 | Resource | People | Temp loss | 13 | 6 | Key team member grounded in Middle East during a regional war. | 1 | Asia | IT/Solution | 2017 | December | 699530
2068 | Resource | People | Temp loss | 10 | 6 | Key contributor out ill at critical time. | 3 | Africa | IT/Solution | 2008 | September | 535950
2069 | Resource | People | Temp loss | 14 | 4 | Client missed the deadline for feedback by several days | 2 | Eur/ME | IT/Solution | 2008 | February | 365428
2070 | Schedule | Delay | Decision | 16 | 4 | Document reviews slipped due to conflicts and low priority. | 0 | Americas | Prod. Dev. | 2019 | February | 934480
2071 | Schedule | Delay | Decision | 22 | 6 | Flood shuts down data center. Delay to restore power and clean up. | 2 | Eur/ME | IT/Solution | 2001 | February | 1729574
2072 | Schedule | Delay | Hardware | 17 | 3 | "Customer supplied" hardware does not work. Replacement required. | 3 | Africa | IT/Solution | 2005 | December | 861322
2073 | Schedule | Delay | Hardware | 9 | 4 | System arrives late, then when it does arrive staff is not available to install it. | 3 | Africa | Prod. Dev. | 2013 | February | 684369
2074 | Schedule | Delay | Hardware | 6 | 4 | System needed was down for scheduled maintenance not in plan. | 1 | Asia | IT/Solution | 2015 | November | 166746
2075 | Schedule | Delay | Hardware | 14 | 6 | Installation of new systems required by project delayed. | 2 | Eur/ME | Prod. Dev. | 2001 | October | 728252
2076 | Schedule | Delay | Hardware | 22 | 7 | Access to required support tools was not established | 2 | Eur/ME | IT/Solution | 2008 | July | 986942
2077 | Schedule | Delay | Information | 7 | 5 | Documentation from the researcher lacks crucial information | 3 | Africa | Prod. Dev. | 2018 | January | 170779
2078 | Schedule | Delay | Information | 8 | 3 | Customer not showing up for key meeting | 0 | Americas | Prod. Dev. | 2019 | December | 512536
2079 | Schedule | Delay | Information | 20 | 5 | No coordinated shipment of system components; last one delays installation. | 2 | Eur/ME | IT/Solution | 2010 | December | 1399080
2080 | Schedule | Delay | Parts | 6 | 6 | Lack of supplies and adequate time for printing | 1 | Asia | IT/Solution | 2017 | January | 431556
2081 | Schedule | Delay | Parts | 21 | 5 | Out of stock on key parts needed for PC boards. | 1 | Asia | Prod. Dev. | 2002 | July | 1094121
2082 | Schedule | Delay | Parts | 14 | 3 | Parts delivery delay | 3 | Africa | Prod. Dev. | 2014 | November | 1036546
2083 | Schedule | Delay | Parts | 22 | 6 | A needed component was not very stable and only available from only one supplier. | 2 | Eur/ME | Prod. Dev. | 2016 | July | 1416866
2084 | Schedule | Delay | Parts | 13 | 7 | Delivery problems on international shipment--paperwork, customs. | 3 | Africa | IT/Solution | 2010 | August | 562640
2085 | Schedule | Delay | Parts | 13 | 7 | Shipping documents not filled in correctly | 1 | Asia | Prod. Dev. | 2015 | February | 321646
2086 | Schedule | Delay | Parts | 6 | 7 | Dependency on other project not discovered until project end. | 0 | Americas | IT/Solution | 2019 | January | 201678
2087 | Schedule | Dependency | Project | 16 | 6 | Deliverable from one project claimed to be done, but receiving project cannot use it. | 0 | Americas | Prod. Dev. | 2019 | January | 1016736
2088 | Schedule | Dependency | Project | 6 | 3 | Other group could not deliver on time, soI had to do work myself | 1 | Asia | IT/Solution | 2002 | August | 319344
2089 | Schedule | Dependency | Project | 9 | 5 | Untried beta software with unknown computer needs required for training | 3 | Africa | IT/Solution | 2019 | February | 287055
2090 | Schedule | Estimates | Judgment | 10 | 6 | Underestimated weight of stumps to be removed | 1 | Asia | IT/Solution | 2012 | March | 645910
2091 | Schedule | Estimates | Judgment | 15 | 6 | Late additional request on a small project delayed completion | 2 | Eur/ME | IT/Solution | 2003 | January | 653025
2092 | Scope | Change | Creep | 12 | 6 | Change to the objective when the project was almost finished | 0 | Americas | IT/Solution | 2019 | September | 688344
2093 | Scope | Change | Creep | 6 | 5 | Additional enhancements requested at the last minute | 3 | Africa | IT/Solution | 2016 | March | 136410
2094 | Scope | Change | Creep | 6 | 5 | Scope continuously changed by client | 0 | Americas | Prod. Dev. | 2019 | December | 397626
2095 | Scope | Change | Creep | 22 | 7 | Late changes resulted in expedite charges and delay | 1 | Asia | Prod. Dev. | 2004 | July | 1070674
2096 | Scope | Change | Creep | 9 | 6 | System move delayed by last minute system changes that delayed and made backups take too long. | 1 | Asia | IT/Solution | 2004 | June | 514656
2097 | Scope | Change | Creep | 5 | 4 | Scope changed after writers had completed initial draft | 0 | Americas | Prod. Dev. | 2019 | August | 229425
2098 | Scope | Change | Creep | 8 | 3 | Legal required late changes to a large print run of materials | 1 | Asia | Prod. Dev. | 2005 | December | 204272
2099 | Scope | Change | Dependency | 10 | 3 | Policy changes made late in a project requiring additional unplanned work. | 2 | Eur/ME | Prod. Dev. | 2014 | March | 718280
2100 | Scope | Change | Dependency | 7 | 5 | Inadequate facilities; had to find alternatives | 1 | Asia | Prod. Dev. | 2005 | December | 498316
2101 | Scope | Change | Dependency | 20 | 6 | Poor definition of training requirements; had to do much more. | 0 | Americas | IT/Solution | 2019 | August | 1320400
2102 | Scope | Change | Gap | 12 | 6 | After project "complete" rework required for customer approval | 2 | Eur/ME | IT/Solution | 2009 | December | 930144
2103 | Scope | Change | Gap | 20 | 3 | Design team failed to collect the details on what was to be displayed to users | 0 | Americas | IT/Solution | 2019 | February | 848760
2104 | Scope | Change | Gap | 13 | 3 | PM did not take the time to determine what the move entailed | 0 | Americas | IT/Solution | 2019 | June | 261976
2105 | Scope | Change | Gap | 9 | 3 | Lack of a solid plan, or any formal scoping | 1 | Asia | Prod. Dev. | 2016 | February | 707247
2106 | Scope | Change | Gap | 18 | 3 | Final burn-in test interrupted by faulty oven. Replacement and retest took extra time. | 1 | Asia | IT/Solution | 2007 | September | 819882
2107 | Scope | Defect | Hardware | 5 | 6 | Old equipment failed at the last minute | 3 | Africa | IT/Solution | 2004 | May | 292585
2108 | Scope | Defect | Hardware | 9 | 5 | A batch of servers came in with the wrong configurations; had to be fixed | 1 | Asia | IT/Solution | 2005 | February | 320922
2109 | Scope | Defect | Hardware | 17 | 7 | Unanticipated fumes form epoxy concrete paint forced a delay in work | 0 | Americas | IT/Solution | 2019 | May | 463148
2110 | Scope | Defect | Hardware | 7 | 4 | Miscalculation on a critical task | 1 | Asia | Prod. Dev. | 2017 | February | 153139
2111 | Scope | Defect | Hardware | 12 | 4 | Vibration in transit caused the loosing of the nuts and bolts of antennas, which eventually caused the collapse of the antennas | 3 | Africa | Prod. Dev. | 2002 | July | 932280
2112 | Scope | Defect | Hardware | 16 | 3 | Cable required had been left off the implementation parts list | 0 | Americas | IT/Solution | 2019 | January | 1274240
2113 | Scope | Defect | Hardware | 17 | 7 | Integration testing is incomplete, causing system failures. | 2 | Eur/ME | IT/Solution | 2015 | May | 383401
2114 | Scope | Defect | Software | 18 | 4 | No problems in test, but production problems required overtime to fix | 2 | Eur/ME | IT/Solution | 2005 | September | 1185444
2115 | Scope | Defect | Software | 12 | 6 | Access problems surfaced in production | 0 | Americas | IT/Solution | 2019 | April | 380076
2116 | Scope | Defect | Software | 18 | 3 | Engineering overlooked the functional design and did not implement correctly | 2 | Eur/ME | IT/Solution | 2002 | August | 660312
2117 | Scope | Defect | Software | 5 | 6 | Bugs were reported by UAT that should have been caught by QA | 3 | Africa | IT/Solution | 2004 | March | 120660
2118 | Scope | Defect | Software | 18 | 5 | Performance issues surfaced following migration | 0 | Americas | IT/Solution | 2019 | October | 631008
2119 | Scope | Defect | Software | 5 | 6 | Servers got stuck in customs | 2 | Eur/ME | IT/Solution | 2019 | February | 298850
2120 | Schedule | Delay | Hardware | 9 | 6 | New technology, required changes to SW to work | 3 | Africa | Prod. Dev. | 2014 | June | 579951
2121 | Scope | Change | Gap | 10 | 5 | Failed to allocate enough resources and missed important parts of scope | 0 | Americas | IT/Solution | 2019 | August | 666350
2122 | Resource | Money | Limitation | 8 | 3 | Mid-project feature revisions. Major impact on effort and schedule; product failed (too late to market). | 1 | Asia | Prod. Dev. | 2011 | August | 274736
2123 | Scope | Change | Creep | 12 | 6 | Development plans failed to include all of the 23 required applications | 3 | Africa | IT/Solution | 2003 | June | 930792
2124 | Scope | Change | Gap | 15 | 5 | Project budget was dramatically cut | 0 | Americas | IT/Solution | 2019 | June | 590115
2125 | Resource | Money | Limitation | 8 | 7 | Merging of multiple standards is needed to support reorganization. Lack of a new, common definition delayed the project to convert data. | 0 | Americas | IT/Solution | 2019 | May | 376992
2126 | Schedule | Delay | Information | 9 | 7 | The other company was unable to stick to needed deadlines | 0 | Americas | Prod. Dev. | 2019 | December | 244368
2127 | Resource | Outsourcing | Late or poor output | 10 | 5 | Severe funding cutbacks (66% of project team) | 2 | Eur/ME | IT/Solution | 2012 | August | 235760
2128 | Resource | Money | Limitation | 17 | 6 | Project Budget was restricted to the bare minimum estimated | 1 | Asia | Prod. Dev. | 2018 | February | 1339634
2129 | Resource | Money | Limitation | 11 | 6 | Project based on standards still in draft form. Several options are possible, but project is only staffed to pursue one. | 2 | Eur/ME | Prod. Dev. | 2001 | July | 657019
2130 | Scope | Change | Gap | 11 | 3 | Due to a re-organization the team lost essential resources | 3 | Africa | Prod. Dev. | 2005 | July | 803990
2131 | Resource | People | Loss | 13 | 4 | Staffing was late and inexperienced | 0 | Americas | IT/Solution | 2019 | March | 417755
2132 | Resource | People | Late start | 18 | 3 | One of the Senior System Analysts who was fully trained on the application resigned | 0 | Americas | IT/Solution | 2019 | February | 636750
2133 | Resource | People | Loss | 12 | 5 | Project experienced shortages in steel rebar and copper electrical wire | 0 | Americas | IT/Solution | 2019 | June | 718188
2134 | Schedule | Delay | Parts | 22 | 3 | Developers on the project were not experienced enough to implement the solution | 2 | Eur/ME | IT/Solution | 2006 | January | 640090
2135 | Schedule | Estimates | Learning | 7 | 4 | Scope not defined well; huge software delays | 2 | Eur/ME | IT/Solution | 2004 | May | 160300
2136 | Scope | Change | Creep | 6 | 6 | New requirements were piled on as the project ran | 1 | Asia | IT/Solution | 2006 | December | 158046
2137 | Scope | Change | Creep | 21 | 7 | Components failure means finding another type of component and redoing tests | 1 | Asia | Prod. Dev. | 2010 | May | 1032570
2138 | Scope | Defect | Hardware | 20 | 4 | Sponsor fails to provide money | 1 | Asia | Prod. Dev. | 2008 | February | 530980
2139 | Resource | Money | Limitation | 14 | 3 | Management never talked to the test department when creating proposals | 2 | Eur/ME | IT/Solution | 2015 | July | 523782
2140 | Scope | Change | Gap | 6 | 6 | Key staff member lacked knowledge, experience and ability | 1 | Asia | IT/Solution | 2005 | January | 389784
2141 | Schedule | Estimates | Learning | 17 | 5 | Lack of understanding by the manager of the system forced the project to replan | 1 | Asia | Prod. Dev. | 2010 | February | 1194199
2142 | Scope | Change | Gap | 19 | 4 | The project manager was assigned to another big project part way through the project | 1 | Asia | IT/Solution | 2004 | December | 455943
2143 | Resource | People | Loss | 9 | 7 | Conflicting priorities. on-going maintenance, and loss of a person led to delay | 2 | Eur/ME | Prod. Dev. | 2008 | September | 198306
2144 | Resource | People | Queuing | 9 | 5 | Lone subject matter expert unavailable when needed during the initial stages | 0 | Americas | Prod. Dev. | 2019 | January | 227880
2145 | Resource | People | Queuing | 5 | 5 | New technology not available on time. | 3 | Africa | IT/Solution | 2001 | November | 143200
2146 | Schedule | Delay | Hardware | 12 | 7 | Insufficient capacity in the cabling system for needed fiber connection | 3 | Africa | IT/Solution | 2019 | July | 680568
2147 | Schedule | Dependency | Infrastructure | 7 | 6 | Iidviduals who must to approve work are unavailable | 0 | Americas | IT/Solution | 2019 | April | 500206
2148 | Schedule | Dependency | Legal | 22 | 4 | Project priorities and criteria are unclear through much of the project, causing lots of unneeded work. | 2 | Eur/ME | IT/Solution | 2002 | July | 648494
2149 | Scope | Change | Creep | 5 | 7 | Poor prework led to assumption that project would be simpler than it was | 1 | Asia | IT/Solution | 2005 | September | 388405
2150 | Scope | Change | Gap | 16 | 3 | Project had limited funding and limited staffing | 1 | Asia | IT/Solution | 2013 | May | 1145040
2151 | Resource | Money | Limitation | 15 | 5 | Work being done more than 3000 miles away was difficult to check | 3 | Africa | Prod. Dev. | 2009 | October | 515175
2152 | Resource | Outsourcing | Late or poor output | 13 | 7 | Due to contractor layoffs, a Subject Matter Expert had to be replaced | 2 | Eur/ME | IT/Solution | 2015 | November | 534521
2153 | Resource | People | Loss | 16 | 7 | Expert at third party required for work not available when needed | 1 | Asia | IT/Solution | 2015 | March | 746000
2154 | Resource | People | Queuing | 14 | 6 | Limited access to management. Decisions and escalations too slow. | 3 | Africa | Prod. Dev. | 2017 | June | 308952
2155 | Schedule | Delay | Decision | 21 | 5 | Did not have the signature of the director | 1 | Asia | IT/Solution | 2016 | August | 687771
2156 | Schedule | Delay | Decision | 19 | 5 | Equipment used for data analysis failed and was down for 2 weeks | 0 | Americas | Prod. Dev. | 2019 | March | 461738
2157 | Schedule | Delay | Hardware | 16 | 3 | Shipping requirements changed. Some shipments bounce, others get stuck in customs. | 0 | Americas | Prod. Dev. | 2019 | October | 1188976
2158 | Schedule | Dependency | Legal | 7 | 3 | Customer reorganization led to new staffing and changed requirements | 1 | Asia | IT/Solution | 2007 | April | 410970
2159 | Scope | Change | Creep | 9 | 6 | Scope creep and resource inadequacy | 2 | Eur/ME | IT/Solution | 2003 | July | 411471
2160 | Scope | Change | Creep | 16 | 5 | Operating system release expected slips; project forced to use prior version missing some needed functionality. | 0 | Americas | Prod. Dev. | 2019 | July | 1161632
2161 | Scope | Change | Dependency | 7 | 4 | Proprietary data needed, but owners unwilling to provide. After delay, partial information shared. | 0 | Americas | Prod. Dev. | 2019 | August | 364924
2162 | Scope | Change | Gap | 12 | 7 | Key packaging engineer was working on a high priority project when needed | 1 | Asia | IT/Solution | 2011 | September | 339420
2163 | Resource | People | Queuing | 17 | 6 | Key team member grounded in Middle East during a regional war. | 0 | Americas | IT/Solution | 2019 | June | 1078565
2164 | Resource | People | Temp loss | 18 | 5 | Customer not showing up for key meeting | 1 | Asia | Prod. Dev. | 2011 | June | 1322550
2165 | Schedule | Delay | Information | 15 | 5 | Inadequate facilities; had to find alternatives | 0 | Americas | Prod. Dev. | 2019 | January | 359190
2166 | Scope | Change | Dependency | 12 | 7 | Project did not have the buy-in for staffing from other departmens | 2 | Eur/ME | IT/Solution | 2010 | February | 436536
2167 | Resource | Money | Limitation | 19 | 3 | Project had limited funding and limited staffing | 1 | Asia | IT/Solution | 2019 | July | 895755
2168 | Resource | Money | Limitation | 10 | 7 | lack of staff availability due to company down-sizing | 1 | Asia | IT/Solution | 2005 | April | 345050
2169 | Resource | Money | Limitation | 22 | 4 | Lack of money for sufficient equipment | 0 | Americas | Prod. Dev. | 2019 | November | 981112
2170 | Resource | Money | Limitation | 20 | 4 | Slow start of work outsourced. | 1 | Asia | IT/Solution | 2018 | June | 1440200
2171 | Resource | Outsourcing | Delayed start | 10 | 7 | Pricing negotiation stalls project work until resolved. | 1 | Asia | IT/Solution | 2019 | January | 645990
2172 | Resource | Outsourcing | Delayed start | 10 | 7 | New supplier, extensive start up and coordination issues. | 0 | Americas | Prod. Dev. | 2019 | February | 646460
2173 | Resource | Outsourcing | Delayed start | 8 | 5 | Subcontractor delay causes compression of later work. | 1 | Asia | IT/Solution | 2009 | October | 464680
2174 | Resource | Outsourcing | Late or poor output | 14 | 4 | Supplier failure, inputs late and inadequate | 1 | Asia | IT/Solution | 2009 | April | 622468
2175 | Resource | Outsourcing | Late or poor output | 8 | 7 | An external part-time consultant wasn't always available when needed | 1 | Asia | IT/Solution | 2002 | April | 195992
2176 | Resource | Outsourcing | Late or poor output | 5 | 5 | Outsource partner replaced several key people on team | 3 | Africa | IT/Solution | 2010 | June | 100185
2177 | Resource | Outsourcing | Late or poor output | 18 | 3 | Local subcontractors lacked needed technical skills | 0 | Americas | IT/Solution | 2019 | February | 365886
2178 | Resource | Outsourcing | Late or poor output | 14 | 4 | Problems with vendor capacity and performance | 0 | Americas | IT/Solution | 2019 | January | 854014
2179 | Resource | Outsourcing | Late or poor output | 20 | 5 | Outsourcing firm had an incompetent design team | 0 | Americas | IT/Solution | 2019 | March | 1029420
2180 | Resource | Outsourcing | Late or poor output | 22 | 4 | Contractors are not close to the business and often overlook requirements | 0 | Americas | IT/Solution | 2019 | May | 1438008
2181 | Resource | Outsourcing | Late or poor output | 20 | 4 | Slow renewal of contract for consultant; interruption in work | 0 | Americas | Prod. Dev. | 2019 | May | 1504200
2182 | Resource | Outsourcing | Late or poor output | 5 | 6 | Task supposed to be done by an outside company was completed late | 3 | Africa | Prod. Dev. | 2006 | June | 154140
2183 | Resource | Outsourcing | Late or poor output | 12 | 4 | Work being done more than 3000 miles away was difficult to check | 0 | Americas | Prod. Dev. | 2019 | August | 807576
2184 | Resource | Outsourcing | Late or poor output | 13 | 6 | High turnover leads to delays and crisis management. | 3 | Africa | Prod. Dev. | 2007 | December | 594932
2185 | Resource | Outsourcing | Late or poor output | 11 | 4 | Contract had no penalties for missing deadlines; 3 weeks taken on 1 week task. | 0 | Americas | IT/Solution | 2019 | September | 679426
2186 | Resource | Outsourcing | Late or poor output | 7 | 4 | Outsourced tasks slipped, but not known until too late. | 3 | Africa | IT/Solution | 2006 | April | 476763
2187 | Resource | Outsourcing | Late or poor output | 8 | 3 | Work from team in Pakistan failed miserably | 1 | Asia | IT/Solution | 2009 | May | 384336
2188 | Resource | Outsourcing | Late or poor output | 12 | 3 | One factory went on labor strike for 2 weeks –Delayed production of 20 pallets | 0 | Americas | Prod. Dev. | 2019 | May | 415332
2189 | Resource | Outsourcing | Late or poor output | 12 | 3 | Labor union of subcontractor went on stike | 3 | Africa | Prod. Dev. | 2004 | July | 319368
2190 | Resource | Outsourcing | Late or poor output | 5 | 4 | Insufficient planning and commitment by the committee involved | 0 | Americas | IT/Solution | 2019 | July | 105970
2191 | Resource | People | Late start | 19 | 3 | Developer from the database group was not available because of another project | 1 | Asia | IT/Solution | 2009 | March | 1247996
2192 | Resource | People | Late start | 15 | 6 | Project start delayed; team busy on other work. | 2 | Eur/ME | Prod. Dev. | 2003 | October | 1064190
2193 | Resource | People | Late start | 11 | 6 | Project start delayed; staffing and buy-in late, required overtime and extra project management. | 2 | Eur/ME | Prod. Dev. | 2004 | May | 755777
2194 | Resource | People | Late start | 12 | 4 | Toward the end of the development life cycle the original QA lead and trainer quit the firm | 1 | Asia | IT/Solution | 2017 | June | 358140
2195 | Resource | People | Loss | 16 | 6 | A key team member was replaced mid-project | 3 | Africa | IT/Solution | 2001 | April | 749952
2196 | Resource | People | Loss | 6 | 7 | Due to contractor layoffs, a Subject Matter Expert had to be replaced | 0 | Americas | IT/Solution | 2019 | July | 379482
2197 | Resource | People | Loss | 15 | 5 | Expert developer left the company | 1 | Asia | IT/Solution | 2008 | May | 828450
2198 | Resource | People | Loss | 7 | 3 | Chief architect quit, and was the only person with critical skills | 0 | Americas | IT/Solution | 2019 | March | 254044
2199 | Resource | People | Loss | 5 | 6 | Contributor is leaving due to contract expiration | 3 | Africa | IT/Solution | 2002 | December | 347385
2200 | Resource | People | Loss | 9 | 4 | At a critical stage of the project the Medical Director left the company | 1 | Asia | Prod. Dev. | 2014 | October | 396162
2201 | Resource | People | Loss | 18 | 6 | Expert developer left the company | 2 | Eur/ME | Prod. Dev. | 2004 | June | 484434
2202 | Resource | People | Loss | 11 | 7 | Key people resigned, leaving too few to complete project and training on time | 1 | Asia | IT/Solution | 2009 | March | 798237
2203 | Resource | People | Loss | 7 | 3 | Late in project, the budget and staff are cut leading to delays, forced overtime, and demotivation. | 3 | Africa | Prod. Dev. | 2013 | June | 185766
2204 | Resource | People | Loss | 18 | 3 | Project involved several departments, several of which were uncooperative | 0 | Americas | IT/Solution | 2019 | July | 669564
2205 | Resource | People | Motivation | 19 | 6 | On a very long project, enthusiasm and motivation falls; tasks stretch out. | 2 | Eur/ME | Prod. Dev. | 2012 | July | 905046
2206 | Resource | People | Motivation | 10 | 7 | Limits on headcount create work backlog | 2 | Eur/ME | IT/Solution | 2006 | July | 746860
2207 | Resource | People | Queuing | 14 | 5 | Expert at third party required for work not available when needed | 1 | Asia | IT/Solution | 2013 | June | 761110
2208 | Resource | People | Queuing | 19 | 6 | Resources thin and tasks queued in backlogs. | 3 | Africa | IT/Solution | 2007 | December | 471599
2209 | Resource | People | Queuing | 20 | 3 | Key people are shared by several projects; lots of queuing. | 1 | Asia | IT/Solution | 2019 | April | 619460
2210 | Resource | People | Queuing | 11 | 7 | A single person was responsible for key reports many wait in queue | 0 | Americas | IT/Solution | 2019 | August | 569910
2211 | Resource | People | Queuing | 12 | 5 | The test capabilities constitute a bottleneck late in release cycles. | 1 | Asia | Prod. Dev. | 2017 | April | 549324
2212 | Resource | People | Queuing | 18 | 4 | Conflict for resources with a higher priority project | 3 | Africa | Prod. Dev. | 2012 | March | 628560
2213 | Resource | People | Queuing | 8 | 3 | Business Operations Analyst was busy with another big project | 1 | Asia | Prod. Dev. | 2001 | February | 583104
2214 | Resource | People | Queuing | 18 | 5 | Failure by project manager to communicate the need for architect’s time | 1 | Asia | Prod. Dev. | 2005 | July | 665244
2215 | Resource | People | Queuing | 11 | 6 | Key work in flu season delayed; most of staff out ill. | 1 | Asia | IT/Solution | 2017 | April | 613481
2216 | Resource | People | Temp loss | 19 | 3 | Production partner had a personal issue which brought production to a halt | 1 | Asia | IT/Solution | 2001 | June | 853879
2217 | Resource | People | Temp loss | 15 | 6 | Project team frequently diverted to support work. | 2 | Eur/ME | Prod. Dev. | 2001 | May | 488745
2218 | Resource | People | Temp loss | 18 | 3 | Staff lost to customer hot site | 3 | Africa | Prod. Dev. | 2001 | February | 1171044
2219 | Resource | People | Temp loss | 7 | 4 | Key resource was pulled off the project twice to fix bugs in a previous product | 1 | Asia | Prod. Dev. | 2005 | November | 550158
2220 | Resource | People | Temp loss | 11 | 6 | Key Designer was out of the office for 2 weeks | 0 | Americas | Prod. Dev. | 2019 | January | 373923
2221 | Resource | People | Temp loss | 9 | 6 | Software engineer was lost to a higher priority project | 0 | Americas | Prod. Dev. | 2019 | September | 563211
2222 | Resource | People | Temp loss | 7 | 4 | Staff illness results in use of temporary staff | 2 | Eur/ME | Prod. Dev. | 2002 | August | 347102
2223 | Resource | People | Temp loss | 16 | 7 | Key contributor "rounded up" after 9/11 (and later released) | 0 | Americas | Prod. Dev. | 2019 | April | 826960
2224 | Resource | People | Temp loss | 16 | 5 | Reorganization during product ramp creates chaos and ownership problems. | 2 | Eur/ME | Prod. Dev. | 2010 | March | 527328
2225 | Resource | People | Temp loss | 18 | 6 | Lead engineer stuck in Japan for 2 weeks longer than expected | 2 | Eur/ME | Prod. Dev. | 2017 | August | 1400256
2226 | Resource | People | Temp loss | 6 | 7 | Staff lost to customer Hot Site | 1 | Asia | Prod. Dev. | 2018 | June | 444072
2227 | Resource | People | Temp loss | 5 | 7 | Poor access to decision makers | 0 | Americas | IT/Solution | 2019 | September | 304975
2228 | Schedule | Delay | Decision | 10 | 3 | Problems getting timely management decisions. | 2 | Eur/ME | Prod. Dev. | 2005 | April | 366680
2229 | Schedule | Delay | Decision | 15 | 3 | Limited access to management. Decisions and escalations too slow. | 1 | Asia | Prod. Dev. | 2002 | October | 981615
2230 | Schedule | Delay | Decision | 17 | 6 | System needed to approve requests went down; ordering required parts delayed. | 1 | Asia | Prod. Dev. | 2013 | June | 996251
2231 | Schedule | Delay | Decision | 8 | 7 | Requisition required the authorization of CEO who was out of town in Finland | 3 | Africa | Prod. Dev. | 2005 | November | 587544
2232 | Schedule | Delay | Decision | 11 | 7 | Code review delayed due to merger | 1 | Asia | Prod. Dev. | 2003 | April | 651717
2233 | Schedule | Delay | Decision | 15 | 4 | Required design review delayed. | 1 | Asia | Prod. Dev. | 2012 | April | 535650
2234 | Schedule | Delay | Decision | 5 | 4 | Project relocated manufacturing to a contract manufacturer. Required management decisions are frequent and too slow. | 1 | Asia | Prod. Dev. | 2014 | July | 296480
2235 | Schedule | Delay | Decision | 10 | 4 | Decisions are too slow due to distance and lack of face-to-face communication | 3 | Africa | Prod. Dev. | 2011 | May | 424710
2236 | Schedule | Delay | Decision | 13 | 5 | Did not have the signature of the director | 3 | Africa | IT/Solution | 2011 | November | 1020734
2237 | Schedule | Delay | Decision | 7 | 4 | Scope definition and stakeholder agreement delayed. | 2 | Eur/ME | Prod. Dev. | 2004 | February | 191408
2238 | Schedule | Delay | Decision | 22 | 3 | Disaster recovery tests delayed at project end; hardware needed tied up with an actual customer problem. | 3 | Africa | IT/Solution | 2019 | October | 687346
2239 | Schedule | Delay | Hardware | 18 | 5 | Equipment needed for project came from a pool of hardware partly in another country. Critical hardware delayed by customs. | 2 | Eur/ME | IT/Solution | 2014 | December | 934182
2240 | Schedule | Delay | Hardware | 15 | 4 | Project work that customer is responsible for slips, causing project slip. | 1 | Asia | IT/Solution | 2012 | July | 322050
2241 | Schedule | Delay | Hardware | 20 | 6 | Team relocated with insufficient time to schedule high speed network lines. Rushed, but did not work; team was down until fixed. | 3 | Africa | IT/Solution | 2005 | February | 1235420
2242 | Schedule | Delay | Hardware | 14 | 3 | Required server was misplaced in shipping | 0 | Americas | IT/Solution | 2019 | January | 779954
2243 | Schedule | Delay | Hardware | 22 | 3 | Test systems shared by 6 projects; queuing and delays common. | 3 | Africa | Prod. Dev. | 2006 | February | 1481458
2244 | Schedule | Delay | Hardware | 5 | 5 | New equipment critical to the success of the product quality was installed late | 1 | Asia | Prod. Dev. | 2007 | September | 212210
2245 | Schedule | Delay | Hardware | 13 | 4 | Equipment used for data analysis failed and was down for 2 weeks | 3 | Africa | Prod. Dev. | 2016 | November | 509288
2246 | Schedule | Delay | Hardware | 11 | 3 | Tests delayed at project end; delayed access to databases | 3 | Africa | IT/Solution | 2017 | April | 803561
2247 | Schedule | Delay | Information | 16 | 5 | Delay to reconfigure printer outside firewall | 2 | Eur/ME | IT/Solution | 2016 | August | 382096
2248 | Schedule | Delay | Information | 17 | 5 | Orders sometimes get lost in manual routing | 2 | Eur/ME | IT/Solution | 2005 | July | 783938
2249 | Schedule | Delay | Information | 18 | 5 | Data submitted by the participating vendors contains errors | 1 | Asia | IT/Solution | 2013 | October | 1321632
2250 | Schedule | Delay | Information | 22 | 3 | Document transfer to sites takes more time and effort than expected. | 2 | Eur/ME | Prod. Dev. | 2008 | June | 1196932
2251 | Schedule | Delay | Information | 17 | 7 | "Overnight" shipping takes extra time in big co. mailrooms | 0 | Americas | Prod. Dev. | 2019 | July | 513536
2252 | Schedule | Delay | Information | 9 | 5 | Errors in input data had to be fixed and reports re-generated | 2 | Eur/ME | Prod. Dev. | 2003 | January | 637263
2253 | Schedule | Delay | Information | 11 | 4 | There was a communication lag | 2 | Eur/ME | Prod. Dev. | 2015 | February | 652993
2254 | Schedule | Delay | Information | 14 | 6 | Parts of development team have a 12 hour time difference. Bugs take 2-3 days longer to fix, on average. | 3 | Africa | IT/Solution | 2004 | July | 634396
2255 | Schedule | Delay | Information | 22 | 3 | Defective parts received. Reorder doubled the time required. | 3 | Africa | IT/Solution | 2007 | April | 573782
2256 | Schedule | Delay | Parts | 5 | 6 | Equipment / parts not delivered on time or in full by the outside supplier | 3 | Africa | IT/Solution | 2009 | December | 235365
2257 | Schedule | Delay | Parts | 13 | 6 | Inventory from vendors could not be secured by the desired transport date | 3 | Africa | IT/Solution | 2005 | November | 1006876
2258 | Schedule | Delay | Parts | 6 | 7 | Incorrect part shipped. Delay for reshipment. | 3 | Africa | Prod. Dev. | 2008 | March | 459258
2259 | Schedule | Delay | Parts | 11 | 5 | Needed parts arrive too late. | 1 | Asia | Prod. Dev. | 2004 | November | 701657
2260 | Schedule | Delay | Parts | 14 | 7 | Parts availability and pricing volatile | 0 | Americas | Prod. Dev. | 2019 | September | 335356
2261 | Schedule | Delay | Parts | 5 | 3 | Boards would fail incoming quality check due to the specs given to fabrication house not being tight enough | 0 | Americas | Prod. Dev. | 2019 | July | 184285
2262 | Schedule | Delay | Parts | 21 | 6 | Production problem with key component | 3 | Africa | Prod. Dev. | 2012 | June | 1368969
2263 | Schedule | Delay | Parts | 8 | 5 | Key contractors have the flu | 1 | Asia | Prod. Dev. | 2005 | February | 527792
2264 | Schedule | Delay | Parts | 12 | 5 | Project manager redesigned the prototype and made inventory invalid | 2 | Eur/ME | Prod. Dev. | 2006 | July | 653160
2265 | Schedule | Delay | Parts | 21 | 6 | International shipment of tape was on time, but the tape was bad. | 0 | Americas | IT/Solution | 2019 | April | 591192
2266 | Schedule | Delay | Parts | 15 | 3 | Delivery problems on international shipment--paperwork, customs. | 1 | Asia | Prod. Dev. | 2006 | February | 963045
2267 | Schedule | Delay | Parts | 9 | 3 | Component needed in China for prototype not available; had to be shipped from US | 1 | Asia | Prod. Dev. | 2011 | August | 457056
2268 | Schedule | Delay | Parts | 15 | 6 | Lack of spare parts and expertise | 2 | Eur/ME | Prod. Dev. | 2007 | February | 546525
2269 | Schedule | Delay | Parts | 14 | 7 | New pumps sent that lacked instructions and spare parts | 3 | Africa | Prod. Dev. | 2016 | February | 649138
2270 | Schedule | Delay | Parts | 8 | 4 | Move out of old location required, but new space is not ready. Interim move to temporary space takes extra time and money. | 1 | Asia | IT/Solution | 2018 | May | 167056
2271 | Schedule | Dependency | Infrastructure | 20 | 3 | Operating system selected (LINUX) has inadequate support for timely solution of conversion and delivery problems. | 1 | Asia | IT/Solution | 2017 | September | 734880
2272 | Schedule | Dependency | Infrastructure | 9 | 4 | Late facility availability | 3 | Africa | Prod. Dev. | 2018 | October | 437022
2273 | Schedule | Dependency | Infrastructure | 5 | 3 | Lack of access to professional translation services | 3 | Africa | Prod. Dev. | 2011 | October | 193115
2274 | Schedule | Dependency | Infrastructure | 22 | 3 | Systems needed for project work failed late in the project, and when work was completed installation delayed further to next possible installation window. | 1 | Asia | IT/Solution | 2014 | May | 588918
2275 | Schedule | Dependency | Infrastructure | 5 | 6 | Telecom line delays | 0 | Americas | IT/Solution | 2019 | August | 260630
2276 | Schedule | Dependency | Infrastructure | 14 | 6 | New requirements that mandated all products that have yet to ship to market to be re-tested | 0 | Americas | IT/Solution | 2019 | February | 540960
2277 | Schedule | Dependency | Legal | 7 | 7 | Shipping requirements changed. Some shipments bounce, others get stuck in customs. | 1 | Asia | Prod. Dev. | 2007 | April | 444850
2278 | Schedule | Dependency | Legal | 13 | 6 | Approvals held up at project completion to wait for delayed support plan. | 2 | Eur/ME | IT/Solution | 2005 | July | 391066
2279 | Schedule | Dependency | Project | 20 | 7 | One team in another country missed deadlines on a complex proposal, creating delay and frustration. | 2 | Eur/ME | IT/Solution | 2004 | October | 1456680
2280 | Schedule | Dependency | Project | 7 | 5 | Lack of coordination between projects causes delays. | 2 | Eur/ME | Prod. Dev. | 2018 | October | 256935
2281 | Schedule | Dependency | Project | 12 | 6 | Clear delegation of work done by project team and by customer never done. Confusion led to delays. | 0 | Americas | IT/Solution | 2019 | February | 290160
2282 | Schedule | Dependency | Project | 6 | 5 | Installation of new systems scheduled by central team, but local people are not ready. | 3 | Africa | IT/Solution | 2007 | January | 415554
2283 | Schedule | Dependency | Project | 6 | 3 | Changes to related systems resulted in wrong/late paychecks | 0 | Americas | IT/Solution | 2019 | December | 325728
2284 | Schedule | Dependency | Project | 6 | 5 | Firewall changes can take 25 days, estimates are capped at 15 | 3 | Africa | IT/Solution | 2001 | January | 225228
2285 | Schedule | Estimates | Deadline | 9 | 3 | Software upgrades take longer each cycle as O/S expands and application list grows. | 0 | Americas | IT/Solution | 2019 | May | 386811
2286 | Schedule | Estimates | Judgment | 15 | 7 | Estimates in proposal too short. Testing takes more time and is highly variable. | 1 | Asia | IT/Solution | 2002 | November | 920865
2287 | Schedule | Estimates | Judgment | 8 | 4 | Work was underestimated by 40% | 0 | Americas | IT/Solution | 2019 | December | 576904
2288 | Schedule | Estimates | Judgment | 6 | 6 | Insufficient time is estimated; the deadline could not be met. | 1 | Asia | Prod. Dev. | 2011 | June | 185466
2289 | Schedule | Estimates | Judgment | 10 | 6 | Issues with testing were severly underestimated | 3 | Africa | Prod. Dev. | 2011 | December | 708590
2290 | Schedule | Estimates | Judgment | 15 | 4 | Insufficient time was scheduled for testing | 2 | Eur/ME | Prod. Dev. | 2012 | December | 756000
2291 | Schedule | Estimates | Judgment | 17 | 7 | Cabling estimates too optimistic. | 3 | Africa | IT/Solution | 2002 | March | 908531
2292 | Schedule | Estimates | Judgment | 21 | 6 | Testing time underestimated. | 3 | Africa | Prod. Dev. | 2018 | December | 746529
2293 | Schedule | Estimates | Judgment | 10 | 7 | Lack of in-house expertise of the source system | 2 | Eur/ME | IT/Solution | 2010 | February | 790260
2294 | Schedule | Estimates | Learning | 6 | 3 | Programmer had a lack of experience in the healthcare industry | 2 | Eur/ME | IT/Solution | 2009 | January | 396390
2295 | Schedule | Estimates | Learning | 16 | 4 | Software could only be delivered to a certified person | 3 | Africa | Prod. Dev. | 2007 | October | 660256
2296 | Schedule | Estimates | Learning | 15 | 5 | Critical technical task was assigned to resource who was a new hire | 2 | Eur/ME | Prod. Dev. | 2003 | June | 885525
2297 | Schedule | Estimates | Learning | 10 | 7 | Customer reorganization led to new staffing and changed requirements | 0 | Americas | IT/Solution | 2019 | January | 221730
2298 | Scope | Change | Creep | 18 | 4 | Project priorities are unclear and secondary, less important work is done delaying required tasks. | 0 | Americas | IT/Solution | 2019 | April | 1268136
2299 | Scope | Change | Creep | 14 | 5 | Project end date moved; unrealistic | 1 | Asia | IT/Solution | 2006 | January | 824908
2300 | Scope | Change | Creep | 11 | 4 | Scope creep and resource inadequacy | 2 | Eur/ME | IT/Solution | 2015 | November | 687742
2301 | Scope | Change | Creep | 18 | 7 | Project benchmarks and requirements were never clearly defined | 2 | Eur/ME | IT/Solution | 2019 | July | 999342
2302 | Scope | Change | Creep | 13 | 4 | Project manager added additional customized reporting (for no additional fee) | 1 | Asia | IT/Solution | 2001 | August | 700141
2303 | Scope | Change | Creep | 16 | 4 | Client changes her mind every step of the way | 1 | Asia | IT/Solution | 2009 | August | 879104
2304 | Scope | Change | Creep | 20 | 7 | Program Manager squeezes in additional functionalities until the very last minute | 0 | Americas | Prod. Dev. | 2019 | January | 826440
2305 | Scope | Change | Creep | 9 | 3 | Scope of product categories was broadened significantly | 0 | Americas | Prod. Dev. | 2019 | November | 484956
2306 | Scope | Change | Creep | 17 | 4 | Senior management decided to change the core switching platform technology | 0 | Americas | Prod. Dev. | 2019 | July | 758897
2307 | Scope | Change | Creep | 12 | 5 | Changes double the work on solution project; no change in funding. | 0 | Americas | IT/Solution | 2019 | December | 856224
2308 | Scope | Change | Creep | 17 | 6 | Excessive scope change in ERP project | 2 | Eur/ME | IT/Solution | 2001 | October | 1226346
2309 | Scope | Change | Creep | 5 | 4 | Translated text was too long | 2 | Eur/ME | IT/Solution | 2012 | June | 227190
2310 | Scope | Change | Creep | 18 | 3 | Late in long project, process rigor falls and changes are managed poorly. | 2 | Eur/ME | Prod. Dev. | 2018 | April | 814734
2311 | Scope | Change | Creep | 10 | 3 | Upgrade to software required. Planning and training caused delays. | 2 | Eur/ME | IT/Solution | 2017 | September | 211290
2312 | Scope | Change | Dependency | 18 | 4 | New software release installed by IT, and inconsistencies with older version caused delay and extra work. | 1 | Asia | IT/Solution | 2006 | January | 383598
2313 | Scope | Change | Dependency | 9 | 5 | Details of requirements were submitted incorrectly | 3 | Africa | Prod. Dev. | 2009 | May | 683739
2314 | Scope | Change | Dependency | 5 | 7 | Patch to software required for project work; extra work required to implement. | 2 | Eur/ME | Prod. Dev. | 2005 | April | 149810
2315 | Scope | Change | Dependency | 15 | 3 | New software installed by IT. It does not work, and causes delay to fix. | 3 | Africa | IT/Solution | 2008 | May | 356460
2316 | Scope | Change | Dependency | 8 | 6 | Operating system release expected slips; project forced to use prior version missing some needed functionality. | 2 | Eur/ME | Prod. Dev. | 2012 | July | 291544
2317 | Scope | Change | Dependency | 22 | 6 | Metrics from many sites required. When collected, additional work required to make consistent. | 1 | Asia | IT/Solution | 2007 | June | 1068672
2318 | Scope | Change | Gap | 19 | 3 | Mismatch in documents and expectations. Adjustments required lots of additional work. | 2 | Eur/ME | IT/Solution | 2002 | February | 950703
2319 | Scope | Change | Gap | 9 | 7 | Scanning of text was estimated before it was known text was bound in volumes | 1 | Asia | IT/Solution | 2003 | July | 298539
2320 | Scope | Change | Gap | 22 | 6 | Scope was poorly defined | 2 | Eur/ME | IT/Solution | 2002 | October | 1142042
2321 | Scope | Change | Gap | 14 | 6 | Online badge printing requirement completely missing from scope definition | 1 | Asia | IT/Solution | 2009 | May | 522550
2322 | Scope | Change | Gap | 18 | 7 | The old production machine fails. The new production machine is pressed into production ahead of schedule; takes longer than planned | 1 | Asia | IT/Solution | 2012 | June | 617814
2323 | Scope | Change | Gap | 17 | 6 | Missing important scope at the beginning of the project | 1 | Asia | IT/Solution | 2019 | April | 925259
2324 | Scope | Change | Gap | 14 | 3 | IT staff failed to understand the user requirements | 0 | Americas | IT/Solution | 2019 | July | 1090278
2325 | Scope | Change | Gap | 9 | 7 | Requirements for compiling and formatting data were not clear | 3 | Africa | IT/Solution | 2011 | April | 525834
2326 | Scope | Change | Gap | 18 | 4 | Scope of the project was underestimated and only detected during analysis | 0 | Americas | IT/Solution | 2019 | May | 951696
2327 | Scope | Change | Gap | 16 | 5 | Scope requirement discovered late in a construction project | 2 | Eur/ME | IT/Solution | 2017 | February | 839840
2328 | Scope | Change | Gap | 22 | 3 | Kitchen remodel required a seismic upgrade | 2 | Eur/ME | IT/Solution | 2018 | December | 947408
2329 | Scope | Change | Gap | 6 | 4 | Database of components had not been updated to current OSHA standards | 0 | Americas | IT/Solution | 2019 | December | 315102
2330 | Scope | Change | Gap | 21 | 5 | IT team did not perform a thorough investigation of the existing infrastructure | 3 | Africa | IT/Solution | 2012 | October | 438459
2331 | Scope | Change | Gap | 16 | 3 | Tests not scheduled for working parts, but mandated for project. Added late. | 1 | Asia | Prod. Dev. | 2005 | February | 878192
2332 | Scope | Change | Gap | 13 | 4 | Proprietary data needed, but owners unwilling to provide. After delay, partial information shared. | 2 | Eur/ME | Prod. Dev. | 2002 | September | 951912
2333 | Scope | Change | Gap | 7 | 6 | Retrofit project discovered hidden damage that had to be fixed | 0 | Americas | Prod. Dev. | 2019 | February | 307951
2334 | Scope | Change | Gap | 22 | 5 | After test, additional requirements surface | 1 | Asia | Prod. Dev. | 2010 | May | 1588620
2335 | Scope | Change | Gap | 16 | 4 | Iadequate analysis prior to iniitating development efforts | 1 | Asia | Prod. Dev. | 2017 | August | 1033440
2336 | Scope | Change | Gap | 22 | 4 | Scope was not discussed with the manufacturer before design was completed | 2 | Eur/ME | Prod. Dev. | 2017 | May | 1027224
2337 | Scope | Change | Gap | 16 | 5 | Technical requirements communicated to developers too late | 1 | Asia | IT/Solution | 2006 | June | 433024
2338 | Scope | Change | Gap | 11 | 6 | System functions well in Germany, but has no German documentation. Delay for translation. | 1 | Asia | IT/Solution | 2015 | January | 282051
2339 | Scope | Change | Gap | 7 | 3 | fittings and assemblies were not up to project standards | 0 | Americas | IT/Solution | 2019 | August | 358442
2340 | Scope | Defect | Hardware | 17 | 5 | Prototype problems excessive; more time to fix than planned. | 3 | Africa | Prod. Dev. | 2008 | September | 443853
2341 | Scope | Defect | Hardware | 13 | 4 | Process reliability was too low and required a new component to work | 3 | Africa | Prod. Dev. | 2003 | April | 915252
2342 | Scope | Defect | Hardware | 9 | 6 | Problem arose that required use of a a novel raw material not in inventory | 2 | Eur/ME | Prod. Dev. | 2001 | November | 476226
2343 | Scope | Defect | Hardware | 10 | 6 | Solution project integrated new, untried technology. Difficulty getting it to work. | 1 | Asia | IT/Solution | 2018 | March | 673950
2344 | Scope | Defect | Hardware | 18 | 4 | Integrating course content that does not comply with LMS specifications | 0 | Americas | IT/Solution | 2019 | March | 1117404
2345 | Scope | Defect | Integration | 10 | 7 | Software modules in system do not work together as planned. | 0 | Americas | Prod. Dev. | 2019 | January | 743890
2346 | Scope | Defect | Integration | 8 | 6 | Following recent upgrade, many bugs were found | 0 | Americas | IT/Solution | 2019 | December | 597576
2347 | Scope | Defect | Integration | 21 | 5 | Excessive bugs detected late; delayed to fix. | 0 | Americas | IT/Solution | 2019 | February | 1035027
2348 | Scope | Defect | Software | 8 | 3 | When testing reveals a performance defect which is due to a conflict between two, or more, of the components significant extra work is required | 1 | Asia | IT/Solution | 2010 | October | 359120
2349 | Scope | Defect | Software | 5 | 5 | Excessive bugs | 1 | Asia | IT/Solution | 2018 | October | 102150
2350 | Scope | Defect | Software | 14 | 4 | New software release causes problems | 0 | Americas | IT/Solution | 2019 | February | 666904
2351 | Scope | Defect | Software | 19 | 6 | Bug could be fixed only by moving to a later version of software | 1 | Asia | IT/Solution | 2002 | April | 1231219
2352 | Scope | Defect | Software | 16 | 6 | Controlled Document rejected by Approvers | 1 | Asia | IT/Solution | 2009 | January | 546368
2353 | Scope | Defect | Software | 17 | 7 | Approvers reject required document | 0 | Americas | Prod. Dev. | 2019 | February | 711688
2354 | Scope | Defect | Software | 19 | 5 | Late quality assurance finds additional translation work is needed | 3 | Africa | Prod. Dev. | 2003 | November | 685634
2355 | Scope | Defect | Software | 7 | 3 | Translations are incomplete | 0 | Americas | IT/Solution | 2006 | January | 321881
2356 | Scope | Defect | Software | 16 | 5 | Quality problems led to late redesign, extra work and plan changes. | 2 | Eur/ME | Prod. Dev. | 2017 | January | 580688
2357 | Scope | Defect | Software | 18 | 6 | Delay in patient recruitment for clinical trials | 2 | Eur/ME | Prod. Dev. | 2004 | July | 1078434
2358 | Schedule | Delay | Decision | 15 | 6 | Engineering would not stop adding “bell and whistles” to GUI | 3 | Africa | Prod. Dev. | 2018 | May | 833340
2359 | Scope | Change | Creep | 12 | 5 | A full bioequivalent (BE) study was unexpectedly needed even though there was only a minor difference | 3 | Africa | IT/Solution | 2005 | February | 813660
2360 | Scope | Change | Dependency | 16 | 5 | Due to poor understanding, a redesign and costing effort was neeed | 2 | Eur/ME | IT/Solution | 2005 | February | 1055808
2361 | Scope | Change | Gap | 10 | 6 | Based on testing, performance was insufficient to gain approval to market | 0 | Americas | Prod. Dev. | 2011 | April | 662970
2362 | Scope | Defect | Hardware | 22 | 5 | Requirements are misunderstood or understood differently by multiple parties | 0 | Americas | Prod. Dev. | 2001 | January | 1273580
2363 | Scope | Change | Gap | 12 | 3 | Sudden exit of the primary developer | 1 | Asia | Prod. Dev. | 2007 | June | 729984
2364 | Resource | People | Loss | 20 | 4 | Change requested and agreed to, but supplier ships late and it does not work. | 2 | Eur/ME | IT/Solution | 2015 | August | 1139040
2365 | Resource | Outsourcing | Late or poor output | 12 | 4 | Lack of head count from a 10% company-wide lay-off. | 1 | Asia | IT/Solution | 2005 | October | 540816
2366 | Resource | People | Loss | 16 | 7 | Neophyte project staff lacked system expertise. | 1 | Asia | IT/Solution | 2017 | May | 1269904
2367 | Schedule | Estimates | Learning | 22 | 6 | New technology to be used failed to meet the needs | 1 | Asia | Prod. Dev. | 2003 | August | 1656732
2368 | Scope | Defect | Software | 16 | 3 | Changes in contracts and scope not managed well | 0 | Americas | Prod. Dev. | 2015 | August | 1000304
2369 | Resource | Outsourcing | Late or poor output | 8 | 6 | High turnover. ( 80%) of developer at off shore development unit left, including project lead | 0 | Americas | IT/Solution | 2017 | November | 375312
2370 | Resource | Outsourcing | Late or poor output | 8 | 6 | Contributor couldn't work due to injury and back pains | 2 | Eur/ME | Prod. Dev. | 2007 | June | 246216
2371 | Resource | People | Temp loss | 17 | 7 | Definition changed late in project. | 3 | Africa | Prod. Dev. | 2017 | April | 392462
2372 | Scope | Change | Creep | 12 | 4 | Management did not plan for a requirements gathering phase | 0 | Americas | Prod. Dev. | 2011 | April | 871068
2373 | Scope | Change | Creep | 13 | 3 | 1000 hour tests required at project end. Failure half-way (or later) requires fix and restart. | 2 | Eur/ME | Prod. Dev. | 2019 | January | 570453
2374 | Scope | Defect | Hardware | 9 | 4 | Project was longer than necessary because one team insisted on doing "half" literally, even though the effort resulting was very lopsided. | 0 | Americas | Prod. Dev. | 2012 | June | 482139
2375 | Scope | Defect | Integration | 10 | 3 | Partner software is incompatible with current applications. | 2 | Eur/ME | IT/Solution | 2018 | February | 674480
2376 | Schedule | Dependency | Project | 18 | 6 | Key person gave notice more than a month before leaving, but nothing was done | 2 | Eur/ME | IT/Solution | 2007 | February | 1138842
2377 | Resource | People | Loss | 14 | 3 | Chip failed and had to be refabricated with changes | 1 | Asia | Prod. Dev. | 2010 | February | 535108
2378 | Schedule | Delay | Parts | 7 | 7 | Unrealistic deadline set; slips unavoidable. | 3 | Africa | IT/Solution | 2012 | May | 476770
2379 | Schedule | Estimates | Deadline | 13 | 6 | Contractual obligations set without adequate knowledge of potential hidden issues | 3 | Africa | IT/Solution | 2006 | June | 427804
2380 | Scope | Change | Gap | 11 | 5 | Server expansion project dependent on delayed tape library decommissioning | 3 | Africa | IT/Solution | 2002 | May | 656766
2381 | Schedule | Dependency | Project | 19 | 5 | 3 week test took 7 due to learning curve and ramp time. | 3 | Africa | Prod. Dev. | 2015 | April | 388284
2382 | Schedule | Estimates | Learning | 5 | 5 | Mid project expansion to include account receivable process | 2 | Eur/ME | IT/Solution | 2015 | September | 375095
2383 | Scope | Change | Creep | 10 | 6 | Construction of subdivision was initiated using old maps | 0 | Americas | IT/Solution | 2009 | November | 400170
2384 | Scope | Change | Gap | 14 | 4 | System with new components fails in final tests. Getting older components difficult. | 0 | Americas | Prod. Dev. | 2015 | March | 296870
2385 | Scope | Defect | Hardware | 13 | 5 | Only one subject matter expert, who was also the PM | 3 | Africa | Prod. Dev. | 2019 | June | 330096
2386 | Resource | People | Queuing | 8 | 7 | Key analyst is scheduled to work on another project | 2 | Eur/ME | IT/Solution | 2001 | October | 211048
2387 | Resource | People | Temp loss | 14 | 3 | Architect who knew how to integrate all components fell sick and was hospitalized | 0 | Americas | IT/Solution | 2008 | April | 621572
2388 | Resource | People | Temp loss | 18 | 4 | One key investigation step failed, and had to be redone | 2 | Eur/ME | Prod. Dev. | 2019 | June | 698076
2389 | Schedule | Delay | Hardware | 18 | 3 | None of the developers had experience with the platform the application needed | 1 | Asia | Prod. Dev. | 2010 | October | 1274544
2390 | Schedule | Estimates | Learning | 16 | 3 | Client made a late change the landscape design, causing overtime, expense and delay | 0 | Americas | IT/Solution | 2014 | April | 581952
2391 | Scope | Change | Creep | 9 | 4 | Didn’t explicitly define the scope, and changed part way through | 3 | Africa | Prod. Dev. | 2014 | October | 369306
2392 | Scope | Change | Creep | 18 | 6 | Late in project, the budget and staff are cut leading to delays, forced overtime, and demotivation. | 0 | Americas | Prod. Dev. | 2019 | March | 666144
2393 | Resource | People | Loss | 18 | 4 | Limits on headcount create work backlog | 1 | Asia | IT/Solution | 2010 | April | 850338
2394 | Resource | People | Queuing | 12 | 3 | Required design review delayed. | 2 | Eur/ME | Prod. Dev. | 2010 | June | 559800
2395 | Schedule | Delay | Decision | 10 | 5 | Lack of spare parts and expertise | 0 | Americas | Prod. Dev. | 2014 | March | 529920
2396 | Schedule | Delay | Parts | 8 | 3 | Approvals held up at project completion to wait for delayed support plan. | 1 | Asia | IT/Solution | 2010 | September | 312864
2397 | Schedule | Dependency | Project | 7 | 5 | Patch to software required for project work; extra work required to implement. | 1 | Asia | Prod. Dev. | 2010 | February | 149450
2398 | Scope | Change | Dependency | 18 | 7 | The old production machine fails. The new production machine is pressed into production ahead of schedule; takes longer than planned | 2 | Eur/ME | IT/Solution | 2018 | December | 394560
2399 | Scope | Change | Gap | 19 | 6 | Scope of the project was underestimated and only detected during analysis | 3 | Africa | IT/Solution | 2017 | January | 692968
2400 | Scope | Change | Gap | 9 | 7 | Outsouced staff lacked the necessary skillset | 3 | Africa | IT/Solution | 2014 | December | 196209
2401 | Resource | Outsourcing | Late or poor output | 13 | 7 | Work at customer site had to be done by union workers; took 6 days to do what project team could do in 1. | 1 | Asia | IT/Solution | 2010 | October | 830232
2402 | Resource | People | Motivation | 7 | 3 | Integration testing is incomplete, causing system failures. | 0 | Americas | IT/Solution | 2012 | May | 406945
2403 | Scope | Defect | Software | 18 | 3 | Part of the project team ran of money three months before the project was scheduled to end | 3 | Africa | Prod. Dev. | 2016 | December | 976410
2404 | Resource | Money | Limitation | 5 | 7 | Development team had insufficient resources assigned to the project | 1 | Asia | Prod. Dev. | 2010 | August | 110765
2405 | Resource | Money | Limitation | 16 | 5 | Unexpectedly high demand requires outlisde help | 0 | Americas | IT/Solution | 2013 | December | 809664
2406 | Resource | Outsourcing | Delayed start | 7 | 3 | Excessive challenge of initiating a project in different time zones | 1 | Asia | IT/Solution | 2010 | February | 444983
2407 | Resource | Outsourcing | Delayed start | 17 | 7 | Key consultant breaks both arms 3 weeks before project end | 3 | Africa | IT/Solution | 2001 | August | 524331
2408 | Resource | Outsourcing | Late or poor output | 16 | 4 | Poor planning for the transition between consultants | 1 | Asia | IT/Solution | 2010 | April | 1000096
2409 | Resource | Outsourcing | Late or poor output | 13 | 3 | Engineering consultant firm laid off a chief structural engineer late in project | 3 | Africa | IT/Solution | 2003 | June | 401856
2410 | Resource | Outsourcing | Late or poor output | 14 | 5 | Growth pushed work to understaffed contract firms | 2 | Eur/ME | IT/Solution | 2002 | January | 323260
2411 | Resource | Outsourcing | Late or poor output | 14 | 6 | Subcontractor late with a critical component | 1 | Asia | IT/Solution | 2010 | June | 722134
2412 | Resource | Outsourcing | Late or poor output | 8 | 3 | Contractor got a bigger project moved most of his team to that | 2 | Eur/ME | IT/Solution | 2012 | August | 502240
2413 | Resource | Outsourcing | Late or poor output | 5 | 5 | Designer doesn’t have skills to finish needed work | 3 | Africa | Prod. Dev. | 2017 | November | 382015
2414 | Resource | Outsourcing | Late or poor output | 22 | 3 | Usual vendor closed its business and had to be replaced | 1 | Asia | Prod. Dev. | 2010 | January | 1332012
2415 | Resource | Outsourcing | Late or poor output | 6 | 7 | Programming object delivered late from India delays integration tests | 2 | Eur/ME | IT/Solution | 2016 | November | 364092
2416 | Resource | Outsourcing | Late or poor output | 6 | 6 | Decision to switch to contract manufacturer near end of project caused delays and cost increases. | 0 | Americas | Prod. Dev. | 2011 | August | 193374
2417 | Resource | Outsourcing | Late or poor output | 8 | 4 | Vendor was inexperienced with relevant equipment | 3 | Africa | Prod. Dev. | 2001 | November | 292592
2418 | Resource | Outsourcing | Late or poor output | 7 | 4 | Subcontractor overbooked; not available when needed | 3 | Africa | IT/Solution | 2018 | May | 268261
2419 | Resource | Outsourcing | Late start | 22 | 4 | Finding instructional designers that know how to use specialized software | 0 | Americas | Prod. Dev. | 2017 | September | 900636
2420 | Resource | People | Late start | 14 | 7 | Critical person went on maternity leave | 3 | Africa | IT/Solution | 2006 | November | 445732
2421 | Resource | People | Loss | 10 | 4 | Key contriobutor quit, and there was insufficient information transfer | 1 | Asia | IT/Solution | 2010 | April | 272820
2422 | Resource | People | Loss | 20 | 3 | The key business user assigned to the ITS project was lost while assisting with a manufacturing problem and was no longer available to the project team | 3 | Africa | Prod. Dev. | 2013 | May | 837800
2423 | Resource | People | Loss | 5 | 6 | Senior technical writer resigns and another takes a leave | 3 | Africa | Prod. Dev. | 2010 | February | 176895
2424 | Resource | People | Loss | 7 | 4 | A senior technical architecte quit | 0 | Americas | Prod. Dev. | 2014 | September | 531895
2425 | Resource | People | Loss | 7 | 6 | The key person responsible for major marketing activities resigned | 2 | Eur/ME | Prod. Dev. | 2012 | May | 404656
2426 | Resource | People | Loss | 17 | 7 | Resources committed to projects reassigned to new projects and not replaced. | 3 | Africa | Prod. Dev. | 2019 | August | 1227009
2427 | Resource | People | Loss | 15 | 4 | Too little management interest and support | 1 | Asia | Prod. Dev. | 2010 | January | 645870
2428 | Resource | People | Motivation | 17 | 3 | People who require training miss classes; more classes required. | 0 | Americas | IT/Solution | 2014 | December | 479077
2429 | Resource | People | Queuing | 11 | 7 | All students did not complete training as scheduled, so the project is completed late | 1 | Asia | IT/Solution | 2010 | March | 846131
2430 | Resource | People | Queuing | 9 | 3 | Two projects depended on one resource for completion and this one had lower priority | 0 | Americas | IT/Solution | 2008 | August | 620397
2431 | Resource | People | Queuing | 17 | 4 | There was only on one experienced consultant who knew the tool | 3 | Africa | IT/Solution | 2008 | January | 1291541
2432 | Resource | People | Queuing | 17 | 3 | Only one subject matter expert, who was also the PM | 0 | Americas | Prod. Dev. | 2018 | January | 1058675
2433 | Resource | People | Queuing | 12 | 6 | "50%" resources are not aligned, resulting in activity delays | 0 | Americas | Prod. Dev. | 2019 | September | 869160
2434 | Resource | People | Queuing | 20 | 6 | Two of the developers were able to work on the project only 60% of their time, not full time | 2 | Eur/ME | Prod. Dev. | 2016 | October | 412740
2435 | Resource | People | Queuing | 7 | 3 | Reduction in work force affects the % commitment of team members | 0 | Americas | Prod. Dev. | 2013 | February | 240534
2436 | Resource | People | Queuing | 10 | 6 | Expert worked on at least 4-5 projects at a time | 2 | Eur/ME | Prod. Dev. | 2005 | April | 285430
2437 | Resource | People | Queuing | 8 | 7 | CMO analyzing output developed a severe backup | 2 | Eur/ME | Prod. Dev. | 2007 | February | 602296
2438 | Resource | People | Queuing | 13 | 3 | During testing phase, resource availability was indaequate due to other priorities | 0 | Americas | Prod. Dev. | 2010 | July | 524030
2439 | Resource | People | Queuing | 16 | 3 | Multiple projects depend on lone expert scientist | 1 | Asia | Prod. Dev. | 2010 | September | 1025792
2440 | Resource | People | Queuing | 5 | 5 | 2 key team members lost for a time because of illness | 0 | Americas | IT/Solution | 2012 | January | 387170
2441 | Resource | People | Temp loss | 15 | 4 | Key analyst is scheduled to work on another project | 0 | Americas | IT/Solution | 2006 | January | 343365
2442 | Resource | People | Temp loss | 6 | 5 | Key IT resources scheduled extensive vacations | 0 | Americas | IT/Solution | 2010 | October | 299700
2443 | Resource | People | Temp loss | 10 | 5 | Study timeline set before staff vacation dates were known | 2 | Eur/ME | IT/Solution | 2001 | August | 373870
2444 | Resource | People | Temp loss | 19 | 7 | Loss of key members of a project team in an already constrained project. | 3 | Africa | Prod. Dev. | 2002 | April | 743698
2445 | Resource | People | Temp loss | 13 | 4 | Architect who knew how to integrate all components fell sick and was hospitalized | 1 | Asia | IT/Solution | 2010 | July | 363753
2446 | Resource | People | Temp loss | 14 | 7 | Earthquake in Taiwan makes part of the project team unavailable for work. | 2 | Eur/ME | Prod. Dev. | 2009 | July | 292880
2447 | Resource | People | Temp loss | 13 | 5 | Only 2 people understood the new system, and neither was available | 2 | Eur/ME | IT/Solution | 2014 | January | 706225
2448 | Resource | People | Temp loss | 12 | 6 | At year-end, engineer in Germenay had to take accrued vacation time | 3 | Africa | Prod. Dev. | 2004 | July | 902484
2449 | Resource | People | Temp loss | 21 | 3 | Senior management approval for software licenses delayed | 3 | Africa | Prod. Dev. | 2016 | October | 1661625
2450 | Schedule | Delay | Decision | 10 | 3 | A component needed for necropsy data analysis failed | 1 | Asia | IT/Solution | 2010 | June | 683170
2451 | Schedule | Delay | Hardware | 6 | 4 | One key investigation step failed, and had to be redone | 2 | Eur/ME | Prod. Dev. | 2016 | September | 178536
2452 | Schedule | Delay | Hardware | 14 | 5 | Needed system delivered to wrong building; lost for weeks. | 1 | Asia | IT/Solution | 2010 | August | 549584
2453 | Schedule | Delay | Hardware | 12 | 7 | Metrics required by process improvement project collected and delivered late. | 0 | Americas | IT/Solution | 2002 | November | 832404
2454 | Schedule | Delay | Information | 13 | 6 | With 12 hour time difference and dependence on E-mail, even simple questions take 2-4 days to resolve. | 3 | Africa | Prod. Dev. | 2002 | January | 756444
2455 | Schedule | Delay | Information | 16 | 6 | Some tasks assigned only by function; no one actually working on them. | 1 | Asia | Prod. Dev. | 2010 | March | 879520
2456 | Schedule | Delay | Information | 11 | 4 | Servers stuck in customs | 1 | Asia | IT/Solution | 2010 | October | 289421
2457 | Schedule | Delay | Parts | 20 | 5 | Had only 1/3 of the units needed on time | 2 | Eur/ME | IT/Solution | 2007 | June | 839940
2458 | Schedule | Delay | Parts | 10 | 3 | Key supplier lost in the middle of a project | 3 | Africa | IT/Solution | 2009 | November | 447150
2459 | Schedule | Delay | Parts | 13 | 4 | Parts unavailable; backordered. | 0 | Americas | Prod. Dev. | 2014 | November | 757354
2460 | Schedule | Delay | Parts | 20 | 3 | ASIC delays | 3 | Africa | Prod. Dev. | 2009 | May | 1581940
2461 | Schedule | Delay | Parts | 16 | 3 | Change to US sourcing created demand and delays | 0 | Americas | Prod. Dev. | 2015 | June | 550592
2462 | Schedule | Delay | Parts | 17 | 3 | Manufacturing problem with key component | 3 | Africa | Prod. Dev. | 2003 | January | 1002201
2463 | Schedule | Delay | Parts | 9 | 3 | Parts shipped by sea from Asia, not air. | 2 | Eur/ME | Prod. Dev. | 2012 | September | 579402
2464 | Schedule | Delay | Parts | 9 | 4 | International shipment of parts supposed to take 6 weeks, actually averages 9. | 0 | Americas | Prod. Dev. | 2009 | October | 257454
2465 | Schedule | Delay | Parts | 13 | 3 | Some parts are damaged in shipping and must be reordered. | 0 | Americas | Prod. Dev. | 2016 | February | 435266
2466 | Schedule | Delay | Parts | 17 | 4 | Samples needed in Spain were late | 3 | Africa | IT/Solution | 2002 | October | 498831
2467 | Schedule | Delay | Parts | 18 | 7 | Needed concrete wasn’t delivered on time | 0 | Americas | IT/Solution | 2019 | November | 1155222
2468 | Schedule | Delay | Parts | 9 | 6 | Component delivery late. Causes ramp delays. | 2 | Eur/ME | Prod. Dev. | 2017 | August | 378477
2469 | Schedule | Delay | Parts | 18 | 5 | Needed wiring not available on time | 1 | Asia | IT/Solution | 2010 | June | 1073844
2470 | Schedule | Dependency | Infrastructure | 5 | 7 | the infrastructure changes needed (network, microwave, etc) were not budgeted for the project | 1 | Asia | IT/Solution | 2010 | February | 306250
2471 | Schedule | Dependency | Infrastructure | 12 | 6 | Space unavailable; needed to implement in old space | 3 | Africa | Prod. Dev. | 2011 | February | 461484
2472 | Schedule | Dependency | Infrastructure | 6 | 7 | Problems due to last minute infrastructure changes | 0 | Americas | Prod. Dev. | 2016 | September | 275256
2473 | Schedule | Dependency | Infrastructure | 15 | 3 | Delay in approval to proceed in France and German | 0 | Americas | Prod. Dev. | 2007 | July | 442110
2474 | Schedule | Dependency | Legal | 12 | 6 | Commitment given, but deliverables were late. | 1 | Asia | IT/Solution | 2010 | December | 957348
2475 | Schedule | Dependency | Project | 16 | 4 | Localization of the web contents delivery is delayed | 3 | Africa | IT/Solution | 2008 | December | 1010368
2476 | Schedule | Dependency | Project | 20 | 7 | ASIC supplier (only source) was fine for low volume, but at lower cost and high volume had quality problems and created delays. | 1 | Asia | Prod. Dev. | 2010 | February | 1125840
2477 | Schedule | Dependency | Project | 20 | 6 | Unrealistic compressed timeline | 2 | Eur/ME | Prod. Dev. | 2001 | April | 982960
2478 | Schedule | Estimates | Deadline | 14 | 4 | Unrealistic deadline set | 1 | Asia | Prod. Dev. | 2010 | September | 897652
2479 | Schedule | Estimates | Deadline | 17 | 7 | Recertification of updated applications took longer than hoped | 3 | Africa | IT/Solution | 2015 | November | 1273232
2480 | Schedule | Estimates | Judgment | 18 | 3 | Components that could have been purchased were developed by team, taking longer than expected. | 2 | Eur/ME | Prod. Dev. | 2008 | July | 1076292
2481 | Schedule | Estimates | Judgment | 12 | 5 | The integration task was not defined and broken down to sufficiently small pieces in the project plan. | 3 | Africa | Prod. Dev. | 2007 | July | 273204
2482 | Schedule | Estimates | Judgment | 19 | 6 | Due to organizational change new person was assigned the work | 3 | Africa | IT/Solution | 2003 | December | 1176689
2483 | Schedule | Estimates | Learning | 19 | 3 | Team was staffed by 3 successive new hires in a six-month period | 3 | Africa | Prod. Dev. | 2005 | June | 1402067
2484 | Schedule | Estimates | Learning | 18 | 7 | None of the developers had experience with the platform the application needed | 2 | Eur/ME | Prod. Dev. | 2015 | August | 1283094
2485 | Schedule | Estimates | Learning | 18 | 7 | Oversea engineering team was inexperienced | 1 | Asia | Prod. Dev. | 2010 | June | 965394
2486 | Schedule | Estimates | Learning | 7 | 5 | Lack of skills with recent university hires | 3 | Africa | IT/Solution | 2016 | July | 461804
2487 | Schedule | Estimates | Learning | 11 | 5 | Client requested "15 minute" change accepted and led to delay and loss on project | 2 | Eur/ME | IT/Solution | 2019 | November | 484561
2488 | Scope | Change | Creep | 18 | 7 | Revision to the story board is required | 1 | Asia | IT/Solution | 2010 | February | 801666
2489 | Scope | Change | Creep | 22 | 4 | Project delayed due to recent/last minute changes to portal interface design | 2 | Eur/ME | IT/Solution | 2013 | June | 1396428
2490 | Scope | Change | Creep | 12 | 6 | Client made a late change the landscape design, causing overtime, expense and delay | 1 | Asia | IT/Solution | 2010 | November | 361236
2491 | Scope | Change | Creep | 12 | 3 | Power configuration change was requested too late in the schedule | 2 | Eur/ME | IT/Solution | 2009 | June | 364908
2492 | Scope | Change | Creep | 20 | 4 | 6 sister organizations with an additional 250 users added to the project late | 1 | Asia | IT/Solution | 2010 | February | 1421680
2493 | Scope | Change | Creep | 22 | 7 | Complex feature added that was not requested by the customer | 2 | Eur/ME | IT/Solution | 2001 | August | 458480
2494 | Scope | Change | Creep | 19 | 3 | Additional deliverable added late | 3 | Africa | IT/Solution | 2006 | February | 725838
2495 | Scope | Change | Creep | 12 | 3 | Late design changes required manufacturing retooling at the last minute. | 1 | Asia | Prod. Dev. | 2010 | December | 402420
2496 | Scope | Change | Creep | 14 | 4 | Didn’t explicitly define the scope, and changed part way through | 2 | Eur/ME | Prod. Dev. | 2005 | May | 519694
2497 | Scope | Change | Creep | 21 | 5 | Escalated late changes from Sponsor | 0 | Americas | Prod. Dev. | 2019 | August | 1646001
2498 | Scope | Change | Creep | 5 | 3 | Project schedule was revised user interface requirements which increased project scope | 3 | Africa | Prod. Dev. | 2016 | November | 252040
2499 | Scope | Change | Creep | 16 | 5 | Integrating late features meant that the existing architecture had to be modified | 2 | Eur/ME | Prod. Dev. | 2006 | October | 550032
2500 | Scope | Change | Creep | 22 | 7 | No proper change control process resulted in unnecessary new requirements | 1 | Asia | Prod. Dev. | 2010 | June | 1752894
2501 | Scope | Change | Creep | 8 | 6 | "Minor" changes added and accepted late in project. Phase work doubled and delayed project end. | 0 | Americas | IT/Solution | 2011 | June | 602208
2502 | Scope | Change | Creep | 9 | 3 | Customer driven late changes | 3 | Africa | IT/Solution | 2007 | June | 535095
2503 | Scope | Change | Creep | 9 | 7 | Customer requirements continually shift; lots of extra work. | 0 | Americas | IT/Solution | 2004 | December | 470529
2504 | Scope | Change | Creep | 13 | 5 | Server technology chage was necessitated to support application | 2 | Eur/ME | IT/Solution | 2018 | August | 774293
2505 | Scope | Change | Dependency | 21 | 4 | Corporate merger delayed project | 3 | Africa | IT/Solution | 2018 | November | 578340
2506 | Scope | Change | Dependency | 20 | 5 | Lack of testing of older WWW browser versions led to custom coding being written before application could be used. | 1 | Asia | IT/Solution | 2010 | February | 810460
2507 | Scope | Change | Gap | 18 | 4 | Incorrect input data provided | 3 | Africa | IT/Solution | 2010 | February | 721044
2508 | Scope | Change | Gap | 6 | 7 | Failure to collect the details about the interfaces and links to the third party websites | 2 | Eur/ME | IT/Solution | 2003 | October | 129660
2509 | Scope | Change | Gap | 18 | 6 | The database assigned for the client did not have sufficient free space for their growing accounts | 0 | Americas | IT/Solution | 2007 | March | 559728
2510 | Scope | Change | Gap | 19 | 3 | Changes were approved by the business users without proper testing | 1 | Asia | IT/Solution | 2010 | June | 1452930
2511 | Scope | Change | Gap | 17 | 5 | Deliverable requirements were discovered during the execution phase | 0 | Americas | IT/Solution | 2016 | February | 893282
2512 | Scope | Change | Gap | 10 | 6 | One week’s analysis is insufficient to capture needed requirements | 1 | Asia | IT/Solution | 2010 | May | 772170
2513 | Scope | Change | Gap | 12 | 6 | Legacy systems and processes were not well documented | 3 | Africa | IT/Solution | 2009 | June | 305280
2514 | Scope | Change | Gap | 14 | 7 | Requireemnts sent via email were never formally documented | 0 | Americas | IT/Solution | 2003 | June | 456792
2515 | Scope | Change | Gap | 18 | 4 | Sponsor failed to communicate his requirements at the start of the project | 2 | Eur/ME | IT/Solution | 2005 | October | 1248930
2516 | Scope | Change | Gap | 15 | 3 | Not enough timewas spent to identify all the requirements for the process | 3 | Africa | IT/Solution | 2002 | January | 749910
2517 | Scope | Change | Gap | 14 | 4 | Lack of communication between the teams | 3 | Africa | IT/Solution | 2003 | October | 885962
2518 | Scope | Change | Gap | 14 | 7 | Programmer didn’t understand what data was needed or why | 2 | Eur/ME | IT/Solution | 2013 | December | 1113952
2519 | Scope | Change | Gap | 14 | 4 | Specifications incomplete and late. Delayed project start. | 3 | Africa | Prod. Dev. | 2007 | November | 1090264
2520 | Scope | Change | Gap | 9 | 6 | Insufficient initial project scope was defined when the estimate given to the client | 0 | Americas | Prod. Dev. | 2019 | March | 310644
2521 | Scope | Change | Gap | 10 | 6 | In testing, it is discovered that 50K words were left untranslated due to updates and changes | 2 | Eur/ME | Prod. Dev. | 2007 | February | 594750
2522 | Scope | Change | Gap | 5 | 7 | Failure to understand the scope of the project | 1 | Asia | Prod. Dev. | 2010 | January | 327905
2523 | Scope | Change | Gap | 16 | 7 | Resistance of the business stakeholders to reach consensus on the project’s scope | 2 | Eur/ME | Prod. Dev. | 2014 | January | 1172112
2524 | Scope | Change | Gap | 20 | 5 | Lack of research and analysis on a key compoent of the deliverable | 2 | Eur/ME | Prod. Dev. | 2008 | March | 407540
2525 | Scope | Change | Gap | 16 | 6 | Analysis group not involved in planning meetings | 1 | Asia | Prod. Dev. | 2010 | November | 774832
2526 | Scope | Change | Gap | 7 | 3 | Instructions provided to the testing facility were too vague, necessitating re-tests | 0 | Americas | Prod. Dev. | 2002 | October | 509250
2527 | Scope | Change | Gap | 11 | 4 | Scoping was much more complex then originally thought | 2 | Eur/ME | Prod. Dev. | 2003 | December | 384131
2528 | Scope | Change | Gap | 21 | 3 | Lack of data and knowledge for the new product | 1 | Asia | Prod. Dev. | 2010 | June | 1454313
2529 | Scope | Change | Gap | 13 | 7 | The development team in Pakistan misinterpreted a number of req'ts | 3 | Africa | IT/Solution | 2005 | September | 577122
2530 | Scope | Change | Gap | 16 | 6 | Documentation provided in only one of two required languages. Delay for translation. | 2 | Eur/ME | IT/Solution | 2011 | May | 374192
2531 | Scope | Change | Gap | 15 | 6 | Documentation needed in French was entirely overlooked | 2 | Eur/ME | Prod. Dev. | 2014 | January | 515085
2532 | Scope | Change | Gap | 14 | 6 | Network configuration sometimes causes the backups to fail intermittently; troubleshooting is hard. | 3 | Africa | IT/Solution | 2012 | April | 346752
2533 | Scope | Defect | Hardware | 7 | 5 | Components were incorrectly measured | 0 | Americas | IT/Solution | 2015 | November | 479150
2534 | Scope | Defect | Hardware | 14 | 3 | PC board failure requires redesign and fabrication. | 0 | Americas | Prod. Dev. | 2008 | June | 394044
2535 | Scope | Defect | Hardware | 12 | 6 | Poor quality control and record keeping on the field installation side resulted in many openings being installed incorrectly | 3 | Africa | Prod. Dev. | 2019 | May | 359256
2536 | Scope | Defect | Hardware | 22 | 6 | Revisions required after review | 2 | Eur/ME | Prod. Dev. | 2009 | December | 1295954
2537 | Scope | Defect | Hardware | 6 | 5 | There was not enough time to redo the programming to fix the errors identified | 1 | Asia | IT/Solution | 2010 | January | 402108
2538 | Scope | Defect | Software | 18 | 7 | Editing text worsened product quality and necessitated retranslation | 0 | Americas | Prod. Dev. | 2015 | October | 553086
2539 | Scope | Defect | Software | 18 | 3 | Errors found in data and critrical reports | 0 | Americas | Prod. Dev. | 2016 | December | 1307196
2540 | Scope | Defect | Software | 21 | 5 | Legacy system (COBOL) fails during system upgrade project. Extra effort required to fix. | 0 | Americas | IT/Solution | 2006 | January | 1424388
2541 | Scope | Defect | Software | 7 | 7 | Key supplier purchased by other company and reorganized. Forced to find new supplier. | 1 | Asia | Prod. Dev. | 2010 | July | 217413
2542 | Resource | Outsourcing | Late or poor output | 21 | 6 | Scoping for a wiring project increased substantially after awarding the business | 1 | Asia | IT/Solution | 2010 | April | 847560
2543 | Scope | Change | Creep | 8 | 4 | The software had around 20 major defects and 80 problems that prevented us from moving forward | 1 | Asia | IT/Solution | 2010 | March | 529736
2544 | Scope | Defect | Software | 17 | 6 | During unit testing, discovered performance issue with bulk loads | 2 | Eur/ME | IT/Solution | 2009 | December | 927435
2545 | Scope | Defect | Software | 18 | 7 | There was a very large mismatch between stakeholder expectations and given scope | 3 | Africa | IT/Solution | 2014 | July | 1031022
2546 | Scope | Change | Gap | 17 | 7 | Lack of people resources (designers, requirement/business analysts, data modelers and QA/Testing) | 3 | Africa | Prod. Dev. | 2017 | May | 674254
2547 | Resource | People | Loss | 8 | 6 | Market change due to Improvements in technology became an ‘urgent’ requirement | 2 | Eur/ME | IT/Solution | 2018 | December | 286248
2548 | Scope | Change | Dependency | 18 | 6 | Due to a layoff no writer was immediately available, so approval was delayed | 1 | Asia | Prod. Dev. | 2010 | March | 814626
2549 | Resource | Money | Limitation | 8 | 3 | New chips caused the mother board to perform poorly | 1 | Asia | Prod. Dev. | 2010 | May | 369592
2550 | Scope | Defect | Hardware | 5 | 5 | Product owner having unique knowledge left the company | 0 | Americas | Prod. Dev. | 2011 | November | 307420
2551 | Resource | People | Loss | 9 | 6 | Poor communications resulted in never truly understanding customer needs | 0 | Americas | IT/Solution | 2010 | May | 601209
2552 | Scope | Change | Gap | 10 | 5 | High attrition in positions requiring unique technical training | 2 | Eur/ME | IT/Solution | 2010 | March | 311840
2553 | Schedule | Estimates | Learning | 5 | 6 | Data for key tables not available when needed | 2 | Eur/ME | IT/Solution | 2018 | October | 177345
2554 | Schedule | Delay | Information | 18 | 3 | Manufacutring group did not have the capcity to produce a critical new enzyme | 2 | Eur/ME | Prod. Dev. | 2006 | August | 645750
2555 | Schedule | Delay | Parts | 21 | 4 | Functionality for email added late to a document retrieval project | 3 | Africa | IT/Solution | 2019 | December | 1100673
2556 | Scope | Change | Creep | 20 | 5 | Project delayed to work on higher profit margin work | 3 | Africa | IT/Solution | 2004 | February | 1018260
2557 | Schedule | Dependency | Project | 17 | 6 | The contractor half-way through the electrical job had a heart attack | 0 | Americas | Prod. Dev. | 2019 | September | 710481
2558 | Resource | People | Loss | 19 | 6 | Real-life data used did not test every scenario possible, so had to be replaced | 2 | Eur/ME | Prod. Dev. | 2007 | October | 1355137
2559 | Scope | Change | Gap | 16 | 6 | Lack of communication between the customer and all vendors involved | 3 | Africa | IT/Solution | 2001 | October | 1137376
2560 | Scope | Change | Gap | 21 | 7 | Delays due to bidding issues and protests | 1 | Asia | IT/Solution | 2010 | March | 1022763
2561 | Resource | Outsourcing | Delayed start | 17 | 6 | Issues discovered late in testing | 3 | Africa | IT/Solution | 2003 | December | 833459
2562 | Scope | Defect | Software | 6 | 5 | Staff lost to customer Hot Site | 3 | Africa | Prod. Dev. | 2001 | May | 402696
2563 | Resource | People | Temp loss | 10 | 6 | International leased line order delayed (management approval) and then only ran at half the desired . | 3 | Africa | IT/Solution | 2013 | June | 348760
2564 | Schedule | Delay | Decision | 10 | 3 | Other organizations are late with promised work, then deliverables do not work as expected. | 1 | Asia | Prod. Dev. | 2010 | April | 600930
2565 | Schedule | Dependency | Project | 9 | 4 | Schedule set without first doing a project feasibility and capacity analysis | 1 | Asia | IT/Solution | 2010 | July | 309726
2566 | Schedule | Estimates | Deadline | 11 | 7 | A senior technical architecte quit | 3 | Africa | Prod. Dev. | 2006 | August | 756558
2567 | Resource | People | Loss | 22 | 3 | During testing phase, resource availability was indaequate due to other priorities | 0 | Americas | Prod. Dev. | 2017 | June | 1668546
2568 | Resource | People | Queuing | 17 | 7 | A key team member was replaced mid-project | 1 | Asia | IT/Solution | 2010 | September | 910758
2569 | Resource | People | Loss | 11 | 4 | International shipment of tape was on time, but the tape was bad. | 1 | Asia | IT/Solution | 2010 | April | 644611
2570 | Schedule | Delay | Parts | 6 | 4 | Project benchmarks and requirements were never clearly defined | 1 | Asia | IT/Solution | 2010 | September | 299958
2571 | Scope | Change | Creep | 16 | 5 | Details of requirements were submitted incorrectly | 3 | Africa | Prod. Dev. | 2003 | February | 1234240
2572 | Scope | Change | Dependency | 17 | 5 | Underestimated weight of stumps to be removed | 1 | Asia | IT/Solution | 2010 | February | 733941
2573 | Schedule | Estimates | Judgment | 5 | 5 | Additional enhancements requested at the last minute | 0 | Americas | IT/Solution | 2005 | July | 318260
2574 | Scope | Change | Creep | 10 | 4 | Design team failed to collect the details on what was to be displayed to users | 2 | Eur/ME | IT/Solution | 2004 | January | 531680
2575 | Scope | Change | Gap | 11 | 5 | Vibration in transit caused the loosing of the nuts and bolts of antennas, which eventually caused the collapse of the antennas | 0 | Americas | Prod. Dev. | 2017 | September | 816629
2576 | Scope | Defect | Hardware | 18 | 3 | Cable required had been left off the implementation parts list | 3 | Africa | IT/Solution | 2013 | January | 754380
2577 | Scope | Defect | Hardware | 9 | 6 | Engineering overlooked the functional design and did not implement correctly | 0 | Americas | IT/Solution | 2015 | June | 234675
2578 | Scope | Defect | Software | 9 | 3 | Key consultant was let go at a critical time for coat reasons | 3 | Africa | IT/Solution | 2012 | December | 491751
2579 | Resource | Money | Limitation | 10 | 6 | Lack of funds for travel at launch | 1 | Asia | Prod. Dev. | 2010 | July | 377990
2580 | Resource | Money | Limitation | 18 | 3 | Contract negotiations delayed by 20 days | 3 | Africa | IT/Solution | 2019 | February | 1268118
2581 | Resource | Outsourcing | Delayed start | 15 | 5 | Vendor currently has limited capacity and could not hire quickly enough to support this product | 1 | Asia | IT/Solution | 2010 | March | 1068045
2582 | Resource | Outsourcing | Delayed start | 8 | 6 | For cost reasons, Asian supplier chosen. Qualification and paperwork caused delays. | 1 | Asia | Prod. Dev. | 2010 | April | 280136
2583 | Resource | Outsourcing | Delayed start | 16 | 5 | Initial stages were outsourced to a professor who started late and lacked needed information | 0 | Americas | IT/Solution | 2018 | June | 715136
2584 | Resource | Outsourcing | Late or poor output | 12 | 5 | Incompetent subcontractor led to delay and unhappy clients | 3 | Africa | IT/Solution | 2016 | July | 951996
2585 | Resource | Outsourcing | Late or poor output | 12 | 6 | Subcontractor did not build stairs according to the drawings and had to redo them | 2 | Eur/ME | IT/Solution | 2003 | December | 280344
2586 | Resource | Outsourcing | Late or poor output | 14 | 5 | Lack of clear definition of the contractor and Lead Tech roles and responsibilities | 3 | Africa | IT/Solution | 2007 | August | 1031688
2587 | Resource | Outsourcing | Late or poor output | 20 | 5 | Vendor made a promise on something they could not deliver | 2 | Eur/ME | IT/Solution | 2016 | July | 718680
2588 | Resource | Outsourcing | Late or poor output | 15 | 5 | Vendor missed validation due date delaying Clinical Trials | 2 | Eur/ME | Prod. Dev. | 2007 | June | 1045740
2589 | Resource | Outsourcing | Late or poor output | 22 | 5 | Contract lab failed to inform us that they had trouble with a genotyping assay | 3 | Africa | Prod. Dev. | 2008 | June | 1694858
2590 | Resource | Outsourcing | Late or poor output | 11 | 3 | Contractor provided inadequate survey data | 0 | Americas | Prod. Dev. | 2009 | July | 284416
2591 | Resource | Outsourcing | Late or poor output | 20 | 3 | Chinese IT company to guarantee the quality of their work | 1 | Asia | IT/Solution | 2010 | August | 777540
2592 | Resource | Outsourcing | Late or poor output | 15 | 3 | Abnormally high turnover and shortage of capable developers in India | 2 | Eur/ME | Prod. Dev. | 2016 | July | 413055
2593 | Resource | Outsourcing | Late or poor output | 15 | 4 | Delay in hiring more engineers due to cost cutting | 2 | Eur/ME | IT/Solution | 2007 | November | 882420
2594 | Resource | People | Late start | 20 | 5 | "Rolling Sledgehammer" Last project ties up (and exhausts) staff; next project starts late and slow. | 2 | Eur/ME | Prod. Dev. | 2012 | June | 825960
2595 | Resource | People | Late start | 20 | 5 | Key person lost mid-project | 2 | Eur/ME | IT/Solution | 2001 | January | 1373280
2596 | Resource | People | Loss | 16 | 6 | Turnover on staff 100% in year, leading to delays and training. | 0 | Americas | IT/Solution | 2002 | July | 636896
2597 | Resource | People | Loss | 18 | 5 | The project manager was assigned to another big project part way through the project | 1 | Asia | IT/Solution | 2010 | February | 1293138
2598 | Resource | People | Loss | 18 | 4 | Layoffs in the company | 1 | Asia | Prod. Dev. | 2010 | November | 1420038
2599 | Resource | People | Loss | 14 | 4 | Loss of a key person | 3 | Africa | Prod. Dev. | 2018 | April | 954786
2600 | Resource | People | Loss | 11 | 3 | Key resource pulled from a high priority project | 0 | Americas | IT/Solution | 2017 | November | 627022
2601 | Resource | People | Loss | 16 | 6 | Key engineer on project leaves the company | 0 | Americas | IT/Solution | 2017 | January | 1009664
2602 | Resource | People | Loss | 22 | 6 | Project team members reassigned. Not replaced; led to overtime, quality problems, missed deadlines. | 0 | Americas | Prod. Dev. | 2009 | July | 1753796
2603 | Resource | People | Loss | 6 | 6 | Team members reassigned to other, higher priority projects. | 3 | Africa | Prod. Dev. | 2001 | January | 397374
2604 | Resource | People | Loss | 22 | 5 | Only one employee with other commitments had both the Cobol and relational database data conversion experience | 3 | Africa | IT/Solution | 2002 | September | 535194
2605 | Resource | People | Queuing | 17 | 5 | Lack of key SME resource availability when needed | 3 | Africa | IT/Solution | 2006 | August | 1003901
2606 | Resource | People | Queuing | 22 | 6 | Key contributor unavailable when needed. | 2 | Eur/ME | Prod. Dev. | 2016 | August | 1050676
2607 | Resource | People | Queuing | 13 | 6 | The trained resource was tied up in other work | 0 | Americas | Prod. Dev. | 2018 | January | 644488
2608 | Resource | People | Queuing | 9 | 3 | Conflicting priorities. on-going maintenance, and loss of a person led to delay | 3 | Africa | Prod. Dev. | 2008 | June | 551502
2609 | Resource | People | Queuing | 18 | 5 | Lone subject matter expert unavailable when needed during the initial stages | 1 | Asia | Prod. Dev. | 2010 | February | 558072
2610 | Resource | People | Queuing | 18 | 7 | Unexpected shutdown at year end delays work and rescheduling it is difficult. | 1 | Asia | IT/Solution | 2010 | January | 517572
2611 | Resource | People | Temp loss | 21 | 4 | A valuable resource gets pulled off of project to work on a larger, higher profile project | 0 | Americas | IT/Solution | 2010 | April | 919800
2612 | Resource | People | Temp loss | 19 | 5 | Key resource tied to a previous project for two weeks | 0 | Americas | IT/Solution | 2003 | March | 482467
2613 | Resource | People | Temp loss | 22 | 6 | No vacation/time-off estimate planning was done | 2 | Eur/ME | IT/Solution | 2012 | December | 1328690
2614 | Resource | People | Temp loss | 7 | 6 | Change Management Lead took unexpected medical leave | 0 | Americas | IT/Solution | 2011 | January | 532637
2615 | Resource | People | Temp loss | 20 | 6 | Contributor has lengthy, unannounced vacation | 2 | Eur/ME | IT/Solution | 2005 | July | 972820
2616 | Resource | People | Temp loss | 17 | 4 | Staff lost to customer Hot Site | 0 | Americas | Prod. Dev. | 2011 | December | 461278
2617 | Resource | People | Temp loss | 16 | 4 | Multiple projects competing for a limited staff to do the work leads to interruptions and delays | 3 | Africa | Prod. Dev. | 2016 | September | 989648
2618 | Resource | People | Temp loss | 14 | 4 | Key code developer had a family emergency | 3 | Africa | IT/Solution | 2002 | July | 1049818
2619 | Resource | People | Temp loss | 11 | 3 | Staff lost to customer Hot Site | 0 | Americas | Prod. Dev. | 2004 | January | 817740
2620 | Resource | People | Temp loss | 16 | 4 | All stakeholders approve project individually, but at meeting together for final approval, disagreements changed and delayed the project. | 0 | Americas | IT/Solution | 2012 | October | 940656
2621 | Schedule | Delay | Decision | 12 | 6 | Decisions are being delayed without apparent reason | 0 | Americas | Prod. Dev. | 2007 | July | 637644
2622 | Schedule | Delay | Decision | 15 | 6 | International leased line order delayed (management approval) and then only ran at half the desired . | 3 | Africa | IT/Solution | 2008 | May | 779820
2623 | Schedule | Delay | Decision | 6 | 7 | Systems required backordered (6 months). Forced to use competitor's system. | 3 | Africa | IT/Solution | 2012 | August | 172782
2624 | Schedule | Delay | Hardware | 18 | 6 | Multiple phase roll out paused near the end, systems temporarily out of stock. | 1 | Asia | IT/Solution | 2010 | November | 597186
2625 | Schedule | Delay | Hardware | 21 | 4 | New technology not available on time. | 0 | Americas | IT/Solution | 2006 | August | 933660
2626 | Schedule | Delay | Hardware | 7 | 7 | Equipment was unreliable and caused slips | 3 | Africa | IT/Solution | 2015 | July | 457408
2627 | Schedule | Delay | Hardware | 22 | 6 | Key parts would be delivered late | 1 | Asia | IT/Solution | 2010 | January | 1470612
2628 | Schedule | Delay | Hardware | 13 | 6 | Key stakeholders were not identified during requirements gathering | 0 | Americas | IT/Solution | 2014 | June | 481169
2629 | Schedule | Delay | Information | 6 | 5 | The business counterparts were not in agreement with which option to choose and went back and forth on the decision | 1 | Asia | Prod. Dev. | 2010 | November | 214656
2630 | Schedule | Delay | Information | 16 | 7 | Communications problems and misinterpretation of the requirements in India | 0 | Americas | IT/Solution | 2007 | October | 412544
2631 | Schedule | Delay | Information | 19 | 5 | Documents could not be translated promptly | 2 | Eur/ME | IT/Solution | 2010 | January | 800641
2632 | Schedule | Delay | Information | 13 | 3 | A special peripheral used for the project deliverable was discontinued | 2 | Eur/ME | IT/Solution | 2013 | February | 309647
2633 | Schedule | Delay | Parts | 13 | 5 | Solar panels arrived late and were not what was ordered | 3 | Africa | IT/Solution | 2017 | May | 770081
2634 | Schedule | Delay | Parts | 9 | 4 | Supplier was unable to make a sample correctly | 3 | Africa | Prod. Dev. | 2001 | April | 700218
2635 | Schedule | Delay | Parts | 12 | 5 | There was a delay in the delivery of test samples | 3 | Africa | Prod. Dev. | 2002 | October | 866292
2636 | Schedule | Delay | Parts | 19 | 6 | Granite countertops had incorrect measurements | 2 | Eur/ME | Prod. Dev. | 2005 | June | 656146
2637 | Schedule | Delay | Parts | 15 | 7 | Insufficient capacity in the cabling system for needed fiber connection | 3 | Africa | IT/Solution | 2015 | August | 457695
2638 | Schedule | Dependency | Infrastructure | 8 | 6 | Scheduling based on small pilot installation, but full roll out backed up the help desk and project was delayed. | 2 | Eur/ME | IT/Solution | 2008 | November | 330960
2639 | Schedule | Dependency | Infrastructure | 9 | 5 | During required short visits, the network was sometimes down for an indefinite amount of time, requiring a second trip | 1 | Asia | IT/Solution | 2010 | September | 304758
2640 | Schedule | Dependency | Infrastructure | 14 | 5 | Last minute infrastructure changes and conflict with another deployment | 0 | Americas | IT/Solution | 2004 | January | 753564
2641 | Schedule | Dependency | Infrastructure | 21 | 7 | Current processes did not scale as needed by project, requiring redesign | 0 | Americas | Prod. Dev. | 2015 | March | 1083579
2642 | Schedule | Dependency | Infrastructure | 13 | 3 | Infrasturcture changes made mid-project | 3 | Africa | Prod. Dev. | 2014 | April | 600093
2643 | Schedule | Dependency | Infrastructure | 8 | 6 | Compilers and open source libraries needed were not available | 2 | Eur/ME | IT/Solution | 2007 | February | 579336
2644 | Schedule | Dependency | Infrastructure | 18 | 6 | Iidviduals who must to approve work are unavailable | 1 | Asia | IT/Solution | 2010 | June | 922248
2645 | Schedule | Dependency | Legal | 12 | 5 | Other organizations are late with promised work, then deliverables do not work as expected. | 0 | Americas | Prod. Dev. | 2011 | March | 505224
2646 | Schedule | Dependency | Project | 15 | 6 | Customer insists on deadline shorter than plan. Attempted, but not possible. | 2 | Eur/ME | IT/Solution | 2015 | July | 1072530
2647 | Schedule | Estimates | Deadline | 11 | 6 | Schedule set without first doing a project feasibility and capacity analysis | 1 | Asia | IT/Solution | 2010 | November | 289179
2648 | Schedule | Estimates | Deadline | 6 | 3 | Plans for project for new customer based on similar work for existing customer. Relationships, infrastructure, jargon and other differences took 50% more effort. | 3 | Africa | IT/Solution | 2018 | March | 180870
2649 | Schedule | Estimates | Judgment | 10 | 4 | Estimated level of effort for project was way too optimistic | 3 | Africa | IT/Solution | 2007 | May | 399060
2650 | Schedule | Estimates | Judgment | 18 | 7 | Development scheduled in parallel leads to frequent rework. | 2 | Eur/ME | Prod. Dev. | 2002 | October | 648954
2651 | Schedule | Estimates | Judgment | 19 | 5 | Headcount required for document management was grossly underestimated | 2 | Eur/ME | IT/Solution | 2017 | February | 1018172
2652 | Schedule | Estimates | Judgment | 21 | 7 | Unavailability of skilled resources | 0 | Americas | IT/Solution | 2011 | July | 894873
2653 | Schedule | Estimates | Learning | 12 | 6 | The team member lacked the right skills for a development job | 2 | Eur/ME | Prod. Dev. | 2018 | November | 448104
2654 | Schedule | Estimates | Learning | 10 | 5 | 3 week test took 7 due to learning curve and ramp time. | 0 | Americas | Prod. Dev. | 2014 | May | 468150
2655 | Schedule | Estimates | Learning | 13 | 4 | New hires used; time for training. | 0 | Americas | Prod. Dev. | 2014 | November | 640029
2656 | Schedule | Estimates | Learning | 7 | 3 | Field Engineers experience a long learning curve | 2 | Eur/ME | Prod. Dev. | 2003 | January | 466193
2657 | Schedule | Estimates | Learning | 22 | 3 | People who would deliver training seeking perfection; required extra work and was late. | 2 | Eur/ME | IT/Solution | 2015 | July | 681252
2658 | Scope | Change | Creep | 18 | 7 | One patch was almost completely tested when it was decided to fix another bug | 2 | Eur/ME | IT/Solution | 2002 | August | 413226
2659 | Scope | Change | Creep | 13 | 4 | Half way through the project the client changed the scope by adding additional work | 2 | Eur/ME | IT/Solution | 2007 | April | 680810
2660 | Scope | Change | Creep | 12 | 4 | Several applications were changed due to change in project requirements | 0 | Americas | IT/Solution | 2012 | January | 899364
2661 | Scope | Change | Creep | 16 | 3 | Mid project expansion to include account receivable process | 2 | Eur/ME | IT/Solution | 2002 | March | 557200
2662 | Scope | Change | Creep | 10 | 7 | Executives added a new requirement late | 0 | Americas | IT/Solution | 2014 | June | 328730
2663 | Scope | Change | Creep | 16 | 5 | Late change to motorized door led to redesign, parts delay, and conflict with other work | 3 | Africa | IT/Solution | 2001 | January | 619568
2664 | Scope | Change | Creep | 7 | 4 | Requested scope expansion took a month to assess and was ultimately rejected | 2 | Eur/ME | IT/Solution | 2005 | November | 337645
2665 | Scope | Change | Creep | 17 | 5 | Twelve additional design and construction tasks were added late | 2 | Eur/ME | IT/Solution | 2017 | March | 676209
2666 | Scope | Change | Creep | 5 | 7 | Client's insisted on the use of "the latest technology | 2 | Eur/ME | IT/Solution | 2017 | February | 232670
2667 | Scope | Change | Creep | 16 | 4 | Project priorities and criteria are unclear through much of the project, causing lots of unneeded work. | 3 | Africa | Prod. Dev. | 2019 | October | 1044976
2668 | Scope | Change | Creep | 13 | 3 | Changing product definition and poor estimation of effort | 0 | Americas | Prod. Dev. | 2001 | August | 934908
2669 | Scope | Change | Creep | 20 | 3 | Project priorities and criteria are unclear through much of the project, causing lots of unneeded work. | 3 | Africa | IT/Solution | 2004 | December | 921220
2670 | Scope | Change | Creep | 14 | 7 | Database used for system changed in mid project; more resources used and delay. | 2 | Eur/ME | IT/Solution | 2013 | June | 478674
2671 | Scope | Change | Creep | 17 | 5 | Design stability poor, requiring rework and late changes for manufacturing. | 2 | Eur/ME | Prod. Dev. | 2003 | September | 975171
2672 | Scope | Change | Creep | 6 | 7 | Specifications poorly defined until late in the project. | 1 | Asia | Prod. Dev. | 2010 | August | 418464
2673 | Scope | Change | Creep | 19 | 6 | Modifying requirements in the middle of a phase | 2 | Eur/ME | Prod. Dev. | 2008 | June | 1465052
2674 | Scope | Change | Creep | 12 | 6 | Operating system release expected canceled; project forced to use prior version. | 3 | Africa | Prod. Dev. | 2014 | August | 420516
2675 | Scope | Change | Dependency | 5 | 3 | New CPU chip to be used in product assumed same as old, but requires additional heat sink and mechanical design work. | 3 | Africa | Prod. Dev. | 2007 | March | 101545
2676 | Scope | Change | Dependency | 22 | 6 | As product increases, new packaging and unexpected shielding needed. | 0 | Americas | Prod. Dev. | 2011 | December | 1523940
2677 | Scope | Change | Dependency | 5 | 4 | User specifications not defined until late in the project. | 2 | Eur/ME | IT/Solution | 2003 | February | 110515
2678 | Scope | Change | Gap | 16 | 5 | Work done by contractors with too little information; components require rework. | 1 | Asia | IT/Solution | 2010 | August | 871072
2679 | Scope | Change | Gap | 19 | 7 | The programmer hadn’t understood how certain parts of the program date-logic worked and hadn’t asked for any assistance. | 3 | Africa | IT/Solution | 2014 | August | 1066261
2680 | Scope | Change | Gap | 14 | 3 | Original scope missed supply chain issues; could not be used without changes | 0 | Americas | IT/Solution | 2011 | May | 358470
2681 | Scope | Change | Gap | 18 | 7 | Scope change adding new categories and fees | 2 | Eur/ME | IT/Solution | 2006 | April | 680688
2682 | Scope | Change | Gap | 11 | 7 | Enterprise Portal improperly specified | 3 | Africa | IT/Solution | 2013 | February | 879934
2683 | Scope | Change | Gap | 7 | 4 | Major Scope change during the design phase due to the complex processes involved | 2 | Eur/ME | IT/Solution | 2004 | June | 262899
2684 | Scope | Change | Gap | 8 | 4 | Poor project planning and missed end-user requirements | 0 | Americas | IT/Solution | 2008 | April | 584480
2685 | Scope | Change | Gap | 14 | 5 | Project had aggressive timeline and due to rush details were poorly defined | 2 | Eur/ME | IT/Solution | 2002 | December | 917728
2686 | Scope | Change | Gap | 21 | 4 | Inexperience of the leader resulted in overcommitment and little planning | 0 | Americas | IT/Solution | 2006 | November | 1679769
2687 | Scope | Change | Gap | 11 | 5 | Design documentation was signed off by users, but had fatal flaws | 1 | Asia | IT/Solution | 2010 | September | 849002
2688 | Scope | Change | Gap | 12 | 4 | Substrate material was initially specified incorrectly and had to be reordered | 1 | Asia | IT/Solution | 2010 | June | 278820
2689 | Scope | Change | Gap | 14 | 3 | Customer did not describe in detail what exactly was needed | 3 | Africa | IT/Solution | 2005 | November | 420924
2690 | Scope | Change | Gap | 9 | 6 | Construction of subdivision was initiated using old maps | 2 | Eur/ME | IT/Solution | 2002 | October | 302373
2691 | Scope | Change | Gap | 22 | 3 | Requested requirement proved impossible, but was not actually needed | 3 | Africa | Prod. Dev. | 2010 | February | 1619728
2692 | Scope | Change | Gap | 16 | 7 | Multiple team program with some work not clearly delegated. Assigned and added late. | 0 | Americas | Prod. Dev. | 2012 | April | 1233104
2693 | Scope | Change | Gap | 13 | 3 | Scoping set and estimated based on just one set of data from one customer | 0 | Americas | Prod. Dev. | 2002 | August | 906243
2694 | Scope | Change | Gap | 6 | 6 | The business analyst failed to fully understand the scientist’s requirements | 0 | Americas | Prod. Dev. | 2011 | January | 125802
2695 | Scope | Change | Gap | 16 | 4 | Flaw was found in the functional design | 1 | Asia | Prod. Dev. | 2010 | November | 1276640
2696 | Scope | Change | Gap | 9 | 6 | System only partly specified until near the end of the project. | 1 | Asia | IT/Solution | 2010 | November | 255285
2697 | Scope | Change | Gap | 13 | 4 | Poor prework led to assumption that project would be simpler than it was | 2 | Eur/ME | IT/Solution | 2007 | February | 279890
2698 | Scope | Change | Gap | 16 | 5 | Complexity not understood or documented. Required work added. | 1 | Asia | Prod. Dev. | 2010 | June | 492480
2699 | Scope | Change | Gap | 21 | 7 | Product developed for multiple platforms, but works only on 2. Delayed to fix some, but others dropped at project end. | 3 | Africa | Prod. Dev. | 2004 | August | 1391964
2700 | Scope | Change | Gap | 10 | 6 | Faulty market & competitive analysis information discovered late; led to changes | 0 | Americas | Prod. Dev. | 2017 | July | 685690
2701 | Scope | Change | Gap | 13 | 3 | Lack of initial consensus on the scope | 1 | Asia | Prod. Dev. | 2010 | July | 523614
2702 | Scope | Change | Gap | 7 | 3 | New technology used, seeking faster results. It does not work and leads to redesign and rework. | 2 | Eur/ME | IT/Solution | 2004 | June | 315798
2703 | Scope | Defect | Hardware | 17 | 4 | Instrument system for customer based on Intel PC. New system released; fails to work as older model did. Finally installed with salvaged older PC. | 1 | Asia | IT/Solution | 2010 | May | 722704
2704 | Scope | Defect | Hardware | 22 | 7 | Testing facilities were too low-tech to verify automated systems | 2 | Eur/ME | IT/Solution | 2016 | December | 1067198
2705 | Scope | Defect | Hardware | 11 | 4 | Components do not work as documented. Replacements and software workarounds required. | 3 | Africa | Prod. Dev. | 2006 | April | 815859
2706 | Scope | Defect | Hardware | 14 | 4 | System with new components fails in final tests. Getting older components difficult. | 0 | Americas | Prod. Dev. | 2011 | October | 450338
2707 | Scope | Defect | Hardware | 12 | 3 | Late test results came back negative | 3 | Africa | Prod. Dev. | 2001 | March | 327324
2708 | Scope | Defect | Hardware | 19 | 6 | Insufficient length of anchor bolts protruding from the concrete foundation to allow the base plate nuts to fully engage | 1 | Asia | Prod. Dev. | 2010 | January | 416822
2709 | Scope | Defect | Hardware | 18 | 4 | During the feedback/review phase it was noticed that the numbers were incorrect | 1 | Asia | Prod. Dev. | 2010 | August | 660780
2710 | Scope | Defect | Hardware | 8 | 6 | After the first run was lost, a third run was added | 2 | Eur/ME | Prod. Dev. | 2003 | November | 578456
2711 | Scope | Defect | Hardware | 16 | 6 | First production run problems necessitated adding a third run | 3 | Africa | Prod. Dev. | 2010 | April | 417136
2712 | Scope | Defect | Hardware | 21 | 7 | Deliverable fails final test; rework to fix. | 1 | Asia | Prod. Dev. | 2010 | October | 1068459
2713 | Scope | Defect | Hardware | 11 | 6 | All components pass tests, but assembled system fails. Rework causes delay. | 1 | Asia | Prod. Dev. | 2010 | May | 732985
2714 | Scope | Defect | Integration | 10 | 5 | Failure to not carefully proofread the documents to be produced before printing | 1 | Asia | Prod. Dev. | 2010 | March | 748780
2715 | Scope | Defect | Integration | 9 | 5 | Process does not scale to production; changes required. | 2 | Eur/ME | Prod. Dev. | 2007 | July | 573309
2716 | Scope | Defect | Integration | 9 | 7 | Problem detected in production due to transaction volume not detected in test | 2 | Eur/ME | IT/Solution | 2008 | May | 412956
2717 | Scope | Defect | Software | 7 | 6 | Bug surfaced one day after implementation | 2 | Eur/ME | IT/Solution | 2018 | December | 230146
2718 | Scope | Defect | Software | 5 | 7 | Purchased software is limited and inflexible. Workarounds and additional software required. | 0 | Americas | IT/Solution | 2010 | October | 119605
2719 | Scope | Defect | Software | 8 | 7 | Late testing failure | 1 | Asia | IT/Solution | 2010 | August | 356600
2720 | Scope | Defect | Software | 13 | 4 | Vendor was unable to control the environment: work had to be repeated | 2 | Eur/ME | Prod. Dev. | 2008 | April | 1000415
2721 | Resource | Outsourcing | Late or poor output | 8 | 3 | Complexity of the investigation was badly underestimated | 2 | Eur/ME | Prod. Dev. | 2012 | July | 617704
2722 | Schedule | Estimates | Judgment | 11 | 5 | Inexperienced staff | 3 | Africa | Prod. Dev. | 2014 | August | 804793
2723 | Schedule | Estimates | Learning | 21 | 5 | The team in Germany did not have the resources or expertise to do testing in key intermediate step | 1 | Asia | Prod. Dev. | 2010 | July | 849051
2724 | Schedule | Estimates | Learning | 22 | 3 | Support offering requires more overhead to span several OS versions | 3 | Africa | Prod. Dev. | 2012 | March | 602646
2725 | Schedule | Dependency | Infrastructure | 20 | 6 | Testing requierments poorly defined, so functionality deferred to phase 2 | 3 | Africa | IT/Solution | 2009 | December | 1122520
2726 | Scope | Change | Gap | 19 | 7 | Contaminated specimen for cell culture had to be replaced by the contract organization | 0 | Americas | Prod. Dev. | 2006 | August | 1065140
2727 | Resource | Outsourcing | Late or poor output | 18 | 4 | Subcontractor failed to understand technology and requirements | 3 | Africa | IT/Solution | 2007 | September | 752868
2728 | Resource | Outsourcing | Late or poor output | 9 | 7 | Late change required new hardware and 2 phase delivery | 1 | Asia | Prod. Dev. | 2010 | May | 265284
2729 | Scope | Change | Creep | 11 | 5 | Defective component--Bugs had to be fixed | 2 | Eur/ME | Prod. Dev. | 2005 | July | 330825
2730 | Scope | Defect | Hardware | 6 | 4 | Project lost irreplaceable experts | 1 | Asia | IT/Solution | 2010 | October | 372906
2731 | Resource | People | Loss | 19 | 6 | Too few disc drives, and insufficient "owned" space | 3 | Africa | Prod. Dev. | 2002 | February | 1462582
2732 | Schedule | Dependency | Infrastructure | 20 | 4 | There was a high fluctuation of pressure that nobody could explain | 3 | Africa | Prod. Dev. | 2004 | May | 1094860
2733 | Schedule | Delay | Hardware | 6 | 6 | Contractors late and unreliable | 1 | Asia | Prod. Dev. | 2010 | August | 357594
2734 | Resource | Outsourcing | Delayed start | 12 | 6 | Needed plants were set too far apart to fertilize initially | 0 | Americas | Prod. Dev. | 2016 | May | 871536
2735 | Scope | Defect | Hardware | 5 | 5 | Workforce reduction left only 3 developers were remaining on the project | 1 | Asia | Prod. Dev. | 2010 | May | 141925
2736 | Resource | People | Loss | 18 | 7 | Materials did not pass quality inspection | 3 | Africa | Prod. Dev. | 2010 | August | 1063134
2737 | Schedule | Delay | Parts | 17 | 7 | Developer had limited experience | 0 | Americas | Prod. Dev. | 2006 | September | 1020289
2738 | Schedule | Estimates | Learning | 8 | 6 | Late requirement changes and shifting priorities | 0 | Americas | Prod. Dev. | 2004 | September | 163888
2739 | Scope | Change | Creep | 20 | 4 | New Requirement addition during the middle of the project | 3 | Africa | Prod. Dev. | 2016 | March | 1534920
2740 | Scope | Change | Creep | 14 | 6 | Contract lab failed to inform us that they had trouble with a genotyping assay | 2 | Eur/ME | Prod. Dev. | 2003 | April | 823032
2741 | Resource | Outsourcing | Late or poor output | 21 | 7 | Chinese IT company to guarantee the quality of their work | 2 | Eur/ME | IT/Solution | 2004 | December | 645729
2742 | Resource | Outsourcing | Late or poor output | 20 | 3 | "Rolling Sledgehammer" Last project ties up (and exhausts) staff; next project starts late and slow. | 1 | Asia | Prod. Dev. | 2010 | September | 1134960
2743 | Resource | People | Late start | 6 | 6 | All stakeholders approve project individually, but at meeting together for final approval, disagreements changed and delayed the project. | 2 | Eur/ME | IT/Solution | 2007 | February | 152064
2744 | Schedule | Delay | Decision | 19 | 3 | Communications problems and misinterpretation of the requirements in India | 3 | Africa | IT/Solution | 2019 | December | 997880
2745 | Schedule | Delay | Information | 5 | 3 | Supplier was unable to make a sample correctly | 1 | Asia | Prod. Dev. | 2010 | August | 113725
2746 | Schedule | Delay | Parts | 11 | 7 | Estimated level of effort for project was way too optimistic | 1 | Asia | IT/Solution | 2010 | October | 655600
2747 | Schedule | Estimates | Judgment | 8 | 4 | Late change to motorized door led to redesign, parts delay, and conflict with other work | 1 | Asia | IT/Solution | 2010 | March | 574120
2748 | Scope | Change | Creep | 15 | 4 | New CPU chip to be used in product assumed same as old, but requires additional heat sink and mechanical design work. | 1 | Asia | Prod. Dev. | 2010 | October | 1188105
2749 | Scope | Change | Dependency | 16 | 3 | Late test results came back negative | 3 | Africa | Prod. Dev. | 2004 | August | 390224
2750 | Scope | Defect | Hardware | 16 | 7 | Problem detected in production due to transaction volume not detected in test | 3 | Africa | IT/Solution | 2001 | July | 1155456
2751 | Scope | Defect | Software | 10 | 5 | Resources committed to projects reassigned to new projects and not replaced. | 1 | Asia | Prod. Dev. | 2010 | May | 371010
2752 | Resource | People | Loss | 21 | 6 | Manufacturing problem with key component | 1 | Asia | Prod. Dev. | 2010 | September | 585501
2753 | Schedule | Delay | Parts | 7 | 7 | Lack of research and analysis on a key compoent of the deliverable | 1 | Asia | Prod. Dev. | 2010 | December | 246407
2754 | Scope | Change | Gap | 6 | 4 | Components were incorrectly measured | 2 | Eur/ME | IT/Solution | 2015 | March | 222054
2755 | Scope | Defect | Hardware | 6 | 3 | A single person was responsible for key reports many wait in queue | 1 | Asia | IT/Solution | 2010 | May | 477252
2756 | Resource | People | Queuing | 11 | 3 | Key resource was pulled off the project twice to fix bugs in a previous product | 0 | Americas | Prod. Dev. | 2007 | July | 300102
2757 | Resource | People | Temp loss | 8 | 5 | Estimates in proposal too short. Testing takes more time and is highly variable. | 3 | Africa | IT/Solution | 2018 | November | 376192
2758 | Schedule | Estimates | Judgment | 15 | 7 | Project end date moved; unrealistic | 1 | Asia | IT/Solution | 2010 | April | 445860
2759 | Scope | Change | Creep | 20 | 4 | People were allocated to too many projects and bottlenecks developed | 0 | Americas | IT/Solution | 2009 | November | 573120
2760 | Resource | People | Queuing | 11 | 5 | Key person not available when needed. | 3 | Africa | Prod. Dev. | 2018 | May | 424468
2761 | Resource | People | Queuing | 16 | 7 | Unannounced audit in mid-project caused delay to prepare and participate. | 3 | Africa | Prod. Dev. | 2004 | November | 1248976
2762 | Resource | People | Temp loss | 10 | 4 | Flood shuts down data center. Delay to restore power and clean up. | 2 | Eur/ME | IT/Solution | 2001 | September | 310300
2763 | Schedule | Delay | Hardware | 14 | 5 | Parts delivery delay | 3 | Africa | Prod. Dev. | 2017 | May | 1109094
2764 | Schedule | Delay | Parts | 5 | 5 | Lack of a solid plan, or any formal scoping | 3 | Africa | Prod. Dev. | 2015 | November | 242590
2765 | Scope | Change | Gap | 17 | 7 | No problems in test, but production problems required overtime to fix | 2 | Eur/ME | IT/Solution | 2011 | May | 949093
2766 | Scope | Defect | Software | 18 | 5 | Layoffs in mid-project | 3 | Africa | IT/Solution | 2015 | April | 1374264
2767 | Resource | Money | Limitation | 16 | 7 | Client slashed the original budget | 3 | Africa | IT/Solution | 2012 | January | 1155696
2768 | Resource | Money | Limitation | 18 | 5 | Inadequate staffing | 2 | Eur/ME | Prod. Dev. | 2007 | May | 481392
2769 | Resource | Money | Limitation | 20 | 4 | Delays due to bidding issues and protests | 0 | Americas | IT/Solution | 2010 | August | 822300
2770 | Resource | Outsourcing | Delayed start | 19 | 5 | Vendor failed to confirm start date, resulting in delay | 1 | Asia | Prod. Dev. | 2010 | September | 804460
2771 | Resource | Outsourcing | Delayed start | 6 | 4 | Failed to get client sign-off for work done in India | 2 | Eur/ME | IT/Solution | 2014 | December | 426216
2772 | Resource | Outsourcing | Delayed start | 7 | 4 | Consultant who worked on benefits was taken off the project | 2 | Eur/ME | IT/Solution | 2014 | July | 348068
2773 | Resource | Outsourcing | Late or poor output | 12 | 6 | Freelancer hired was a nutjob, and lacked the correct skills | 1 | Asia | IT/Solution | 2010 | December | 501768
2774 | Resource | Outsourcing | Late or poor output | 15 | 5 | Management pushed plans to outsource printing operations, causing problems | 1 | Asia | IT/Solution | 2010 | October | 1053105
2775 | Resource | Outsourcing | Late or poor output | 17 | 5 | Contractor was uncooperative and late | 2 | Eur/ME | IT/Solution | 2002 | January | 485367
2776 | Resource | Outsourcing | Late or poor output | 18 | 4 | Consulting agency had not fulfilled its obligations under the terms of the contract | 1 | Asia | IT/Solution | 2010 | December | 944802
2777 | Resource | Outsourcing | Late or poor output | 9 | 3 | Outsourcing delayed the order entry process for all U.S. Based customers | 0 | Americas | IT/Solution | 2003 | April | 291033
2778 | Resource | Outsourcing | Late or poor output | 15 | 4 | Legacy systems not retired as planned; project team tied up in unplanned support. | 1 | Asia | IT/Solution | 2010 | March | 810300
2779 | Resource | People | Late start | 6 | 6 | Delay in getting a firewall PM and a firewall engineer assigned | 0 | Americas | IT/Solution | 2016 | December | 456756
2780 | Resource | People | Late start | 16 | 5 | Resources were not available at the time the project started | 0 | Americas | IT/Solution | 2015 | May | 1080032
2781 | Resource | People | Late start | 13 | 3 | Project has funding, but limited staff delays start. | 0 | Americas | Prod. Dev. | 2003 | March | 652119
2782 | Resource | People | Late start | 19 | 7 | Critical skills unique in the head of a 62-yearl old programmer who had a heart attack | 1 | Asia | IT/Solution | 2010 | February | 523070
2783 | Resource | People | Loss | 10 | 3 | Lost a key programmer | 3 | Africa | IT/Solution | 2013 | May | 247520
2784 | Resource | People | Loss | 22 | 5 | Workforce reduction left only 3 developers were remaining on the project | 3 | Africa | Prod. Dev. | 2006 | October | 907632
2785 | Resource | People | Loss | 12 | 7 | Key contributor left the company | 0 | Americas | Prod. Dev. | 2018 | March | 636720
2786 | Resource | People | Loss | 8 | 4 | Technical lead had a “command and control" style that caused animosity | 1 | Asia | IT/Solution | 2010 | July | 500016
2787 | Resource | People | Motivation | 18 | 7 | Parallel tasks require resources beyond what is available | 2 | Eur/ME | IT/Solution | 2002 | March | 624348
2788 | Resource | People | Queuing | 10 | 3 | There were not enough study directors to conduct all the studies needed | 2 | Eur/ME | Prod. Dev. | 2010 | August | 303140
2789 | Resource | People | Queuing | 20 | 4 | Six other projects required time and effort from our assigned engineer | 3 | Africa | Prod. Dev. | 2005 | September | 639460
2790 | Resource | People | Queuing | 11 | 6 | Project was dependent on onekey resource and had to wait | 2 | Eur/ME | Prod. Dev. | 2008 | January | 807466
2791 | Resource | People | Queuing | 8 | 3 | Critical training had to be postponed because of a last minute emergency leave by the lead designer | 3 | Africa | Prod. Dev. | 2019 | January | 621120
2792 | Resource | People | Temp loss | 12 | 4 | Feedback from South Korea delayed due to a few months of sick leave by product manager | 1 | Asia | Prod. Dev. | 2010 | July | 830472
2793 | Resource | People | Temp loss | 18 | 5 | There were not enough vendors who had the capacity to manufacture specialized tools | 0 | Americas | IT/Solution | 2005 | January | 1338174
2794 | Schedule | Delay | Hardware | 21 | 5 | The Project Lead did not hold the customer/business line accountable for their delay | 3 | Africa | Prod. Dev. | 2016 | January | 451374
2795 | Schedule | Delay | Information | 16 | 6 | Internal supplier problem; needed components delayed. | 0 | Americas | Prod. Dev. | 2018 | May | 591600
2796 | Schedule | Delay | Parts | 6 | 5 | Materials did not pass quality inspection | 1 | Asia | Prod. Dev. | 2010 | January | 252810
2797 | Schedule | Delay | Parts | 14 | 4 | New technology was analyzed and didn’t meet the needs | 0 | Americas | Prod. Dev. | 2011 | October | 922390
2798 | Schedule | Delay | Parts | 14 | 3 | Foundation was inadaquate and needed upgrading | 0 | Americas | IT/Solution | 2003 | March | 859236
2799 | Schedule | Dependency | Infrastructure | 17 | 5 | Issues found with the SOX documents provided by the legal team | 2 | Eur/ME | IT/Solution | 2007 | May | 474878
2800 | Schedule | Dependency | Legal | 10 | 7 | Reviews delayed on complex program, waiting for last team to finish phase work. | 0 | Americas | Prod. Dev. | 2004 | March | 551430
2801 | Schedule | Dependency | Project | 19 | 7 | Server expansion project dependent on delayed tape library decommissioning | 0 | Americas | IT/Solution | 2012 | May | 454632
2802 | Schedule | Dependency | Project | 20 | 7 | Work was intentionally underestimatged to win the contract | 1 | Asia | IT/Solution | 2010 | July | 638340
2803 | Schedule | Estimates | Deadline | 16 | 5 | Chronic optimism on completion dates for work | 2 | Eur/ME | Prod. Dev. | 2015 | August | 1266672
2804 | Schedule | Estimates | Judgment | 8 | 7 | Key staff member lacked knowledge, experience and ability | 1 | Asia | IT/Solution | 2010 | May | 263032
2805 | Schedule | Estimates | Learning | 8 | 3 | Software engineers, not technicians skilled in the work, were used to complete product testing | 1 | Asia | Prod. Dev. | 2010 | December | 232656
2806 | Schedule | Estimates | Learning | 19 | 6 | Developer had limited experience | 1 | Asia | Prod. Dev. | 2010 | March | 1473792
2807 | Schedule | Estimates | Learning | 18 | 7 | Big scope change in the middle of the project | 0 | Americas | Prod. Dev. | 2005 | April | 1276020
2808 | Scope | Change | Creep | 16 | 4 | Late requirement changes and shifting priorities | 1 | Asia | Prod. Dev. | 2010 | June | 1017456
2809 | Scope | Change | Creep | 11 | 4 | New Requirement addition during the middle of the project | 0 | Americas | Prod. Dev. | 2003 | March | 300366
2810 | Scope | Change | Creep | 14 | 3 | Extra release added just a month before a major upgrade go live date | 1 | Asia | Prod. Dev. | 2010 | December | 876834
2811 | Scope | Change | Creep | 12 | 6 | Two new Features were introduced midway during development | 1 | Asia | Prod. Dev. | 2010 | February | 558408
2812 | Scope | Change | Creep | 5 | 5 | Problems associated with confidential patient information in transit without a tracking mechanism surfaced during the project | 2 | Eur/ME | IT/Solution | 2010 | December | 167695
2813 | Scope | Change | Gap | 6 | 6 | Late change required to meet code | 1 | Asia | IT/Solution | 2010 | April | 448470
2814 | Scope | Change | Gap | 18 | 3 | Project required a change to the current website technology | 3 | Africa | IT/Solution | 2014 | March | 780534
2815 | Scope | Change | Gap | 8 | 6 | Responsibilities not defined well for project | 3 | Africa | Prod. Dev. | 2014 | May | 488376
2816 | Scope | Change | Gap | 12 | 5 | Lack of understanding by the manager of the system forced the project to replan | 3 | Africa | Prod. Dev. | 2016 | December | 951672
2817 | Scope | Change | Gap | 15 | 3 | A critical issue was neglected resulting in a significant scope gap | 1 | Asia | Prod. Dev. | 2010 | November | 872535
2818 | Scope | Change | Gap | 22 | 7 | Scope gaps became apparent when legal department was consulted too late | 0 | Americas | Prod. Dev. | 2011 | March | 938388
2819 | Scope | Change | Gap | 14 | 5 | Instructions to contract testing facility were too vague and tests had to be repeated | 0 | Americas | Prod. Dev. | 2002 | September | 361704
2820 | Scope | Change | Gap | 14 | 7 | Flaw found in functional design specifications | 3 | Africa | Prod. Dev. | 2008 | June | 933660
2821 | Scope | Change | Gap | 21 | 6 | Some of the cross functional teams were not involved early enough | 1 | Asia | Prod. Dev. | 2010 | October | 1261029
2822 | Scope | Change | Gap | 22 | 3 | Functional design was not properly done, due to limited access to users; led to changes | 0 | Americas | Prod. Dev. | 2004 | August | 953458
2823 | Scope | Change | Gap | 17 | 6 | Development team in France was unable to convey their requests, issues and concerns | 1 | Asia | IT/Solution | 2010 | March | 405161
2824 | Scope | Change | Gap | 10 | 5 | Half way through the upgrade; the new processor failed | 2 | Eur/ME | IT/Solution | 2004 | August | 508440
2825 | Scope | Defect | Hardware | 15 | 6 | In large system conversion, new applications cannot find and work with existing data as expected. Lots of redirecting and conversion is required. | 1 | Asia | IT/Solution | 2010 | June | 307380
2826 | Scope | Defect | Integration | 7 | 3 | Memory problems not detected in test caused server crashes; backed out for more than a month | 3 | Africa | IT/Solution | 2018 | April | 211463
2827 | Scope | Defect | Software | 13 | 4 | Issues discovered late in testing | 2 | Eur/ME | IT/Solution | 2013 | November | 322361
2828 | Scope | Defect | Software | 9 | 3 | Errors were discovered in reports that had to be fixed following release | 3 | Africa | IT/Solution | 2015 | May | 535779
2829 | Scope | Defect | Software | 18 | 7 | Software is developed in Israel. In a week, there was less than one working day for teleconference and war made it impractical to travel. Needed info was always late. | 2 | Eur/ME | IT/Solution | 2004 | July | 829098
2830 | Schedule | Delay | Information | 19 | 3 | Scope definition was poor and change was rampant | 1 | Asia | IT/Solution | 2010 | May | 728897
2831 | Scope | Change | Creep | 16 | 4 | Research and development were outsourced, but the relationship was not managed well, and all work was ultimately redone | 0 | Americas | Prod. Dev. | 2003 | May | 673040
2832 | Resource | Outsourcing | Late or poor output | 16 | 3 | System for expense analysis expanded into redesign of most major internal systems | 0 | Americas | Prod. Dev. | 2015 | November | 1226352
2833 | Scope | Change | Creep | 20 | 6 | Deliverable received was inadequate | 2 | Eur/ME | IT/Solution | 2019 | July | 601840
2834 | Resource | Outsourcing | Late or poor output | 10 | 6 | There was a design flaw in the roof detail | 0 | Americas | IT/Solution | 2013 | May | 776470
2835 | Scope | Change | Gap | 8 | 7 | Apartments were sold before construction begins with commitments based on requests, not planning | 1 | Asia | IT/Solution | 2010 | August | 480688
2836 | Schedule | Estimates | Deadline | 12 | 3 | Project specifications had changed and the material needed during the design phase had to be imported from overseas | 2 | Eur/ME | Prod. Dev. | 2008 | April | 934380
2837 | Scope | Change | Creep | 8 | 3 | Scope initially consisted only of general objectives | 0 | Americas | IT/Solution | 2008 | February | 310000
2838 | Scope | Change | Gap | 10 | 7 | Manager quit his job because of his mother's illness | 0 | Americas | IT/Solution | 2015 | August | 714670
2839 | Resource | People | Loss | 18 | 5 | Delay due to testing requirements uncovered late and shifting priorities | 2 | Eur/ME | IT/Solution | 2012 | April | 778464
2840 | Scope | Change | Gap | 12 | 7 | Project was new to the company and needed to hire people and develop a team | 0 | Americas | Prod. Dev. | 2009 | July | 820956
2841 | Resource | People | Late start | 18 | 6 | Initial scoping for a minor upgrade was not sufficient | 2 | Eur/ME | Prod. Dev. | 2017 | May | 764658
2842 | Scope | Change | Creep | 19 | 7 | Migration project (to NT from UNIX) saddled with increasing list of changes. | 3 | Africa | IT/Solution | 2005 | June | 816525
2843 | Scope | Change | Creep | 19 | 7 | After the upgrade was released, issues with the software were discovered | 3 | Africa | IT/Solution | 2003 | January | 771286
2844 | Scope | Defect | Software | 11 | 3 | Additional scope added; slipped project | 0 | Americas | IT/Solution | 2014 | April | 580074
2845 | Scope | Change | Creep | 13 | 7 | Product manager was out due to sick leave (a few months long) | 2 | Eur/ME | Prod. Dev. | 2011 | July | 876980
2846 | Resource | People | Temp loss | 6 | 3 | Technical lead had a “command and control" style that caused animosity | 2 | Eur/ME | IT/Solution | 2014 | May | 416304
2847 | Resource | People | Motivation | 21 | 5 | Critical training had to be postponed because of a last minute emergency leave by the lead designer | 1 | Asia | Prod. Dev. | 2010 | January | 1600725
2848 | Resource | People | Loss | 15 | 5 | Extra release added just a month before a major upgrade go live date | 1 | Asia | Prod. Dev. | 2004 | August | 778770
2849 | Schedule | Delay | Parts | 7 | 7 | Development team in France was unable to convey their requests, issues and concerns | 3 | Africa | IT/Solution | 2001 | March | 522627
2850 | Schedule | Estimates | Learning | 9 | 3 | Errors were discovered in reports that had to be fixed following release | 2 | Eur/ME | IT/Solution | 2008 | August | 486540
2851 | Scope | Change | Creep | 21 | 7 | Field Engineers experience a long learning curve | 3 | Africa | Prod. Dev. | 2018 | December | 1253994
2852 | Scope | Change | Creep | 21 | 5 | People who would deliver training seeking perfection; required extra work and was late. | 1 | Asia | IT/Solution | 2002 | September | 807492
2853 | Scope | Defect | Hardware | 12 | 5 | Executives added a new requirement late | 3 | Africa | IT/Solution | 2016 | June | 920520
2854 | Resource | Money | Limitation | 20 | 4 | Unexpectedly high demand requires outlisde help | 0 | Americas | IT/Solution | 2005 | July | 692300
2855 | Scope | Change | Gap | 7 | 4 | Recertification of updated applications took longer than hoped | 0 | Americas | IT/Solution | 2006 | July | 317471
2856 | Schedule | Estimates | Learning | 12 | 3 | Project schedule was revised user interface requirements which increased project scope | 0 | Americas | Prod. Dev. | 2018 | September | 573660
2857 | Scope | Change | Gap | 17 | 5 | Lack of testing of older WWW browser versions led to custom coding being written before application could be used. | 3 | Africa | IT/Solution | 2008 | May | 493204
2858 | Resource | People | Loss | 8 | 5 | Incorrect input data provided | 3 | Africa | IT/Solution | 2003 | July | 388224
2859 | Resource | People | Queuing | 19 | 4 | The database assigned for the client did not have sufficient free space for their growing accounts | 2 | Eur/ME | IT/Solution | 2011 | February | 1036602
2860 | Resource | People | Queuing | 20 | 6 | In testing, it is discovered that 50K words were left untranslated due to updates and changes | 3 | Africa | Prod. Dev. | 2015 | April | 1548820
2861 | Schedule | Delay | Hardware | 18 | 3 | lack of staff availability due to company down-sizing | 0 | Americas | IT/Solution | 2014 | July | 1228248
2862 | Schedule | Dependency | Infrastructure | 16 | 3 | Pricing negotiation stalls project work until resolved. | 3 | Africa | IT/Solution | 2004 | February | 1099456
2863 | Schedule | Dependency | Legal | 5 | 5 | Outsourced tasks slipped, but not known until too late. | 1 | Asia | IT/Solution | 2019 | June | 261705
2864 | Scope | Change | Creep | 13 | 4 | Equipment needed for project came from a pool of hardware partly in another country. Critical hardware delayed by customs. | 3 | Africa | IT/Solution | 2007 | April | 943358
2865 | Scope | Change | Gap | 21 | 5 | Parts availability and pricing volatile | 0 | Americas | Prod. Dev. | 2014 | July | 767634
2866 | Resource | Money | Limitation | 19 | 6 | Production problem with key component | 0 | Americas | Prod. Dev. | 2016 | October | 581020
2867 | Resource | Outsourcing | Late or poor output | 7 | 6 | Scope requirement discovered late in a construction project | 2 | Eur/ME | IT/Solution | 2010 | March | 236943
2868 | Resource | People | Loss | 21 | 5 | After test, additional requirements surface | 1 | Asia | Prod. Dev. | 2016 | March | 1418802
2869 | Resource | People | Queuing | 13 | 6 | Approvers reject required document | 1 | Asia | Prod. Dev. | 2019 | January | 1003834
2870 | Schedule | Delay | Decision | 10 | 7 | A needed component was not very stable and only available from only one supplier. | 1 | Asia | Prod. Dev. | 2003 | January | 305810
2871 | Schedule | Delay | Decision | 10 | 4 | A batch of servers came in with the wrong configurations; had to be fixed | 1 | Asia | IT/Solution | 2012 | September | 360140
2872 | Schedule | Delay | Hardware | 17 | 6 | Delayed start of work due to negotiation of contract. | 1 | Asia | Prod. Dev. | 2013 | January | 876877
2873 | Schedule | Dependency | Legal | 22 | 6 | Contractors late and unreliable | 1 | Asia | Prod. Dev. | 2002 | July | 752356
2874 | Scope | Change | Creep | 14 | 5 | Unrelaible and incopentent contractors | 0 | Americas | IT/Solution | 2004 | September | 1078840
2875 | Scope | Change | Creep | 13 | 5 | Contractor installed smaller wire sizes than specified causing rework (after a fire) | 2 | Eur/ME | IT/Solution | 2001 | May | 718380
2876 | Scope | Change | Dependency | 17 | 4 | At start of project, insufficient research on the level of local expertise | 0 | Americas | IT/Solution | 2013 | August | 1075590
2877 | Scope | Change | Gap | 14 | 3 | Outsourcing partner in Switzerland did unneeded work, delaying their inputs | 1 | Asia | Prod. Dev. | 2013 | March | 592466
2878 | Resource | People | Queuing | 5 | 6 | Supply chain expert needed was hard to find and engage. | 3 | Africa | Prod. Dev. | 2013 | September | 240690
2879 | Resource | People | Temp loss | 6 | 6 | Key person gave notice more than a month before leaving, but nothing was done | 1 | Asia | IT/Solution | 2001 | September | 346548
2880 | Schedule | Delay | Information | 18 | 4 | The contractor half-way through the electrical job had a heart attack | 3 | Africa | Prod. Dev. | 2011 | February | 1142766
2881 | Scope | Change | Dependency | 6 | 4 | Lead Engineer’s resignation | 0 | Americas | Prod. Dev. | 2007 | May | 200568
2882 | Resource | Money | Limitation | 10 | 7 | Project leader resigns and is not replaced promptly | 1 | Asia | IT/Solution | 2002 | January | 722530
2883 | Resource | Money | Limitation | 12 | 3 | The business analyst was unavailable for project work due to her backup role for a higher priority project | 3 | Africa | IT/Solution | 2003 | January | 410628
2884 | Schedule | Estimates | Judgment | 16 | 5 | Product manager was out due to sick leave (a few months long) | 0 | Americas | Prod. Dev. | 2013 | August | 1108448
2885 | Resource | People | Queuing | 22 | 5 | Negotiation and training on a new tool took more time than planned | 1 | Asia | IT/Solution | 2007 | October | 458832
2886 | Scope | Change | Creep | 6 | 4 | It took a over month to get the custom designed equipment | 2 | Eur/ME | IT/Solution | 2019 | June | 407922
2887 | Resource | People | Queuing | 21 | 3 | The vendor sent equipment to a wrong location in Michigan instead of the Bay Area | 2 | Eur/ME | Prod. Dev. | 2017 | July | 670971
2888 | Resource | People | Temp loss | 18 | 5 | Need to get input from one of the external group for specific info; late | 2 | Eur/ME | IT/Solution | 2015 | September | 790812
2889 | Scope | Change | Dependency | 17 | 6 | Lack of communication and trust between locations | 0 | Americas | IT/Solution | 2007 | March | 398157
2890 | Scope | Change | Gap | 11 | 6 | Ship sinks with critical part; forced to replace with remanufactured old component | 0 | Americas | Prod. Dev. | 2008 | August | 799062
2891 | Scope | Defect | Hardware | 12 | 5 | Delay in getting material when a fermentation run crashes | 0 | Americas | Prod. Dev. | 2012 | January | 948216
2892 | Scope | Defect | Integration | 13 | 6 | Chip failed and had to be refabricated with changes | 3 | Africa | Prod. Dev. | 2006 | June | 697827
2893 | Resource | Outsourcing | Late or poor output | 9 | 3 | Inadequate water supply available to complete project, needed to be trucked in | 3 | Africa | Prod. Dev. | 2005 | February | 475785
2894 | Scope | Defect | Software | 10 | 4 | Lack of communication with the project team in Germany | 3 | Africa | Prod. Dev. | 2017 | August | 359850
2895 | Schedule | Estimates | Learning | 18 | 4 | Unrealistic deadline set; slips unavoidable. | 1 | Asia | IT/Solution | 2002 | February | 1221498
2896 | Scope | Change | Creep | 6 | 3 | Company underestimated the scope of the project | 0 | Americas | IT/Solution | 2003 | May | 388266
2897 | Resource | Outsourcing | Late or poor output | 14 | 4 | Expert opinion was 2 weeks; work took 8. | 0 | Americas | Prod. Dev. | 2007 | September | 772926
2898 | Resource | People | Temp loss | 21 | 6 | Problems using trainers and training materials from Germany | 2 | Eur/ME | Prod. Dev. | 2016 | July | 841008
2899 | Schedule | Delay | Hardware | 19 | 4 | Inexperienced staff | 0 | Americas | IT/Solution | 2005 | May | 601768
2900 | Scope | Change | Dependency | 11 | 4 | Entry level employees lacked needed skill and experience | 0 | Americas | Prod. Dev. | 2010 | August | 619828
2901 | Schedule | Estimates | Learning | 6 | 4 | No cross training within the team to make more knowledgeable resources available | 3 | Africa | Prod. Dev. | 2002 | February | 389466
2902 | Schedule | Delay | Parts | 5 | 4 | Late features were added | 0 | Americas | IT/Solution | 2012 | August | 328185
2903 | Schedule | Delay | Parts | 8 | 4 | Late stakeholders redefine requiremnts | 2 | Eur/ME | IT/Solution | 2012 | January | 422512
2904 | Schedule | Delay | Information | 21 | 5 | Conflicting design attributes and an unfocused process resulted in confusion and changes | 3 | Africa | Prod. Dev. | 2018 | January | 1006929
2905 | Scope | Defect | Software | 9 | 5 | Late addition of a USB port to a recharging adapter | 1 | Asia | Prod. Dev. | 2011 | March | 324522
2906 | Resource | People | Queuing | 8 | 6 | Sponsor agreed to specifications on door, loading docks, structural supports etc that impeded efficient work flows | 2 | Eur/ME | Prod. Dev. | 2018 | December | 267256
2907 | Resource | People | Queuing | 8 | 7 | Constant design changes occurred and parts had to be scrapped and replaced | 0 | Americas | Prod. Dev. | 2012 | December | 570368
2908 | Schedule | Dependency | Project | 16 | 7 | The scope of the project was poorly defined | 1 | Asia | Prod. Dev. | 2013 | January | 976032
2909 | Scope | Change | Gap | 17 | 7 | Client added new web pages to showcase the European site | 3 | Africa | IT/Solution | 2010 | August | 642736
2910 | Schedule | Dependency | Infrastructure | 10 | 6 | Old hardware became unavailable and product had to be tested on the new series | 3 | Africa | IT/Solution | 2003 | August | 357100
2911 | Scope | Change | Gap | 16 | 3 | The statement of work did not indicate clearly the responsibilities of the outsourced programmers | 0 | Americas | IT/Solution | 2013 | September | 658544
2912 | Resource | Outsourcing | Late or poor output | 18 | 5 | The statement of work was not as specific as the authors thought and the deliverable from the vendor did not function as expected | 3 | Africa | IT/Solution | 2009 | April | 830574
2913 | Schedule | Estimates | Deadline | 16 | 6 | Contractual obligations set without adequate knowledge of potential hidden issues | 3 | Africa | IT/Solution | 2007 | November | 873088
2914 | Scope | Change | Creep | 17 | 7 | The delivery of the content started without the content being finalized | 3 | Africa | Prod. Dev. | 2016 | March | 632553
2915 | Resource | Outsourcing | Late or poor output | 6 | 4 | Manufacturing process was not scalable and had to be redesigned | 1 | Asia | Prod. Dev. | 2013 | August | 239358
2916 | Resource | Outsourcing | Late or poor output | 10 | 4 | Real-life data used did not test every scenario possible, so had to be replaced | 2 | Eur/ME | Prod. Dev. | 2008 | August | 604690
2917 | Resource | People | Loss | 11 | 5 | Lack of communication between the customer and all vendors involved | 3 | Africa | IT/Solution | 2011 | November | 873543
2918 | Resource | People | Temp loss | 15 | 6 | Management never talked to the test department when creating proposals | 1 | Asia | IT/Solution | 2008 | March | 533430
2919 | Schedule | Delay | Information | 7 | 6 | Needed plants were set too far apart to fertilize initially | 3 | Africa | Prod. Dev. | 2007 | June | 484414
2920 | Scope | Change | Creep | 16 | 7 | Chp failed due to a hardware design issue and had to be redesigned and refabricated | 1 | Asia | Prod. Dev. | 2005 | June | 535072
2921 | Scope | Defect | Integration | 20 | 6 | New application works, but data collected is not accessible. | 2 | Eur/ME | IT/Solution | 2011 | February | 647920
2922 | Resource | People | Loss | 15 | 4 | Defects discovered in late testing | 1 | Asia | IT/Solution | 2011 | April | 986505
2923 | Resource | People | Loss | 7 | 6 | Application required its own server, delay for installation | 3 | Africa | IT/Solution | 2004 | November | 403928
2924 | Scope | Change | Gap | 16 | 5 | Excessive defects in Web Page translations | 3 | Africa | IT/Solution | 2017 | June | 1228976
2925 | Resource | People | Temp loss | 8 | 4 | Understaffing causes overtime and leads to loss of staff | 0 | Americas | IT/Solution | 2009 | December | 516824
2926 | Schedule | Delay | Decision | 19 | 5 | Money for needed software was not in the budget; project was delayed to push expense into next quarter | 2 | Eur/ME | Prod. Dev. | 2012 | June | 436696
2927 | Schedule | Dependency | Infrastructure | 15 | 7 | Project manager thought the solution was only one task, but there were four | 0 | Americas | Prod. Dev. | 2004 | June | 1089735
2928 | Schedule | Dependency | Infrastructure | 5 | 4 | Lack of consensus on the spec resulted in modifications during the second phase of the project | 0 | Americas | IT/Solution | 2010 | November | 228900
2929 | Scope | Change | Gap | 6 | 3 | Critical application delivery late | 0 | Americas | Prod. Dev. | 2010 | February | 305538
2930 | Scope | Change | Gap | 10 | 7 | Prior work was completed late | 3 | Africa | IT/Solution | 2003 | May | 293960
2931 | Scope | Defect | Integration | 13 | 5 | Insufficient resources and little change control | 0 | Americas | Prod. Dev. | 2012 | December | 424970
2932 | Scope | Defect | Software | 8 | 4 | Unique and specific requirements were poorly understood | 2 | Eur/ME | IT/Solution | 2008 | February | 515976
2933 | Resource | People | Loss | 5 | 4 | Subcontracted work failed to meet client's criteria | 1 | Asia | IT/Solution | 2004 | October | 150150
2934 | Resource | People | Queuing | 8 | 4 | Planning the terms of the agreement and negotiating the contracts took time, making the project begin late | 0 | Americas | Prod. Dev. | 2018 | August | 235680
2935 | Resource | People | Queuing | 8 | 6 | Old application to be modified for Y2K had no documentation, and finding original code took weeks. | 1 | Asia | Prod. Dev. | 2002 | June | 224336
2936 | Resource | People | Temp loss | 19 | 5 | Peak season begun earlier than expected and Higher Freight Volume than usual | 1 | Asia | IT/Solution | 2019 | August | 1404594
2937 | Resource | People | Temp loss | 13 | 5 | Key requirements were uncovered late | 2 | Eur/ME | Prod. Dev. | 2011 | June | 699647
2938 | Schedule | Delay | Information | 8 | 3 | Initial code release was a major failure | 1 | Asia | IT/Solution | 2019 | August | 267424
2939 | Schedule | Delay | Parts | 11 | 3 | High turnover led to training and low productivity throughout project. | 2 | Eur/ME | IT/Solution | 2007 | March | 874038
2940 | Schedule | Estimates | Learning | 6 | 3 | Initial ubjects for tests did not meet project requirements | 0 | Americas | Prod. Dev. | 2003 | September | 232548
2941 | Scope | Change | Gap | 6 | 5 | Subcontractor goes out of business and it took 2 months to replace them. | 2 | Eur/ME | Prod. Dev. | 2017 | May | 129432
2942 | Schedule | Delay | Decision | 16 | 3 | Key contributor on jury duty | 3 | Africa | IT/Solution | 2006 | December | 688832
2943 | Schedule | Dependency | Infrastructure | 15 | 4 | To expand business, unrealistic commitments were made to win the project | 3 | Africa | IT/Solution | 2011 | December | 328725
2944 | Schedule | Estimates | Judgment | 20 | 5 | Completion criteria were not documented well | 2 | Eur/ME | IT/Solution | 2004 | October | 1495400
2945 | Scope | Change | Creep | 11 | 4 | Complex system designed in pieces, and integration fails. Redesign is required. | 2 | Eur/ME | IT/Solution | 2003 | November | 433279
2946 | Scope | Change | Dependency | 10 | 5 | Freelancer hired was a nutjob, and lacked the correct skills | 3 | Africa | IT/Solution | 2018 | February | 520090
2947 | Schedule | Dependency | Project | 12 | 7 | Resources were not available at the time the project started | 0 | Americas | IT/Solution | 2012 | December | 297492
2948 | Scope | Change | Dependency | 7 | 6 | Unexpected shutdown at year end delays work and rescheduling it is difficult. | 0 | Americas | IT/Solution | 2002 | December | 443898
2949 | Schedule | Dependency | Legal | 7 | 7 | Infrasturcture changes made mid-project | 1 | Asia | Prod. Dev. | 2008 | August | 207550
2950 | Scope | Defect | Integration | 9 | 4 | Plans for project for new customer based on similar work for existing customer. Relationships, infrastructure, jargon and other differences took 50% more effort. | 1 | Asia | IT/Solution | 2008 | February | 679428
2951 | Scope | Change | Gap | 17 | 5 | One patch was almost completely tested when it was decided to fix another bug | 2 | Eur/ME | IT/Solution | 2001 | December | 348330
2952 | Scope | Change | Gap | 21 | 5 | Design stability poor, requiring rework and late changes for manufacturing. | 3 | Africa | Prod. Dev. | 2009 | October | 1279362
2953 | Resource | Outsourcing | Late or poor output | 13 | 3 | Poor project planning and missed end-user requirements | 1 | Asia | IT/Solution | 2011 | February | 804570
2954 | Scope | Defect | Software | 8 | 5 | First production run problems necessitated adding a third run | 2 | Eur/ME | Prod. Dev. | 2011 | February | 425408
2955 | Scope | Change | Creep | 19 | 3 | Purchased software is limited and inflexible. Workarounds and additional software required. | 0 | Americas | IT/Solution | 2006 | August | 1154022
2956 | Schedule | Estimates | Judgment | 16 | 5 | Senior technical writer resigns and another takes a leave | 3 | Africa | Prod. Dev. | 2007 | February | 698624
2957 | Scope | Defect | Software | 18 | 6 | Servers stuck in customs | 3 | Africa | IT/Solution | 2016 | June | 911610
2958 | Resource | Outsourcing | Late or poor output | 20 | 7 | Legacy systems and processes were not well documented | 3 | Africa | IT/Solution | 2001 | May | 1289920
2959 | Schedule | Delay | Hardware | 5 | 7 | Legacy system (COBOL) fails during system upgrade project. Extra effort required to fix. | 1 | Asia | IT/Solution | 2004 | October | 325335
2960 | Schedule | Estimates | Learning | 16 | 4 | Contractors are not close to the business and often overlook requirements | 0 | Americas | IT/Solution | 2002 | October | 796288
2961 | Scope | Change | Creep | 16 | 6 | Requisition required the authorization of CEO who was out of town in Finland | 0 | Americas | Prod. Dev. | 2018 | August | 820128
2962 | Scope | Change | Creep | 16 | 6 | Key contractors have the flu | 2 | Eur/ME | Prod. Dev. | 2012 | January | 554912
2963 | Resource | Outsourcing | Late or poor output | 20 | 3 | Work was underestimated by 40% | 0 | Americas | IT/Solution | 2017 | July | 612700
2964 | Resource | Outsourcing | Late or poor output | 9 | 3 | Project manager added additional customized reporting (for no additional fee) | 1 | Asia | IT/Solution | 2001 | April | 697743
2965 | Schedule | Dependency | Infrastructure | 13 | 4 | Scanning of text was estimated before it was known text was bound in volumes | 3 | Africa | IT/Solution | 2017 | May | 526955
2966 | Schedule | Estimates | Deadline | 8 | 6 | Lack of supplies and adequate time for printing | 1 | Asia | IT/Solution | 2016 | December | 403872
2967 | Scope | Change | Gap | 14 | 3 | Late additional request on a small project delayed completion | 3 | Africa | IT/Solution | 2014 | August | 692048
2968 | Scope | Defect | Integration | 18 | 7 | Poor definition of training requirements; had to do much more. | 0 | Americas | IT/Solution | 2017 | April | 1419336
2969 | Resource | Outsourcing | Late or poor output | 18 | 7 | After project "complete" rework required for customer approval | 3 | Africa | IT/Solution | 2004 | July | 370782
2970 | Resource | Outsourcing | Late or poor output | 8 | 3 | Access problems surfaced in production | 0 | Americas | IT/Solution | 2001 | June | 581192
2971 | Resource | People | Loss | 16 | 7 | Outsource company’s abilities were poor and they had to be replaced | 2 | Eur/ME | IT/Solution | 2016 | January | 1194992
2972 | Resource | People | Loss | 7 | 7 | Vendor had a poor resource plan | 3 | Africa | IT/Solution | 2008 | June | 256179
2973 | Resource | People | Temp loss | 11 | 6 | There was a high fluctuation of pressure that nobody could explain | 2 | Eur/ME | Prod. Dev. | 2005 | November | 416097
2974 | Schedule | Delay | Information | 5 | 3 | Partner software is incompatible with current applications. | 2 | Eur/ME | IT/Solution | 2013 | August | 265885
2975 | Scope | Defect | Integration | 7 | 7 | Project delayed to work on higher profit margin work | 0 | Americas | IT/Solution | 2015 | March | 184653
2976 | Resource | Outsourcing | Late or poor output | 8 | 6 | Additional scope added; slipped project | 3 | Africa | IT/Solution | 2016 | January | 274360
2977 | Resource | Outsourcing | Late or poor output | 16 | 5 | New specs provided and priorities changed in the middle of the project | 1 | Asia | Prod. Dev. | 2017 | February | 851440
2978 | Resource | People | Queuing | 11 | 3 | Did not have the correct people validate requirements | 2 | Eur/ME | IT/Solution | 2019 | February | 504108
2979 | Resource | People | Queuing | 10 | 4 | No understanding of the scope and not enough system resources | 1 | Asia | IT/Solution | 2002 | October | 360250
2980 | Resource | People | Queuing | 13 | 7 | Additional localization requirements will cost significant extra effort and time | 3 | Africa | Prod. Dev. | 2005 | November | 750594
2981 | Scope | Defect | Software | 9 | 7 | Purchased electronic component failed with a very high rate of 30% and had to be replaced with a designed one | 1 | Asia | Prod. Dev. | 2019 | January | 410274
2982 | Schedule | Delay | Information | 17 | 6 | Indefinite loss of key staff member | 2 | Eur/ME | IT/Solution | 2013 | February | 1152430
2983 | Schedule | Estimates | Judgment | 18 | 3 | Incompetent developer | 1 | Asia | Prod. Dev. | 2004 | November | 1342008
2984 | Scope | Change | Gap | 19 | 7 | Product was scoped with unnecessary requirements and was late | 1 | Asia | Prod. Dev. | 2007 | February | 1434158
2985 | Scope | Defect | Software | 9 | 7 | Without funding, all work ceased, contracts were effectively terminated with no prospect of renewal | 3 | Africa | Prod. Dev. | 2015 | February | 627597
2986 | Schedule | Delay | Parts | 18 | 3 | Inaccurate comparison between our requirements and the software | 3 | Africa | IT/Solution | 2004 | December | 1409940
2987 | Resource | Outsourcing | Late or poor output | 11 | 6 | New application was slow and some initial requirements were missed | 2 | Eur/ME | IT/Solution | 2008 | July | 842930
2988 | Resource | People | Loss | 6 | 5 | Project manager had very few skills in this field | 0 | Americas | IT/Solution | 2002 | April | 149682
2989 | Schedule | Delay | Information | 18 | 4 | One company expands scope in web design project without communicating or getting approval from others | 3 | Africa | IT/Solution | 2014 | April | 597888
2990 | Schedule | Delay | Parts | 11 | 6 | Subject matter experts were let go to save money | 2 | Eur/ME | Prod. Dev. | 2014 | May | 759242
2991 | Schedule | Dependency | Infrastructure | 5 | 4 | Loss of a programmer | 1 | Asia | Prod. Dev. | 2018 | July | 379410
2992 | Schedule | Dependency | Legal | 16 | 5 | Work was significantly underestimated for the project | 1 | Asia | IT/Solution | 2004 | November | 354128
2993 | Schedule | Dependency | Project | 5 | 4 | Lacked expertise needed for project (SOW too high level | 1 | Asia | Prod. Dev. | 2016 | October | 241070
2994 | Scope | Change | Creep | 12 | 7 | “Off the shelf” software package was to support migration from mainframe to client-server application. Lots of unexpected customization required. | 1 | Asia | IT/Solution | 2002 | June | 285960
2995 | Scope | Change | Creep | 18 | 3 | PM unavailable due to Jury Duty | 1 | Asia | Prod. Dev. | 2019 | July | 606582
2996 | Scope | Change | Creep | 6 | 5 | Combining two features into one project release created unexpected complexity | 1 | Asia | IT/Solution | 2003 | December | 158418
2997 | Scope | Change | Gap | 16 | 3 | Kitchen remodel expanded to renovating the bathrooms | 1 | Asia | IT/Solution | 2012 | August | 864752
2998 | Scope | Change | Gap | 12 | 7 | At start of project, insufficient research on the level of local expertise | 1 | Asia | IT/Solution | 2015 | December | 536784
2999 | Resource | Money | Limitation | 7 | 6 | Client added new web pages to showcase the European site | 0 | Americas | IT/Solution | 2005 | June | 553441
3000 | Schedule | Delay | Parts | 20 | 4 | Responsibilities not defined well for project | 0 | Americas | Prod. Dev. | 2010 | November | 1189240
3001 | Schedule | Estimates | Learning | 11 | 3 | Instructions to contract testing facility were too vague and tests had to be repeated | 0 | Americas | Prod. Dev. | 2005 | September | 400169
3002 | Scope | Change | Gap | 18 | 5 | Systems required backordered (6 months). Forced to use competitor's system. | 0 | Americas | IT/Solution | 2018 | April | 671760
3003 | Scope | Change | Gap | 13 | 3 | Documents could not be translated promptly | 1 | Asia | IT/Solution | 2003 | August | 1021514
3004 | Resource | People | Temp loss | 10 | 5 | The business analyst failed to fully understand the scientist’s requirements | 2 | Eur/ME | Prod. Dev. | 2015 | November | 256030
3005 | Schedule | Delay | Hardware | 13 | 6 | Contractor got a bigger project moved most of his team to that | 3 | Africa | IT/Solution | 2017 | November | 303706
3006 | Scope | Change | Creep | 19 | 4 | Programming object delivered late from India delays integration tests | 3 | Africa | IT/Solution | 2009 | March | 1457053
3007 | Resource | Money | Limitation | 16 | 6 | Decision to switch to contract manufacturer near end of project caused delays and cost increases. | 3 | Africa | Prod. Dev. | 2002 | October | 369312
3008 | Resource | Outsourcing | Delayed start | 8 | 6 | The key business user assigned to the ITS project was lost while assisting with a manufacturing problem and was no longer available to the project team | 1 | Asia | Prod. Dev. | 2015 | January | 437000
3009 | Resource | Outsourcing | Late or poor output | 5 | 3 | Needed wiring not available on time | 0 | Americas | IT/Solution | 2012 | July | 236375
3010 | Schedule | Estimates | Judgment | 5 | 3 | Escalated late changes from Sponsor | 2 | Eur/ME | Prod. Dev. | 2012 | February | 277760
3011 | Scope | Change | Gap | 21 | 6 | Customer requirements continually shift; lots of extra work. | 0 | Americas | IT/Solution | 2016 | June | 1157772
3012 | Schedule | Delay | Hardware | 5 | 7 | An external part-time consultant wasn't always available when needed | 3 | Africa | IT/Solution | 2005 | June | 362250
3013 | Schedule | Estimates | Deadline | 10 | 7 | Resources thin and tasks queued in backlogs. | 2 | Eur/ME | IT/Solution | 2010 | March | 397450
3014 | Scope | Change | Gap | 14 | 5 | Move out of old location required, but new space is not ready. Interim move to temporary space takes extra time and money. | 3 | Africa | IT/Solution | 2006 | July | 388192
3015 | Scope | Change | Gap | 21 | 3 | Late facility availability | 3 | Africa | Prod. Dev. | 2007 | July | 1426698
3016 | Schedule | Dependency | Project | 16 | 3 | Installation of new systems scheduled by central team, but local people are not ready. | 0 | Americas | IT/Solution | 2016 | February | 1029488
3017 | Schedule | Dependency | Project | 22 | 4 | Changes to related systems resulted in wrong/late paychecks | 1 | Asia | IT/Solution | 2018 | June | 1303764
3018 | Schedule | Estimates | Judgment | 21 | 7 | Software could only be delivered to a certified person | 1 | Asia | Prod. Dev. | 2005 | July | 1081017
3019 | Schedule | Estimates | Learning | 6 | 3 | IT team did not perform a thorough investigation of the existing infrastructure | 0 | Americas | IT/Solution | 2019 | November | 151950
3020 | Scope | Change | Creep | 8 | 4 | New software release causes problems | 3 | Africa | IT/Solution | 2018 | July | 297912
3021 | Scope | Change | Gap | 17 | 5 | Contractor setup delayed by a week | 3 | Africa | Prod. Dev. | 2010 | May | 787406
3022 | Scope | Change | Gap | 13 | 7 | Contractors failed to show up as committed | 3 | Africa | IT/Solution | 2011 | February | 809172
3023 | Scope | Change | Gap | 9 | 3 | Late changes resulted in expedite charges and delay | 1 | Asia | Prod. Dev. | 2012 | January | 525105
3024 | Scope | Defect | Hardware | 18 | 6 | Consultants failed to secure required resources in timely manner | 3 | Africa | IT/Solution | 2002 | July | 1212102
3025 | Resource | People | Temp loss | 21 | 3 | WWW code supplied by third party late and poor quality; major delay and rework. | 2 | Eur/ME | IT/Solution | 2003 | April | 829584
3026 | Schedule | Delay | Decision | 13 | 5 | Subcontractor refused to follow the core vendor’s processes | 3 | Africa | IT/Solution | 2013 | December | 959647
3027 | Schedule | Delay | Information | 17 | 3 | Because of incopetence, a second consultant was hired to redo the work | 0 | Americas | IT/Solution | 2001 | November | 385203
3028 | Scope | Change | Creep | 9 | 5 | Contracted with a small outside firm that didn’t understand the business | 0 | Americas | Prod. Dev. | 2007 | December | 709587
3029 | Scope | Change | Gap | 18 | 5 | High turnover. ( 80%) of developer at off shore development unit left, including project lead | 2 | Eur/ME | IT/Solution | 2006 | July | 933246
3030 | Scope | Change | Gap | 13 | 7 | Subcontractor goes out of business and it took 2 months to replace them. | 2 | Eur/ME | Prod. Dev. | 2017 | June | 615186
3031 | Scope | Defect | Hardware | 8 | 7 | Government contract required only US born nationals; company had too few | 3 | Africa | IT/Solution | 2006 | December | 235648
3032 | Scope | Defect | Software | 10 | 3 | Project was new to the company and needed to hire people and develop a team | 3 | Africa | Prod. Dev. | 2006 | April | 325870
3033 | Resource | People | Queuing | 15 | 5 | Staffing was late and inexperienced | 3 | Africa | IT/Solution | 2015 | February | 1186230
3034 | Resource | People | Temp loss | 5 | 5 | The only experienced programmer gave notice and left the company | 0 | Americas | IT/Solution | 2003 | October | 263040
3035 | Schedule | Delay | Parts | 14 | 7 | One of the Senior System Analysts who was fully trained on the application resigned | 1 | Asia | IT/Solution | 2004 | November | 655760
3036 | Resource | People | Motivation | 8 | 3 | Team leader reassigned to another project and a new leader was assigned | 3 | Africa | IT/Solution | 2012 | July | 352104
3037 | Schedule | Delay | Parts | 22 | 5 | Lack of IT subject matter experts | 2 | Eur/ME | IT/Solution | 2017 | June | 450714
3038 | Schedule | Delay | Parts | 10 | 7 | Key contributor on jury duty | 3 | Africa | IT/Solution | 2013 | January | 660350
3039 | Schedule | Dependency | Project | 12 | 3 | Project lost irreplaceable experts | 2 | Eur/ME | IT/Solution | 2002 | October | 490848
3040 | Scope | Change | Creep | 11 | 5 | Executive director stayed two months and then left | 0 | Americas | Prod. Dev. | 2018 | September | 583737
3041 | Scope | Change | Creep | 19 | 4 | A company-wide reduction in force let go some of the people who were supposed to lead the next phase | 2 | Eur/ME | Prod. Dev. | 2011 | December | 1265780
3042 | Scope | Change | Creep | 13 | 3 | Applications Engineer found another job and left the company | 3 | Africa | Prod. Dev. | 2014 | May | 932828
3043 | Scope | Change | Gap | 11 | 5 | Both the full time developers assigned to the project quit the company | 2 | Eur/ME | Prod. Dev. | 2007 | January | 503723
3044 | Scope | Change | Gap | 17 | 4 | Project leader was transferred to another project | 3 | Africa | IT/Solution | 2013 | October | 1314134
3045 | Scope | Defect | Hardware | 16 | 4 | Half way through the project three of the engineers had to return to China due to visa issues | 1 | Asia | Prod. Dev. | 2010 | July | 702448
3046 | Scope | Defect | Software | 12 | 3 | Project work estimated to take 1 month took 3 due to loss of staff to do the work. | 0 | Americas | Prod. Dev. | 2004 | August | 514728
3047 | Schedule | Dependency | Project | 18 | 3 | Projects with similar objectives taken on centrally and locally at the same time. Lots of overlap, redundancy and arguing. | 0 | Americas | IT/Solution | 2015 | August | 840726
3048 | Resource | People | Motivation | 14 | 6 | Project is not complete until all users are trained. Coordinating schedules requires 4 months, not 2. | 2 | Eur/ME | Prod. Dev. | 2019 | September | 1114232
3049 | Scope | Change | Creep | 14 | 6 | Specialist was busy with a lot of work | 2 | Eur/ME | IT/Solution | 2001 | August | 987140
3050 | Resource | Outsourcing | Late or poor output | 14 | 6 | Mid-way in design stage, a key Engineer had a family emergency and had to leave the country for a month | 1 | Asia | IT/Solution | 2001 | May | 666904
3051 | Schedule | Estimates | Learning | 5 | 7 | Key engineer was pulled out of the team to work on another project. | 2 | Eur/ME | IT/Solution | 2007 | March | 389150
3052 | Scope | Defect | Hardware | 13 | 5 | Two of the SAP technicians were reassigned to a more “business critical” project midway through the system development phase. | 2 | Eur/ME | IT/Solution | 2004 | October | 1000298
3053 | Scope | Defect | Software | 11 | 6 | PM unavailable due to Jury Duty | 2 | Eur/ME | Prod. Dev. | 2002 | March | 513667
3054 | Schedule | Estimates | Judgment | 8 | 5 | Contributor couldn't work due to injury and back pains | 2 | Eur/ME | IT/Solution | 2013 | November | 345976
3055 | Scope | Change | Gap | 12 | 3 | Sponsorship not sustained and decisions and resources are problematic. | 1 | Asia | IT/Solution | 2019 | June | 890196
3056 | Scope | Defect | Software | 18 | 6 | Endless debate over choice of three possible approaches for project work | 2 | Eur/ME | IT/Solution | 2012 | February | 929484
3057 | Scope | Defect | Software | 6 | 5 | Color printer version of app fails on WAN | 3 | Africa | IT/Solution | 2001 | September | 207714
3058 | Schedule | Delay | Information | 12 | 4 | Vendor merger caused interruption in hardware availability; had to recertify | 0 | Americas | IT/Solution | 2004 | December | 844164
3059 | Resource | People | Loss | 22 | 8 | Data for key tables not available when needed | 3 | Africa | IT/Solution | 2015 | October | 1480006
3060 | Resource | People | Loss | 17 | 6 | Old application to be modified had no one left who knew it and no documentation. | 3 | Africa | Prod. Dev. | 2014 | December | 881637
3061 | Resource | People | Queuing | 9 | 9 | Quantity of Intel CPU processors needed not available | 2 | Eur/ME | Prod. Dev. | 2011 | September | 612909
3062 | Scope | Change | Creep | 10 | 4 | Existing systems were removed from market, requiring changes for new model | 2 | Eur/ME | IT/Solution | 2002 | May | 462970
3063 | Scope | Change | Gap | 18 | 2 | Partner misses bimaontly shipping deadline | 1 | Asia | Prod. Dev. | 2018 | February | 1347138
3064 | Scope | Change | Gap | 19 | 1 | Manufacutring group did not have the capcity to produce a critical new enzyme | 3 | Africa | Prod. Dev. | 2009 | February | 488300
3065 | Scope | Change | Gap | 11 | 6 | Project experienced shortages in steel rebar and copper electrical wire | 0 | Americas | Prod. Dev. | 2005 | May | 725032
3066 | Scope | Change | Creep | 22 | 2 | Too few disc drives, and insufficient "owned" space | 0 | Americas | IT/Solution | 2018 | July | 1021988
3067 | Scope | Change | Dependency | 10 | 3 | Sponsors who knew the system well didn't bother to analyze the impact of rolling out sensitive data to global users without security in place | 2 | Eur/ME | IT/Solution | 2013 | September | 429750
3068 | Resource | Money | Limitation | 20 | 7 | A six month conversion period from the date a contract is signed is the norm, but project goal is four months | 1 | Asia | IT/Solution | 2018 | October | 496400
3069 | Schedule | Delay | Information | 22 | 8 | To expand business, unrealistic commitments were made to win the project | 3 | Africa | Prod. Dev. | 2012 | July | 718850
3070 | Resource | People | Loss | 5 | 7 | Unrealistic deadline set; slips unavoidable. | 3 | Africa | IT/Solution | 2011 | October | 223560
3071 | Resource | People | Loss | 20 | 5 | Combining two features into one project release created unexpected complexity | 1 | Asia | IT/Solution | 2001 | February | 1135660
3072 | Resource | People | Temp loss | 18 | 6 | Software development underestimated by a factor of three. | 3 | Africa | Prod. Dev. | 2007 | November | 1064718
3073 | Schedule | Estimates | Judgment | 16 | 9 | Few of the administrators and developers hired for executing this project had the right skill sets to execute the project | 1 | Asia | IT/Solution | 2006 | August | 564752
3074 | Scope | Change | Creep | 21 | 7 | Developers on the project were not experienced enough to implement the solution | 1 | Asia | Prod. Dev. | 2019 | January | 1365651
3075 | Scope | Defect | Hardware | 15 | 8 | No staff that was knowledgeable in the technology | 2 | Eur/ME | IT/Solution | 2005 | December | 531420
3076 | Resource | Money | Limitation | 13 | 5 | Redesign added late in maintenance project for legacy system. Major slip. | 0 | Americas | Prod. Dev. | 2007 | September | 585260
3077 | Resource | Outsourcing | Late or poor output | 21 | 4 | Scope not defined well; huge software delays | 1 | Asia | Prod. Dev. | 2002 | September | 1638609
3078 | Resource | People | Late start | 21 | 6 | Functionality for email added late to a document retrieval project | 3 | Africa | IT/Solution | 2010 | September | 1039710
3079 | Resource | People | Temp loss | 19 | 6 | Continuous revisions to the specifications for a building remodel | 1 | Asia | IT/Solution | 2001 | May | 593180
3080 | Schedule | Delay | Parts | 6 | 4 | Kitchen remodel expanded to renovating the bathrooms | 2 | Eur/ME | Prod. Dev. | 2009 | April | 301704
3081 | Schedule | Delay | Parts | 14 | 6 | Additional three manufacturing sites meant using another server for this project | 2 | Eur/ME | Prod. Dev. | 2016 | August | 715862
3082 | Schedule | Estimates | Learning | 15 | 5 | New requirements were piled on as the project ran | 0 | Americas | Prod. Dev. | 2016 | April | 513885
3083 | Scope | Change | Creep | 7 | 3 | Requirements were unclear at the beginning of the project | 1 | Asia | IT/Solution | 2003 | August | 405741
3084 | Scope | Change | Gap | 19 | 8 | Definition changed late in project. | 1 | Asia | Prod. Dev. | 2017 | September | 1180793
3085 | Scope | Defect | Software | 9 | 8 | After more than 2/3 of the original budget had been expended, a major design change resulted in major requirement modifications and additions | 3 | Africa | IT/Solution | 2016 | August | 592560
3086 | Resource | Money | Limitation | 7 | 2 | Processes were changed and made more complex late in the project | 0 | Americas | Prod. Dev. | 2016 | January | 141246
3087 | Schedule | Delay | Hardware | 13 | 9 | Additional renovations added late that were not in the original plan | 1 | Asia | IT/Solution | 2016 | August | 855413
3088 | Resource | Outsourcing | Late or poor output | 19 | 7 | Initial scoping for a minor upgrade was not sufficient | 0 | Americas | IT/Solution | 2008 | June | 487540
3089 | Resource | Outsourcing | Late or poor output | 16 | 9 | Management did not plan for a requirements gathering phase | 1 | Asia | IT/Solution | 2003 | May | 1099296
3090 | Resource | People | Late start | 13 | 1 | Solution project priced "to win" and had few details on work; led to big losses and delays. | 1 | Asia | IT/Solution | 2015 | February | 361348
3091 | Resource | People | Loss | 15 | 8 | Migration project (to NT from UNIX) saddled with increasing list of changes. | 1 | Asia | IT/Solution | 2004 | August | 392130
3092 | Resource | People | Loss | 13 | 7 | Sponsor demanded specification changes late in the project | 3 | Africa | IT/Solution | 2010 | December | 412451
3093 | Resource | People | Queuing | 11 | 3 | Sales reps did not clearly understand the client’s request | 2 | Eur/ME | Prod. Dev. | 2001 | June | 336259
3094 | Schedule | Delay | Decision | 11 | 5 | Requirements document for a new database system were not specific enough regarding user interface details | 1 | Asia | Prod. Dev. | 2018 | April | 451616
3095 | Schedule | Delay | Hardware | 14 | 4 | Incorrect decimal pay rate did not reflect the true and accurate pay | 1 | Asia | IT/Solution | 2010 | December | 316120
3096 | Schedule | Delay | Information | 15 | 4 | Procurement is done based on out-of date drawings | 2 | Eur/ME | Prod. Dev. | 2012 | September | 361290
3097 | Schedule | Delay | Parts | 9 | 1 | Completion criteria were not documented well | 1 | Asia | Prod. Dev. | 2019 | April | 510651
3098 | Schedule | Dependency | Legal | 6 | 5 | Sufficient time was not allocated to understand client needs and assumptions | 0 | Americas | Prod. Dev. | 2003 | November | 235188
3099 | Schedule | Dependency | Project | 14 | 5 | No clear requirements from management | 3 | Africa | Prod. Dev. | 2012 | May | 280980
3100 | Schedule | Estimates | Judgment | 13 | 7 | Unique data in each region prevented information flow | 2 | Eur/ME | IT/Solution | 2001 | May | 507624
3101 | Schedule | Estimates | Learning | 14 | 6 | Website wasn't as simple as it iniitally seemed | 2 | Eur/ME | IT/Solution | 2018 | August | 1050070
3102 | Schedule | Estimates | Learning | 8 | 9 | Lead engineer thought he had a good ‘understanding’ of what needed to be done | 1 | Asia | IT/Solution | 2015 | March | 287808
3103 | Schedule | Estimates | Learning | 21 | 3 | Partner company introduced a changed requirement late in development | 2 | Eur/ME | IT/Solution | 2009 | November | 1073667
3104 | Scope | Change | Creep | 5 | 9 | Key telecom requirement detected late | 2 | Eur/ME | Prod. Dev. | 2004 | June | 259635
3105 | Scope | Change | Creep | 19 | 4 | Need to upgrade detected only at project end | 0 | Americas | IT/Solution | 2004 | March | 447450
3106 | Scope | Change | Creep | 8 | 1 | The students in a new course had insufficient knowledge of reading and math | 0 | Americas | IT/Solution | 2012 | November | 566672
3107 | Scope | Change | Creep | 16 | 5 | Redesign required late in printer project to meet paper speed goals. OT and delays. | 0 | Americas | IT/Solution | 2005 | October | 576464
3108 | Scope | Change | Creep | 12 | 6 | Components failure means finding another type of component and redoing tests | 2 | Eur/ME | IT/Solution | 2013 | October | 695328
3109 | Scope | Change | Creep | 8 | 7 | To reduce costs and speed time to market there were too few pre-launch product builds performed | 2 | Eur/ME | Prod. Dev. | 2014 | February | 550736
3110 | Scope | Change | Creep | 5 | 7 | 1000 hour tests required at project end. Failure half-way (or later) requires fix and restart. | 1 | Asia | Prod. Dev. | 2009 | November | 363095
3111 | Scope | Change | Creep | 21 | 4 | Packaging for a critical white board component was too flimsy to withstand standard shipping stress | 1 | Asia | IT/Solution | 2004 | January | 1128519
3112 | Scope | Change | Creep | 12 | 6 | Test hardware does not work. All tests done manually using extra time and effort. | 0 | Americas | IT/Solution | 2015 | December | 605112
3113 | Scope | Change | Creep | 6 | 7 | Complex system designed in pieces, and integration fails. Redesign is required. | 0 | Americas | IT/Solution | 2016 | January | 148602
3114 | Scope | Change | Creep | 22 | 7 | Unusual usage caused problems in the integration process | 0 | Americas | IT/Solution | 2015 | December | 515944
3115 | Scope | Change | Dependency | 15 | 9 | Two related projects failed to successfully synchronize and missed a release | 1 | Asia | IT/Solution | 2002 | March | 836700
3116 | Scope | Change | Gap | 13 | 8 | Project was longer than necessary because one team insisted on doing "half" literally, even though the effort resulting was very lopsided. | 2 | Eur/ME | IT/Solution | 2014 | May | 627055
3117 | Scope | Change | Gap | 5 | 3 | Major failure in the Validation tests | 3 | Africa | IT/Solution | 2004 | November | 264450
3118 | Scope | Change | Gap | 5 | 7 | After the upgrade was released, issues with the software were discovered | 2 | Eur/ME | IT/Solution | 2014 | December | 327240
3119 | Scope | Change | Gap | 19 | 2 | A patch breaks other functionality in the system and is backed out until the next maintenance window | 3 | Africa | Prod. Dev. | 2012 | September | 1106864
3120 | Scope | Change | Gap | 11 | 5 | Poorly implemented web tool causes ongoing support issues | 2 | Eur/ME | IT/Solution | 2010 | August | 562078
3121 | Scope | Change | Gap | 16 | 3 | Problems detected and solution developed based on presumed root cause. Cause was actually something else and led to major slip. | 3 | Africa | Prod. Dev. | 2004 | May | 750272
3122 | Scope | Change | Gap | 6 | 2 | During the printing test, the printer couldn’t interpret the incoming file | 3 | Africa | IT/Solution | 2006 | October | 321366
3123 | Scope | Change | Gap | 16 | 3 | insufficient staff to carry out the implementation plan | 2 | Eur/ME | IT/Solution | 2004 | March | 1216336
3124 | Scope | Change | Gap | 5 | 5 | Reduced staff with a bare minimum budget was assigned to the project | 3 | Africa | IT/Solution | 2019 | September | 260285
3125 | Scope | Change | Gap | 12 | 7 | Sponsor fails to provide money | 3 | Africa | Prod. Dev. | 2010 | September | 595800
3126 | Scope | Change | Gap | 10 | 7 | Project needs $150K per month in supplies but limit is $100K, which delayed progress. | 0 | Americas | IT/Solution | 2004 | December | 668040
3127 | Scope | Defect | Hardware | 15 | 6 | The travel budget for the project was cut and led to inefficient long-distance collaboration | 1 | Asia | Prod. Dev. | 2012 | May | 681810
3128 | Scope | Defect | Integration | 18 | 5 | Chronically understaffed business environment | 3 | Africa | Prod. Dev. | 2003 | September | 559800
3129 | Scope | Defect | Software | 11 | 4 | Severe learning curve of somestaff slowed progress | 2 | Eur/ME | Prod. Dev. | 2012 | June | 982300
3130 | Scope | Defect | Software | 17 | 3 | Not enough staff to cover the load and failure to prioritize | 1 | Asia | IT/Solution | 2013 | January | 1111222
3131 | Scope | Defect | Software | 15 | 1 | Process change led to recertification requirements and delay | 2 | Eur/ME | IT/Solution | 2010 | November | 1491120
3132 | Scope | Defect | Software | 17 | 6 | Developer added a new routine that was not fully tested, and release window passed | 2 | Eur/ME | IT/Solution | 2017 | June | 555679
3133 | Resource | Money | Limitation | 15 | 1 | A team of 5 contract engineers were let go | 1 | Asia | IT/Solution | 2011 | June | 619125
3134 | Resource | Money | Limitation | 20 | 9 | Insufficient amount of test material was sent to the contract lab | 0 | Americas | IT/Solution | 2007 | March | 263660
3135 | Resource | Money | Limitation | 7 | 7 | System expanded to into include two more cities for political reasons | 0 | Americas | IT/Solution | 2010 | January | 463855
3136 | Resource | Money | Limitation | 5 | 9 | Poor scoping led to scope creep | 2 | Eur/ME | Prod. Dev. | 2012 | December | 245010
3137 | Resource | Money | Limitation | 11 | 4 | Insufficient resources assigned to the project | 0 | Americas | Prod. Dev. | 2014 | February | 205095
3138 | Scope | Defect | Software | 13 | 9 | For cost reasons, critical work was transferred out of Japan | 2 | Eur/ME | IT/Solution | 2007 | September | 340327
3139 | Scope | Defect | Hardware | 19 | 8 | Mixture given to test animals caused too many side-effects | 1 | Asia | IT/Solution | 2016 | June | 1105173
3140 | Resource | Outsourcing | Late or poor output | 16 | 9 | Existing systems were removed from market, requiring changes for new model | 0 | Americas | Prod. Dev. | 2010 | January | 603072
3141 | Resource | People | Motivation | 11 | 9 | Additional three manufacturing sites meant using another server for this project | 2 | Eur/ME | IT/Solution | 2019 | March | 908578
3142 | Resource | People | Loss | 9 | 5 | Procurement is done based on out-of date drawings | 3 | Africa | Prod. Dev. | 2005 | January | 659133
3143 | Scope | Change | Gap | 14 | 5 | insufficient staff to carry out the implementation plan | 1 | Asia | Prod. Dev. | 2016 | May | 1195236
3144 | Resource | Money | Limitation | 21 | 4 | Lack of communication and trust between locations | 2 | Eur/ME | IT/Solution | 2018 | July | 396375
3145 | Resource | People | Late start | 22 | 7 | The statement of work was not as specific as the authors thought and the deliverable from the vendor did not function as expected | 0 | Americas | IT/Solution | 2014 | February | 1715230
3146 | Scope | Defect | Software | 19 | 7 | Equipment was unreliable and caused slips | 2 | Eur/ME | IT/Solution | 2014 | February | 940671
3147 | Schedule | Delay | Parts | 20 | 7 | Testing facilities were too low-tech to verify automated systems | 3 | Africa | IT/Solution | 2012 | December | 956280
3148 | Resource | People | Queuing | 6 | 4 | Development team had insufficient resources assigned to the project | 0 | Americas | IT/Solution | 2006 | April | 79248
3149 | Scope | Change | Gap | 12 | 7 | At year-end, engineer in Germenay had to take accrued vacation time | 0 | Americas | IT/Solution | 2002 | March | 425304
3150 | Schedule | Dependency | Infrastructure | 15 | 8 | A component needed for necropsy data analysis failed | 0 | Americas | Prod. Dev. | 2016 | August | 210840
3151 | Schedule | Estimates | Learning | 7 | 2 | Some tasks assigned only by function; no one actually working on them. | 1 | Asia | IT/Solution | 2014 | November | 140728
3152 | Scope | Change | Creep | 13 | 2 | Complex feature added that was not requested by the customer | 0 | Americas | IT/Solution | 2006 | November | 258804
3153 | Scope | Change | Creep | 22 | 3 | Additional deliverable added late | 2 | Eur/ME | Prod. Dev. | 2001 | September | 1091508
3154 | Scope | Change | Gap | 6 | 2 | Editing text worsened product quality and necessitated retranslation | 0 | Americas | IT/Solution | 2008 | March | 579168
3155 | Schedule | Delay | Decision | 12 | 4 | Project did not have the buy-in for staffing from other departmens | 1 | Asia | Prod. Dev. | 2001 | October | 312036
3156 | Schedule | Delay | Parts | 6 | 9 | Task supposed to be done by an outside company was completed late | 0 | Americas | Prod. Dev. | 2003 | October | 466974
3157 | Schedule | Estimates | Judgment | 9 | 4 | Staff lost to customer hot site | 3 | Africa | IT/Solution | 2013 | January | 276300
3158 | Scope | Change | Creep | 6 | 9 | Disaster recovery tests delayed at project end; hardware needed tied up with an actual customer problem. | 1 | Asia | IT/Solution | 2013 | July | 532374
3159 | Scope | Change | Gap | 15 | 6 | Test systems shared by 6 projects; queuing and delays common. | 1 | Asia | Prod. Dev. | 2006 | October | 289380
3160 | Scope | Change | Gap | 22 | 9 | New equipment critical to the success of the product quality was installed late | 0 | Americas | Prod. Dev. | 2012 | May | 1252086
3161 | Resource | People | Queuing | 16 | 2 | New requirements that mandated all products that have yet to ship to market to be re-tested | 1 | Asia | IT/Solution | 2018 | October | 1464368
3162 | Resource | People | Temp loss | 13 | 1 | Clear delegation of work done by project team and by customer never done. Confusion led to delays. | 0 | Americas | IT/Solution | 2018 | November | 475423
3163 | Schedule | Delay | Decision | 17 | 9 | Firewall changes can take 25 days, estimates are capped at 15 | 0 | Americas | Prod. Dev. | 2007 | March | 578272
3164 | Schedule | Delay | Parts | 16 | 3 | Mismatch in documents and expectations. Adjustments required lots of additional work. | 0 | Americas | Prod. Dev. | 2011 | November | 1421296
3165 | Schedule | Dependency | Infrastructure | 11 | 4 | Integrating course content that does not comply with LMS specifications | 2 | Eur/ME | IT/Solution | 2019 | January | 399124
3166 | Scope | Change | Creep | 21 | 5 | Engineer responsible to program the ISDN router called in sick | 2 | Eur/ME | IT/Solution | 2014 | October | 232785
3167 | Scope | Change | Dependency | 8 | 7 | Documentation from the researcher lacks crucial information | 1 | Asia | IT/Solution | 2012 | November | 359856
3168 | Resource | Outsourcing | Late or poor output | 8 | 6 | Performance issues surfaced following migration | 0 | Americas | Prod. Dev. | 2001 | August | 495648
3169 | Schedule | Delay | Hardware | 20 | 9 | Delay in contract signing because legal had a higher priority contract to review | 2 | Eur/ME | IT/Solution | 2018 | August | 1161040
3170 | Scope | Change | Creep | 6 | 9 | Contractors are not sufficiently skilled nor motivated | 1 | Asia | IT/Solution | 2007 | November | 138396
3171 | Scope | Change | Creep | 5 | 7 | Key contributor injured in a car accident | 0 | Americas | Prod. Dev. | 2004 | September | 398870
3172 | Resource | Money | Limitation | 11 | 3 | Employees terminated for sexual harassment | 1 | Asia | IT/Solution | 2018 | July | 819159
3173 | Resource | Outsourcing | Delayed start | 6 | 6 | Key staff member assigned to project was changed 3 times during the project | 1 | Asia | IT/Solution | 2009 | July | 537540
3174 | Resource | Outsourcing | Late or poor output | 17 | 4 | Due to a re-organization the team lost essential resources | 2 | Eur/ME | IT/Solution | 2008 | February | 1529388
3175 | Resource | Outsourcing | Late or poor output | 20 | 7 | Initial ubjects for tests did not meet project requirements | 1 | Asia | IT/Solution | 2009 | October | 237040
3176 | Resource | Outsourcing | Late or poor output | 6 | 1 | Manufacutring group did not have the capcity to produce a critical new enzyme | 0 | Americas | IT/Solution | 2007 | February | 224670
3177 | Resource | Outsourcing | Late or poor output | 6 | 4 | State government overtime and holiday compensation rules just before a new payroll application goes live | 0 | Americas | IT/Solution | 2005 | October | 367314
3178 | Resource | People | Late start | 22 | 2 | Mixture given to test animals caused too many side-effects | 1 | Asia | IT/Solution | 2015 | January | 953854
3179 | Resource | People | Loss | 10 | 4 | Data conversion problems made the implementation of a new system dependent on manual reentry of data | 2 | Eur/ME | IT/Solution | 2015 | January | 164310
3180 | Resource | People | Motivation | 10 | 9 | IT department was underfunded and had insuffient staff | 1 | Asia | Prod. Dev. | 2008 | October | 921250
3181 | Resource | People | Queuing | 19 | 2 | Staffing was not sufficient to complete all assigned tasks with deadlines | 0 | Americas | Prod. Dev. | 2004 | May | 1325763
3182 | Resource | People | Queuing | 14 | 9 | Staff cutbacks (and dropped scope as well) | 2 | Eur/ME | Prod. Dev. | 2016 | March | 717542
3183 | Resource | People | Queuing | 13 | 8 | Defect discovered after delivery to customer | 0 | Americas | Prod. Dev. | 2008 | November | 361738
3184 | Resource | People | Queuing | 14 | 3 | Approvals were late so campaign could be pushed out of the Sales Team | 0 | Americas | IT/Solution | 2012 | March | 409514
3185 | Resource | People | Queuing | 22 | 3 | State government overtime and holiday compensation rules just before a new payroll application goes live | 0 | Americas | IT/Solution | 2005 | February | 511544
3186 | Resource | People | Queuing | 20 | 5 | Staffing was not sufficient to complete all assigned tasks with deadlines | 1 | Asia | IT/Solution | 2004 | December | 729960
3187 | Resource | People | Temp loss | 22 | 7 | Key engineer was pulled out of the team to work on another project. | 0 | Americas | Prod. Dev. | 2011 | May | 820380
3188 | Resource | People | Temp loss | 18 | 9 | Partner misses bimaontly shipping deadline | 2 | Eur/ME | Prod. Dev. | 2004 | September | 1644606
3189 | Resource | People | Temp loss | 16 | 7 | Continuous revisions to the specifications for a building remodel | 2 | Eur/ME | IT/Solution | 2008 | August | 1131312
3190 | Resource | People | Temp loss | 15 | 2 | Website wasn't as simple as it iniitally seemed | 0 | Americas | IT/Solution | 2003 | October | 222600
3191 | Resource | People | Temp loss | 21 | 9 | Redesign required late in printer project to meet paper speed goals. OT and delays. | 2 | Eur/ME | Prod. Dev. | 2003 | October | 1971123
3192 | Resource | People | Temp loss | 5 | 2 | New specs provided and priorities changed in the middle of the project | 0 | Americas | Prod. Dev. | 2004 | February | 269840
3193 | Schedule | Delay | Decision | 13 | 2 | Purchased electronic component failed with a very high rate of 30% and had to be replaced with a designed one | 0 | Americas | IT/Solution | 2016 | July | 1190865
3194 | Schedule | Delay | Decision | 8 | 4 | Lack of communication with the project team in Germany | 1 | Asia | IT/Solution | 2016 | January | 387112
3195 | Schedule | Delay | Hardware | 13 | 7 | Chp failed due to a hardware design issue and had to be redesigned and refabricated | 0 | Americas | IT/Solution | 2005 | October | 751166
3196 | Schedule | Delay | Hardware | 12 | 7 | Defects discovered in late testing | 0 | Americas | IT/Solution | 2014 | January | 137640
3197 | Schedule | Delay | Hardware | 15 | 2 | Feedback from South Korea delayed due to a few months of sick leave by product manager | 1 | Asia | IT/Solution | 2002 | December | 503280
3198 | Schedule | Delay | Hardware | 8 | 3 | Multiple projects competing for a limited staff to do the work leads to interruptions and delays | 2 | Eur/ME | IT/Solution | 2013 | August | 799688
3199 | Schedule | Delay | Hardware | 14 | 7 | System only partly specified until near the end of the project. | 0 | Americas | Prod. Dev. | 2011 | March | 1297212
3200 | Schedule | Delay | Information | 8 | 5 | Key contriobutor quit, and there was insufficient information transfer | 0 | Americas | Prod. Dev. | 2005 | July | 371256
3201 | Schedule | Delay | Information | 12 | 8 | People who require training miss classes; more classes required. | 0 | Americas | IT/Solution | 2012 | March | 759396
3202 | Schedule | Delay | Information | 16 | 3 | Space unavailable; needed to implement in old space | 1 | Asia | Prod. Dev. | 2013 | August | 1010064
3203 | Schedule | Delay | Parts | 12 | 6 | Revision to the story board is required | 0 | Americas | IT/Solution | 2019 | November | 638808
3204 | Schedule | Delay | Parts | 19 | 2 | Revisions required after review | 2 | Eur/ME | Prod. Dev. | 2017 | November | 832523
3205 | Schedule | Delay | Parts | 10 | 5 | Expert developer left the company | 0 | Americas | IT/Solution | 2007 | September | 200590
3206 | Schedule | Delay | Parts | 16 | 1 | "Overnight" shipping takes extra time in big co. mailrooms | 0 | Americas | IT/Solution | 2016 | July | 1238272
3207 | Schedule | Delay | Parts | 8 | 5 | Operating system selected (LINUX) has inadequate support for timely solution of conversion and delivery problems. | 0 | Americas | IT/Solution | 2016 | April | 650224
3208 | Schedule | Delay | Parts | 19 | 1 | Iadequate analysis prior to iniitating development efforts | 1 | Asia | IT/Solution | 2019 | December | 1839637
3209 | Schedule | Delay | Parts | 21 | 6 | Final burn-in test interrupted by faulty oven. Replacement and retest took extra time. | 0 | Americas | IT/Solution | 2016 | October | 913311
3210 | Schedule | Dependency | Project | 5 | 4 | RFP Process was flawed and created delays | 2 | Eur/ME | Prod. Dev. | 2005 | October | 465445
3211 | Schedule | Dependency | Project | 12 | 2 | High turnover led to training and low productivity throughout project. | 2 | Eur/ME | Prod. Dev. | 2017 | July | 163800
3212 | Schedule | Dependency | Project | 15 | 3 | Changes in contracts and scope not managed well | 0 | Americas | Prod. Dev. | 2001 | August | 1115595
3213 | Schedule | Estimates | Judgment | 5 | 5 | On this long project, turnover was high on project team and at customer. | 0 | Americas | Prod. Dev. | 2001 | May | 491040
3214 | Schedule | Estimates | Judgment | 22 | 3 | Process improvement project has low priority and high turnover. | 2 | Eur/ME | IT/Solution | 2011 | August | 352880
3215 | Scope | Change | Creep | 8 | 8 | Cardiologist on the project team resigned and had to be replaced | 0 | Americas | IT/Solution | 2015 | November | 636016
3216 | Scope | Change | Creep | 7 | 5 | Key programmer resigned | 0 | Americas | Prod. Dev. | 2013 | May | 126210
3217 | Scope | Change | Creep | 19 | 2 | Approvals were late so campaign could be pushed out of the Sales Team | 1 | Asia | Prod. Dev. | 2001 | May | 1504819
3218 | Scope | Change | Creep | 10 | 2 | Project has customer info, but also needs supplier data. Project to provide this is delayed. | 0 | Americas | Prod. Dev. | 2001 | May | 217170
3219 | Scope | Change | Creep | 20 | 5 | Project had to wait until all data collection was finished before starting analysis | 2 | Eur/ME | Prod. Dev. | 2018 | March | 1746140
3220 | Scope | Change | Creep | 18 | 8 | Test run is rejected or lost | 1 | Asia | Prod. Dev. | 2005 | May | 1570068
3221 | Scope | Change | Creep | 11 | 6 | Adopting the selected system required several new pieces of major software | 1 | Asia | Prod. Dev. | 2017 | February | 294437
3222 | Scope | Change | Dependency | 20 | 2 | High attrition in positions requiring unique technical training | 0 | Americas | Prod. Dev. | 2011 | May | 937260
3223 | Scope | Change | Dependency | 15 | 3 | Development team didn’t have the expertise to implement the modules | 0 | Americas | Prod. Dev. | 2001 | November | 986070
3224 | Scope | Change | Dependency | 20 | 8 | Late inclusions resulted in change orders and delay | 2 | Eur/ME | Prod. Dev. | 2007 | November | 608320
3225 | Scope | Change | Gap | 18 | 3 | New product features were added at every weekly meeting and stage review | 1 | Asia | Prod. Dev. | 2009 | June | 1540692
3226 | Scope | Change | Gap | 8 | 7 | Business environment shifts forcing project changes, | 0 | Americas | IT/Solution | 2015 | April | 363208
3227 | Scope | Change | Gap | 11 | 2 | The scope was not clearly defined | 2 | Eur/ME | Prod. Dev. | 2016 | July | 301730
3228 | Scope | Change | Gap | 21 | 5 | Requesters failed to understand the complexity and did not make their wishes clear | 0 | Americas | Prod. Dev. | 2003 | July | 1685754
3229 | Scope | Change | Gap | 6 | 4 | Project based on standards still in draft form. Several options are possible, but project is only staffed to pursue one. | 1 | Asia | Prod. Dev. | 2009 | April | 317394
3230 | Scope | Defect | Hardware | 13 | 9 | The Product Manager never told the team what the customer was asking for | 0 | Americas | Prod. Dev. | 2018 | March | 875927
3231 | Scope | Defect | Hardware | 21 | 7 | Project team was not aware that the new release would have a new UI | 0 | Americas | Prod. Dev. | 2008 | October | 743421
3232 | Scope | Defect | Hardware | 5 | 5 | Delay due to testing requirements uncovered late and shifting priorities | 0 | Americas | Prod. Dev. | 2009 | November | 314325
3233 | Scope | Defect | Hardware | 6 | 6 | Supplier code changes resulted in major backlog | 2 | Eur/ME | Prod. Dev. | 2019 | December | 179394
3234 | Scope | Defect | Hardware | 11 | 2 | Technology used for design is unstable | 0 | Americas | Prod. Dev. | 2018 | December | 213224
3235 | Scope | Defect | Hardware | 21 | 9 | Conversion from legacy system to SAP has multiple modules that cause unanticipated problems leading to delays of 3 to 10 days each to fix. | 2 | Eur/ME | IT/Solution | 2017 | April | 2033829
3236 | Scope | Defect | Hardware | 17 | 1 | “Off the shelf” software package was to support migration from mainframe to client-server application. Lots of unexpected customization required. | 2 | Eur/ME | Prod. Dev. | 2017 | June | 940389
3237 | Scope | Defect | Software | 5 | 1 | Too few staff members | 0 | Americas | IT/Solution | 2017 | January | 214260
3238 | Scope | Defect | Software | 15 | 6 | For cost reasons, critical work was transferred out of Japan | 0 | Americas | IT/Solution | 2002 | August | 1087965
3239 | Scope | Defect | Software | 12 | 6 | The contract indicated state of the art retrofit materials; differing meaning over 2 years | 0 | Americas | IT/Solution | 2004 | March | 154440
3240 | Scope | Defect | Software | 10 | 6 | Extension of scope in Japan was not managed or controlled well | 2 | Eur/ME | IT/Solution | 2006 | October | 802840
3241 | Scope | Defect | Software | 8 | 7 | Redesign required late in printer project to meet print quality goals. Major slip. | 0 | Americas | IT/Solution | 2001 | November | 657160
3242 | Scope | Defect | Software | 15 | 8 | Failure to finalize Product Definition Document requirements | 1 | Asia | Prod. Dev. | 2004 | May | 765750
3243 | Schedule | Delay | Hardware | 8 | 5 | Scope of the project increased following final requirements review | 2 | Eur/ME | Prod. Dev. | 2017 | June | 617816
3244 | Scope | Change | Gap | 7 | 9 | There were gaps in the functional document | 0 | Americas | Prod. Dev. | 2012 | June | 459578
3245 | Resource | Money | Limitation | 6 | 1 | Virus destroys interface software in two required languages, requiring rework to replace them. | 0 | Americas | IT/Solution | 2002 | June | 404832
3246 | Scope | Change | Creep | 9 | 9 | Components delayed, and contractors were committed to other work and were only able to work part-time | 0 | Americas | IT/Solution | 2006 | December | 874269
3247 | Scope | Change | Gap | 20 | 6 | Process improvement project has low priority and high turnover. | 0 | Americas | IT/Solution | 2006 | September | 1547920
3248 | Resource | Money | Limitation | 7 | 3 | Processes were changed and made more complex late in the project | 0 | Americas | IT/Solution | 2010 | March | 429296
3249 | Schedule | Delay | Information | 7 | 5 | Incorrect decimal pay rate did not reflect the true and accurate pay | 2 | Eur/ME | Prod. Dev. | 2003 | March | 434700
3250 | Resource | Outsourcing | Late or poor output | 13 | 5 | Test hardware does not work. All tests done manually using extra time and effort. | 2 | Eur/ME | Prod. Dev. | 2011 | February | 1112371
3251 | Resource | Money | Limitation | 6 | 5 | During the printing test, the printer couldn’t interpret the incoming file | 2 | Eur/ME | Prod. Dev. | 2019 | July | 395190
3252 | Resource | Money | Limitation | 6 | 3 | Delayed start of work due to negotiation of contract. | 1 | Asia | Prod. Dev. | 2008 | October | 89886
3253 | Scope | Change | Gap | 16 | 1 | Company underestimated the scope of the project | 0 | Americas | IT/Solution | 2004 | September | 259264
3254 | Resource | People | Loss | 14 | 3 | Inadequate staffing | 2 | Eur/ME | IT/Solution | 2014 | January | 589554
3255 | Resource | People | Late start | 19 | 4 | There were not enough study directors to conduct all the studies needed | 2 | Eur/ME | IT/Solution | 2009 | December | 1198881
3256 | Resource | People | Loss | 16 | 4 | Software engineers, not technicians skilled in the work, were used to complete product testing | 1 | Asia | IT/Solution | 2016 | July | 1009328
3257 | Schedule | Delay | Parts | 6 | 6 | Key engineer on project leaves the company | 0 | Americas | Prod. Dev. | 2011 | August | 323622
3258 | Schedule | Estimates | Learning | 20 | 3 | Specifications poorly defined until late in the project. | 1 | Asia | Prod. Dev. | 2018 | December | 1365760
3259 | Scope | Change | Creep | 20 | 5 | Scope change adding new categories and fees | 2 | Eur/ME | Prod. Dev. | 2005 | December | 1590900
3260 | Scope | Change | Creep | 20 | 6 | Components do not work as documented. Replacements and software workarounds required. | 0 | Americas | Prod. Dev. | 2016 | December | 1565420
3261 | Scope | Defect | Hardware | 9 | 2 | Key supplier lost in the middle of a project | 1 | Asia | Prod. Dev. | 2002 | August | 423126
3262 | Resource | Money | Limitation | 14 | 9 | Parts shipped by sea from Asia, not air. | 1 | Asia | Prod. Dev. | 2015 | October | 1020810
3263 | Scope | Change | Gap | 11 | 6 | Commitment given, but deliverables were late. | 0 | Americas | Prod. Dev. | 2016 | January | 225115
3264 | Schedule | Estimates | Learning | 13 | 6 | Unrealistic compressed timeline | 1 | Asia | IT/Solution | 2014 | November | 1036178
3265 | Scope | Change | Gap | 8 | 6 | Specifications incomplete and late. Delayed project start. | 2 | Eur/ME | Prod. Dev. | 2002 | July | 743264
3266 | Resource | People | Loss | 11 | 9 | Resistance of the business stakeholders to reach consensus on the project’s scope | 2 | Eur/ME | Prod. Dev. | 2019 | January | 456401
3267 | Resource | People | Queuing | 19 | 3 | Outsource partner replaced several key people on team | 0 | Americas | Prod. Dev. | 2004 | March | 1467655
3268 | Resource | People | Queuing | 15 | 6 | High turnover leads to delays and crisis management. | 0 | Americas | Prod. Dev. | 2012 | June | 1492440
3269 | Schedule | Delay | Hardware | 20 | 6 | Conflict for resources with a higher priority project | 0 | Americas | IT/Solution | 2004 | November | 979620
3270 | Schedule | Dependency | Infrastructure | 15 | 6 | Software engineer was lost to a higher priority project | 2 | Eur/ME | IT/Solution | 2014 | November | 1130640
3271 | Schedule | Dependency | Legal | 9 | 3 | Required server was misplaced in shipping | 1 | Asia | Prod. Dev. | 2005 | August | 452007
3272 | Scope | Change | Creep | 20 | 5 | Kitchen remodel required a seismic upgrade | 0 | Americas | Prod. Dev. | 2002 | January | 1243900
3273 | Scope | Change | Gap | 8 | 7 | System functions well in Germany, but has no German documentation. Delay for translation. | 2 | Eur/ME | IT/Solution | 2013 | March | 664736
3274 | Resource | Money | Limitation | 15 | 4 | Critical task assigned to a heavily booked expert | 0 | Americas | IT/Solution | 2012 | October | 200730
3275 | Resource | Outsourcing | Late or poor output | 20 | 3 | Components delayed, and contractors were committed to other work and were only able to work part-time | 1 | Asia | IT/Solution | 2002 | September | 1511180
3276 | Resource | People | Loss | 13 | 2 | Manager quit his job because of his mother's illness | 0 | Americas | Prod. Dev. | 2001 | July | 1268904
3277 | Resource | People | Queuing | 18 | 3 | Purchased component never delivered (vaporware). Workaround developed by brute force (not high-tech and difficult to support). | 1 | Asia | IT/Solution | 2002 | November | 1280664
3278 | Schedule | Delay | Decision | 5 | 3 | Coordination of the scopes of work between several projects | 2 | Eur/ME | IT/Solution | 2018 | November | 377915
3279 | Schedule | Delay | Decision | 9 | 3 | Insufficient budget and Staff Resources allocated | 2 | Eur/ME | Prod. Dev. | 2002 | March | 756450
3280 | Schedule | Delay | Hardware | 5 | 9 | Poor scoping and missed end-user requirements | 0 | Americas | IT/Solution | 2018 | January | 124835
3281 | Schedule | Dependency | Legal | 7 | 9 | PM had insufficient decision-making authority | 1 | Asia | IT/Solution | 2003 | February | 123151
3282 | Scope | Change | Creep | 5 | 4 | Homeland security has changed Import requirements late | 1 | Asia | IT/Solution | 2013 | May | 450675
3283 | Scope | Change | Creep | 15 | 5 | There was no detailed description of the software deliverable in the project plan | 2 | Eur/ME | IT/Solution | 2004 | August | 913125
3284 | Scope | Change | Dependency | 8 | 8 | Development team didn’t have the expertise to implement the modules | 1 | Asia | IT/Solution | 2010 | June | 91656
3285 | Scope | Change | Gap | 14 | 4 | Key contributor injured in a car accident | 0 | Americas | IT/Solution | 2019 | June | 736736
3286 | Resource | People | Queuing | 5 | 8 | Project leader was transferred to another project | 0 | Americas | IT/Solution | 2017 | January | 107345
3287 | Resource | People | Temp loss | 17 | 6 | Endless debate over choice of three possible approaches for project work | 0 | Americas | Prod. Dev. | 2015 | April | 1640670
3288 | Schedule | Delay | Information | 7 | 6 | Sponsors who knew the system well didn't bother to analyze the impact of rolling out sensitive data to global users without security in place | 0 | Americas | Prod. Dev. | 2007 | August | 236026
3289 | Scope | Change | Dependency | 19 | 3 | A six month conversion period from the date a contract is signed is the norm, but project goal is four months | 0 | Americas | Prod. Dev. | 2012 | November | 407094
3290 | Resource | Money | Limitation | 22 | 1 | Unique data in each region prevented information flow | 0 | Americas | IT/Solution | 2007 | June | 634964
3291 | Resource | Money | Limitation | 20 | 5 | Packaging for a critical white board component was too flimsy to withstand standard shipping stress | 1 | Asia | Prod. Dev. | 2007 | February | 609740
3292 | Resource | Money | Limitation | 7 | 3 | Manufacturing process was not scalable and had to be redesigned | 2 | Eur/ME | IT/Solution | 2009 | August | 74508
3293 | Resource | Money | Limitation | 15 | 4 | Project has funding, but limited staff delays start. | 0 | Americas | IT/Solution | 2005 | April | 957585
3294 | Resource | Outsourcing | Delayed start | 12 | 6 | Lack of funds for travel at launch | 2 | Eur/ME | Prod. Dev. | 2001 | November | 608964
3295 | Resource | Outsourcing | Delayed start | 11 | 5 | Vendor currently has limited capacity and could not hire quickly enough to support this product | 2 | Eur/ME | Prod. Dev. | 2004 | December | 186769
3296 | Resource | Outsourcing | Delayed start | 17 | 8 | Key resource pulled from a high priority project | 0 | Americas | IT/Solution | 2003 | June | 928013
3297 | Resource | Outsourcing | Late or poor output | 5 | 1 | No vacation/time-off estimate planning was done | 0 | Americas | IT/Solution | 2012 | September | 279090
3298 | Resource | Outsourcing | Late or poor output | 14 | 6 | Changing product definition and poor estimation of effort | 2 | Eur/ME | IT/Solution | 2008 | March | 1085770
3299 | Resource | Outsourcing | Late or poor output | 7 | 2 | User specifications not defined until late in the project. | 2 | Eur/ME | IT/Solution | 2007 | March | 502194
3300 | Resource | Outsourcing | Late or poor output | 10 | 8 | Multiple team program with some work not clearly delegated. Assigned and added late. | 1 | Asia | IT/Solution | 2019 | August | 310890
3301 | Resource | Outsourcing | Late or poor output | 5 | 8 | Product developed for multiple platforms, but works only on 2. Delayed to fix some, but others dropped at project end. | 0 | Americas | IT/Solution | 2012 | October | 394135
3302 | Resource | Outsourcing | Late or poor output | 14 | 1 | Lack of initial consensus on the scope | 2 | Eur/ME | IT/Solution | 2014 | October | 1069110
3303 | Resource | Outsourcing | Late or poor output | 7 | 7 | Vendor was inexperienced with relevant equipment | 1 | Asia | Prod. Dev. | 2006 | March | 501466
3304 | Resource | Outsourcing | Late or poor output | 7 | 3 | Metrics required by process improvement project collected and delivered late. | 2 | Eur/ME | Prod. Dev. | 2001 | March | 680414
3305 | Resource | Outsourcing | Late or poor output | 13 | 2 | Changes were approved by the business users without proper testing | 1 | Asia | Prod. Dev. | 2004 | March | 1060449
3306 | Resource | Outsourcing | Late or poor output | 20 | 4 | One week’s analysis is insufficient to capture needed requirements | 0 | Americas | IT/Solution | 2006 | September | 566820
3307 | Resource | Outsourcing | Late or poor output | 21 | 3 | Analysis group not involved in planning meetings | 2 | Eur/ME | IT/Solution | 2011 | July | 1775340
3308 | Resource | Outsourcing | Late or poor output | 13 | 5 | New supplier, extensive start up and coordination issues. | 2 | Eur/ME | IT/Solution | 2007 | November | 1286350
3309 | Resource | Outsourcing | Late or poor output | 10 | 4 | Work from team in Pakistan failed miserably | 0 | Americas | Prod. Dev. | 2001 | March | 548610
3310 | Resource | Outsourcing | Late or poor output | 16 | 2 | Labor union of subcontractor went on stike | 1 | Asia | IT/Solution | 2014 | May | 281920
3311 | Resource | Outsourcing | Late or poor output | 9 | 9 | Expert developer left the company | 0 | Americas | IT/Solution | 2005 | July | 139347
3312 | Resource | Outsourcing | Late or poor output | 13 | 4 | Chief architect quit, and was the only person with critical skills | 2 | Eur/ME | Prod. Dev. | 2003 | January | 1133704
3313 | Resource | Outsourcing | Late or poor output | 11 | 7 | Production partner had a personal issue which brought production to a halt | 1 | Asia | Prod. Dev. | 2011 | September | 302720
3314 | Resource | People | Late start | 17 | 9 | Tests delayed at project end; delayed access to databases | 0 | Americas | IT/Solution | 2002 | May | 795345
3315 | Resource | People | Late start | 20 | 6 | Parts of development team have a 12 hour time difference. Bugs take 2-3 days longer to fix, on average. | 2 | Eur/ME | Prod. Dev. | 2005 | April | 520620
3316 | Resource | People | Late start | 6 | 5 | Cabling estimates too optimistic. | 0 | Americas | IT/Solution | 2017 | July | 502692
3317 | Resource | People | Late start | 17 | 1 | Lack of in-house expertise of the source system | 0 | Americas | IT/Solution | 2011 | October | 1401990
3318 | Resource | People | Loss | 19 | 5 | Database of components had not been updated to current OSHA standards | 0 | Americas | IT/Solution | 2010 | January | 1528417
3319 | Resource | People | Loss | 8 | 3 | Prototype problems excessive; more time to fix than planned. | 0 | Americas | IT/Solution | 2016 | June | 542784
3320 | Resource | People | Loss | 14 | 5 | Scope continuously changed by client | 1 | Asia | IT/Solution | 2003 | December | 447384
3321 | Resource | People | Loss | 18 | 3 | Planning the terms of the agreement and negotiating the contracts took time, making the project begin late | 2 | Eur/ME | IT/Solution | 2007 | August | 253026
3322 | Resource | People | Loss | 15 | 6 | Change requested and agreed to, but supplier ships late and it does not work. | 0 | Americas | IT/Solution | 2017 | September | 945285
3323 | Resource | People | Loss | 9 | 2 | Contaminated specimen for cell culture had to be replaced by the contract organization | 2 | Eur/ME | IT/Solution | 2006 | June | 586593
3324 | Resource | People | Loss | 17 | 1 | Subcontractor failed to understand technology and requirements | 0 | Americas | IT/Solution | 2001 | February | 196554
3325 | Resource | People | Loss | 2 | 7 | Partner on project defaults. | 0 | Americas | IT/Solution | 2019 | February | 183624
3326 | Resource | People | Loss | 23 | 8 | The other company was unable to stick to needed deadlines | 2 | Eur/ME | IT/Solution | 2005 | July | 474237
3327 | Resource | People | Loss | 25 | 2 | People still on prior project | 0 | Americas | IT/Solution | 2002 | July | 1417725
3328 | Resource | People | Motivation | 10 | 4 | Loss of a programmer | 1 | Asia | IT/Solution | 2016 | January | 439140
3329 | Resource | People | Motivation | 24 | 8 | Lack of head count from a 10% company-wide lay-off. | 0 | Americas | IT/Solution | 2003 | March | 2002488
3330 | Resource | People | Queuing | 12 | 9 | Project manger and the Product Manager didn’t get along on an interpersonal level | 0 | Americas | Prod. Dev. | 2001 | June | 702252
3331 | Resource | People | Queuing | 2 | 2 | Key decisions stalled when system architect not available. | 2 | Eur/ME | Prod. Dev. | 2015 | June | 126540
3332 | Resource | People | Queuing | 2 | 7 | One SME for several projects | 2 | Eur/ME | Prod. Dev. | 2009 | February | 168266
3333 | Resource | People | Queuing | 8 | 1 | Peak season begins earlier than expected and impedes project progress | 1 | Asia | Prod. Dev. | 2008 | April | 696392
3334 | Resource | People | Queuing | 5 | 9 | PM had insufficient decision-making authority | 2 | Eur/ME | Prod. Dev. | 2015 | August | 249825
3335 | Resource | People | Queuing | 12 | 4 | Old application to be modified for Y2K had no documentation, and finding original code took weeks. | 2 | Eur/ME | Prod. Dev. | 2010 | May | 584580
3336 | Resource | People | Queuing | 7 | 4 | Delay in the delivery of the test samples | 2 | Eur/ME | IT/Solution | 2018 | July | 307209
3337 | Resource | People | Queuing | 25 | 6 | Building permit was issued late due to roof damages | 0 | Americas | IT/Solution | 2002 | June | 2227875
3338 | Resource | People | Queuing | 12 | 7 | Fix for critical bug was delayed | 0 | Americas | IT/Solution | 2002 | December | 751344
3339 | Resource | People | Temp loss | 12 | 1 | Apartments were sold before construction begins with commitments based on requests, not planning | 1 | Asia | Prod. Dev. | 2014 | June | 1179852
3340 | Resource | People | Temp loss | 21 | 7 | Work was significantly underestimated for the project | 0 | Americas | Prod. Dev. | 2006 | March | 1565676
3341 | Resource | People | Temp loss | 15 | 3 | Effort estimate was significantly under-estimated | 0 | Americas | Prod. Dev. | 2018 | June | 362925
3342 | Resource | People | Temp loss | 4 | 2 | Neophyte project staff lacked system expertise. | 1 | Asia | IT/Solution | 2012 | October | 151756
3343 | Resource | People | Temp loss | 11 | 7 | Lack of expertise, experience and inadequate training | 0 | Americas | IT/Solution | 2013 | June | 647163
3344 | Resource | People | Temp loss | 17 | 1 | Lacked expertise needed for project (SOW too high level | 2 | Eur/ME | Prod. Dev. | 2002 | February | 1216605
3345 | Resource | People | Temp loss | 24 | 8 | Scope expanded during the course of the project | 1 | Asia | IT/Solution | 2017 | December | 2055624
3346 | Resource | People | Temp loss | 6 | 9 | System expanded to into include two more cities for political reasons | 1 | Asia | IT/Solution | 2014 | August | 467412
3347 | Resource | People | Temp loss | 17 | 7 | Poor scoping led to scope creep | 0 | Americas | IT/Solution | 2018 | January | 662643
3348 | Resource | People | Temp loss | 1 | 4 | Project specifications had changed and the material needed during the design phase had to be imported from overseas | 1 | Asia | IT/Solution | 2011 | June | 61150
3349 | Resource | People | Temp loss | 12 | 3 | Adding two more configurations tripled the scope with the same staff | 2 | Eur/ME | IT/Solution | 2017 | October | 125700
3350 | Resource | People | Temp loss | 12 | 9 | Significant growth of scope in renovation project | 1 | Asia | IT/Solution | 2011 | May | 1197576
3351 | Schedule | Delay | Decision | 4 | 5 | Late change required new hardware and 2 phase delivery | 0 | Americas | IT/Solution | 2010 | June | 203696
3352 | Schedule | Delay | Decision | 2 | 8 | Application changed for prospective Chinese customer (who did not buy) | 0 | Americas | Prod. Dev. | 2004 | April | 21432
3353 | Schedule | Delay | Decision | 13 | 3 | Homeland security has changed Import requirements late | 2 | Eur/ME | Prod. Dev. | 2016 | September | 1185236
3354 | Schedule | Delay | Decision | 22 | 2 | There was no detailed description of the software deliverable in the project plan | 2 | Eur/ME | IT/Solution | 2014 | May | 918962
3355 | Schedule | Delay | Decision | 16 | 3 | A mid-project review turned up numerous regulations that were not implemented | 0 | Americas | Prod. Dev. | 2004 | August | 442880
3356 | Schedule | Delay | Decision | 19 | 5 | Significant additional testing required; discovered late | 0 | Americas | Prod. Dev. | 2002 | November | 1787444
3357 | Schedule | Delay | Decision | 16 | 3 | Peak season begun earlier than expected and Higher Freight Volume than usual | 0 | Americas | Prod. Dev. | 2004 | June | 1572304
3358 | Schedule | Delay | Decision | 21 | 4 | Bad choice of billing threshold problems forced system redesign | 1 | Asia | IT/Solution | 2008 | February | 1182258
3359 | Schedule | Delay | Decision | 13 | 2 | Scope initially consisted only of general objectives | 2 | Eur/ME | IT/Solution | 2018 | April | 1160328
3360 | Schedule | Delay | Decision | 25 | 2 | There were gaps in the functional document | 2 | Eur/ME | Prod. Dev. | 2010 | November | 350775
3361 | Schedule | Delay | Decision | 13 | 5 | Problems with manufacturing arose that were not seen in the original analysis | 0 | Americas | Prod. Dev. | 2015 | August | 579891
3362 | Schedule | Delay | Hardware | 24 | 6 | Key requirements were uncovered late | 2 | Eur/ME | Prod. Dev. | 2019 | January | 364272
3363 | Schedule | Delay | Hardware | 3 | 2 | Poor stakeholder buy-in | 1 | Asia | IT/Solution | 2019 | October | 91707
3364 | Schedule | Delay | Hardware | 22 | 2 | Module 1 team did not involve other developers during the initial scoping | 0 | Americas | IT/Solution | 2003 | September | 1050060
3365 | Schedule | Delay | Hardware | 5 | 1 | Defect discovered after delivery to customer | 2 | Eur/ME | IT/Solution | 2008 | January | 84925
3366 | Schedule | Delay | Hardware | 7 | 8 | Late ramp problem. Quadrupled resources and caused major slip. | 0 | Americas | Prod. Dev. | 2007 | December | 605822
3367 | Schedule | Delay | Hardware | 14 | 8 | Defective component--Bugs had to be fixed | 2 | Eur/ME | Prod. Dev. | 2009 | November | 628894
3368 | Schedule | Delay | Hardware | 22 | 4 | System tool could not be scaled to a huge web application | 1 | Asia | IT/Solution | 2001 | December | 1255034
3369 | Schedule | Delay | Hardware | 7 | 2 | Database contains incorrect information and the QA environment is unstable | 0 | Americas | Prod. Dev. | 2004 | November | 371098
3370 | Schedule | Delay | Information | 24 | 5 | Initial code release was a major failure | 0 | Americas | Prod. Dev. | 2009 | July | 1633248
3371 | Schedule | Delay | Information | 5 | 5 | Virus destroys interface software in two required languages, requiring rework to replace them. | 0 | Americas | Prod. Dev. | 2001 | November | 96540
3372 | Schedule | Delay | Information | 13 | 8 | New technology to be used failed to meet the needs | 0 | Americas | Prod. Dev. | 2003 | February | 262236
3373 | Schedule | Delay | Information | 16 | 8 | Purchased application led to performance problems. | 0 | Americas | Prod. Dev. | 2019 | November | 188816
3374 | Schedule | Delay | Information | 9 | 1 | Internal resources were not available on a full time basis | 2 | Eur/ME | IT/Solution | 2008 | April | 740682
3375 | Schedule | Delay | Information | 22 | 3 | Severe funding cutbacks (66% of project team) | 0 | Americas | IT/Solution | 2012 | March | 882222
3376 | Schedule | Delay | Information | 1 | 6 | Insufficient resources assigned to the project | 2 | Eur/ME | Prod. Dev. | 2012 | August | 57610
3377 | Schedule | Delay | Information | 3 | 5 | Project Budget was restricted to the bare minimum estimated | 0 | Americas | IT/Solution | 2019 | August | 212229
3378 | Schedule | Delay | Information | 21 | 1 | Contract had no input from project team and few defined specs. Changes poorly managed and project was very late. | 0 | Americas | IT/Solution | 2003 | January | 299691
3379 | Schedule | Delay | Parts | 10 | 8 | The project team agreed to new requirements; unfortunately, some of the changes promised were not even possible | 1 | Asia | IT/Solution | 2005 | December | 777760
3380 | Schedule | Delay | Parts | 20 | 7 | In UAT testing, a fatal flaw sent the deliverable back to development | 0 | Americas | Prod. Dev. | 2010 | April | 470220
3381 | Schedule | Delay | Parts | 10 | 1 | Goal of 90% participation in study is proved infeasible | 0 | Americas | IT/Solution | 2019 | July | 763780
3382 | Schedule | Delay | Parts | 8 | 9 | 75% of the requirements were unknowninitially to the project staff | 0 | Americas | IT/Solution | 2019 | August | 149080
3383 | Schedule | Delay | Parts | 16 | 7 | Serbian Developers took longer than expected to complete the project | 0 | Americas | Prod. Dev. | 2019 | January | 933936
3384 | Schedule | Delay | Parts | 10 | 3 | Effort estimate was significantly under-estimated | 1 | Asia | Prod. Dev. | 2011 | June | 632470
3385 | Schedule | Delay | Parts | 13 | 5 | Cardiologist on the project team resigned and had to be replaced | 1 | Asia | IT/Solution | 2018 | February | 1221740
3386 | Schedule | Delay | Parts | 14 | 6 | Key programmer resigned | 0 | Americas | IT/Solution | 2006 | November | 1234198
3387 | Schedule | Delay | Parts | 9 | 4 | Late inclusions resulted in change orders and delay | 1 | Asia | Prod. Dev. | 2015 | January | 147501
3388 | Schedule | Delay | Parts | 23 | 2 | Manufacutring group did not have the capcity to produce a critical new enzyme | 2 | Eur/ME | Prod. Dev. | 2018 | May | 1326479
3389 | Schedule | Delay | Parts | 20 | 1 | Executive director stayed two months and then left | 1 | Asia | IT/Solution | 2003 | March | 906400
3390 | Schedule | Delay | Parts | 15 | 5 | Half way through the project three of the engineers had to return to China due to visa issues | 2 | Eur/ME | Prod. Dev. | 2007 | December | 1487040
3391 | Schedule | Delay | Parts | 26 | 7 | Solution project priced "to win" and had few details on work; led to big losses and delays. | 2 | Eur/ME | Prod. Dev. | 2005 | August | 1858116
3392 | Schedule | Delay | Parts | 1 | 3 | Requirements document for a new database system were not specific enough regarding user interface details | 0 | Americas | IT/Solution | 2010 | September | 93236
3393 | Schedule | Delay | Parts | 9 | 8 | Key telecom requirement detected late | 2 | Eur/ME | Prod. Dev. | 2004 | October | 581904
3394 | Schedule | Dependency | Infrastructure | 26 | 6 | Need to upgrade detected only at project end | 2 | Eur/ME | Prod. Dev. | 2003 | March | 2357602
3395 | Schedule | Dependency | Infrastructure | 5 | 5 | Negotiation and training on a new tool took more time than planned | 2 | Eur/ME | IT/Solution | 2003 | May | 329505
3396 | Schedule | Dependency | Infrastructure | 13 | 6 | Sponsor agreed to specifications on door, loading docks, structural supports etc that impeded efficient work flows | 0 | Americas | Prod. Dev. | 2005 | August | 285064
3397 | Schedule | Dependency | Infrastructure | 14 | 5 | Half way through the upgrade; the new processor failed | 0 | Americas | IT/Solution | 2005 | August | 667478
3398 | Schedule | Dependency | Infrastructure | 21 | 7 | Loss of a key person | 2 | Eur/ME | IT/Solution | 2019 | June | 1512966
3399 | Schedule | Dependency | Infrastructure | 16 | 8 | Last minute infrastructure changes and conflict with another deployment | 2 | Eur/ME | IT/Solution | 2006 | March | 242800
3400 | Schedule | Dependency | Legal | 8 | 6 | Excessive challenge of initiating a project in different time zones | 2 | Eur/ME | IT/Solution | 2013 | February | 785560
3401 | Schedule | Dependency | Legal | 17 | 2 | Subcontractor overbooked; not available when needed | 0 | Americas | IT/Solution | 2010 | May | 1200948
3402 | Schedule | Dependency | Project | 7 | 3 | 2 key team members lost for a time because of illness | 1 | Asia | Prod. Dev. | 2002 | February | 76055
3403 | Schedule | Dependency | Project | 2 | 9 | Loss of key members of a project team in an already constrained project. | 2 | Eur/ME | Prod. Dev. | 2008 | July | 75170
3404 | Schedule | Dependency | Project | 15 | 7 | The development team in Pakistan misinterpreted a number of req'ts | 2 | Eur/ME | IT/Solution | 2005 | July | 1472775
3405 | Schedule | Dependency | Project | 13 | 2 | Supplier failure, inputs late and inadequate | 2 | Eur/ME | IT/Solution | 2011 | August | 638209
3406 | Schedule | Dependency | Project | 13 | 4 | Key people resigned, leaving too few to complete project and training on time | 0 | Americas | IT/Solution | 2018 | August | 654654
3407 | Schedule | Dependency | Project | 8 | 8 | The test capabilities constitute a bottleneck late in release cycles. | 0 | Americas | IT/Solution | 2007 | July | 662368
3408 | Schedule | Estimates | Deadline | 8 | 3 | Reorganization during product ramp creates chaos and ownership problems. | 1 | Asia | IT/Solution | 2009 | April | 717704
3409 | Schedule | Estimates | Judgment | 1 | 9 | Problems getting timely management decisions. | 0 | Americas | IT/Solution | 2004 | September | 60093
3410 | Schedule | Estimates | Judgment | 15 | 5 | fittings and assemblies were not up to project standards | 1 | Asia | IT/Solution | 2003 | April | 986295
3411 | Schedule | Estimates | Judgment | 14 | 9 | Process reliability was too low and required a new component to work | 0 | Americas | IT/Solution | 2013 | May | 390978
3412 | Schedule | Estimates | Judgment | 24 | 1 | Chef quit two days before the café was scheduled to open | 1 | Asia | Prod. Dev. | 2016 | February | 412224
3413 | Schedule | Estimates | Judgment | 3 | 3 | Key contributor out ill at critical time. | 0 | Americas | Prod. Dev. | 2013 | April | 256578
3414 | Schedule | Estimates | Judgment | 1 | 4 | Shipping documents not filled in correctly | 1 | Asia | IT/Solution | 2018 | October | 18764
3415 | Schedule | Estimates | Judgment | 16 | 2 | PM did not take the time to determine what the move entailed | 2 | Eur/ME | Prod. Dev. | 2015 | January | 1344384
3416 | Schedule | Estimates | Judgment | 19 | 9 | Subcontracted work failed to meet client's criteria | 0 | Americas | Prod. Dev. | 2003 | May | 1799566
3417 | Schedule | Estimates | Learning | 26 | 8 | Serbian Developers took longer than expected to complete the project | 0 | Americas | IT/Solution | 2007 | January | 1571024
3418 | Schedule | Estimates | Learning | 16 | 9 | Expert Cardiologist no longer available | 1 | Asia | Prod. Dev. | 2011 | March | 708400
3419 | Schedule | Estimates | Learning | 17 | 1 | Sudden exit of the primary developer | 0 | Americas | IT/Solution | 2004 | May | 1338665
3420 | Schedule | Estimates | Learning | 21 | 8 | Product owner having unique knowledge left the company | 0 | Americas | IT/Solution | 2010 | January | 1323168
3421 | Scope | Change | Creep | 9 | 5 | Several employees had to take a leave of absence due to a family emergency | 0 | Americas | Prod. Dev. | 2019 | June | 719100
3422 | Scope | Change | Creep | 11 | 2 | Stakeholders were numerous and unable to come to a timely decision | 1 | Asia | Prod. Dev. | 2008 | September | 1048630
3423 | Scope | Change | Creep | 8 | 9 | Merging of multiple standards is needed to support reorganization. Lack of a new, common definition delayed the project to convert data. | 0 | Americas | Prod. Dev. | 2019 | December | 799736
3424 | Scope | Change | Creep | 20 | 6 | Insufficient amount of test material was sent to the contract lab | 1 | Asia | Prod. Dev. | 2011 | December | 1451340
3425 | Scope | Change | Creep | 12 | 8 | Team did not break down the processes enough to clearly identify each step | 0 | Americas | Prod. Dev. | 2003 | May | 324924
3426 | Scope | Change | Creep | 2 | 6 | Poor scoping and missed end-user requirements | 1 | Asia | Prod. Dev. | 2005 | July | 165684
3427 | Scope | Change | Creep | 12 | 9 | Some countries provided incomplete requirements | 1 | Asia | IT/Solution | 2005 | October | 646908
3428 | Scope | Change | Creep | 1 | 8 | Testing requierments poorly defined, so functionality deferred to phase 2 | 2 | Eur/ME | IT/Solution | 2016 | June | 68714
3429 | Scope | Change | Creep | 22 | 3 | Poor communications resulted in never truly understanding customer needs | 1 | Asia | IT/Solution | 2013 | December | 685014
3430 | Scope | Change | Creep | 21 | 5 | Poor communications and assumptions were not backed by written agreements | 0 | Americas | IT/Solution | 2004 | October | 1669395
3431 | Scope | Change | Creep | 8 | 6 | There was a design flaw in the roof detail | 2 | Eur/ME | Prod. Dev. | 2004 | September | 361320
3432 | Scope | Change | Creep | 8 | 6 | Scope of the project increased following final requirements review | 2 | Eur/ME | Prod. Dev. | 2015 | January | 621816
3433 | Scope | Change | Creep | 3 | 1 | Original product requirements document was incomplete | 0 | Americas | Prod. Dev. | 2014 | September | 75030
3434 | Scope | Change | Creep | 24 | 1 | Tests revealed a fatal issue, deferring release to next quartely update | 0 | Americas | Prod. Dev. | 2018 | September | 1822896
3435 | Scope | Change | Dependency | 9 | 7 | Clinical evidence was insufficient for European market | 1 | Asia | Prod. Dev. | 2013 | December | 459099
3436 | Scope | Change | Dependency | 26 | 6 | Lack of understanding the business processes used to develop manual reports and insufficient relevant experience | 2 | Eur/ME | Prod. Dev. | 2007 | December | 1625000
3437 | Scope | Change | Dependency | 13 | 6 | Stakeholders were numerous and unable to come to a timely decision | 0 | Americas | Prod. Dev. | 2006 | September | 468390
3438 | Scope | Change | Dependency | 24 | 2 | People still on prior project | 0 | Americas | Prod. Dev. | 2017 | July | 645360
3439 | Scope | Change | Dependency | 2 | 3 | Adding two more configurations tripled the scope with the same staff | 2 | Eur/ME | IT/Solution | 2012 | March | 117034
3440 | Scope | Change | Dependency | 16 | 7 | On this long project, turnover was high on project team and at customer. | 0 | Americas | IT/Solution | 2007 | June | 610800
3441 | Scope | Change | Gap | 6 | 5 | Technology used for design is unstable | 0 | Americas | IT/Solution | 2005 | December | 467028
3442 | Scope | Change | Gap | 18 | 1 | Data conversion problems made the implementation of a new system dependent on manual reentry of data | 0 | Americas | IT/Solution | 2002 | June | 334044
3443 | Scope | Change | Gap | 16 | 1 | Contracted with a small outside firm that didn’t understand the business | 2 | Eur/ME | Prod. Dev. | 2015 | August | 909808
3444 | Scope | Change | Gap | 26 | 1 | The only experienced programmer gave notice and left the company | 0 | Americas | IT/Solution | 2012 | September | 1700764
3445 | Scope | Change | Gap | 11 | 5 | Both the full time developers assigned to the project quit the company | 2 | Eur/ME | Prod. Dev. | 2011 | June | 987074
3446 | Scope | Change | Gap | 4 | 7 | Project is not complete until all users are trained. Coordinating schedules requires 4 months, not 2. | 1 | Asia | IT/Solution | 2003 | February | 150212
3447 | Scope | Change | Gap | 3 | 3 | A patch breaks other functionality in the system and is backed out until the next maintenance window | 2 | Eur/ME | Prod. Dev. | 2012 | February | 242571
3448 | Scope | Change | Gap | 11 | 3 | The travel budget for the project was cut and led to inefficient long-distance collaboration | 0 | Americas | Prod. Dev. | 2019 | March | 1095886
3449 | Scope | Change | Gap | 24 | 5 | Management pushed plans to outsource printing operations, causing problems | 0 | Americas | IT/Solution | 2017 | November | 1573104
3450 | Scope | Change | Gap | 26 | 1 | Consulting agency had not fulfilled its obligations under the terms of the contract | 0 | Americas | Prod. Dev. | 2018 | February | 1513954
3451 | Scope | Change | Gap | 10 | 1 | Two new Features were introduced midway during development | 2 | Eur/ME | IT/Solution | 2006 | December | 262840
3452 | Scope | Change | Gap | 2 | 9 | Memory problems not detected in test caused server crashes; backed out for more than a month | 1 | Asia | IT/Solution | 2006 | March | 175158
3453 | Scope | Change | Gap | 21 | 7 | Key consultant was let go at a critical time for coat reasons | 1 | Asia | Prod. Dev. | 2003 | April | 438963
3454 | Scope | Change | Gap | 19 | 8 | Contractor provided inadequate survey data | 0 | Americas | Prod. Dev. | 2008 | March | 1087750
3455 | Scope | Change | Gap | 21 | 8 | Multiple phase roll out paused near the end, systems temporarily out of stock. | 0 | Americas | IT/Solution | 2008 | April | 1727145
3456 | Scope | Change | Gap | 5 | 5 | Twelve additional design and construction tasks were added late | 0 | Americas | IT/Solution | 2011 | December | 400275
3457 | Scope | Change | Gap | 15 | 4 | Database used for system changed in mid project; more resources used and delay. | 0 | Americas | IT/Solution | 2014 | May | 1488855
3458 | Scope | Change | Gap | 14 | 2 | Instrument system for customer based on Intel PC. New system released; fails to work as older model did. Finally installed with salvaged older PC. | 0 | Americas | Prod. Dev. | 2005 | March | 1181530
3459 | Scope | Change | Gap | 21 | 8 | Late testing failure | 0 | Americas | Prod. Dev. | 2008 | June | 1810011
3460 | Scope | Change | Gap | 13 | 7 | Samples needed in Spain were late | 0 | Americas | Prod. Dev. | 2011 | August | 1216176
3461 | Scope | Change | Gap | 15 | 7 | Component delivery late. Causes ramp delays. | 0 | Americas | Prod. Dev. | 2019 | March | 1452120
3462 | Scope | Change | Gap | 5 | 2 | Late design changes required manufacturing retooling at the last minute. | 0 | Americas | Prod. Dev. | 2013 | November | 350055
3463 | Scope | Defect | Hardware | 4 | 2 | Programmer didn’t understand what data was needed or why | 2 | Eur/ME | Prod. Dev. | 2004 | November | 198312
3464 | Scope | Defect | Hardware | 23 | 9 | Slow start of work outsourced. | 1 | Asia | Prod. Dev. | 2010 | September | 1056252
3465 | Scope | Defect | Hardware | 4 | 4 | Slow renewal of contract for consultant; interruption in work | 2 | Eur/ME | IT/Solution | 2018 | November | 72940
3466 | Scope | Defect | Hardware | 9 | 8 | Project start delayed; team busy on other work. | 0 | Americas | IT/Solution | 2004 | July | 138060
3467 | Scope | Defect | Hardware | 5 | 5 | Business Operations Analyst was busy with another big project | 0 | Americas | Prod. Dev. | 2015 | August | 418860
3468 | Scope | Defect | Integration | 9 | 6 | Boards would fail incoming quality check due to the specs given to fabrication house not being tight enough | 0 | Americas | IT/Solution | 2014 | March | 675234
3469 | Scope | Defect | Integration | 26 | 3 | Program Manager squeezes in additional functionalities until the very last minute | 0 | Americas | IT/Solution | 2014 | January | 2226432
3470 | Scope | Defect | Integration | 14 | 1 | Problem arose that required use of a a novel raw material not in inventory | 2 | Eur/ME | Prod. Dev. | 2011 | January | 1298640
3471 | Scope | Defect | Software | 23 | 3 | No engineer is available or has enough knowledge | 2 | Eur/ME | Prod. Dev. | 2008 | January | 1475864
3472 | Scope | Defect | Software | 17 | 8 | Document reviews slipped due to conflicts and low priority. | 0 | Americas | Prod. Dev. | 2003 | May | 752403
3473 | Scope | Defect | Software | 16 | 3 | Access to required support tools was not established | 2 | Eur/ME | IT/Solution | 2012 | December | 1080224
3474 | Scope | Defect | Software | 13 | 9 | Lack of oversight and quality assurance led to short cuts being taken | 2 | Eur/ME | IT/Solution | 2005 | June | 287027
3475 | Scope | Defect | Software | 6 | 9 | Failure to finalize Product Definition Document requirements | 0 | Americas | Prod. Dev. | 2004 | May | 369882
3476 | Scope | Defect | Software | 5 | 6 | Deficiency in the scope due to cutting corners | 1 | Asia | Prod. Dev. | 2005 | December | 385910
3477 | Scope | Defect | Software | 6 | 9 | New chips caused the mother board to perform poorly | 2 | Eur/ME | Prod. Dev. | 2003 | September | 527514
3478 | Scope | Defect | Software | 4 | 2 | A team of 5 contract engineers were let go | 0 | Americas | IT/Solution | 2017 | April | 131848
3479 | Scope | Defect | Software | 10 | 6 | Late rescoping of 2-year project led to half-year slip. | 0 | Americas | Prod. Dev. | 2007 | February | 910560
3480 | Scope | Defect | Software | 2 | 6 | Excessive late changes | 0 | Americas | Prod. Dev. | 2002 | August | 89100
3481 | Schedule | Delay | Decision | 18 | 2 | A company-wide reduction in force let go some of the people who were supposed to lead the next phase | 1 | Asia | IT/Solution | 2008 | October | 1577682
3482 | Scope | Change | Creep | 10 | 6 | Mid-way in design stage, a key Engineer had a family emergency and had to leave the country for a month | 1 | Asia | Prod. Dev. | 2001 | July | 729640
3483 | Scope | Change | Dependency | 20 | 9 | Old application to be modified had no one left who knew it and no documentation. | 0 | Americas | Prod. Dev. | 2006 | September | 961740
3484 | Scope | Change | Gap | 9 | 9 | Quantity of Intel CPU processors needed not available | 0 | Americas | Prod. Dev. | 2017 | September | 186831
3485 | Scope | Defect | Hardware | 24 | 7 | No staff that was knowledgeable in the technology | 0 | Americas | IT/Solution | 2002 | March | 800328
3486 | Scope | Change | Gap | 15 | 2 | Project needs $150K per month in supplies but limit is $100K, which delayed progress. | 2 | Eur/ME | IT/Solution | 2015 | August | 574845
3487 | Resource | People | Loss | 21 | 7 | The vendor sent equipment to a wrong location in Michigan instead of the Bay Area | 0 | Americas | IT/Solution | 2008 | April | 703626
3488 | Resource | Outsourcing | Late or poor output | 7 | 7 | Problems using trainers and training materials from Germany | 1 | Asia | IT/Solution | 2007 | September | 458395
3489 | Resource | People | Loss | 14 | 7 | Some of the cross functional teams were not involved early enough | 1 | Asia | IT/Solution | 2017 | August | 723674
3490 | Schedule | Estimates | Learning | 10 | 8 | Subcontractor did not build stairs according to the drawings and had to redo them | 1 | Asia | IT/Solution | 2011 | August | 512860
3491 | Scope | Defect | Software | 12 | 3 | Key contributor unavailable when needed. | 0 | Americas | IT/Solution | 2006 | May | 214752
3492 | Resource | Outsourcing | Late or poor output | 14 | 4 | Half way through the project the client changed the scope by adding additional work | 1 | Asia | IT/Solution | 2004 | February | 542136
3493 | Resource | Outsourcing | Late or poor output | 10 | 3 | The key person responsible for major marketing activities resigned | 2 | Eur/ME | IT/Solution | 2015 | January | 205710
3494 | Resource | People | Temp loss | 3 | 4 | Earthquake in Taiwan makes part of the project team unavailable for work. | 1 | Asia | Prod. Dev. | 2006 | September | 291486
3495 | Scope | Change | Creep | 23 | 9 | Delay in approval to proceed in France and German | 0 | Americas | Prod. Dev. | 2005 | April | 769534
3496 | Scope | Change | Creep | 24 | 4 | Unrealistic deadline set | 1 | Asia | Prod. Dev. | 2014 | July | 593136
3497 | Scope | Defect | Hardware | 20 | 2 | Power configuration change was requested too late in the schedule | 0 | Americas | Prod. Dev. | 2012 | September | 1911540
3498 | Scope | Defect | Integration | 13 | 4 | 6 sister organizations with an additional 250 users added to the project late | 1 | Asia | Prod. Dev. | 2012 | December | 1006785
3499 | Schedule | Dependency | Project | 5 | 3 | "Minor" changes added and accepted late in project. Phase work doubled and delayed project end. | 2 | Eur/ME | Prod. Dev. | 2007 | April | 247095
3500 | Resource | People | Loss | 12 | 5 | Sponsor failed to communicate his requirements at the start of the project | 1 | Asia | IT/Solution | 2010 | March | 255960
3501 | Schedule | Delay | Parts | 14 | 4 | Lack of money for sufficient equipment | 0 | Americas | IT/Solution | 2014 | April | 709520
3502 | Schedule | Estimates | Deadline | 11 | 7 | Local subcontractors lacked needed technical skills | 2 | Eur/ME | IT/Solution | 2018 | March | 321277
3503 | Scope | Change | Gap | 7 | 7 | Problems with vendor capacity and performance | 1 | Asia | IT/Solution | 2014 | June | 215061
3504 | Schedule | Dependency | Project | 2 | 1 | At a critical stage of the project the Medical Director left the company | 0 | Americas | IT/Solution | 2002 | August | 55314
3505 | Schedule | Estimates | Learning | 13 | 1 | Key work in flu season delayed; most of staff out ill. | 2 | Eur/ME | IT/Solution | 2012 | January | 209339
3506 | Scope | Change | Creep | 10 | 4 | Errors in input data had to be fixed and reports re-generated | 1 | Asia | IT/Solution | 2010 | May | 409870
3507 | Scope | Change | Gap | 6 | 9 | Changes double the work on solution project; no change in funding. | 0 | Americas | IT/Solution | 2019 | October | 129564
3508 | Scope | Defect | Hardware | 21 | 7 | IT staff failed to understand the user requirements | 0 | Americas | IT/Solution | 2012 | March | 1701966
3509 | Resource | People | Queuing | 9 | 7 | Client missed the deadline for feedback by several days | 2 | Eur/ME | IT/Solution | 2003 | August | 568242
3510 | Resource | People | Temp loss | 9 | 2 | Delivery problems on international shipment--paperwork, customs. | 2 | Eur/ME | IT/Solution | 2001 | September | 542574
3511 | Resource | People | Temp loss | 25 | 8 | Other group could not deliver on time, soI had to do work myself | 0 | Americas | IT/Solution | 2002 | December | 1480550
3512 | Schedule | Delay | Hardware | 16 | 7 | Vendor was just starting out and didn’t have the equipment necessary | 0 | Americas | IT/Solution | 2019 | March | 1319968
3513 | Schedule | Estimates | Learning | 1 | 1 | Firmware needed for an add-on paper handler dropped from printer project. | 0 | Americas | IT/Solution | 2006 | September | 26736
3514 | Scope | Change | Creep | 18 | 8 | Scope initially proposed for the project was not signed off by the upper management | 2 | Eur/ME | IT/Solution | 2013 | October | 1138842
3515 | Scope | Change | Creep | 5 | 2 | Subject matter experts were let go to save money | 0 | Americas | IT/Solution | 2016 | June | 340385
3516 | Resource | People | Loss | 21 | 5 | Insufficient QA resources to cover the auditing tasks and training tasks. | 0 | Americas | IT/Solution | 2007 | November | 1751253
3517 | Resource | People | Queuing | 13 | 1 | Volume requirements increased late in project, requiring extensive rework | 1 | Asia | IT/Solution | 2001 | September | 310310
3518 | Schedule | Delay | Decision | 24 | 2 | Poor Fit/Gap analysis | 1 | Asia | Prod. Dev. | 2006 | November | 2094336
3519 | Schedule | Delay | Parts | 15 | 9 | Architect determined that the new design plan for the medical clinic would be considerably more complex than a simple remodeling job | 0 | Americas | Prod. Dev. | 2014 | September | 1331220
3520 | Schedule | Dependency | Project | 23 | 9 | The manager of a related project allowed stakeholders to change the scope, driving continual changes | 0 | Americas | Prod. Dev. | 2011 | April | 603451
3521 | Scope | Change | Dependency | 16 | 6 | Code freeze not done until the release date, making training and documentation late | 1 | Asia | Prod. Dev. | 2011 | January | 1262720
3522 | Scope | Change | Gap | 24 | 5 | Vendor was just starting out and didn’t have the equipment necessary | 2 | Eur/ME | Prod. Dev. | 2014 | August | 1500048
3523 | Scope | Change | Gap | 24 | 8 | Several employees had to take a leave of absence due to a family emergency | 1 | Asia | Prod. Dev. | 2011 | August | 2301120
3524 | Resource | Outsourcing | Late or poor output | 9 | 9 | Poor communications and assumptions were not backed by written agreements | 1 | Asia | Prod. Dev. | 2007 | February | 587709
3525 | Resource | People | Motivation | 2 | 8 | Peak season begins earlier than expected and impedes project progress | 1 | Asia | Prod. Dev. | 2013 | September | 173956
3526 | Scope | Defect | Software | 19 | 4 | Scope expanded during the course of the project | 0 | Americas | Prod. Dev. | 2004 | July | 396872
3527 | Resource | Money | Limitation | 2 | 4 | Late ramp problem. Quadrupled resources and caused major slip. | 0 | Americas | Prod. Dev. | 2013 | August | 175926
3528 | Resource | Money | Limitation | 12 | 9 | Internal resources were not available on a full time basis | 1 | Asia | IT/Solution | 2003 | October | 604080
3529 | Resource | Outsourcing | Delayed start | 23 | 1 | Contractors are not sufficiently skilled nor motivated | 2 | Eur/ME | IT/Solution | 2018 | August | 1030860
3530 | Resource | Outsourcing | Delayed start | 18 | 6 | Contractor installed smaller wire sizes than specified causing rework (after a fire) | 0 | Americas | Prod. Dev. | 2017 | December | 683118
3531 | Resource | Outsourcing | Late or poor output | 26 | 8 | The delivery of the content started without the content being finalized | 1 | Asia | IT/Solution | 2010 | May | 1316848
3532 | Resource | Outsourcing | Late or poor output | 19 | 3 | For cost reasons, Asian supplier chosen. Qualification and paperwork caused delays. | 0 | Americas | IT/Solution | 2019 | July | 502227
3533 | Resource | Outsourcing | Late or poor output | 22 | 7 | Only one employee with other commitments had both the Cobol and relational database data conversion experience | 0 | Americas | Prod. Dev. | 2016 | December | 1099494
3534 | Resource | Outsourcing | Late or poor output | 4 | 8 | The trained resource was tied up in other work | 0 | Americas | Prod. Dev. | 2015 | April | 272616
3535 | Resource | Outsourcing | Late or poor output | 7 | 2 | The business counterparts were not in agreement with which option to choose and went back and forth on the decision | 0 | Americas | Prod. Dev. | 2019 | March | 173523
3536 | Resource | Outsourcing | Late or poor output | 18 | 9 | Current processes did not scale as needed by project, requiring redesign | 0 | Americas | IT/Solution | 2006 | September | 530550
3537 | Resource | Outsourcing | Late or poor output | 19 | 7 | Project priorities and criteria are unclear through much of the project, causing lots of unneeded work. | 0 | Americas | Prod. Dev. | 2015 | April | 481403
3538 | Resource | Outsourcing | Late or poor output | 20 | 5 | Original scope missed supply chain issues; could not be used without changes | 0 | Americas | Prod. Dev. | 2005 | February | 1627760
3539 | Resource | Outsourcing | Late or poor output | 11 | 4 | Faulty market & competitive analysis information discovered late; led to changes | 0 | Americas | IT/Solution | 2015 | January | 594968
3540 | Resource | Outsourcing | Late or poor output | 2 | 8 | During the feedback/review phase it was noticed that the numbers were incorrect | 2 | Eur/ME | Prod. Dev. | 2008 | February | 174068
3541 | Resource | Outsourcing | Late or poor output | 17 | 1 | There was only on one experienced consultant who knew the tool | 0 | Americas | IT/Solution | 2009 | March | 1295366
3542 | Resource | Outsourcing | Late start | 16 | 7 | the infrastructure changes needed (network, microwave, etc) were not budgeted for the project | 1 | Asia | IT/Solution | 2008 | January | 853184
3543 | Resource | People | Late start | 26 | 4 | Subcontractor delay causes compression of later work. | 1 | Asia | IT/Solution | 2018 | December | 1150994
3544 | Resource | People | Loss | 25 | 5 | One factory went on labor strike for 2 weeks –Delayed production of 20 pallets | 0 | Americas | IT/Solution | 2015 | July | 352350
3545 | Resource | People | Loss | 2 | 5 | Project work that customer is responsible for slips, causing project slip. | 0 | Americas | Prod. Dev. | 2015 | July | 181948
3546 | Resource | People | Loss | 7 | 6 | Delivery problems on international shipment--paperwork, customs. | 0 | Americas | IT/Solution | 2019 | July | 687449
3547 | Resource | People | Loss | 3 | 9 | Component needed in China for prototype not available; had to be shipped from US | 1 | Asia | Prod. Dev. | 2008 | October | 135999
3548 | Resource | People | Loss | 9 | 8 | Retrofit project discovered hidden damage that had to be fixed | 1 | Asia | Prod. Dev. | 2018 | November | 453474
3549 | Resource | People | Loss | 1 | 5 | When testing reveals a performance defect which is due to a conflict between two, or more, of the components significant extra work is required | 0 | Americas | Prod. Dev. | 2013 | April | 63261
3550 | Resource | People | Loss | 14 | 7 | Late quality assurance finds additional translation work is needed | 1 | Asia | IT/Solution | 2004 | April | 1051344
3551 | Resource | People | Motivation | 16 | 6 | Translations are incomplete | 0 | Americas | IT/Solution | 2018 | January | 404400
3552 | Resource | People | Queuing | 21 | 3 | Old equipment failed at the last minute | 1 | Asia | IT/Solution | 2013 | October | 807786
3553 | Resource | People | Queuing | 5 | 3 | A key component of the system was outsourced | 2 | Eur/ME | Prod. Dev. | 2005 | March | 476430
3554 | Resource | People | Queuing | 13 | 1 | Contract manufacturer failed to deliver a new drug | 2 | Eur/ME | IT/Solution | 2016 | March | 793364
3555 | Resource | People | Queuing | 18 | 2 | Deliverable received was inadequate | 2 | Eur/ME | IT/Solution | 2013 | February | 685278
3556 | Resource | People | Queuing | 25 | 1 | A pool of unqualified, poorly performing, marginal staff to work with | 1 | Asia | Prod. Dev. | 2013 | September | 2041850
3557 | Resource | People | Queuing | 24 | 3 | Inadequate procedures for acceptance, quality, and communications with development in India | 1 | Asia | Prod. Dev. | 2015 | May | 2052144
3558 | Resource | People | Queuing | 24 | 5 | Ramp-up required 40 new test engineers | 2 | Eur/ME | IT/Solution | 2001 | September | 246576
3559 | Resource | People | Queuing | 20 | 2 | One company expands scope in web design project without communicating or getting approval from others | 1 | Asia | IT/Solution | 2012 | March | 1473500
3560 | Resource | People | Queuing | 26 | 2 | Six weeks in, a redesign to the most fundamental part of the research was done | 0 | Americas | IT/Solution | 2011 | July | 1928602
3561 | Resource | People | Queuing | 17 | 8 | Market change due to Improvements in technology became an ‘urgent’ requirement | 1 | Asia | Prod. Dev. | 2016 | August | 983348
3562 | Resource | People | Queuing | 16 | 1 | Customer requirement discovered late in project | 0 | Americas | IT/Solution | 2012 | November | 1254544
3563 | Resource | People | Queuing | 3 | 6 | Requirements are misunderstood or understood differently by multiple parties | 2 | Eur/ME | Prod. Dev. | 2012 | February | 274386
3564 | Resource | People | Temp loss | 8 | 4 | Problem was not fully understood, leading to many changes | 0 | Americas | IT/Solution | 2018 | December | 241032
3565 | Resource | People | Temp loss | 20 | 8 | Our server crashed, which contains 4 months worth of info. No backup, had to be reentered. | 0 | Americas | Prod. Dev. | 2006 | June | 1754880
3566 | Resource | People | Temp loss | 9 | 3 | Hardware fails near the end of a three-month final test. Refabrication and retest required. | 1 | Asia | Prod. Dev. | 2002 | November | 732096
3567 | Resource | People | Temp loss | 3 | 5 | Some users couldn't login because of mixed case passwords | 0 | Americas | IT/Solution | 2019 | September | 134055
3568 | Resource | People | Temp loss | 9 | 6 | Software in use casused unacceptable image distortion | 1 | Asia | IT/Solution | 2006 | January | 121617
3569 | Resource | People | Temp loss | 6 | 8 | Due to a layoff no writer was immediately available, so approval was delayed | 0 | Americas | IT/Solution | 2013 | October | 535014
3570 | Resource | People | Temp loss | 24 | 1 | Insufficient budget and Staff Resources allocated | 1 | Asia | Prod. Dev. | 2018 | September | 870888
3571 | Resource | People | Temp loss | 12 | 6 | Major system was begun with insufficient internal resources and without good requirements information | 0 | Americas | IT/Solution | 2018 | November | 255648
3572 | Resource | People | Temp loss | 3 | 3 | Interdependencies in complex program underestimated and detected late. | 1 | Asia | IT/Solution | 2004 | April | 175158
3573 | Schedule | Delay | Decision | 23 | 1 | Complexities of solution not understood, even well into project | 0 | Americas | IT/Solution | 2010 | April | 1536814
3574 | Schedule | Delay | Hardware | 26 | 7 | In creating a new system, there was too little involvement from the end users | 1 | Asia | Prod. Dev. | 2002 | August | 1952574
3575 | Schedule | Delay | Hardware | 16 | 5 | Building permit was issued late due to roof damages | 2 | Eur/ME | IT/Solution | 2013 | January | 1581728
3576 | Schedule | Delay | Hardware | 6 | 2 | Business environment shifts forcing project changes, | 0 | Americas | IT/Solution | 2004 | February | 456180
3577 | Schedule | Delay | Information | 22 | 3 | Project team was not aware that the new release would have a new UI | 2 | Eur/ME | IT/Solution | 2016 | January | 2023054
3578 | Schedule | Delay | Information | 1 | 4 | Conversion from legacy system to SAP has multiple modules that cause unanticipated problems leading to delays of 3 to 10 days each to fix. | 2 | Eur/ME | Prod. Dev. | 2012 | January | 60740
3579 | Schedule | Delay | Information | 14 | 9 | Delay in contract signing because legal had a higher priority contract to review | 1 | Asia | IT/Solution | 2004 | March | 686938
3580 | Schedule | Delay | Parts | 24 | 2 | Team leader reassigned to another project and a new leader was assigned | 0 | Americas | IT/Solution | 2014 | November | 2366784
3581 | Schedule | Delay | Parts | 24 | 3 | Applications Engineer found another job and left the company | 1 | Asia | Prod. Dev. | 2009 | January | 1168416
3582 | Schedule | Delay | Parts | 22 | 3 | Sponsorship not sustained and decisions and resources are problematic. | 0 | Americas | IT/Solution | 2018 | January | 1755732
3583 | Schedule | Delay | Parts | 25 | 5 | Redesign added late in maintenance project for legacy system. Major slip. | 1 | Asia | IT/Solution | 2016 | November | 1078350
3584 | Schedule | Delay | Parts | 6 | 6 | Sufficient time was not allocated to understand client needs and assumptions | 2 | Eur/ME | IT/Solution | 2013 | October | 333408
3585 | Schedule | Delay | Parts | 25 | 5 | Vendor had a poor resource plan | 1 | Asia | IT/Solution | 2003 | January | 1402750
3586 | Schedule | Delay | Parts | 16 | 7 | Supply chain expert needed was hard to find and engage. | 0 | Americas | IT/Solution | 2015 | July | 1153136
3587 | Schedule | Delay | Parts | 23 | 7 | Inadequate water supply available to complete project, needed to be trucked in | 1 | Asia | Prod. Dev. | 2010 | February | 1267668
3588 | Schedule | Delay | Parts | 18 | 5 | Late features were added | 1 | Asia | Prod. Dev. | 2012 | November | 1426122
3589 | Schedule | Delay | Parts | 16 | 9 | Conflicting design attributes and an unfocused process resulted in confusion and changes | 0 | Americas | Prod. Dev. | 2015 | June | 968192
3590 | Schedule | Delay | Parts | 10 | 4 | Functional design was not properly done, due to limited access to users; led to changes | 0 | Americas | IT/Solution | 2012 | September | 149950
3591 | Schedule | Delay | Parts | 5 | 4 | Vendor made a promise on something they could not deliver | 0 | Americas | Prod. Dev. | 2009 | June | 246310
3592 | Schedule | Delay | Parts | 7 | 2 | Key code developer had a family emergency | 1 | Asia | IT/Solution | 2007 | November | 264068
3593 | Schedule | Dependency | Infrastructure | 9 | 3 | Unavailability of skilled resources | 0 | Americas | Prod. Dev. | 2019 | December | 133542
3594 | Schedule | Dependency | Infrastructure | 3 | 7 | Operating system release expected canceled; project forced to use prior version. | 0 | Americas | IT/Solution | 2018 | August | 230565
3595 | Schedule | Dependency | Infrastructure | 9 | 6 | Deliverable fails final test; rework to fix. | 0 | Americas | IT/Solution | 2003 | December | 828432
3596 | Schedule | Dependency | Infrastructure | 22 | 6 | Key consultant breaks both arms 3 weeks before project end | 2 | Eur/ME | IT/Solution | 2018 | April | 1909270
3597 | Schedule | Dependency | Legal | 6 | 2 | Usual vendor closed its business and had to be replaced | 2 | Eur/ME | Prod. Dev. | 2017 | April | 196950
3598 | Schedule | Dependency | Project | 16 | 1 | Problems due to last minute infrastructure changes | 0 | Americas | Prod. Dev. | 2005 | October | 863840
3599 | Schedule | Dependency | Project | 8 | 1 | Lack of skills with recent university hires | 0 | Americas | IT/Solution | 2008 | June | 384712
3600 | Schedule | Dependency | Project | 12 | 1 | Server technology chage was necessitated to support application | 1 | Asia | IT/Solution | 2006 | September | 932508
3601 | Schedule | Estimates | Deadline | 2 | 4 | Project team frequently diverted to support work. | 1 | Asia | Prod. Dev. | 2004 | August | 142086
3602 | Schedule | Estimates | Deadline | 13 | 7 | System needed to approve requests went down; ordering required parts delayed. | 1 | Asia | Prod. Dev. | 2004 | November | 1068470
3603 | Schedule | Estimates | Judgment | 20 | 2 | Team relocated with insufficient time to schedule high speed network lines. Rushed, but did not work; team was down until fixed. | 1 | Asia | IT/Solution | 2010 | July | 261980
3604 | Schedule | Estimates | Judgment | 10 | 7 | Equipment / parts not delivered on time or in full by the outside supplier | 2 | Eur/ME | IT/Solution | 2019 | October | 652220
3605 | Schedule | Estimates | Judgment | 2 | 2 | Lack of access to professional translation services | 2 | Eur/ME | Prod. Dev. | 2011 | June | 45472
3606 | Schedule | Estimates | Learning | 22 | 4 | One team in another country missed deadlines on a complex proposal, creating delay and frustration. | 1 | Asia | Prod. Dev. | 2004 | November | 1301410
3607 | Schedule | Estimates | Learning | 14 | 3 | Issues with testing were severly underestimated | 2 | Eur/ME | Prod. Dev. | 2002 | February | 170044
3608 | Schedule | Estimates | Learning | 8 | 6 | Excessive scope change in ERP project | 0 | Americas | Prod. Dev. | 2004 | July | 326904
3609 | Schedule | Estimates | Learning | 10 | 5 | Tests not scheduled for working parts, but mandated for project. Added late. | 0 | Americas | IT/Solution | 2012 | December | 125550
3610 | Schedule | Estimates | Learning | 2 | 6 | Following recent upgrade, many bugs were found | 2 | Eur/ME | IT/Solution | 2007 | July | 91846
3611 | Scope | Change | Creep | 16 | 6 | Scope changed after writers had completed initial draft | 2 | Eur/ME | IT/Solution | 2017 | July | 1094240
3612 | Scope | Change | Creep | 9 | 9 | Unrealistic commit made in order to win the business | 0 | Americas | IT/Solution | 2016 | November | 214056
3613 | Scope | Change | Creep | 11 | 1 | Project manager had very few skills in this field | 0 | Americas | IT/Solution | 2014 | May | 119735
3614 | Scope | Change | Creep | 3 | 1 | Excessive late changes | 1 | Asia | IT/Solution | 2014 | July | 271374
3615 | Scope | Change | Creep | 26 | 9 | Developer added a new routine that was not fully tested, and release window passed | 0 | Americas | Prod. Dev. | 2008 | October | 1974674
3616 | Scope | Change | Creep | 15 | 7 | Company wasted time developing functionality that was ultimately unimportant | 2 | Eur/ME | Prod. Dev. | 2003 | November | 270300
3617 | Scope | Change | Creep | 25 | 1 | New database wouldn’t work with the proposed platform | 2 | Eur/ME | IT/Solution | 2015 | May | 2204675
3618 | Scope | Change | Creep | 14 | 4 | Project budget was dramatically cut | 2 | Eur/ME | Prod. Dev. | 2002 | August | 501186
3619 | Scope | Change | Creep | 17 | 5 | Late scope change added customer choice in subscription ticket selection | 0 | Americas | IT/Solution | 2013 | January | 640050
3620 | Scope | Change | Creep | 12 | 3 | Poor requirements definition | 0 | Americas | Prod. Dev. | 2014 | March | 650964
3621 | Scope | Change | Creep | 8 | 5 | Project manger and the Product Manager didn’t get along on an interpersonal level | 1 | Asia | IT/Solution | 2018 | October | 449704
3622 | Scope | Change | Creep | 20 | 6 | Poor stakeholder buy-in | 2 | Eur/ME | IT/Solution | 2010 | April | 298200
3623 | Scope | Change | Creep | 6 | 9 | Test run is rejected or lost | 0 | Americas | IT/Solution | 2001 | April | 412770
3624 | Scope | Change | Creep | 10 | 9 | Employees terminated for sexual harassment | 0 | Americas | IT/Solution | 2012 | December | 446560
3625 | Scope | Change | Creep | 20 | 9 | Key staff member assigned to project was changed 3 times during the project | 0 | Americas | IT/Solution | 2003 | February | 754580
3626 | Scope | Change | Creep | 9 | 8 | Projects with similar objectives taken on centrally and locally at the same time. Lots of overlap, redundancy and arguing. | 1 | Asia | IT/Solution | 2010 | May | 645840
3627 | Scope | Change | Creep | 11 | 9 | Sponsor demanded specification changes late in the project | 2 | Eur/ME | IT/Solution | 2006 | February | 748693
3628 | Scope | Change | Dependency | 2 | 9 | Reduced staff with a bare minimum budget was assigned to the project | 0 | Americas | Prod. Dev. | 2010 | January | 86590
3629 | Scope | Change | Dependency | 19 | 9 | Project leader resigns and is not replaced promptly | 2 | Eur/ME | IT/Solution | 2009 | June | 426892
3630 | Scope | Change | Gap | 23 | 6 | Ship sinks with critical part; forced to replace with remanufactured old component | 0 | Americas | IT/Solution | 2011 | October | 909719
3631 | Scope | Change | Gap | 1 | 5 | Inexperienced staff | 1 | Asia | IT/Solution | 2003 | February | 17512
3632 | Scope | Change | Gap | 9 | 3 | Application required its own server, delay for installation | 0 | Americas | IT/Solution | 2015 | October | 833679
3633 | Scope | Change | Gap | 5 | 4 | Vendor failed to confirm start date, resulting in delay | 0 | Americas | Prod. Dev. | 2018 | April | 429235
3634 | Scope | Change | Gap | 13 | 9 | Critical skills unique in the head of a 62-yearl old programmer who had a heart attack | 0 | Americas | Prod. Dev. | 2004 | July | 770692
3635 | Scope | Change | Gap | 8 | 8 | A critical issue was neglected resulting in a significant scope gap | 0 | Americas | Prod. Dev. | 2010 | February | 684176
3636 | Scope | Change | Gap | 22 | 7 | Scope gaps became apparent when legal department was consulted too late | 0 | Americas | IT/Solution | 2004 | April | 976030
3637 | Scope | Change | Gap | 7 | 9 | Complexity not understood or documented. Required work added. | 2 | Eur/ME | IT/Solution | 2006 | April | 337260
3638 | Scope | Change | Gap | 4 | 9 | After the first run was lost, a third run was added | 1 | Asia | IT/Solution | 2012 | September | 349880
3639 | Scope | Change | Gap | 12 | 1 | Subcontractor late with a critical component | 0 | Americas | IT/Solution | 2017 | March | 401040
3640 | Scope | Change | Gap | 21 | 6 | CMO analyzing output developed a severe backup | 2 | Eur/ME | Prod. Dev. | 2016 | August | 364602
3641 | Scope | Change | Gap | 26 | 6 | Integrating late features meant that the existing architecture had to be modified | 0 | Americas | Prod. Dev. | 2003 | April | 895570
3642 | Scope | Change | Gap | 14 | 2 | Not enough timewas spent to identify all the requirements for the process | 1 | Asia | IT/Solution | 2002 | January | 1352974
3643 | Scope | Change | Gap | 5 | 1 | Key contributor "rounded up" after 9/11 (and later released) | 2 | Eur/ME | IT/Solution | 2012 | May | 458195
3644 | Scope | Change | Gap | 5 | 9 | Delay to reconfigure printer outside firewall | 1 | Asia | Prod. Dev. | 2001 | March | 62985
3645 | Scope | Change | Gap | 13 | 1 | Inventory from vendors could not be secured by the desired transport date | 0 | Americas | IT/Solution | 2018 | July | 772369
3646 | Scope | Change | Gap | 12 | 7 | Insufficient time is estimated; the deadline could not be met. | 0 | Americas | IT/Solution | 2017 | November | 833004
3647 | Scope | Change | Gap | 9 | 9 | Requirements for compiling and formatting data were not clear | 1 | Asia | IT/Solution | 2003 | July | 692055
3648 | Scope | Change | Gap | 15 | 3 | System arrives late, then when it does arrive staff is not available to install it. | 0 | Americas | IT/Solution | 2008 | October | 815475
3649 | Scope | Change | Gap | 20 | 5 | Support offering requires more overhead to span several OS versions | 1 | Asia | Prod. Dev. | 2016 | April | 574160
3650 | Scope | Change | Gap | 10 | 8 | Coordination of the scopes of work between several projects | 1 | Asia | IT/Solution | 2005 | May | 280670
3651 | Scope | Change | Gap | 20 | 8 | Added resources failed to cut the schedule in half | 0 | Americas | IT/Solution | 2017 | April | 1591640
3652 | Scope | Change | Gap | 4 | 1 | Excessive changes made | 0 | Americas | Prod. Dev. | 2008 | November | 59364
3653 | Scope | Change | Gap | 10 | 4 | Unique and specific requirements were poorly understood | 1 | Asia | Prod. Dev. | 2014 | April | 971520
3654 | Scope | Change | Gap | 15 | 7 | 75% of the requirements were unknowninitially to the project staff | 1 | Asia | Prod. Dev. | 2012 | July | 380475
3655 | Scope | Change | Gap | 10 | 9 | Found some strange and unusual contamination of an entire batch of petri plates | 0 | Americas | Prod. Dev. | 2012 | September | 720810
3656 | Scope | Defect | Hardware | 19 | 6 | Significant delay in patient recruitment | 1 | Asia | IT/Solution | 2017 | February | 1846857
3657 | Scope | Defect | Hardware | 15 | 9 | An extra specialty service to the hospital was added | 1 | Asia | IT/Solution | 2007 | February | 1487025
3658 | Scope | Defect | Hardware | 9 | 9 | Team failed to engage the critical “power-users” early enough | 1 | Asia | IT/Solution | 2013 | April | 508554
3659 | Scope | Defect | Hardware | 7 | 6 | Incomplete design was a result of not considering the particular country needs | 2 | Eur/ME | IT/Solution | 2012 | August | 129248
3660 | Scope | Defect | Hardware | 1 | 8 | Survey data required for project assigned to several people in some countries; each assumes others will do work | 1 | Asia | IT/Solution | 2009 | February | 86670
3661 | Scope | Defect | Software | 1 | 5 | During a company-wide OS refresh of all desktops and laptops, a merger occurred. Complexity added. | 0 | Americas | IT/Solution | 2007 | October | 47784
3662 | Scope | Defect | Software | 10 | 6 | Selected motor was not able to operate reliably requiring redesign | 0 | Americas | IT/Solution | 2009 | November | 529840
3663 | Scope | Defect | Software | 19 | 2 | New database wouldn’t work with the proposed platform | 0 | Americas | IT/Solution | 2013 | March | 237120
3664 | Scope | Defect | Software | 10 | 8 | Deficiency in the scope due to cutting corners | 0 | Americas | IT/Solution | 2013 | February | 148730
3665 | Resource | Outsourcing | Late or poor output | 3 | 8 | Delay in the delivery of the test samples | 1 | Asia | IT/Solution | 2013 | March | 155835
3666 | Scope | Change | Creep | 3 | 6 | Bad choice of billing threshold problems forced system redesign | 0 | Americas | Prod. Dev. | 2004 | February | 117441
3667 | Scope | Defect | Software | 10 | 5 | Purchased application led to performance problems. | 2 | Eur/ME | Prod. Dev. | 2002 | May | 771590
3668 | Scope | Defect | Software | 2 | 2 | RFP Process was flawed and created delays | 1 | Asia | IT/Solution | 2007 | May | 176478
3669 | Scope | Change | Gap | 3 | 4 | New product features were added at every weekly meeting and stage review | 0 | Americas | IT/Solution | 2019 | July | 293691
3670 | Resource | People | Loss | 25 | 1 | Sales reps did not clearly understand the client’s request | 0 | Americas | Prod. Dev. | 2012 | February | 1404850
3671 | Scope | Change | Dependency | 16 | 4 | The students in a new course had insufficient knowledge of reading and math | 2 | Eur/ME | Prod. Dev. | 2006 | June | 874304
3672 | Resource | Money | Limitation | 18 | 7 | To reduce costs and speed time to market there were too few pre-launch product builds performed | 2 | Eur/ME | Prod. Dev. | 2018 | July | 1213236
3673 | Scope | Defect | Hardware | 22 | 4 | No understanding of the scope and not enough system resources | 1 | Asia | Prod. Dev. | 2001 | March | 1934790
3674 | Resource | People | Loss | 13 | 4 | Money for needed software was not in the budget; project was delayed to push expense into next quarter | 2 | Eur/ME | Prod. Dev. | 2013 | October | 999843
3675 | Scope | Change | Gap | 6 | 7 | Incompetent subcontractor led to delay and unhappy clients | 2 | Eur/ME | Prod. Dev. | 2009 | February | 158304
3676 | Schedule | Estimates | Learning | 8 | 8 | A valuable resource gets pulled off of project to work on a larger, higher profile project | 0 | Americas | IT/Solution | 2013 | July | 292224
3677 | Schedule | Delay | Information | 22 | 1 | A special peripheral used for the project deliverable was discontinued | 0 | Americas | IT/Solution | 2003 | February | 964700
3678 | Schedule | Delay | Parts | 17 | 8 | The team member lacked the right skills for a development job | 0 | Americas | IT/Solution | 2017 | December | 1523336
3679 | Scope | Change | Creep | 17 | 3 | Inexperience of the leader resulted in overcommitment and little planning | 2 | Eur/ME | IT/Solution | 2019 | January | 1686638
3680 | Schedule | Dependency | Project | 6 | 4 | Substrate material was initially specified incorrectly and had to be reordered | 0 | Americas | IT/Solution | 2019 | November | 166410
3681 | Resource | People | Loss | 12 | 3 | Reduction in work force affects the % commitment of team members | 1 | Asia | IT/Solution | 2002 | July | 441612
3682 | Scope | Change | Gap | 6 | 5 | Parts unavailable; backordered. | 2 | Eur/ME | IT/Solution | 2011 | October | 421566
3683 | Scope | Change | Gap | 18 | 2 | Customer driven late changes | 0 | Americas | IT/Solution | 2011 | August | 510138
3684 | Resource | Outsourcing | Delayed start | 20 | 4 | Corporate merger delayed project | 2 | Eur/ME | IT/Solution | 2006 | December | 1216780
3685 | Scope | Defect | Software | 7 | 8 | Requireemnts sent via email were never formally documented | 1 | Asia | IT/Solution | 2004 | April | 287098
3686 | Resource | People | Temp loss | 8 | 4 | Poor quality control and record keeping on the field installation side resulted in many openings being installed incorrectly | 2 | Eur/ME | IT/Solution | 2018 | April | 202240
3687 | Schedule | Delay | Decision | 13 | 6 | Key Designer was out of the office for 2 weeks | 0 | Americas | IT/Solution | 2012 | April | 775788
3688 | Schedule | Dependency | Project | 8 | 4 | Scope definition and stakeholder agreement delayed. | 0 | Americas | IT/Solution | 2013 | January | 754768
3689 | Schedule | Estimates | Deadline | 25 | 4 | Data submitted by the participating vendors contains errors | 0 | Americas | IT/Solution | 2014 | August | 1791500
3690 | Resource | People | Loss | 17 | 4 | Defective parts received. Reorder doubled the time required. | 2 | Eur/ME | Prod. Dev. | 2002 | July | 1428391
3691 | Resource | People | Queuing | 9 | 1 | Needed parts arrive too late. | 0 | Americas | Prod. Dev. | 2009 | March | 284706
3692 | Resource | People | Loss | 13 | 1 | Software upgrades take longer each cycle as O/S expands and application list grows. | 1 | Asia | Prod. Dev. | 2007 | November | 1240577
3693 | Schedule | Delay | Parts | 4 | 5 | Missing important scope at the beginning of the project | 1 | Asia | Prod. Dev. | 2019 | November | 391348
3694 | Scope | Change | Creep | 24 | 2 | Controlled Document rejected by Approvers | 0 | Americas | Prod. Dev. | 2016 | January | 255000
3695 | Scope | Change | Dependency | 22 | 7 | Deliverable from one project claimed to be done, but receiving project cannot use it. | 0 | Americas | IT/Solution | 2017 | March | 1681108
3696 | Schedule | Estimates | Judgment | 22 | 7 | Major infrastructure project cut back; delayed fixes cost a lot of money, and resources needed were assigned to other work. | 0 | Americas | IT/Solution | 2016 | September | 1824570
3697 | Scope | Change | Creep | 1 | 1 | Programmers were volunteers, and ultimately all of them quit | 0 | Americas | Prod. Dev. | 2003 | November | 53837
3698 | Scope | Change | Gap | 4 | 3 | Complexity of new software was underestimated | 0 | Americas | Prod. Dev. | 2008 | February | 186736
3699 | Scope | Defect | Hardware | 16 | 9 | Unrealistic commit made in order to win the business | 1 | Asia | Prod. Dev. | 2014 | December | 416224
3700 | Scope | Defect | Hardware | 5 | 2 | Hardware fails near the end of a three-month final test. Refabrication and retest required. | 1 | Asia | Prod. Dev. | 2013 | January | 235105
3701 | Scope | Defect | Software | 3 | 9 | Firmware needed for an add-on paper handler dropped from printer project. | 1 | Asia | IT/Solution | 2013 | May | 168726
3702 | Resource | Money | Limitation | 14 | 3 | Some countries provided incomplete requirements | 1 | Asia | IT/Solution | 2001 | January | 451220
3703 | Resource | Money | Limitation | 16 | 7 | Original product requirements document was incomplete | 2 | Eur/ME | IT/Solution | 2007 | October | 322512
3704 | Resource | Outsourcing | Delayed start | 5 | 6 | Lack of expertise, experience and inadequate training | 0 | Americas | Prod. Dev. | 2015 | March | 220665
3705 | Resource | Outsourcing | Delayed start | 26 | 2 | Project had to wait until all data collection was finished before starting analysis | 2 | Eur/ME | Prod. Dev. | 2001 | October | 2543034
3706 | Resource | Outsourcing | Delayed start | 14 | 9 | IT department was underfunded and had insuffient staff | 0 | Americas | Prod. Dev. | 2016 | May | 1028356
3707 | Resource | Outsourcing | Late or poor output | 1 | 5 | Few of the administrators and developers hired for executing this project had the right skill sets to execute the project | 0 | Americas | Prod. Dev. | 2005 | March | 67354
3708 | Resource | Outsourcing | Late or poor output | 7 | 2 | Unusual usage caused problems in the integration process | 1 | Asia | Prod. Dev. | 2018 | December | 128037
3709 | Resource | Outsourcing | Late or poor output | 1 | 4 | Two related projects failed to successfully synchronize and missed a release | 1 | Asia | Prod. Dev. | 2019 | August | 33762
3710 | Resource | Outsourcing | Late or poor output | 18 | 5 | Poorly implemented web tool causes ongoing support issues | 1 | Asia | Prod. Dev. | 2003 | May | 389394
3711 | Resource | Outsourcing | Late or poor output | 17 | 6 | Entry level employees lacked needed skill and experience | 1 | Asia | Prod. Dev. | 2004 | September | 213843
3712 | Resource | Outsourcing | Late or poor output | 22 | 5 | The statement of work did not indicate clearly the responsibilities of the outsourced programmers | 0 | Americas | Prod. Dev. | 2017 | June | 1427668
3713 | Resource | Outsourcing | Late or poor output | 5 | 4 | Excessive defects in Web Page translations | 2 | Eur/ME | Prod. Dev. | 2001 | July | 435760
3714 | Resource | Outsourcing | Late or poor output | 15 | 9 | New technology was analyzed and didn’t meet the needs | 0 | Americas | Prod. Dev. | 2012 | September | 828045
3715 | Resource | Outsourcing | Late or poor output | 25 | 8 | Contract negotiations delayed by 20 days | 2 | Eur/ME | IT/Solution | 2016 | August | 820975
3716 | Resource | Outsourcing | Late or poor output | 1 | 3 | Lack of clear definition of the contractor and Lead Tech roles and responsibilities | 0 | Americas | IT/Solution | 2013 | March | 90094
3717 | Resource | People | Late start | 12 | 1 | Solar panels arrived late and were not what was ordered | 0 | Americas | IT/Solution | 2003 | February | 779952
3718 | Resource | People | Late start | 3 | 8 | Granite countertops had incorrect measurements | 0 | Americas | IT/Solution | 2001 | May | 204462
3719 | Resource | People | Loss | 2 | 3 | Requested scope expansion took a month to assess and was ultimately rejected | 0 | Americas | Prod. Dev. | 2008 | July | 69308
3720 | Resource | People | Loss | 20 | 9 | Enterprise Portal improperly specified | 1 | Asia | Prod. Dev. | 2005 | January | 1406080
3721 | Resource | People | Loss | 1 | 7 | Major Scope change during the design phase due to the complex processes involved | 0 | Americas | Prod. Dev. | 2007 | June | 39479
3722 | Resource | People | Loss | 6 | 3 | Customer did not describe in detail what exactly was needed | 0 | Americas | Prod. Dev. | 2005 | May | 358068
3723 | Resource | People | Loss | 8 | 7 | Needed system delivered to wrong building; lost for weeks. | 1 | Asia | Prod. Dev. | 2002 | October | 347136
3724 | Resource | People | Loss | 10 | 5 | Scoping was much more complex then originally thought | 1 | Asia | IT/Solution | 2012 | August | 750170
3725 | Resource | People | Loss | 1 | 9 | PC board failure requires redesign and fabrication. | 1 | Asia | Prod. Dev. | 2001 | April | 13419
3726 | Resource | People | Loss | 24 | 9 | Project start delayed; staffing and buy-in late, required overtime and extra project management. | 1 | Asia | IT/Solution | 2011 | June | 2090328
3727 | Resource | People | Loss | 12 | 3 | Failure by project manager to communicate the need for architect’s time | 0 | Americas | Prod. Dev. | 2012 | December | 769884
3728 | Resource | People | Queuing | 8 | 3 | Critical technical task was assigned to resource who was a new hire | 0 | Americas | Prod. Dev. | 2003 | April | 277784
3729 | Resource | People | Queuing | 24 | 7 | Technical requirements communicated to developers too late | 2 | Eur/ME | IT/Solution | 2006 | December | 249336
3730 | Resource | People | Queuing | 24 | 6 | Planning delayed due to staff being still tied up in testing on prior project. | 0 | Americas | Prod. Dev. | 2015 | August | 2324688
3731 | Resource | People | Queuing | 3 | 4 | Untried beta software with unknown computer needs required for training | 1 | Asia | Prod. Dev. | 2010 | October | 99846
3732 | Resource | People | Queuing | 6 | 7 | Unanticipated fumes form epoxy concrete paint forced a delay in work | 0 | Americas | Prod. Dev. | 2017 | November | 418350
3733 | Resource | People | Queuing | 21 | 1 | Lack of specialized labor to perform the task | 1 | Asia | Prod. Dev. | 2007 | September | 1376445
3734 | Resource | People | Temp loss | 22 | 4 | Programmers were volunteers, and ultimately all of them quit | 0 | Americas | Prod. Dev. | 2015 | July | 1975996
3735 | Resource | People | Temp loss | 5 | 3 | Prior work was completed late | 0 | Americas | Prod. Dev. | 2014 | August | 176810
3736 | Resource | People | Temp loss | 9 | 6 | Goal of 90% participation in study is proved infeasible | 2 | Eur/ME | Prod. Dev. | 2012 | May | 431946
3737 | Resource | People | Temp loss | 23 | 8 | The team in Germany did not have the resources or expertise to do testing in key intermediate step | 1 | Asia | Prod. Dev. | 2003 | May | 1445665
3738 | Resource | People | Temp loss | 6 | 7 | Complexity of new software was underestimated | 2 | Eur/ME | Prod. Dev. | 2002 | August | 536868
3739 | Resource | People | Temp loss | 1 | 7 | New application was slow and some initial requirements were missed | 1 | Asia | Prod. Dev. | 2010 | November | 31961
3740 | Resource | People | Temp loss | 23 | 5 | Development plans failed to include all of the 23 required applications | 0 | Americas | IT/Solution | 2016 | January | 2286108
3741 | Resource | People | Temp loss | 18 | 5 | Lack of understanding the business processes used to develop manual reports and insufficient relevant experience | 2 | Eur/ME | Prod. Dev. | 2016 | April | 1160064
3742 | Resource | People | Temp loss | 1 | 9 | In creating a new system, there was too little involvement from the end users | 1 | Asia | IT/Solution | 2013 | November | 82708
3743 | Resource | People | Temp loss | 2 | 7 | Selected motor was not able to operate reliably requiring redesign | 0 | Americas | IT/Solution | 2006 | February | 127370
3744 | Schedule | Delay | Decision | 8 | 5 | Insufficient resources and little change control | 1 | Asia | Prod. Dev. | 2014 | January | 275224
3745 | Schedule | Delay | Decision | 17 | 4 | Insufficient analysis of new technology introduced late | 0 | Americas | IT/Solution | 2010 | March | 671840
3746 | Schedule | Delay | Decision | 14 | 6 | Development methods have limited (6-month) validation; if project slips, must be recertified | 1 | Asia | IT/Solution | 2014 | February | 1329860
3747 | Schedule | Delay | Hardware | 21 | 1 | Databases were not built to share information across systems | 2 | Eur/ME | Prod. Dev. | 2003 | March | 1106217
3748 | Schedule | Delay | Hardware | 5 | 6 | Lack of specialized labor to perform the task | 0 | Americas | Prod. Dev. | 2006 | March | 77010
3749 | Schedule | Delay | Hardware | 16 | 3 | Problem was not fully understood, leading to many changes | 0 | Americas | IT/Solution | 2013 | July | 696832
3750 | Schedule | Delay | Hardware | 16 | 8 | Module 1 team did not involve other developers during the initial scoping | 1 | Asia | Prod. Dev. | 2018 | July | 876432
3751 | Schedule | Delay | Hardware | 12 | 4 | Requesters failed to understand the complexity and did not make their wishes clear | 0 | Americas | Prod. Dev. | 2008 | December | 910860
3752 | Schedule | Delay | Information | 3 | 2 | Supplier code changes resulted in major backlog | 0 | Americas | Prod. Dev. | 2019 | November | 233832
3753 | Schedule | Delay | Information | 15 | 5 | Consultants failed to secure required resources in timely manner | 1 | Asia | IT/Solution | 2015 | September | 176085
3754 | Schedule | Delay | Information | 19 | 4 | WWW code supplied by third party late and poor quality; major delay and rework. | 2 | Eur/ME | IT/Solution | 2003 | December | 609387
3755 | Schedule | Delay | Information | 20 | 1 | Subcontractor refused to follow the core vendor’s processes | 2 | Eur/ME | Prod. Dev. | 2016 | May | 1141220
3756 | Schedule | Delay | Parts | 5 | 6 | Color printer version of app fails on WAN | 2 | Eur/ME | IT/Solution | 2019 | July | 442105
3757 | Schedule | Delay | Parts | 25 | 3 | Chronically understaffed business environment | 2 | Eur/ME | IT/Solution | 2016 | December | 407550
3758 | Schedule | Delay | Parts | 17 | 9 | Client slashed the original budget | 2 | Eur/ME | IT/Solution | 2016 | June | 1103759
3759 | Schedule | Delay | Parts | 9 | 2 | Legacy systems not retired as planned; project team tied up in unplanned support. | 2 | Eur/ME | Prod. Dev. | 2009 | August | 428562
3760 | Schedule | Delay | Parts | 5 | 2 | Delay in getting a firewall PM and a firewall engineer assigned | 2 | Eur/ME | Prod. Dev. | 2012 | August | 120655
3761 | Schedule | Dependency | Infrastructure | 25 | 9 | Parallel tasks require resources beyond what is available | 2 | Eur/ME | IT/Solution | 2002 | April | 1437325
3762 | Schedule | Dependency | Infrastructure | 22 | 5 | There were not enough vendors who had the capacity to manufacture specialized tools | 0 | Americas | Prod. Dev. | 2018 | May | 1317074
3763 | Schedule | Dependency | Infrastructure | 17 | 4 | Internal supplier problem; needed components delayed. | 1 | Asia | Prod. Dev. | 2019 | March | 1439815
3764 | Schedule | Dependency | Infrastructure | 16 | 2 | Issues found with the SOX documents provided by the legal team | 0 | Americas | IT/Solution | 2011 | April | 443152
3765 | Schedule | Dependency | Infrastructure | 10 | 9 | Reviews delayed on complex program, waiting for last team to finish phase work. | 1 | Asia | IT/Solution | 2010 | April | 934740
3766 | Schedule | Dependency | Infrastructure | 24 | 7 | Abnormally high turnover and shortage of capable developers in India | 2 | Eur/ME | IT/Solution | 2008 | January | 1915968
3767 | Schedule | Dependency | Infrastructure | 8 | 7 | Delay in hiring more engineers due to cost cutting | 1 | Asia | Prod. Dev. | 2004 | October | 677744
3768 | Schedule | Dependency | Legal | 15 | 4 | Turnover on staff 100% in year, leading to delays and training. | 0 | Americas | IT/Solution | 2015 | October | 912855
3769 | Schedule | Dependency | Project | 1 | 8 | There was a delay in the delivery of test samples | 0 | Americas | Prod. Dev. | 2008 | March | 69029
3770 | Schedule | Estimates | Deadline | 20 | 3 | Headcount required for document management was grossly underestimated | 0 | Americas | IT/Solution | 2001 | October | 1672960
3771 | Schedule | Estimates | Deadline | 25 | 7 | Flaw was found in the functional design | 0 | Americas | IT/Solution | 2008 | December | 971525
3772 | Schedule | Estimates | Judgment | 14 | 7 | Too little management interest and support | 0 | Americas | IT/Solution | 2001 | August | 738612
3773 | Schedule | Estimates | Judgment | 10 | 5 | Two projects depended on one resource for completion and this one had lower priority | 0 | Americas | IT/Solution | 2005 | October | 378550
3774 | Schedule | Estimates | Judgment | 19 | 8 | Change to US sourcing created demand and delays | 0 | Americas | IT/Solution | 2013 | January | 1022010
3775 | Schedule | Estimates | Judgment | 9 | 2 | Some parts are damaged in shipping and must be reordered. | 0 | Americas | IT/Solution | 2003 | May | 825867
3776 | Schedule | Estimates | Learning | 16 | 5 | Failure to collect the details about the interfaces and links to the third party websites | 0 | Americas | IT/Solution | 2017 | January | 771184
3777 | Schedule | Estimates | Learning | 9 | 5 | Developer from the database group was not available because of another project | 2 | Eur/ME | IT/Solution | 2004 | June | 586467
3778 | Schedule | Estimates | Learning | 15 | 3 | Toward the end of the development life cycle the original QA lead and trainer quit the firm | 0 | Americas | IT/Solution | 2019 | May | 996555
3779 | Schedule | Estimates | Learning | 9 | 2 | Contributor is leaving due to contract expiration | 2 | Eur/ME | IT/Solution | 2019 | April | 108396
3780 | Schedule | Estimates | Learning | 1 | 9 | On a very long project, enthusiasm and motivation falls; tasks stretch out. | 0 | Americas | Prod. Dev. | 2018 | September | 35285
3781 | Scope | Change | Creep | 12 | 2 | Staff lost to customer Hot Site | 0 | Americas | IT/Solution | 2007 | August | 713064
3782 | Scope | Change | Creep | 21 | 9 | Poor access to decision makers | 1 | Asia | IT/Solution | 2001 | December | 1281735
3783 | Scope | Change | Creep | 3 | 2 | Document transfer to sites takes more time and effort than expected. | 0 | Americas | Prod. Dev. | 2001 | October | 124332
3784 | Scope | Change | Creep | 12 | 4 | New pumps sent that lacked instructions and spare parts | 0 | Americas | Prod. Dev. | 2013 | December | 177792
3785 | Scope | Change | Creep | 5 | 7 | Lack of coordination between projects causes delays. | 2 | Eur/ME | IT/Solution | 2013 | November | 133190
3786 | Scope | Change | Creep | 20 | 9 | Translated text was too long | 0 | Americas | IT/Solution | 2001 | November | 1718380
3787 | Scope | Change | Creep | 19 | 8 | Scope was poorly defined | 1 | Asia | Prod. Dev. | 2011 | June | 1191623
3788 | Scope | Change | Creep | 24 | 9 | Software modules in system do not work together as planned. | 0 | Americas | Prod. Dev. | 2006 | November | 1244184
3789 | Scope | Change | Creep | 22 | 6 | Quality problems led to late redesign, extra work and plan changes. | 2 | Eur/ME | Prod. Dev. | 2011 | May | 1772496
3790 | Scope | Change | Creep | 13 | 6 | System move delayed by last minute system changes that delayed and made backups take too long. | 1 | Asia | Prod. Dev. | 2018 | April | 1024270
3791 | Scope | Change | Creep | 7 | 1 | Miscalculation on a critical task | 0 | Americas | Prod. Dev. | 2007 | May | 372834
3792 | Scope | Change | Creep | 5 | 1 | Bugs were reported by UAT that should have been caught by QA | 2 | Eur/ME | IT/Solution | 2014 | June | 434660
3793 | Resource | Outsourcing | Late or poor output | 18 | 6 | Databases were not built to share information across systems | 0 | Americas | Prod. Dev. | 2006 | October | 1444014
3794 | Resource | People | Loss | 23 | 6 | Added resources failed to cut the schedule in half | 0 | Americas | Prod. Dev. | 2009 | November | 1884528
3795 | Resource | People | Loss | 19 | 6 | Company wasted time developing functionality that was ultimately unimportant | 2 | Eur/ME | Prod. Dev. | 2004 | July | 1213435
3796 | Resource | People | Loss | 6 | 3 | Six weeks in, a redesign to the most fundamental part of the research was done | 0 | Americas | Prod. Dev. | 2006 | September | 337530
3797 | Resource | People | Temp loss | 19 | 7 | Partner on project defaults. | 0 | Americas | IT/Solution | 2010 | May | 1517682
3798 | Schedule | Delay | Decision | 24 | 7 | Significant growth of scope in renovation project | 0 | Americas | IT/Solution | 2006 | January | 1889880
3799 | Schedule | Delay | Information | 3 | 5 | No clear requirements from management | 2 | Eur/ME | Prod. Dev. | 2006 | September | 57465
3800 | Schedule | Delay | Parts | 24 | 4 | Did not have the correct people validate requirements | 1 | Asia | IT/Solution | 2004 | February | 1971720
3801 | Schedule | Estimates | Judgment | 23 | 9 | Expert opinion was 2 weeks; work took 8. | 0 | Americas | IT/Solution | 2002 | June | 1172034
3802 | Scope | Change | Gap | 24 | 7 | Six other projects required time and effort from our assigned engineer | 0 | Americas | Prod. Dev. | 2009 | October | 1091280
3803 | Scope | Change | Gap | 23 | 6 | Big scope change in the middle of the project | 2 | Eur/ME | IT/Solution | 2009 | July | 917861
3804 | Scope | Change | Gap | 18 | 9 | Lack of key SME resource availability when needed | 1 | Asia | Prod. Dev. | 2012 | October | 1275354
3805 | Scope | Change | Gap | 14 | 9 | Key resource tied to a previous project for two weeks | 2 | Eur/ME | Prod. Dev. | 2009 | September | 1197112
3806 | Scope | Change | Gap | 5 | 6 | As product increases, new packaging and unexpected shielding needed. | 2 | Eur/ME | Prod. Dev. | 2005 | September | 338350
3807 | Scope | Change | Gap | 6 | 5 | Requested requirement proved impossible, but was not actually needed | 0 | Americas | Prod. Dev. | 2009 | January | 244956
3808 | Scope | Change | Gap | 21 | 6 | New technology used, seeking faster results. It does not work and leads to redesign and rework. | 1 | Asia | Prod. Dev. | 2010 | March | 1705452
3809 | Scope | Change | Gap | 11 | 7 | Process does not scale to production; changes required. | 0 | Americas | Prod. Dev. | 2012 | March | 327228
3810 | Scope | Defect | Software | 21 | 3 | Designer doesn’t have skills to finish needed work | 1 | Asia | Prod. Dev. | 2019 | March | 591276
3811 | Scope | Change | Gap | 19 | 8 | There was not enough time to redo the programming to fix the errors identified | 1 | Asia | IT/Solution | 2014 | November | 1440922
3812 | Scope | Change | Gap | 3 | 1 | Programmer had a lack of experience in the healthcare industry | 0 | Americas | IT/Solution | 2016 | November | 258009
3813 | Schedule | Delay | Decision | 19 | 4 | Project priorities are unclear and secondary, less important work is done delaying required tasks. | 2 | Eur/ME | IT/Solution | 2001 | October | 1123071
3814 | Resource | People | Late start | 12 | 2 | Third-party vendor inadvertently introduced a bug during an upgrade | 0 | Americas | Prod. Dev. | 2016 | December | 874188
3815 | Scope | Change | Creep | 9 | 9 | Manufacturing volumes spiked and diverted project contributors. | 2 | Eur/ME | Prod. Dev. | 2002 | November | 707661
3816 | Resource | People | Loss | 18 | 6 | System needed was down for scheduled maintenance not in plan. | 0 | Americas | Prod. Dev. | 2010 | January | 1579140
3817 | Scope | Defect | Integration | 1 | 4 | Policy changes made late in a project requiring additional unplanned work. | 1 | Asia | Prod. Dev. | 2017 | June | 27810
3818 | Scope | Defect | Software | 15 | 3 | Development team members were hired regardless of the lack of business knowledge | 0 | Americas | Prod. Dev. | 2013 | December | 750330
3819 | Resource | Outsourcing | Late or poor output | 20 | 3 | Part was too long to ship, so it was cut. Result was useful only as raw material. | 0 | Americas | Prod. Dev. | 2019 | October | 1231240
3820 | Resource | People | Loss | 17 | 2 | Volume of new IC chip required for ramp not available. Major backlog on product delivery. | 0 | Americas | Prod. Dev. | 2018 | December | 279378
3821 | Resource | People | Loss | 13 | 1 | Inadequate procedures for acceptance, quality, and communications with development in India | 1 | Asia | Prod. Dev. | 2001 | April | 898482
3822 | Resource | People | Queuing | 11 | 1 | Some users couldn't login because of mixed case passwords | 2 | Eur/ME | IT/Solution | 2017 | September | 701393
3823 | Scope | Defect | Software | 14 | 7 | Key decisions stalled when system architect not available. | 2 | Eur/ME | IT/Solution | 2001 | July | 1235654
3824 | Resource | Money | Limitation | 10 | 5 | One SME for several projects | 1 | Asia | IT/Solution | 2014 | August | 145380
3825 | Resource | Outsourcing | Late or poor output | 1 | 2 | Fix for critical bug was delayed | 1 | Asia | IT/Solution | 2002 | December | 91628
3826 | Resource | Outsourcing | Late or poor output | 5 | 1 | Problems with manufacturing arose that were not seen in the original analysis | 0 | Americas | IT/Solution | 2001 | August | 230445
3827 | Scope | Change | Creep | 5 | 8 | Adopting the selected system required several new pieces of major software | 1 | Asia | IT/Solution | 2007 | August | 334240
3828 | Scope | Defect | Software | 19 | 4 | The Product Manager never told the team what the customer was asking for | 2 | Eur/ME | IT/Solution | 2017 | July | 989995
3829 | Resource | Money | Limitation | 12 | 6 | Because of incopetence, a second consultant was hired to redo the work | 1 | Asia | IT/Solution | 2018 | November | 828492
3830 | Resource | Outsourcing | Late or poor output | 15 | 1 | Unrealistic deadline set; slips unavoidable. | 2 | Eur/ME | Prod. Dev. | 2003 | March | 505605
3831 | Schedule | Delay | Hardware | 22 | 4 | After more than 2/3 of the original budget had been expended, a major design change resulted in major requirement modifications and additions | 2 | Eur/ME | Prod. Dev. | 2003 | March | 2085204
3832 | Scope | Change | Creep | 26 | 9 | Outsource company’s abilities were poor and they had to be replaced | 2 | Eur/ME | IT/Solution | 2007 | February | 1920308
3833 | Scope | Change | Creep | 25 | 5 | Outsourcing partner in Switzerland did unneeded work, delaying their inputs | 0 | Americas | IT/Solution | 2011 | September | 1732050
3834 | Scope | Defect | Hardware | 26 | 6 | Lead Engineer’s resignation | 0 | Americas | IT/Solution | 2011 | September | 915616
3835 | Scope | Defect | Software | 23 | 1 | The business analyst was unavailable for project work due to her backup role for a higher priority project | 1 | Asia | Prod. Dev. | 2003 | September | 1068304
3836 | Schedule | Delay | Parts | 18 | 3 | Need to get input from one of the external group for specific info; late | 2 | Eur/ME | IT/Solution | 2005 | February | 434736
3837 | Schedule | Delay | Parts | 15 | 4 | The scope of the project was poorly defined | 1 | Asia | IT/Solution | 2003 | April | 1327260
3838 | Scope | Change | Creep | 26 | 7 | New application works, but data collected is not accessible. | 0 | Americas | IT/Solution | 2005 | December | 1961206
3839 | Scope | Change | Gap | 24 | 7 | Lost a key programmer | 1 | Asia | Prod. Dev. | 2008 | August | 1309200
3840 | Resource | Outsourcing | Delayed start | 19 | 6 | Key contributor left the company | 1 | Asia | Prod. Dev. | 2003 | December | 1719177
3841 | Resource | Outsourcing | Late or poor output | 7 | 4 | Problems associated with confidential patient information in transit without a tracking mechanism surfaced during the project | 2 | Eur/ME | IT/Solution | 2005 | December | 564459
3842 | Resource | People | Late start | 26 | 3 | Change Management Lead took unexpected medical leave | 1 | Asia | IT/Solution | 2003 | November | 2562560
3843 | Resource | People | Queuing | 22 | 3 | Decisions are being delayed without apparent reason | 0 | Americas | IT/Solution | 2018 | November | 1117512
3844 | Schedule | Delay | Parts | 20 | 7 | During required short visits, the network was sometimes down for an indefinite amount of time, requiring a second trip | 1 | Asia | Prod. Dev. | 2003 | January | 615940
3845 | Scope | Change | Creep | 3 | 4 | Compilers and open source libraries needed were not available | 0 | Americas | IT/Solution | 2010 | January | 80706
3846 | Scope | Defect | Hardware | 5 | 1 | Project had aggressive timeline and due to rush details were poorly defined | 0 | Americas | Prod. Dev. | 2016 | September | 464040
3847 | Resource | People | Queuing | 2 | 8 | Design documentation was signed off by users, but had fatal flaws | 1 | Asia | Prod. Dev. | 2005 | July | 141652
3848 | Schedule | Delay | Decision | 1 | 4 | Failure to not carefully proofread the documents to be produced before printing | 2 | Eur/ME | IT/Solution | 2018 | December | 22756
3849 | Schedule | Delay | Information | 14 | 9 | Bug surfaced one day after implementation | 2 | Eur/ME | IT/Solution | 2001 | August | 1073884
3850 | Resource | Outsourcing | Late or poor output | 1 | 7 | Critical person went on maternity leave | 2 | Eur/ME | Prod. Dev. | 2015 | July | 88101
3851 | Scope | Change | Creep | 13 | 8 | "50%" resources are not aligned, resulting in activity delays | 1 | Asia | IT/Solution | 2006 | January | 861861
3852 | Scope | Change | Gap | 15 | 8 | Two of the developers were able to work on the project only 60% of their time, not full time | 2 | Eur/ME | IT/Solution | 2011 | July | 1496085
3853 | Scope | Defect | Hardware | 8 | 6 | Key IT resources scheduled extensive vacations | 2 | Eur/ME | IT/Solution | 2011 | January | 575992
3854 | Resource | Money | Limitation | 11 | 9 | Study timeline set before staff vacation dates were known | 2 | Eur/ME | IT/Solution | 2001 | August | 816574
3855 | Scope | Change | Creep | 6 | 2 | With 12 hour time difference and dependence on E-mail, even simple questions take 2-4 days to resolve. | 0 | Americas | Prod. Dev. | 2010 | January | 417792
3856 | Scope | Change | Creep | 24 | 4 | Had only 1/3 of the units needed on time | 1 | Asia | IT/Solution | 2014 | April | 1237680
3857 | Resource | People | Loss | 25 | 7 | Team was staffed by 3 successive new hires in a six-month period | 2 | Eur/ME | IT/Solution | 2010 | March | 2050425
3858 | Resource | People | Temp loss | 7 | 6 | Deliverable requirements were discovered during the execution phase | 2 | Eur/ME | IT/Solution | 2009 | December | 328482
3859 | Schedule | Delay | Information | 15 | 7 | Project relocated manufacturing to a contract manufacturer. Required management decisions are frequent and too slow. | 0 | Americas | Prod. Dev. | 2015 | April | 360840
3860 | Schedule | Delay | Parts | 22 | 1 | Telecom line delays | 0 | Americas | IT/Solution | 2015 | August | 1869670
3861 | Schedule | Estimates | Learning | 2 | 5 | Insufficient time was scheduled for testing | 2 | Eur/ME | IT/Solution | 2014 | March | 34948
3862 | Resource | Money | Limitation | 5 | 4 | Scope of product categories was broadened significantly | 0 | Americas | IT/Solution | 2012 | August | 351185
3863 | Schedule | Delay | Hardware | 16 | 8 | New software installed by IT. It does not work, and causes delay to fix. | 0 | Americas | IT/Solution | 2004 | August | 1161040
3864 | Schedule | Estimates | Judgment | 16 | 4 | Dependency on other project not discovered until project end. | 0 | Americas | Prod. Dev. | 2006 | November | 1271264
3865 | Scope | Change | Gap | 4 | 8 | Legal required late changes to a large print run of materials | 0 | Americas | Prod. Dev. | 2016 | June | 286984
3866 | Resource | Outsourcing | Late or poor output | 23 | 8 | Unexpectedly, the FDA requires a long-term toxicity study | 0 | Americas | IT/Solution | 2001 | November | 1741100
3867 | Resource | People | Queuing | 20 | 5 | SumTotal LMS user interface is significantly more complex than the Docent LMS user interface it is to replace | 0 | Americas | Prod. Dev. | 2005 | December | 1359760
3868 | Scope | Change | Creep | 20 | 2 | Unrealistic scope in very short timeframe. | 0 | Americas | Prod. Dev. | 2006 | February | 821320
3869 | Resource | People | Loss | 6 | 8 | Scope initially proposed for the project was not signed off by the upper management | 0 | Americas | Prod. Dev. | 2014 | April | 391860
3870 | Resource | People | Temp loss | 7 | 9 | Lack of oversight and quality assurance led to short cuts being taken | 0 | Americas | IT/Solution | 2019 | August | 652743
3871 | Schedule | Dependency | Legal | 16 | 2 | Tests revealed a fatal issue, deferring release to next quartely update | 2 | Eur/ME | Prod. Dev. | 2018 | November | 1518544
3872 | Schedule | Estimates | Deadline | 5 | 8 | Application changed for prospective Chinese customer (who did not buy) | 0 | Americas | Prod. Dev. | 2013 | December | 302370
3873 | Scope | Change | Creep | 18 | 3 | Software development underestimated by a factor of three. | 0 | Americas | IT/Solution | 2014 | August | 1276218
3874 | Scope | Change | Creep | 20 | 1 | Major failure in the Validation tests | 2 | Eur/ME | IT/Solution | 2018 | March | 1765220
3875 | Scope | Change | Creep | 19 | 4 | Unrelaible and incopentent contractors | 1 | Asia | IT/Solution | 2012 | February | 1480366
3876 | Scope | Change | Gap | 3 | 3 | It took a over month to get the custom designed equipment | 0 | Americas | Prod. Dev. | 2005 | October | 45396
3877 | Resource | Money | Limitation | 18 | 7 | No cross training within the team to make more knowledgeable resources available | 2 | Eur/ME | Prod. Dev. | 2018 | November | 585504
3878 | Resource | Outsourcing | Late or poor output | 22 | 8 | Late stakeholders redefine requiremnts | 2 | Eur/ME | IT/Solution | 2017 | April | 2035968
3879 | Resource | Outsourcing | Late or poor output | 3 | 9 | Constant design changes occurred and parts had to be scrapped and replaced | 0 | Americas | Prod. Dev. | 2004 | July | 279045
3880 | Resource | People | Loss | 21 | 9 | Contractor was uncooperative and late | 2 | Eur/ME | Prod. Dev. | 2014 | May | 940002
3881 | Resource | People | Temp loss | 26 | 8 | Outsourcing delayed the order entry process for all U.S. Based customers | 0 | Americas | IT/Solution | 2014 | August | 1663480
3882 | Schedule | Delay | Information | 25 | 5 | Foundation was inadaquate and needed upgrading | 0 | Americas | IT/Solution | 2003 | February | 2200725
3883 | Scope | Change | Creep | 17 | 2 | Work was intentionally underestimatged to win the contract | 0 | Americas | Prod. Dev. | 2017 | December | 1277091
3884 | Scope | Change | Gap | 10 | 9 | Project required a change to the current website technology | 2 | Eur/ME | IT/Solution | 2015 | March | 576780
3885 | Schedule | Delay | Decision | 19 | 6 | In large system conversion, new applications cannot find and work with existing data as expected. Lots of redirecting and conversion is required. | 0 | Americas | IT/Solution | 2009 | March | 1438889
3886 | Schedule | Delay | Parts | 14 | 9 | Initial stages were outsourced to a professor who started late and lacked needed information | 1 | Asia | Prod. Dev. | 2012 | January | 626612
3887 | Schedule | Dependency | Project | 11 | 6 | Vendor missed validation due date delaying Clinical Trials | 0 | Americas | IT/Solution | 2004 | July | 984170
3888 | Resource | Outsourcing | Late or poor output | 16 | 1 | Layoffs in the company | 2 | Eur/ME | IT/Solution | 2001 | January | 1005664
3889 | Schedule | Dependency | Project | 24 | 5 | Project team members reassigned. Not replaced; led to overtime, quality problems, missed deadlines. | 2 | Eur/ME | Prod. Dev. | 2013 | December | 1201320
3890 | Scope | Change | Gap | 26 | 1 | Staff lost to customer Hot Site | 2 | Eur/ME | Prod. Dev. | 2014 | June | 1369862
3891 | Resource | Money | Limitation | 20 | 9 | Key stakeholders were not identified during requirements gathering | 0 | Americas | Prod. Dev. | 2012 | February | 304540
3892 | Resource | People | Queuing | 15 | 4 | All components pass tests, but assembled system fails. Rework causes delay. | 0 | Americas | Prod. Dev. | 2011 | April | 1242885
3893 | Scope | Change | Creep | 8 | 3 | Poor planning for the transition between consultants | 0 | Americas | Prod. Dev. | 2002 | April | 393552
3894 | Scope | Change | Gap | 25 | 8 | Engineering consultant firm laid off a chief structural engineer late in project | 0 | Americas | IT/Solution | 2012 | March | 408675
3895 | Scope | Change | Gap | 4 | 7 | All students did not complete training as scheduled, so the project is completed late | 0 | Americas | IT/Solution | 2017 | October | 123752
3896 | Schedule | Dependency | Project | 17 | 1 | Expert worked on at least 4-5 projects at a time | 2 | Eur/ME | Prod. Dev. | 2013 | September | 1617142
3897 | Scope | Change | Creep | 26 | 9 | Multiple projects depend on lone expert scientist | 1 | Asia | Prod. Dev. | 2006 | August | 2194530
3898 | Resource | Outsourcing | Late or poor output | 21 | 5 | Errors found in data and critrical reports | 1 | Asia | IT/Solution | 2011 | March | 2040171
3899 | Resource | People | Temp loss | 12 | 4 | There was a communication lag | 2 | Eur/ME | Prod. Dev. | 2018 | August | 1165140
3900 | Scope | Change | Gap | 15 | 7 | Testing time underestimated. | 2 | Eur/ME | Prod. Dev. | 2013 | March | 410175
3901 | Resource | People | Temp loss | 14 | 8 | Metrics from many sites required. When collected, additional work required to make consistent. | 0 | Americas | IT/Solution | 2010 | December | 340858
3902 | Scope | Change | Creep | 6 | 2 | Bug could be fixed only by moving to a later version of software | 2 | Eur/ME | IT/Solution | 2002 | April | 250260
3903 | Scope | Defect | Hardware | 6 | 8 | Out of stock on key parts needed for PC boards. | 0 | Americas | Prod. Dev. | 2014 | June | 459972
3904 | Resource | Money | Limitation | 14 | 3 | Research and development were outsourced, but the relationship was not managed well, and all work was ultimately redone | 2 | Eur/ME | Prod. Dev. | 2008 | November | 1203188
3905 | Resource | Outsourcing | Late or poor output | 6 | 1 | Lack of people resources (designers, requirement/business analysts, data modelers and QA/Testing) | 0 | Americas | Prod. Dev. | 2018 | August | 179616
3906 | Resource | Outsourcing | Late or poor output | 1 | 6 | Complexities of solution not understood, even well into project | 0 | Americas | Prod. Dev. | 2009 | February | 98771
3907 | Scope | Change | Gap | 25 | 2 | Critical application delivery late | 0 | Americas | Prod. Dev. | 2019 | December | 555575
3908 | Resource | Outsourcing | Delayed start | 4 | 1 | Development methods have limited (6-month) validation; if project slips, must be recertified | 0 | Americas | IT/Solution | 2013 | June | 166756
3909 | Resource | People | Queuing | 23 | 2 | Process change led to recertification requirements and delay | 1 | Asia | IT/Solution | 2016 | September | 301392
3910 | Resource | People | Queuing | 4 | 9 | The manager of a related project allowed stakeholders to change the scope, driving continual changes | 1 | Asia | IT/Solution | 2006 | February | 292576
3911 | Schedule | Delay | Information | 16 | 6 | During a company-wide OS refresh of all desktops and laptops, a merger occurred. Complexity added. | 2 | Eur/ME | IT/Solution | 2010 | January | 1052496
3912 | Schedule | Dependency | Infrastructure | 16 | 7 | System for expense analysis expanded into redesign of most major internal systems | 2 | Eur/ME | IT/Solution | 2004 | June | 1280224
3913 | Scope | Change | Creep | 5 | 2 | Code freeze not done until the release date, making training and documentation late | 0 | Americas | Prod. Dev. | 2006 | October | 335715
3914 | Scope | Change | Gap | 6 | 6 | Unrealistic scope in very short timeframe. | 0 | Americas | Prod. Dev. | 2013 | June | 182514
3915 | Scope | Change | Gap | 13 | 8 | Inaccurate comparison between our requirements and the software | 0 | Americas | Prod. Dev. | 2008 | January | 708695
3916 | Scope | Defect | Hardware | 7 | 9 | Lack of Stakeholder commitment and oversight | 1 | Asia | IT/Solution | 2010 | February | 558362
3917 | Resource | People | Queuing | 23 | 5 | Changes to outside providers resulted in major delays | 0 | Americas | IT/Solution | 2019 | April | 521226
3918 | Schedule | Dependency | Infrastructure | 26 | 2 | Development team members were hired regardless of the lack of business knowledge | 1 | Asia | Prod. Dev. | 2019 | September | 1662622
3919 | Resource | Outsourcing | Late or poor output | 11 | 4 | Customer requirement discovered late in project | 1 | Asia | Prod. Dev. | 2002 | July | 484957
3920 | Resource | Outsourcing | Late or poor output | 3 | 7 | Significant additional testing required; discovered late | 1 | Asia | IT/Solution | 2017 | June | 217710
3921 | Schedule | Delay | Hardware | 16 | 1 | Two of the SAP technicians were reassigned to a more “business critical” project midway through the system development phase. | 1 | Asia | IT/Solution | 2004 | December | 742208
3922 | Schedule | Delay | Parts | 20 | 8 | Vendor merger caused interruption in hardware availability; had to recertify | 0 | Americas | IT/Solution | 2007 | November | 1441620
3923 | Schedule | Delay | Parts | 6 | 3 | Requirements were unclear at the beginning of the project | 0 | Americas | IT/Solution | 2016 | August | 421266
3924 | Scope | Change | Gap | 12 | 6 | Layoffs in mid-project | 0 | Americas | IT/Solution | 2003 | December | 947280
3925 | Scope | Defect | Software | 19 | 7 | Failed to get client sign-off for work done in India | 1 | Asia | Prod. Dev. | 2003 | May | 1890538
3926 | Scope | Defect | Software | 19 | 1 | Consultant who worked on benefits was taken off the project | 0 | Americas | Prod. Dev. | 2016 | November | 1142337
3927 | Scope | Defect | Software | 11 | 5 | Chronic optimism on completion dates for work | 1 | Asia | IT/Solution | 2006 | June | 972312
3928 | Scope | Defect | Hardware | 14 | 7 | Late change required to meet code | 0 | Americas | Prod. Dev. | 2014 | July | 373772
3929 | Resource | Outsourcing | Late or poor output | 5 | 7 | Key parts would be delivered late | 1 | Asia | IT/Solution | 2011 | October | 98385
3930 | Resource | Outsourcing | Late or poor output | 19 | 5 | Customer insists on deadline shorter than plan. Attempted, but not possible. | 0 | Americas | Prod. Dev. | 2017 | June | 1635463
3931 | Resource | Outsourcing | Late or poor output | 24 | 4 | Work done by contractors with too little information; components require rework. | 2 | Eur/ME | IT/Solution | 2011 | July | 548784
3932 | Resource | People | Motivation | 15 | 7 | The programmer hadn’t understood how certain parts of the program date-logic worked and hadn’t asked for any assistance. | 1 | Asia | IT/Solution | 2013 | April | 210900
3933 | Schedule | Delay | Information | 4 | 3 | Localization of the web contents delivery is delayed | 0 | Americas | Prod. Dev. | 2016 | May | 75856
3934 | Schedule | Estimates | Learning | 15 | 5 | ASIC supplier (only source) was fine for low volume, but at lower cost and high volume had quality problems and created delays. | 0 | Americas | Prod. Dev. | 2019 | March | 996180
3935 | Scope | Change | Creep | 21 | 8 | The integration task was not defined and broken down to sufficiently small pieces in the project plan. | 0 | Americas | IT/Solution | 2008 | September | 827295
3936 | Scope | Change | Creep | 19 | 2 | Oversea engineering team was inexperienced | 0 | Americas | Prod. Dev. | 2008 | July | 1339804
3937 | Scope | Change | Dependency | 8 | 1 | No proper change control process resulted in unnecessary new requirements | 0 | Americas | IT/Solution | 2003 | May | 464928
3938 | Scope | Change | Gap | 16 | 9 | Lack of communication between the teams | 1 | Asia | IT/Solution | 2012 | July | 339840
3939 | Scope | Change | Gap | 2 | 3 | Failure to understand the scope of the project | 0 | Americas | Prod. Dev. | 2017 | June | 138412
3940 | Scope | Change | Gap | 25 | 6 | Instructions provided to the testing facility were too vague, necessitating re-tests | 0 | Americas | Prod. Dev. | 2012 | June | 1772125
3941 | Scope | Defect | Hardware | 22 | 6 | Network configuration sometimes causes the backups to fail intermittently; troubleshooting is hard. | 0 | Americas | IT/Solution | 2018 | May | 1687466
3942 | Scope | Defect | Hardware | 1 | 1 | Lead engineer stuck in Japan for 2 weeks longer than expected | 0 | Americas | IT/Solution | 2015 | September | 91006
3943 | Scope | Defect | Software | 20 | 7 | Code review delayed due to merger | 0 | Americas | IT/Solution | 2018 | December | 209480
3944 | Scope | Defect | Software | 26 | 2 | Orders sometimes get lost in manual routing | 1 | Asia | IT/Solution | 2010 | January | 276224
3945 | Resource | Money | Limitation | 17 | 2 | Client changes her mind every step of the way | 1 | Asia | IT/Solution | 2001 | April | 1251574
3946 | Resource | Money | Limitation | 3 | 8 | Online badge printing requirement completely missing from scope definition | 0 | Americas | IT/Solution | 2016 | April | 128853
3947 | Scope | Change | Gap | 10 | 9 | Scope was not discussed with the manufacturer before design was completed | 0 | Americas | IT/Solution | 2009 | November | 889680
3948 | Schedule | Dependency | Project | 25 | 3 | Solution project integrated new, untried technology. Difficulty getting it to work. | 2 | Eur/ME | Prod. Dev. | 2009 | March | 1213800
3949 | Schedule | Delay | Information | 10 | 9 | Excessive bugs detected late; delayed to fix. | 1 | Asia | IT/Solution | 2002 | October | 663540
3950 | Scope | Change | Gap | 2 | 7 | US expertise needed for project in Asia. Team member flies to US, but expert is busy. | 0 | Americas | IT/Solution | 2007 | January | 124954
3951 | Schedule | Dependency | Infrastructure | 11 | 8 | Key welding staff are out with flu | 0 | Americas | Prod. Dev. | 2011 | March | 941127
3952 | Scope | Change | Dependency | 20 | 4 | No coordinated shipment of system components; last one delays installation. | 2 | Eur/ME | IT/Solution | 2014 | September | 1474400
3953 | Scope | Change | Gap | 3 | 4 | Project wanted by management but never gets team buy-in. Even with heavy monitoring, project work is slow. | 0 | Americas | Prod. Dev. | 2003 | March | 112179
3954 | Scope | Defect | Software | 7 | 7 | Volume of new IC chip required for ramp not available. Major backlog on product delivery. | 0 | Americas | IT/Solution | 2012 | April | 674821
3955 | Resource | Outsourcing | Delayed start | 9 | 3 | Changes to outside providers resulted in major delays | 2 | Eur/ME | Prod. Dev. | 2006 | June | 847566
3956 | Resource | People | Loss | 24 | 1 | Interdependencies in complex program underestimated and detected late. | 0 | Americas | IT/Solution | 2001 | May | 1548048
3957 | Resource | People | Loss | 2 | 5 | Late rescoping of 2-year project led to half-year slip. | 2 | Eur/ME | IT/Solution | 2006 | March | 94610
3958 | Schedule | Delay | Decision | 3 | 3 | Extension of scope in Japan was not managed or controlled well | 2 | Eur/ME | IT/Solution | 2015 | December | 31779
3959 | Scope | Change | Creep | 12 | 5 | Mid-project feature revisions. Major impact on effort and schedule; product failed (too late to market). | 0 | Americas | IT/Solution | 2014 | May | 605148
3960 | Scope | Change | Gap | 18 | 2 | Survey data required for project assigned to several people in some countries; each assumes others will do work | 0 | Americas | Prod. Dev. | 2013 | February | 1585116
3961 | Resource | Outsourcing | Late or poor output | 8 | 3 | There was a very large mismatch between stakeholder expectations and given scope | 2 | Eur/ME | Prod. Dev. | 2001 | January | 727184
3962 | Resource | People | Late start | 10 | 6 | Redesign required late in printer project to meet print quality goals. Major slip. | 0 | Americas | IT/Solution | 2019 | December | 389390
3963 | Schedule | Delay | Parts | 22 | 8 | Purchased component never delivered (vaporware). Workaround developed by brute force (not high-tech and difficult to support). | 0 | Americas | IT/Solution | 2001 | July | 935110
3964 | Scope | Change | Creep | 14 | 6 | Project was constantly having resources pulled for higher priority work | 2 | Eur/ME | IT/Solution | 2015 | July | 265160
3965 | Scope | Change | Creep | 3 | 7 | Project wanted by management but never gets team buy-in. Even with heavy monitoring, project work is slow. | 2 | Eur/ME | IT/Solution | 2013 | January | 195495
3966 | Scope | Change | Gap | 2 | 9 | Excessive changes made | 2 | Eur/ME | IT/Solution | 2018 | August | 94672
3967 | Resource | Outsourcing | Late or poor output | 1 | 8 | Contract manufacturer failed to deliver a new drug | 2 | Eur/ME | IT/Solution | 2017 | September | 75969
3968 | Resource | People | Temp loss | 24 | 2 | Ramp-up required 40 new test engineers | 0 | Americas | IT/Solution | 2006 | September | 1222968
3969 | Schedule | Estimates | Learning | 4 | 1 | Our server crashed, which contains 4 months worth of info. No backup, had to be reentered. | 1 | Asia | IT/Solution | 2014 | January | 395436
3970 | Scope | Change | Dependency | 2 | 5 | Software in use casused unacceptable image distortion | 2 | Eur/ME | IT/Solution | 2017 | December | 199146
3971 | Scope | Defect | Hardware | 5 | 2 | Team did not break down the processes enough to clearly identify each step | 2 | Eur/ME | IT/Solution | 2008 | July | 90785
3972 | Resource | Outsourcing | Late or poor output | 1 | 5 | A mid-project review turned up numerous regulations that were not implemented | 1 | Asia | Prod. Dev. | 2011 | February | 56366
3973 | Resource | Outsourcing | Late or poor output | 16 | 8 | System tool could not be scaled to a huge web application | 2 | Eur/ME | IT/Solution | 2018 | November | 217200
3974 | Schedule | Dependency | Infrastructure | 26 | 6 | Database contains incorrect information and the QA environment is unstable | 0 | Americas | IT/Solution | 2018 | January | 1880138
3975 | Schedule | Estimates | Learning | 6 | 7 | Project has customer info, but also needs supplier data. Project to provide this is delayed. | 0 | Americas | IT/Solution | 2019 | January | 569094
3976 | Scope | Change | Dependency | 19 | 7 | Lack of IT subject matter experts | 1 | Asia | Prod. Dev. | 2003 | May | 1449947
3977 | Resource | People | Temp loss | 5 | 2 | Project work estimated to take 1 month took 3 due to loss of staff to do the work. | 1 | Asia | IT/Solution | 2006 | March | 210350
3978 | Schedule | Delay | Decision | 16 | 5 | Specialist was busy with a lot of work | 0 | Americas | IT/Solution | 2007 | November | 1174480
3979 | Schedule | Delay | Hardware | 15 | 4 | Additional renovations added late that were not in the original plan | 0 | Americas | Prod. Dev. | 2016 | May | 307545
3980 | Schedule | Delay | Parts | 24 | 8 | Lead engineer thought he had a good ‘understanding’ of what needed to be done | 2 | Eur/ME | Prod. Dev. | 2012 | October | 1243728
3981 | Schedule | Dependency | Infrastructure | 4 | 7 | Partner company introduced a changed requirement late in development | 1 | Asia | IT/Solution | 2012 | January | 147052
3982 | Schedule | Dependency | Project | 18 | 4 | Additional localization requirements will cost significant extra effort and time | 1 | Asia | Prod. Dev. | 2011 | September | 256194
3983 | Schedule | Estimates | Judgment | 8 | 5 | Late addition of a USB port to a recharging adapter | 0 | Americas | Prod. Dev. | 2016 | September | 154136
3984 | Scope | Change | Creep | 8 | 2 | Old hardware became unavailable and product had to be tested on the new series | 0 | Americas | Prod. Dev. | 2010 | April | 410384
3985 | Scope | Change | Gap | 19 | 8 | Understaffing causes overtime and leads to loss of staff | 1 | Asia | IT/Solution | 2006 | September | 1518404
3986 | Scope | Defect | Integration | 7 | 6 | The Project Lead did not hold the customer/business line accountable for their delay | 1 | Asia | IT/Solution | 2019 | December | 286398
3987 | Scope | Change | Creep | 2 | 8 | Key person lost mid-project | 0 | Americas | IT/Solution | 2019 | September | 198268
3988 | Schedule | Estimates | Deadline | 23 | 3 | Team members reassigned to other, higher priority projects. | 0 | Americas | IT/Solution | 2013 | July | 680662
3989 | Schedule | Estimates | Learning | 3 | 9 | Contributor has lengthy, unannounced vacation | 0 | Americas | Prod. Dev. | 2006 | March | 243138
3990 | Scope | Change | Creep | 2 | 4 | Development scheduled in parallel leads to frequent rework. | 0 | Americas | Prod. Dev. | 2019 | September | 119094
3991 | Scope | Change | Creep | 8 | 9 | Several applications were changed due to change in project requirements | 1 | Asia | IT/Solution | 2010 | December | 740432
3992 | Scope | Change | Creep | 13 | 1 | Insufficient length of anchor bolts protruding from the concrete foundation to allow the base plate nuts to fully engage | 0 | Americas | Prod. Dev. | 2007 | November | 625027
3993 | Scope | Change | Gap | 3 | 9 | Part of the project team ran of money three months before the project was scheduled to end | 0 | Americas | IT/Solution | 2016 | December | 80763
3994 | Resource | Money | Limitation | 8 | 8 | Growth pushed work to understaffed contract firms | 1 | Asia | Prod. Dev. | 2011 | April | 464920
3995 | Scope | Change | Creep | 5 | 4 | Finding instructional designers that know how to use specialized software | 0 | Americas | IT/Solution | 2011 | September | 452895
3996 | Scope | Change | Gap | 10 | 1 | Only 2 people understood the new system, and neither was available | 0 | Americas | IT/Solution | 2011 | May | 848450
3997 | Resource | People | Motivation | 11 | 7 | ASIC delays | 1 | Asia | IT/Solution | 2006 | March | 568799
3998 | Scope | Change | Gap | 21 | 1 | International shipment of parts supposed to take 6 weeks, actually averages 9. | 0 | Americas | IT/Solution | 2012 | August | 1018416
3999 | Schedule | Delay | Parts | 15 | 9 | Due to organizational change new person was assigned the work | 0 | Americas | Prod. Dev. | 2012 | May | 649200
4000 | Resource | People | Loss | 26 | 9 | Client requested "15 minute" change accepted and led to delay and loss on project | 1 | Asia | Prod. Dev. | 2003 | November | 2098902
4001 | Resource | People | Loss | 19 | 4 | Lack of data and knowledge for the new product | 0 | Americas | IT/Solution | 2008 | October | 199272
4002 | Resource | People | Motivation | 8 | 8 | Documentation provided in only one of two required languages. Delay for translation. | 0 | Americas | IT/Solution | 2005 | August | 121656
4003 | Scope | Change | Creep | 12 | 8 | Outsourcing firm had an incompetent design team | 0 | Americas | Prod. Dev. | 2008 | November | 865452
4004 | Resource | Money | Limitation | 10 | 8 | Contract had no penalties for missing deadlines; 3 weeks taken on 1 week task. | 0 | Americas | IT/Solution | 2005 | August | 759950
4005 | Resource | People | Loss | 20 | 7 | Insufficient planning and commitment by the committee involved | 1 | Asia | IT/Solution | 2012 | May | 1840260
4006 | Schedule | Delay | Parts | 12 | 8 | Project involved several departments, several of which were uncooperative | 0 | Americas | Prod. Dev. | 2018 | October | 882216
4007 | Schedule | Estimates | Learning | 4 | 4 | Incorrect part shipped. Delay for reshipment. | 0 | Americas | Prod. Dev. | 2019 | September | 320148
4008 | Scope | Defect | Software | 6 | 3 | Late in long project, process rigor falls and changes are managed poorly. | 0 | Americas | IT/Solution | 2010 | April | 173046
4009 | Resource | Outsourcing | Delayed start | 25 | 1 | Upgrade to software required. Planning and training caused delays. | 0 | Americas | Prod. Dev. | 2016 | April | 1933950
4010 | Resource | People | Loss | 10 | 9 | Excessive bugs | 0 | Americas | IT/Solution | 2013 | May | 558230
4011 | Scope | Change | Gap | 6 | 9 | Did not have sufficient resources and the contingency plan was inadequate | 1 | Asia | IT/Solution | 2001 | October | 92160
4012 | Scope | Change | Gap | 10 | 8 | "Customer supplied" hardware does not work. Replacement required. | 0 | Americas | IT/Solution | 2016 | March | 207230
4013 | Scope | Change | Gap | 14 | 4 | Vendor was unable to control the environment: work had to be repeated | 0 | Americas | IT/Solution | 2019 | July | 1013880
4014 | Scope | Defect | Hardware | 13 | 3 | Key supplier purchased by other company and reorganized. Forced to find new supplier. | 1 | Asia | Prod. Dev. | 2012 | December | 167414
4015 | Resource | Outsourcing | Late or poor output | 22 | 7 | Significant delay in patient recruitment | 0 | Americas | IT/Solution | 2005 | November | 716804
4016 | Resource | People | Queuing | 17 | 3 | Indefinite loss of key staff member | 0 | Americas | IT/Solution | 2011 | August | 834445
4017 | Scope | Change | Creep | 16 | 1 | Staff cutbacks (and dropped scope as well) | 1 | Asia | Prod. Dev. | 2016 | July | 533840
4018 | Scope | Change | Gap | 9 | 8 | Insufficient QA resources to cover the auditing tasks and training tasks. | 0 | Americas | IT/Solution | 2016 | December | 668538
4019 | Resource | People | Temp loss | 16 | 2 | Delay in patient recruitment for clinical trials | 0 | Americas | IT/Solution | 2006 | September | 1372832
4020 | Schedule | Delay | Information | 13 | 8 | Servers got stuck in customs | 0 | Americas | Prod. Dev. | 2007 | November | 816933
4021 | Schedule | Delay | Parts | 6 | 4 | Software is developed in Israel. In a week, there was less than one working day for teleconference and war made it impractical to travel. Needed info was always late. | 0 | Americas | IT/Solution | 2008 | February | 174438
4022 | Schedule | Estimates | Judgment | 20 | 5 | Part was too long to ship, so it was cut. Result was useful only as raw material. | 0 | Americas | Prod. Dev. | 2006 | May | 865100
4023 | Scope | Change | Gap | 24 | 7 | Unexpectedly, the FDA requires a long-term toxicity study | 0 | Americas | IT/Solution | 2007 | August | 605400
4024 | Schedule | Delay | Hardware | 12 | 6 | Project was constantly having resources pulled for higher priority work | 0 | Americas | IT/Solution | 2015 | April | 1072608
4025 | Schedule | Dependency | Infrastructure | 8 | 8 | Complexity of the investigation was badly underestimated | 0 | Americas | IT/Solution | 2019 | January | 334456
4026 | Schedule | Dependency | Project | 5 | 4 | Severe learning curve of somestaff slowed progress | 0 | Americas | IT/Solution | 2018 | December | 173990
4027 | Schedule | Estimates | Deadline | 24 | 4 | Inexperienced staff | 0 | Americas | Prod. Dev. | 2004 | June | 834408
4028 | Scope | Change | Creep | 3 | 9 | Incompetent developer | 0 | Americas | IT/Solution | 2017 | November | 270135
4029 | Scope | Change | Gap | 11 | 9 | Contract had no input from project team and few defined specs. Changes poorly managed and project was very late. | 0 | Americas | Prod. Dev. | 2004 | May | 843909
4030 | Scope | Change | Gap | 17 | 5 | Scoping for a wiring project increased substantially after awarding the business | 1 | Asia | IT/Solution | 2007 | August | 1546864
4031 | Scope | Defect | Hardware | 21 | 6 | Late scope change added customer choice in subscription ticket selection | 0 | Americas | Prod. Dev. | 2018 | July | 1677144
4032 | Resource | People | Late start | 14 | 5 | An extra specialty service to the hospital was added | 0 | Americas | IT/Solution | 2005 | December | 1276380
4033 | Scope | Change | Creep | 23 | 1 | Insufficient analysis of new technology introduced late | 0 | Americas | IT/Solution | 2006 | May | 362089
4034 | Scope | Change | Gap | 10 | 3 | The contract indicated state of the art retrofit materials; differing meaning over 2 years | 0 | Americas | IT/Solution | 2006 | July | 551650
4035 | Scope | Change | Gap | 22 | 6 | The project team agreed to new requirements; unfortunately, some of the changes promised were not even possible | 0 | Americas | IT/Solution | 2015 | September | 1987920
4036 | Scope | Change | Gap | 23 | 7 | Volume requirements increased late in project, requiring extensive rework | 1 | Asia | IT/Solution | 2015 | January | 1739076
4037 | Scope | Change | Creep | 14 | 8 | Product was scoped with unnecessary requirements and was late | 0 | Americas | IT/Solution | 2008 | June | 828534
4038 | Scope | Defect | Hardware | 15 | 8 | Engineering would not stop adding “bell and whistles” to GUI | 1 | Asia | IT/Solution | 2016 | July | 864525
4039 | Scope | Change | Gap | 10 | 9 | Scope definition was poor and change was rampant | 1 | Asia | Prod. Dev. | 2013 | December | 525470
4040 | Scope | Change | Gap | 12 | 6 | A full bioequivalent (BE) study was unexpectedly needed even though there was only a minor difference | 1 | Asia | Prod. Dev. | 2016 | December | 987576
4041 | Schedule | Delay | Parts | 2 | 9 | Major system was begun with insufficient internal resources and without good requirements information | 0 | Americas | Prod. Dev. | 2011 | November | 46520
4042 | Scope | Change | Gap | 9 | 8 | Due to poor understanding, a redesign and costing effort was neeed | 0 | Americas | Prod. Dev. | 2018 | July | 254781
4043 | Scope | Defect | Software | 9 | 2 | Team failed to engage the critical “power-users” early enough | 0 | Americas | IT/Solution | 2015 | October | 699498
4044 | Resource | Outsourcing | Delayed start | 20 | 1 | Project manager thought the solution was only one task, but there were four | 1 | Asia | Prod. Dev. | 2010 | July | 1765260
4045 | Scope | Change | Creep | 7 | 6 | New technology, required changes to SW to work | 0 | Americas | Prod. Dev. | 2003 | October | 295568
4046 | Scope | Change | Gap | 12 | 9 | Poor Fit/Gap analysis | 0 | Americas | IT/Solution | 2010 | May | 217560
4047 | Scope | Change | Gap | 3 | 4 | Poor requirements definition | 0 | Americas | Prod. Dev. | 2008 | January | 118959
4048 | Scope | Defect | Hardware | 26 | 5 | Incomplete design was a result of not considering the particular country needs | 0 | Americas | IT/Solution | 2011 | September | 637754
4049 | Scope | Change | Gap | 5 | 9 | Architect determined that the new design plan for the medical clinic would be considerably more complex than a simple remodeling job | 0 | Americas | IT/Solution | 2002 | March | 334275
4050 | Resource | Money | Limitation | 3 | 7 | Lack of consensus on the spec resulted in modifications during the second phase of the project | 1 | Asia | IT/Solution | 2017 | May | 282489
4051 | Resource | Outsourcing | Late or poor output | 7 | 9 | Clinical evidence was insufficient for European market | 0 | Americas | IT/Solution | 2012 | October | 673127
4052 | Resource | People | Temp loss | 21 | 7 | Based on testing, performance was insufficient to gain approval to market | 0 | Americas | Prod. Dev. | 2004 | October | 1807785
4053 | Schedule | Delay | Parts | 16 | 9 | SumTotal LMS user interface is significantly more complex than the Docent LMS user interface it is to replace | 0 | Americas | IT/Solution | 2018 | July | 943808
4054 | Schedule | Estimates | Learning | 25 | 4 | The software had around 20 major defects and 80 problems that prevented us from moving forward | 0 | Americas | IT/Solution | 2009 | November | 1666550
4055 | Scope | Change | Gap | 2 | 2 | In UAT testing, a fatal flaw sent the deliverable back to development | 0 | Americas | IT/Solution | 2010 | May | 120192
4056 | Scope | Change | Gap | 9 | 4 | During unit testing, discovered performance issue with bulk loads | 0 | Americas | IT/Solution | 2012 | June | 349713
4057 | Resource | People | Queuing | 6 | 8 | Serious issues arose with large loads of data, causing performance problems | 0 | Americas | IT/Solution | 2008 | September | 513858
4058 | Schedule | Delay | Parts | 23 | 6 | Lack of Stakeholder commitment and oversight | 0 | Americas | IT/Solution | 2005 | August | 1669294
4059 | Scope | Change | Creep | 11 | 5 | Failed to allocate enough resources and missed important parts of scope | 0 | Americas | Prod. Dev. | 2003 | March | 727034
4060 | Scope | Change | Dependency | 13 | 8 | Without funding, all work ceased, contracts were effectively terminated with no prospect of renewal | 0 | Americas | Prod. Dev. | 2002 | May | 641056
4061 | Scope | Change | Gap | 15 | 5 | Not enough staff to cover the load and failure to prioritize | 1 | Asia | IT/Solution | 2002 | November | 460650
4062 | Scope | Defect | Hardware | 3 | 1 | Major infrastructure project cut back; delayed fixes cost a lot of money, and resources needed were assigned to other work. | 0 | Americas | Prod. Dev. | 2011 | March | 166473
4063 | Resource | People | Temp loss | 14 | 5 | Serious issues arose with large loads of data, causing performance problems | 0 | Americas | Prod. Dev. | 2017 | July | 1254414
4064 | Schedule | Delay | Decision | 22 | 4 | Found some strange and unusual contamination of an entire batch of petri plates | 0 | Americas | Prod. Dev. | 2010 | November | 1669052
4065 | Schedule | Delay | Information | 4 | 6 | A key component of the system was outsourced | 0 | Americas | IT/Solution | 2018 | March | 172808
4066 | Schedule | Delay | Parts | 12 | 2 | A pool of unqualified, poorly performing, marginal staff to work with | 1 | Asia | IT/Solution | 2016 | July | 575832
4067 | Schedule | Delay | Parts | 12 | 1 | Expert Cardiologist no longer available | 0 | Americas | IT/Solution | 2007 | February | 807084
4068 | Schedule | Estimates | Judgment | 17 | 4 | The scope was not clearly defined | 1 | Asia | Prod. Dev. | 2007 | June | 1520310
4069 | Scope | Change | Gap | 4 | 1 | Too few staff members | 0 | Americas | IT/Solution | 2010 | June | 252340
4070 | Scope | Defect | Software | 23 | 1 | Government contract required only US born nationals; company had too few | 0 | Americas | IT/Solution | 2001 | September | 494132
4071 | Schedule | Dependency | Project | 1 | 1 | Problems detected and solution developed based on presumed root cause. Cause was actually something else and led to major slip. | 1 | Asia | Prod. Dev. | 2015 | May | 40202
4072 | Resource | Money | Limitation | 26 | 9 | Delay in getting material when a fermentation run crashes | 0 | Americas | IT/Solution | 2014 | February | 1552278
4073 | Resource | People | Motivation | 7 | 4 | Project was dependent on onekey resource and had to wait | 0 | Americas | Prod. Dev. | 2015 | July | 267561
4074 | Schedule | Estimates | Learning | 18 | 5 | Flaw found in functional design specifications | 0 | Americas | IT/Solution | 2005 | September | 191916
4075 | Schedule | Estimates | Deadline | 11 | 2 | Scheduling based on small pilot installation, but full roll out backed up the help desk and project was delayed. | 0 | Americas | Prod. Dev. | 2014 | August | 1032526
4076 | Scope | Defect | Hardware | 18 | 4 | New hires used; time for training. | 1 | Asia | Prod. Dev. | 2006 | May | 1479168
4077 | Schedule | Dependency | Project | 26 | 5 | Client's insisted on the use of "the latest technology | 0 | Americas | IT/Solution | 2010 | May | 2526342
4078 | Scope | Change | Gap | 18 | 6 | Modifying requirements in the middle of a phase | 0 | Americas | IT/Solution | 2014 | June | 1737990
4079 | Scope | Change | Gap | 20 | 8 | Scoping set and estimated based on just one set of data from one customer | 0 | Americas | Prod. Dev. | 2011 | January | 1332740
4080 | Schedule | Estimates | Learning | 14 | 8 | Senior management approval for software licenses delayed | 0 | Americas | Prod. Dev. | 2013 | December | 453460
4081 | Schedule | Delay | Information | 25 | 5 | Needed concrete wasn’t delivered on time | 0 | Americas | Prod. Dev. | 2013 | March | 729925
4082 | Resource | Money | Limitation | 24 | 1 | Components that could have been purchased were developed by team, taking longer than expected. | 0 | Americas | IT/Solution | 2017 | December | 1864824
4083 | Schedule | Estimates | Learning | 22 | 5 | Project delayed due to recent/last minute changes to portal interface design | 1 | Asia | Prod. Dev. | 2014 | March | 2150148
4084 | Scope | Defect | Integration | 18 | 4 | Insufficient initial project scope was defined when the estimate given to the client | 0 | Americas | IT/Solution | 2007 | May | 1153080
4085 | Scope | Defect | Integration | 3 | 2 | Documentation needed in French was entirely overlooked | 1 | Asia | Prod. Dev. | 2005 | August | 157992
4086 | Scope | Defect | Software | 17 | 2 | Key people are shared by several projects; lots of queuing. | 0 | Americas | IT/Solution | 2004 | July | 209712
4087 | Schedule | Estimates | Learning | 17 | 6 | Staff illness results in use of temporary staff | 0 | Americas | IT/Solution | 2013 | August | 254779
4088 | Scope | Change | Gap | 15 | 3 | Decisions are too slow due to distance and lack of face-to-face communication | 0 | Americas | IT/Solution | 2018 | February | 1353855
4089 | Scope | Defect | Software | 18 | 7 | Project manager redesigned the prototype and made inventory invalid | 0 | Americas | IT/Solution | 2008 | June | 276822
4090 | Schedule | Delay | Parts | 4 | 6 | Systems needed for project work failed late in the project, and when work was completed installation delayed further to next possible installation window. | 0 | Americas | IT/Solution | 2006 | February | 191540
4091 | Resource | Outsourcing | Delayed start | 21 | 1 | Senior management decided to change the core switching platform technology | 0 | Americas | IT/Solution | 2016 | February | 1828953
4092 | Resource | Outsourcing | Late or poor output | 21 | 8 | New software release installed by IT, and inconsistencies with older version caused delay and extra work. | 1 | Asia | Prod. Dev. | 2017 | December | 756924
4093 | Schedule | Delay | Parts | 16 | 9 | Contractor did not spend time on the project because his organization used him for other work | 0 | Americas | Prod. Dev. | 2013 | May | 1403440
4094 | Schedule | Delay | Parts | 7 | 1 | Installation of new systems required by project delayed. | 0 | Americas | IT/Solution | 2016 | November | 501291
4095 | Scope | Change | Creep | 11 | 5 | Change to the objective when the project was almost finished | 1 | Asia | Prod. Dev. | 2014 | November | 294569
4096 | Scope | Change | Gap | 16 | 9 | Did not have sufficient resources and the contingency plan was inadequate | 1 | Asia | Prod. Dev. | 2016 | January | 324432
4097 | Scope | Change | Gap | 16 | 6 | Contractor setup delayed by a week | 1 | Asia | Prod. Dev. | 2013 | September | 947568
4098 | Scope | Change | Gap | 7 | 7 | Contractor did not spend time on the project because his organization used him for other work | 0 | Americas | Prod. Dev. | 2013 | March | 358813
4099 | Schedule | Delay | Hardware | 12 | 3 | Contractors failed to show up as committed | 0 | Americas | IT/Solution | 2014 | April | 276036
4100 | Scope | Change | Gap | 8 | 7 | Third-party vendor inadvertently introduced a bug during an upgrade | 1 | Asia | IT/Solution | 2007 | December | 172400
4101 | Scope | Defect | Hardware | 24 | 5 | Outsouced staff lacked the necessary skillset | 0 | Americas | IT/Solution | 2001 | April | 972024
4102 | Resource | People | Late start | 25 | 2 | Planning delayed due to staff being still tied up in testing on prior project. | 0 | Americas | IT/Solution | 2005 | January | 1058350
4103 | Resource | People | Queuing | 22 | 7 | Chef quit two days before the café was scheduled to open | 0 | Americas | Prod. Dev. | 2017 | February | 823746
4104 | Schedule | Estimates | Learning | 6 | 3 | Work at customer site had to be done by union workers; took 6 days to do what project team could do in 1. | 0 | Americas | IT/Solution | 2015 | April | 313488
4105 | Scope | Change | Gap | 25 | 3 | Critical task assigned to a heavily booked expert | 1 | Asia | IT/Solution | 2017 | December | 1060925
4106 | Resource | People | Late start | 3 | 7 | Key packaging engineer was working on a high priority project when needed | 0 | Americas | IT/Solution | 2019 | September | 185877
4107 | Schedule | Estimates | Judgment | 12 | 5 | No engineer is available or has enough knowledge | 0 | Americas | IT/Solution | 2018 | January | 226812
4108 | Scope | Defect | Hardware | 1 | 2 | People were allocated to too many projects and bottlenecks developed | 0 | Americas | Prod. Dev. | 2018 | May | 62610
4109 | Resource | People | Late start | 5 | 3 | Key person not available when needed. | 1 | Asia | Prod. Dev. | 2012 | January | 431685
4110 | Resource | People | Motivation | 11 | 8 | US expertise needed for project in Asia. Team member flies to US, but expert is busy. | 0 | Americas | IT/Solution | 2006 | February | 590326
4111 | Schedule | Dependency | Project | 22 | 5 | Engineer responsible to program the ISDN router called in sick | 0 | Americas | IT/Solution | 2017 | November | 1435368
4112 | Schedule | Estimates | Judgment | 4 | 9 | Key welding staff are out with flu | 2 | Eur/ME | IT/Solution | 2018 | January | 249412
4113 | Schedule | Estimates | Learning | 13 | 4 | Manufacturing volumes spiked and diverted project contributors. | 2 | Eur/ME | IT/Solution | 2007 | July | 657995
4114 | Schedule | Estimates | Learning | 7 | 7 | Unannounced audit in mid-project caused delay to prepare and participate. | 0 | Americas | IT/Solution | 2010 | May | 406434
4115 | Scope | Change | Gap | 24 | 1 | Key team member grounded in Middle East during a regional war. | 0 | Americas | IT/Solution | 2011 | November | 1681464
4116 | Scope | Change | Gap | 25 | 6 | Key contributor out ill at critical time. | 0 | Americas | IT/Solution | 2019 | December | 2371375
4117 | Scope | Change | Gap | 1 | 5 | Client missed the deadline for feedback by several days | 0 | Americas | IT/Solution | 2001 | October | 89627
4118 | Scope | Change | Gap | 20 | 7 | Document reviews slipped due to conflicts and low priority. | 2 | Eur/ME | Prod. Dev. | 2003 | December | 1681320
4119 | Scope | Defect | Hardware | 19 | 6 | Flood shuts down data center. Delay to restore power and clean up. | 0 | Americas | IT/Solution | 2010 | June | 1323711
4120 | Resource | Money | Limitation | 7 | 1 | "Customer supplied" hardware does not work. Replacement required. | 0 | Americas | Prod. Dev. | 2016 | January | 564207
4121 | Scope | Change | Creep | 16 | 8 | System arrives late, then when it does arrive staff is not available to install it. | 0 | Americas | IT/Solution | 2018 | October | 1447392
4122 | Schedule | Dependency | Infrastructure | 17 | 8 | System needed was down for scheduled maintenance not in plan. | 1 | Asia | IT/Solution | 2013 | June | 999736
4123 | Scope | Change | Gap | 15 | 5 | Installation of new systems required by project delayed. | 0 | Americas | IT/Solution | 2019 | April | 841815
4124 | Resource | People | Late start | 8 | 8 | Access to required support tools was not established | 0 | Americas | Prod. Dev. | 2009 | May | 663496
4125 | Scope | Change | Gap | 17 | 8 | Documentation from the researcher lacks crucial information | 2 | Eur/ME | IT/Solution | 2009 | June | 1427473
4126 | Scope | Change | Gap | 16 | 6 | Customer not showing up for key meeting | 1 | Asia | Prod. Dev. | 2010 | June | 1534784
4127 | Scope | Change | Gap | 8 | 6 | No coordinated shipment of system components; last one delays installation. | 0 | Americas | Prod. Dev. | 2019 | September | 677704
4128 | Scope | Change | Gap | 23 | 7 | Lack of supplies and adequate time for printing | 2 | Eur/ME | Prod. Dev. | 2011 | December | 1823716
4129 | Resource | Outsourcing | Delayed start | 15 | 5 | Out of stock on key parts needed for PC boards. | 0 | Americas | IT/Solution | 2005 | September | 1061325
4130 | Resource | Outsourcing | Late or poor output | 20 | 3 | Parts delivery delay | 0 | Americas | IT/Solution | 2019 | July | 1579340
4131 | Resource | Outsourcing | Late or poor output | 18 | 9 | A needed component was not very stable and only available from only one supplier. | 0 | Americas | IT/Solution | 2015 | October | 1385586
4132 | Schedule | Delay | Hardware | 13 | 1 | Delivery problems on international shipment--paperwork, customs. | 0 | Americas | IT/Solution | 2008 | April | 683891
4133 | Resource | Money | Limitation | 24 | 6 | Shipping documents not filled in correctly | 0 | Americas | IT/Solution | 2006 | March | 2383512
4134 | Resource | Money | Limitation | 17 | 7 | Dependency on other project not discovered until project end. | 0 | Americas | IT/Solution | 2013 | August | 1035181
4135 | Resource | People | Late start | 7 | 2 | Deliverable from one project claimed to be done, but receiving project cannot use it. | 2 | Eur/ME | Prod. Dev. | 2006 | January | 513968
4136 | Resource | People | Late start | 16 | 9 | Other group could not deliver on time, soI had to do work myself | 2 | Eur/ME | Prod. Dev. | 2006 | October | 957040
4137 | Resource | People | Queuing | 8 | 7 | Untried beta software with unknown computer needs required for training | 2 | Eur/ME | IT/Solution | 2011 | January | 698928
4138 | Schedule | Delay | Hardware | 18 | 3 | Underestimated weight of stumps to be removed | 0 | Americas | IT/Solution | 2004 | July | 1629306
4139 | Schedule | Delay | Parts | 9 | 9 | Late additional request on a small project delayed completion | 0 | Americas | Prod. Dev. | 2013 | December | 870444
4140 | Schedule | Dependency | Legal | 5 | 9 | Change to the objective when the project was almost finished | 2 | Eur/ME | IT/Solution | 2013 | January | 351160
4141 | Schedule | Dependency | Project | 7 | 2 | Additional enhancements requested at the last minute | 0 | Americas | Prod. Dev. | 2007 | November | 588063
4142 | Resource | Outsourcing | Late or poor output | 4 | 2 | Scope continuously changed by client | 2 | Eur/ME | Prod. Dev. | 2018 | April | 258908
4143 | Resource | People | Late start | 5 | 2 | Late changes resulted in expedite charges and delay | 0 | Americas | IT/Solution | 2019 | October | 456940
4144 | Resource | People | Loss | 5 | 7 | System move delayed by last minute system changes that delayed and made backups take too long. | 2 | Eur/ME | IT/Solution | 2019 | June | 333930
4145 | Schedule | Delay | Parts | 1 | 2 | Scope changed after writers had completed initial draft | 0 | Americas | IT/Solution | 2001 | September | 66908
4146 | Schedule | Estimates | Judgment | 16 | 4 | Legal required late changes to a large print run of materials | 0 | Americas | IT/Solution | 2003 | July | 906816
4147 | Scope | Change | Gap | 5 | 5 | Policy changes made late in a project requiring additional unplanned work. | 2 | Eur/ME | IT/Solution | 2017 | May | 251280
4148 | Resource | People | Motivation | 14 | 9 | Inadequate facilities; had to find alternatives | 0 | Americas | IT/Solution | 2013 | February | 911792
4149 | Resource | People | Queuing | 5 | 1 | Poor definition of training requirements; had to do much more. | 0 | Americas | Prod. Dev. | 2009 | February | 459750
4150 | Schedule | Delay | Parts | 20 | 3 | After project "complete" rework required for customer approval | 0 | Americas | IT/Solution | 2010 | September | 1084520
4151 | Schedule | Delay | Parts | 3 | 2 | Design team failed to collect the details on what was to be displayed to users | 0 | Americas | IT/Solution | 2013 | November | 209628
4152 | Scope | Change | Gap | 23 | 4 | PM did not take the time to determine what the move entailed | 0 | Americas | Prod. Dev. | 2019 | September | 1573499
4153 | Resource | People | Late start | 6 | 4 | Lack of a solid plan, or any formal scoping | 0 | Americas | IT/Solution | 2012 | April | 537492
4154 | Resource | People | Loss | 12 | 9 | Final burn-in test interrupted by faulty oven. Replacement and retest took extra time. | 0 | Americas | Prod. Dev. | 2001 | April | 1015812
4155 | Resource | People | Loss | 24 | 3 | Old equipment failed at the last minute | 2 | Eur/ME | Prod. Dev. | 2016 | April | 1860480
4156 | Resource | People | Motivation | 4 | 1 | A batch of servers came in with the wrong configurations; had to be fixed | 0 | Americas | IT/Solution | 2008 | October | 269616
4157 | Resource | People | Temp loss | 17 | 3 | Unanticipated fumes form epoxy concrete paint forced a delay in work | 0 | Americas | IT/Solution | 2016 | October | 1190255
4158 | Schedule | Delay | Decision | 3 | 7 | Miscalculation on a critical task | 0 | Americas | Prod. Dev. | 2017 | October | 241749
4159 | Schedule | Delay | Information | 17 | 8 | Vibration in transit caused the loosing of the nuts and bolts of antennas, which eventually caused the collapse of the antennas | 2 | Eur/ME | Prod. Dev. | 2006 | November | 1358555
4160 | Schedule | Delay | Parts | 24 | 7 | Cable required had been left off the implementation parts list | 2 | Eur/ME | IT/Solution | 2006 | April | 2106312
4161 | Schedule | Dependency | Project | 17 | 3 | Integration testing is incomplete, causing system failures. | 0 | Americas | IT/Solution | 2004 | January | 983739
4162 | Scope | Change | Creep | 5 | 2 | No problems in test, but production problems required overtime to fix | 0 | Americas | Prod. Dev. | 2010 | September | 442545
4163 | Scope | Change | Gap | 3 | 9 | Access problems surfaced in production | 0 | Americas | Prod. Dev. | 2013 | May | 223578
4164 | Scope | Defect | Integration | 3 | 5 | Engineering overlooked the functional design and did not implement correctly | 0 | Americas | IT/Solution | 2004 | August | 243051
4165 | Scope | Defect | Software | 3 | 7 | Bugs were reported by UAT that should have been caught by QA | 0 | Americas | IT/Solution | 2013 | July | 274500
4166 | Scope | Change | Creep | 4 | 5 | Performance issues surfaced following migration | 2 | Eur/ME | IT/Solution | 2011 | July | 327276
4167 | Scope | Defect | Hardware | 8 | 8 | Servers got stuck in customs | 0 | Americas | Prod. Dev. | 2018 | December | 660752
4168 | Scope | Defect | Software | 11 | 6 | New technology, required changes to SW to work | 2 | Eur/ME | IT/Solution | 2012 | February | 617133
4169 | Scope | Change | Gap | 20 | 8 | Failed to allocate enough resources and missed important parts of scope | 0 | Americas | IT/Solution | 2006 | March | 1826920
4170 | Schedule | Estimates | Deadline | 4 | 3 | Mid-project feature revisions. Major impact on effort and schedule; product failed (too late to market). | 0 | Americas | Prod. Dev. | 2005 | January | 269956
4171 | Scope | Change | Creep | 3 | 7 | Development plans failed to include all of the 23 required applications | 0 | Americas | IT/Solution | 2005 | March | 227328
4172 | Scope | Change | Creep | 19 | 6 | Project budget was dramatically cut | 0 | Americas | IT/Solution | 2012 | October | 1811156
4173 | Resource | Outsourcing | Late or poor output | 13 | 3 | Merging of multiple standards is needed to support reorganization. Lack of a new, common definition delayed the project to convert data. | 0 | Americas | IT/Solution | 2004 | July | 1242059
4174 | Scope | Change | Creep | 19 | 1 | The other company was unable to stick to needed deadlines | 0 | Americas | IT/Solution | 2002 | December | 1510633
4175 | Scope | Change | Gap | 14 | 6 | Severe funding cutbacks (66% of project team) | 0 | Americas | IT/Solution | 2016 | February | 1059366
4176 | Scope | Change | Gap | 5 | 7 | Project Budget was restricted to the bare minimum estimated | 0 | Americas | IT/Solution | 2001 | August | 304460
4177 | Schedule | Estimates | Judgment | 5 | 7 | Project based on standards still in draft form. Several options are possible, but project is only staffed to pursue one. | 0 | Americas | IT/Solution | 2014 | May | 264835
4178 | Resource | People | Queuing | 10 | 7 | Due to a re-organization the team lost essential resources | 0 | Americas | IT/Solution | 2009 | December | 820070
4179 | Scope | Change | Creep | 18 | 7 | Staffing was late and inexperienced | 0 | Americas | Prod. Dev. | 2009 | January | 1609452
4180 | Resource | People | Queuing | 15 | 3 | One of the Senior System Analysts who was fully trained on the application resigned | 0 | Americas | Prod. Dev. | 2016 | June | 1253160
4181 | Resource | People | Temp loss | 13 | 7 | Project experienced shortages in steel rebar and copper electrical wire | 2 | Eur/ME | Prod. Dev. | 2009 | January | 798928
4182 | Scope | Change | Dependency | 23 | 4 | Developers on the project were not experienced enough to implement the solution | 0 | Americas | Prod. Dev. | 2014 | March | 1587414
4183 | Scope | Change | Gap | 25 | 9 | Scope not defined well; huge software delays | 0 | Americas | IT/Solution | 2003 | July | 2075050
4184 | Scope | Defect | Hardware | 15 | 8 | New requirements were piled on as the project ran | 0 | Americas | IT/Solution | 2013 | September | 1304025
4185 | Scope | Defect | Integration | 17 | 7 | Components failure means finding another type of component and redoing tests | 0 | Americas | IT/Solution | 2016 | April | 879478
4186 | Resource | Outsourcing | Late or poor output | 1 | 7 | Sponsor fails to provide money | 0 | Americas | Prod. Dev. | 2016 | October | 79928
4187 | Scope | Defect | Software | 14 | 3 | Management never talked to the test department when creating proposals | 2 | Eur/ME | Prod. Dev. | 2005 | June | 993314
4188 | Schedule | Estimates | Learning | 25 | 8 | Key staff member lacked knowledge, experience and ability | 0 | Americas | IT/Solution | 2019 | April | 1873925
4189 | Scope | Change | Creep | 14 | 9 | Lack of understanding by the manager of the system forced the project to replan | 0 | Americas | IT/Solution | 2013 | September | 1266314
4190 | Resource | Outsourcing | Late or poor output | 13 | 4 | The project manager was assigned to another big project part way through the project | 0 | Americas | Prod. Dev. | 2004 | May | 934232
4191 | Resource | People | Temp loss | 1 | 9 | Conflicting priorities. on-going maintenance, and loss of a person led to delay | 0 | Americas | Prod. Dev. | 2019 | June | 91077
4192 | Schedule | Delay | Hardware | 11 | 9 | Lone subject matter expert unavailable when needed during the initial stages | 0 | Americas | IT/Solution | 2001 | July | 617188
4193 | Scope | Change | Dependency | 15 | 9 | New technology not available on time. | 0 | Americas | IT/Solution | 2018 | February | 1350315
4194 | Schedule | Estimates | Learning | 8 | 7 | Insufficient capacity in the cabling system for needed fiber connection | 0 | Americas | IT/Solution | 2003 | October | 570528
4195 | Schedule | Delay | Parts | 9 | 2 | Iidviduals who must to approve work are unavailable | 2 | Eur/ME | IT/Solution | 2016 | June | 603171
4196 | Schedule | Delay | Parts | 7 | 8 | Project priorities and criteria are unclear through much of the project, causing lots of unneeded work. | 0 | Americas | IT/Solution | 2015 | March | 452865
4197 | Schedule | Delay | Information | 14 | 3 | Poor prework led to assumption that project would be simpler than it was | 2 | Eur/ME | IT/Solution | 2011 | August | 807730
4198 | Scope | Defect | Software | 19 | 4 | Project had limited funding and limited staffing | 0 | Americas | Prod. Dev. | 2002 | March | 1021573
4199 | Resource | People | Queuing | 22 | 5 | Work being done more than 3000 miles away was difficult to check | 0 | Americas | Prod. Dev. | 2005 | August | 1804550
4200 | Resource | People | Queuing | 5 | 2 | Due to contractor layoffs, a Subject Matter Expert had to be replaced | 2 | Eur/ME | IT/Solution | 2006 | December | 477220
4201 | Schedule | Dependency | Project | 26 | 8 | Expert at third party required for work not available when needed | 0 | Americas | Prod. Dev. | 2001 | July | 1749280
4202 | Scope | Change | Gap | 16 | 1 | Limited access to management. Decisions and escalations too slow. | 0 | Americas | IT/Solution | 2013 | November | 871296
4203 | Schedule | Dependency | Infrastructure | 20 | 7 | Did not have the signature of the director | 0 | Americas | Prod. Dev. | 2010 | September | 1000060
4204 | Scope | Change | Gap | 21 | 7 | Equipment used for data analysis failed and was down for 2 weeks | 0 | Americas | IT/Solution | 2017 | February | 1597407
4205 | Resource | Outsourcing | Late or poor output | 26 | 4 | Shipping requirements changed. Some shipments bounce, others get stuck in customs. | 0 | Americas | IT/Solution | 2009 | November | 1493050
4206 | Schedule | Estimates | Deadline | 24 | 3 | Customer reorganization led to new staffing and changed requirements | 0 | Americas | IT/Solution | 2018 | October | 1570200
4207 | Scope | Change | Creep | 14 | 6 | Scope creep and resource inadequacy | 2 | Eur/ME | IT/Solution | 2014 | January | 1396752
4208 | Resource | Outsourcing | Late or poor output | 12 | 9 | Operating system release expected slips; project forced to use prior version missing some needed functionality. | 2 | Eur/ME | IT/Solution | 2008 | June | 706800
4209 | Resource | Outsourcing | Late or poor output | 6 | 4 | Proprietary data needed, but owners unwilling to provide. After delay, partial information shared. | 0 | Americas | Prod. Dev. | 2009 | March | 487770
4210 | Resource | People | Loss | 3 | 8 | Key packaging engineer was working on a high priority project when needed | 0 | Americas | Prod. Dev. | 2016 | February | 272553
4211 | Resource | People | Temp loss | 17 | 6 | Key team member grounded in Middle East during a regional war. | 0 | Americas | Prod. Dev. | 2012 | April | 1643288
4212 | Schedule | Delay | Information | 18 | 9 | Customer not showing up for key meeting | 0 | Americas | Prod. Dev. | 2015 | September | 1667952
4213 | Scope | Change | Creep | 5 | 3 | Inadequate facilities; had to find alternatives | 0 | Americas | IT/Solution | 2013 | December | 412045
4214 | Scope | Defect | Integration | 19 | 2 | Project did not have the buy-in for staffing from other departmens | 0 | Americas | IT/Solution | 2014 | June | 1238952
4215 | Resource | People | Loss | 22 | 2 | Project had limited funding and limited staffing | 2 | Eur/ME | Prod. Dev. | 2019 | May | 1155418
4216 | Resource | People | Loss | 14 | 1 | lack of staff availability due to company down-sizing | 0 | Americas | Prod. Dev. | 2001 | April | 746032
4217 | Scope | Change | Gap | 2 | 4 | Lack of money for sufficient equipment | 0 | Americas | Prod. Dev. | 2002 | August | 174984
4218 | Resource | People | Temp loss | 6 | 6 | Slow start of work outsourced. | 0 | Americas | Prod. Dev. | 2012 | January | 455292
4219 | Schedule | Delay | Decision | 7 | 2 | Pricing negotiation stalls project work until resolved. | 0 | Americas | Prod. Dev. | 2015 | May | 572299
4220 | Schedule | Dependency | Infrastructure | 7 | 3 | New supplier, extensive start up and coordination issues. | 0 | Americas | Prod. Dev. | 2010 | July | 374066
4221 | Schedule | Dependency | Infrastructure | 11 | 1 | Subcontractor delay causes compression of later work. | 0 | Americas | Prod. Dev. | 2019 | November | 925298
4222 | Scope | Change | Gap | 17 | 8 | Supplier failure, inputs late and inadequate | 2 | Eur/ME | Prod. Dev. | 2001 | May | 1124737
4223 | Scope | Change | Gap | 26 | 9 | An external part-time consultant wasn't always available when needed | 0 | Americas | Prod. Dev. | 2002 | March | 1859910
4224 | Scope | Defect | Integration | 21 | 6 | Outsource partner replaced several key people on team | 0 | Americas | Prod. Dev. | 2008 | March | 1522374
4225 | Scope | Defect | Software | 8 | 2 | Local subcontractors lacked needed technical skills | 0 | Americas | IT/Solution | 2019 | December | 664824
4226 | Resource | People | Loss | 13 | 2 | Problems with vendor capacity and performance | 2 | Eur/ME | Prod. Dev. | 2007 | July | 1110473
4227 | Resource | People | Queuing | 3 | 3 | Outsourcing firm had an incompetent design team | 0 | Americas | Prod. Dev. | 2017 | April | 199038
4228 | Resource | People | Queuing | 15 | 1 | Contractors are not close to the business and often overlook requirements | 2 | Eur/ME | Prod. Dev. | 2012 | June | 1121010
4229 | Resource | People | Temp loss | 16 | 8 | Slow renewal of contract for consultant; interruption in work | 0 | Americas | Prod. Dev. | 2013 | January | 1334176
4230 | Resource | People | Temp loss | 4 | 5 | Task supposed to be done by an outside company was completed late | 0 | Americas | Prod. Dev. | 2004 | March | 299544
4231 | Schedule | Delay | Information | 13 | 4 | Work being done more than 3000 miles away was difficult to check | 0 | Americas | Prod. Dev. | 2017 | March | 724425
4232 | Schedule | Delay | Parts | 21 | 1 | High turnover leads to delays and crisis management. | 0 | Americas | Prod. Dev. | 2007 | May | 1879710
4233 | Schedule | Estimates | Learning | 16 | 3 | Contract had no penalties for missing deadlines; 3 weeks taken on 1 week task. | 0 | Americas | Prod. Dev. | 2013 | December | 1237120
4234 | Scope | Change | Gap | 15 | 9 | Outsourced tasks slipped, but not known until too late. | 0 | Americas | IT/Solution | 2018 | February | 1135200
4235 | Schedule | Delay | Decision | 12 | 6 | Work from team in Pakistan failed miserably | 2 | Eur/ME | Prod. Dev. | 2012 | July | 844716
4236 | Schedule | Dependency | Infrastructure | 9 | 2 | One factory went on labor strike for 2 weeks –Delayed production of 20 pallets | 0 | Americas | IT/Solution | 2003 | May | 701910
4237 | Schedule | Estimates | Judgment | 19 | 2 | Labor union of subcontractor went on stike | 2 | Eur/ME | IT/Solution | 2017 | May | 1387665
4238 | Scope | Change | Creep | 18 | 5 | Insufficient planning and commitment by the committee involved | 0 | Americas | IT/Solution | 2009 | March | 944172
4239 | Scope | Change | Dependency | 17 | 5 | Developer from the database group was not available because of another project | 0 | Americas | IT/Solution | 2005 | January | 1361020
4240 | Schedule | Dependency | Project | 5 | 1 | Project start delayed; team busy on other work. | 0 | Americas | IT/Solution | 2010 | April | 338480
4241 | Scope | Change | Dependency | 22 | 6 | Project start delayed; staffing and buy-in late, required overtime and extra project management. | 0 | Americas | Prod. Dev. | 2017 | December | 1134518
4242 | Schedule | Dependency | Legal | 11 | 7 | Toward the end of the development life cycle the original QA lead and trainer quit the firm | 0 | Americas | Prod. Dev. | 2010 | November | 890472
4243 | Scope | Defect | Integration | 11 | 8 | A key team member was replaced mid-project | 0 | Americas | Prod. Dev. | 2010 | June | 804331
4244 | Scope | Change | Gap | 25 | 2 | Due to contractor layoffs, a Subject Matter Expert had to be replaced | 0 | Americas | IT/Solution | 2006 | July | 1493325
4245 | Scope | Change | Gap | 12 | 7 | Expert developer left the company | 0 | Americas | IT/Solution | 2001 | September | 906192
4246 | Resource | Outsourcing | Late or poor output | 14 | 6 | Chief architect quit, and was the only person with critical skills | 0 | Americas | IT/Solution | 2010 | December | 1351448
4247 | Scope | Defect | Software | 16 | 9 | Contributor is leaving due to contract expiration | 0 | Americas | IT/Solution | 2018 | January | 1267744
4248 | Scope | Change | Creep | 16 | 1 | At a critical stage of the project the Medical Director left the company | 0 | Americas | Prod. Dev. | 2002 | February | 1228208
4249 | Schedule | Estimates | Judgment | 8 | 2 | Expert developer left the company | 0 | Americas | Prod. Dev. | 2019 | July | 502528
4250 | Scope | Defect | Software | 10 | 1 | Key people resigned, leaving too few to complete project and training on time | 0 | Americas | Prod. Dev. | 2006 | November | 784110
4251 | Resource | Outsourcing | Late or poor output | 26 | 2 | Late in project, the budget and staff are cut leading to delays, forced overtime, and demotivation. | 0 | Americas | Prod. Dev. | 2017 | March | 2350920
4252 | Schedule | Delay | Hardware | 10 | 9 | Project involved several departments, several of which were uncooperative | 0 | Americas | IT/Solution | 2013 | March | 537470
4253 | Schedule | Estimates | Learning | 17 | 7 | On a very long project, enthusiasm and motivation falls; tasks stretch out. | 0 | Americas | IT/Solution | 2018 | August | 1186260
4254 | Scope | Change | Creep | 11 | 1 | Limits on headcount create work backlog | 2 | Eur/ME | IT/Solution | 2008 | October | 876238
4255 | Scope | Change | Creep | 5 | 2 | Expert at third party required for work not available when needed | 0 | Americas | IT/Solution | 2016 | July | 293175
4256 | Resource | Outsourcing | Late or poor output | 23 | 9 | Resources thin and tasks queued in backlogs. | 0 | Americas | Prod. Dev. | 2002 | July | 1994169
4257 | Resource | Outsourcing | Late or poor output | 21 | 2 | Key people are shared by several projects; lots of queuing. | 0 | Americas | Prod. Dev. | 2001 | November | 1870302
4258 | Schedule | Dependency | Infrastructure | 20 | 1 | A single person was responsible for key reports many wait in queue | 0 | Americas | Prod. Dev. | 2010 | September | 1699840
4259 | Schedule | Estimates | Deadline | 17 | 6 | The test capabilities constitute a bottleneck late in release cycles. | 0 | Americas | Prod. Dev. | 2012 | November | 891361
4260 | Scope | Change | Gap | 17 | 1 | Conflict for resources with a higher priority project | 0 | Americas | Prod. Dev. | 2009 | November | 945149
4261 | Scope | Defect | Integration | 13 | 8 | Business Operations Analyst was busy with another big project | 0 | Americas | Prod. Dev. | 2010 | June | 1003717
4262 | Resource | Outsourcing | Late or poor output | 13 | 7 | Failure by project manager to communicate the need for architect’s time | 0 | Americas | Prod. Dev. | 2008 | June | 847431
4263 | Resource | Outsourcing | Late or poor output | 8 | 6 | Key work in flu season delayed; most of staff out ill. | 2 | Eur/ME | IT/Solution | 2007 | October | 755168
4264 | Resource | People | Loss | 26 | 5 | Production partner had a personal issue which brought production to a halt | 0 | Americas | Prod. Dev. | 2001 | January | 1705470
4265 | Resource | People | Loss | 23 | 6 | Project team frequently diverted to support work. | 0 | Americas | Prod. Dev. | 2001 | October | 1429243
4266 | Resource | People | Temp loss | 7 | 7 | Staff lost to customer hot site | 2 | Eur/ME | Prod. Dev. | 2003 | January | 479129
4267 | Schedule | Delay | Information | 20 | 7 | Key resource was pulled off the project twice to fix bugs in a previous product | 0 | Americas | Prod. Dev. | 2010 | January | 1289340
4268 | Scope | Defect | Integration | 11 | 2 | Key Designer was out of the office for 2 weeks | 0 | Americas | IT/Solution | 2015 | September | 1021592
4269 | Resource | Outsourcing | Late or poor output | 1 | 9 | Software engineer was lost to a higher priority project | 0 | Americas | IT/Solution | 2013 | February | 90218
4270 | Resource | Outsourcing | Late or poor output | 7 | 6 | Staff illness results in use of temporary staff | 2 | Eur/ME | Prod. Dev. | 2017 | October | 400603
4271 | Resource | People | Queuing | 15 | 4 | Key contributor "rounded up" after 9/11 (and later released) | 0 | Americas | Prod. Dev. | 2001 | May | 1471305
4272 | Resource | People | Queuing | 8 | 5 | Reorganization during product ramp creates chaos and ownership problems. | 0 | Americas | IT/Solution | 2005 | May | 632624
4273 | Resource | People | Queuing | 15 | 2 | Lead engineer stuck in Japan for 2 weeks longer than expected | 0 | Americas | IT/Solution | 2018 | June | 1174290
4274 | Scope | Defect | Software | 5 | 8 | Staff lost to customer Hot Site | 0 | Americas | IT/Solution | 2005 | March | 450775
4275 | Schedule | Delay | Information | 22 | 2 | Poor access to decision makers | 0 | Americas | Prod. Dev. | 2011 | September | 1747724
4276 | Schedule | Estimates | Judgment | 3 | 2 | Problems getting timely management decisions. | 0 | Americas | IT/Solution | 2010 | January | 284331
4277 | Scope | Change | Gap | 10 | 4 | Limited access to management. Decisions and escalations too slow. | 0 | Americas | IT/Solution | 2010 | November | 599980
4278 | Scope | Defect | Software | 4 | 7 | System needed to approve requests went down; ordering required parts delayed. | 0 | Americas | Prod. Dev. | 2006 | January | 372920
4279 | Schedule | Delay | Parts | 18 | 9 | Requisition required the authorization of CEO who was out of town in Finland | 0 | Americas | IT/Solution | 2009 | March | 1123218
4280 | Resource | Outsourcing | Late or poor output | 16 | 8 | Code review delayed due to merger | 0 | Americas | IT/Solution | 2017 | July | 1210816
4281 | Resource | People | Loss | 22 | 9 | Required design review delayed. | 2 | Eur/ME | IT/Solution | 2002 | October | 1532278
4282 | Schedule | Delay | Information | 3 | 8 | Project relocated manufacturing to a contract manufacturer. Required management decisions are frequent and too slow. | 0 | Americas | IT/Solution | 2010 | May | 284061
4283 | Schedule | Delay | Parts | 10 | 2 | Decisions are too slow due to distance and lack of face-to-face communication | 0 | Americas | IT/Solution | 2010 | November | 613550
4284 | Schedule | Dependency | Infrastructure | 15 | 5 | Did not have the signature of the director | 0 | Americas | IT/Solution | 2011 | November | 888390
4285 | Schedule | Dependency | Legal | 21 | 5 | Scope definition and stakeholder agreement delayed. | 0 | Americas | IT/Solution | 2016 | October | 1626723
4286 | Schedule | Dependency | Project | 15 | 8 | Disaster recovery tests delayed at project end; hardware needed tied up with an actual customer problem. | 0 | Americas | Prod. Dev. | 2010 | January | 1336050
4287 | Scope | Change | Creep | 21 | 7 | Equipment needed for project came from a pool of hardware partly in another country. Critical hardware delayed by customs. | 2 | Eur/ME | Prod. Dev. | 2015 | March | 1203447
4288 | Scope | Change | Creep | 10 | 5 | Project work that customer is responsible for slips, causing project slip. | 0 | Americas | Prod. Dev. | 2009 | July | 504050
4289 | Scope | Change | Creep | 24 | 2 | Team relocated with insufficient time to schedule high speed network lines. Rushed, but did not work; team was down until fixed. | 0 | Americas | IT/Solution | 2003 | September | 1566096
4290 | Scope | Change | Gap | 17 | 2 | Required server was misplaced in shipping | 0 | Americas | Prod. Dev. | 2004 | September | 1583550
4291 | Scope | Change | Gap | 4 | 1 | Test systems shared by 6 projects; queuing and delays common. | 0 | Americas | IT/Solution | 2005 | April | 399504
4292 | Resource | Money | Limitation | 16 | 7 | New equipment critical to the success of the product quality was installed late | 0 | Americas | IT/Solution | 2010 | December | 1262176
4293 | Schedule | Delay | Parts | 1 | 6 | Equipment used for data analysis failed and was down for 2 weeks | 2 | Eur/ME | Prod. Dev. | 2011 | June | 61549
4294 | Schedule | Estimates | Learning | 15 | 6 | Tests delayed at project end; delayed access to databases | 0 | Americas | Prod. Dev. | 2003 | December | 1245570
4295 | Scope | Change | Gap | 15 | 7 | Delay to reconfigure printer outside firewall | 0 | Americas | IT/Solution | 2004 | March | 1438905
4296 | Scope | Change | Gap | 10 | 5 | Orders sometimes get lost in manual routing | 0 | Americas | IT/Solution | 2010 | November | 647090
4297 | Resource | People | Temp loss | 17 | 2 | Data submitted by the participating vendors contains errors | 0 | Americas | IT/Solution | 2014 | October | 1398828
4298 | Schedule | Delay | Hardware | 9 | 8 | Document transfer to sites takes more time and effort than expected. | 2 | Eur/ME | IT/Solution | 2001 | March | 624393
4299 | Scope | Change | Creep | 7 | 9 | "Overnight" shipping takes extra time in big co. mailrooms | 0 | Americas | IT/Solution | 2008 | December | 593831
4300 | Resource | Money | Limitation | 15 | 2 | Errors in input data had to be fixed and reports re-generated | 0 | Americas | IT/Solution | 2007 | August | 1133325
4301 | Resource | Outsourcing | Delayed start | 1 | 5 | There was a communication lag | 2 | Eur/ME | IT/Solution | 2013 | August | 83125
4302 | Resource | Outsourcing | Late or poor output | 23 | 6 | Parts of development team have a 12 hour time difference. Bugs take 2-3 days longer to fix, on average. | 0 | Americas | Prod. Dev. | 2010 | September | 1310954
4303 | Schedule | Estimates | Judgment | 12 | 4 | Defective parts received. Reorder doubled the time required. | 0 | Americas | Prod. Dev. | 2015 | July | 1132320
4304 | Scope | Change | Gap | 10 | 4 | Equipment / parts not delivered on time or in full by the outside supplier | 0 | Americas | Prod. Dev. | 2006 | December | 883400
4305 | Schedule | Delay | Hardware | 6 | 5 | Inventory from vendors could not be secured by the desired transport date | 0 | Americas | IT/Solution | 2016 | February | 309342
4306 | Schedule | Estimates | Deadline | 3 | 3 | Incorrect part shipped. Delay for reshipment. | 0 | Americas | IT/Solution | 2002 | November | 172812
4307 | Scope | Change | Gap | 12 | 6 | Needed parts arrive too late. | 0 | Americas | IT/Solution | 2001 | March | 646764
4308 | Scope | Change | Gap | 20 | 6 | Parts availability and pricing volatile | 2 | Eur/ME | Prod. Dev. | 2014 | November | 1882640
4309 | Schedule | Dependency | Project | 15 | 2 | Boards would fail incoming quality check due to the specs given to fabrication house not being tight enough | 0 | Americas | IT/Solution | 2013 | February | 983115
4310 | Schedule | Dependency | Project | 13 | 5 | Production problem with key component | 0 | Americas | IT/Solution | 2003 | August | 808301
4311 | Schedule | Estimates | Judgment | 7 | 8 | Key contractors have the flu | 2 | Eur/ME | Prod. Dev. | 2007 | August | 670187
4312 | Schedule | Estimates | Learning | 20 | 9 | Project manager redesigned the prototype and made inventory invalid | 0 | Americas | Prod. Dev. | 2013 | September | 1130840
4313 | Scope | Change | Creep | 13 | 9 | International shipment of tape was on time, but the tape was bad. | 0 | Americas | IT/Solution | 2006 | December | 1286259
4314 | Scope | Change | Gap | 24 | 5 | Delivery problems on international shipment--paperwork, customs. | 0 | Americas | Prod. Dev. | 2010 | December | 1665888
4315 | Scope | Change | Gap | 5 | 1 | Component needed in China for prototype not available; had to be shipped from US | 0 | Americas | IT/Solution | 2010 | December | 401575
4316 | Scope | Change | Gap | 23 | 9 | Lack of spare parts and expertise | 0 | Americas | IT/Solution | 2011 | August | 2092333
4317 | Scope | Defect | Hardware | 23 | 8 | New pumps sent that lacked instructions and spare parts | 0 | Americas | IT/Solution | 2010 | July | 1300374
4318 | Resource | People | Temp loss | 22 | 2 | Move out of old location required, but new space is not ready. Interim move to temporary space takes extra time and money. | 2 | Eur/ME | IT/Solution | 2017 | November | 2052248
4319 | Schedule | Delay | Decision | 10 | 7 | Operating system selected (LINUX) has inadequate support for timely solution of conversion and delivery problems. | 0 | Americas | IT/Solution | 2002 | December | 540460
4320 | Schedule | Delay | Information | 17 | 4 | Late facility availability | 0 | Americas | IT/Solution | 2012 | December | 1629501
4321 | Scope | Change | Creep | 17 | 8 | Lack of access to professional translation services | 2 | Eur/ME | IT/Solution | 2002 | November | 1303849
4322 | Scope | Change | Gap | 17 | 5 | Systems needed for project work failed late in the project, and when work was completed installation delayed further to next possible installation window. | 2 | Eur/ME | IT/Solution | 2016 | April | 1610648
4323 | Scope | Change | Gap | 21 | 4 | Telecom line delays | 2 | Eur/ME | IT/Solution | 2018 | September | 1661814
4324 | Scope | Defect | Hardware | 25 | 5 | New requirements that mandated all products that have yet to ship to market to be re-tested | 0 | Americas | IT/Solution | 2010 | November | 1914700
4325 | Scope | Defect | Software | 25 | 6 | Shipping requirements changed. Some shipments bounce, others get stuck in customs. | 2 | Eur/ME | IT/Solution | 2016 | May | 1635900
4326 | Resource | People | Queuing | 25 | 6 | Approvals held up at project completion to wait for delayed support plan. | 2 | Eur/ME | IT/Solution | 2003 | June | 1960725
4327 | Resource | People | Temp loss | 11 | 9 | One team in another country missed deadlines on a complex proposal, creating delay and frustration. | 0 | Americas | IT/Solution | 2002 | April | 787050
4328 | Schedule | Delay | Parts | 18 | 5 | Lack of coordination between projects causes delays. | 0 | Americas | IT/Solution | 2010 | April | 952812
4329 | Resource | People | Motivation | 26 | 7 | Clear delegation of work done by project team and by customer never done. Confusion led to delays. | 2 | Eur/ME | Prod. Dev. | 2004 | July | 1729702
4330 | Schedule | Delay | Parts | 16 | 5 | Installation of new systems scheduled by central team, but local people are not ready. | 2 | Eur/ME | Prod. Dev. | 2008 | January | 1507472
4331 | Schedule | Delay | Parts | 16 | 3 | Changes to related systems resulted in wrong/late paychecks | 2 | Eur/ME | Prod. Dev. | 2019 | June | 1490912
4332 | Schedule | Dependency | Project | 24 | 3 | Firewall changes can take 25 days, estimates are capped at 15 | 2 | Eur/ME | Prod. Dev. | 2004 | April | 1729440
4333 | Scope | Change | Creep | 24 | 1 | Software upgrades take longer each cycle as O/S expands and application list grows. | 2 | Eur/ME | Prod. Dev. | 2018 | May | 1555464
4334 | Scope | Change | Creep | 20 | 8 | Estimates in proposal too short. Testing takes more time and is highly variable. | 0 | Americas | Prod. Dev. | 2008 | November | 1369640
4335 | Scope | Change | Creep | 21 | 3 | Work was underestimated by 40% | 0 | Americas | IT/Solution | 2003 | October | 1492008
4336 | Scope | Change | Gap | 18 | 2 | Insufficient time is estimated; the deadline could not be met. | 0 | Americas | IT/Solution | 2017 | December | 1511478
4337 | Scope | Change | Gap | 8 | 9 | Issues with testing were severly underestimated | 0 | Americas | IT/Solution | 2010 | November | 747104
4338 | Scope | Defect | Hardware | 14 | 1 | Insufficient time was scheduled for testing | 0 | Americas | Prod. Dev. | 2014 | March | 788564
4339 | Scope | Defect | Software | 20 | 1 | Cabling estimates too optimistic. | 0 | Americas | Prod. Dev. | 2010 | October | 1752420
4340 | Schedule | Dependency | Project | 17 | 3 | Testing time underestimated. | 0 | Americas | Prod. Dev. | 2010 | August | 1168665
4341 | Resource | People | Motivation | 5 | 6 | Lack of in-house expertise of the source system | 0 | Americas | IT/Solution | 2010 | September | 258620
4342 | Scope | Change | Creep | 11 | 6 | Programmer had a lack of experience in the healthcare industry | 0 | Americas | IT/Solution | 2013 | December | 1019942
4343 | Resource | Outsourcing | Late or poor output | 1 | 1 | Software could only be delivered to a certified person | 0 | Americas | Prod. Dev. | 2018 | January | 51298
4344 | Schedule | Estimates | Learning | 12 | 8 | Critical technical task was assigned to resource who was a new hire | 2 | Eur/ME | IT/Solution | 2013 | June | 738816
4345 | Scope | Defect | Hardware | 13 | 4 | Customer reorganization led to new staffing and changed requirements | 2 | Eur/ME | IT/Solution | 2013 | December | 842933
4346 | Scope | Defect | Software | 14 | 5 | Project priorities are unclear and secondary, less important work is done delaying required tasks. | 2 | Eur/ME | IT/Solution | 2008 | January | 719054
4347 | Schedule | Estimates | Judgment | 7 | 3 | Project end date moved; unrealistic | 2 | Eur/ME | IT/Solution | 2012 | November | 511133
4348 | Scope | Change | Gap | 18 | 5 | Scope creep and resource inadequacy | 0 | Americas | IT/Solution | 2004 | January | 978030
4349 | Scope | Defect | Software | 1 | 5 | Project benchmarks and requirements were never clearly defined | 0 | Americas | IT/Solution | 2001 | July | 80359
4350 | Scope | Defect | Software | 22 | 8 | Project manager added additional customized reporting (for no additional fee) | 0 | Americas | IT/Solution | 2010 | December | 1481678
4351 | Schedule | Delay | Information | 8 | 4 | Client changes her mind every step of the way | 0 | Americas | Prod. Dev. | 2011 | September | 751208
4352 | Resource | People | Loss | 8 | 5 | Program Manager squeezes in additional functionalities until the very last minute | 0 | Americas | Prod. Dev. | 2010 | July | 501752
4353 | Resource | People | Loss | 15 | 2 | Scope of product categories was broadened significantly | 0 | Americas | IT/Solution | 2010 | August | 1485465
4354 | Resource | People | Queuing | 8 | 4 | Senior management decided to change the core switching platform technology | 0 | Americas | Prod. Dev. | 2006 | January | 733088
4355 | Scope | Change | Creep | 13 | 3 | Changes double the work on solution project; no change in funding. | 0 | Americas | Prod. Dev. | 2005 | May | 966498
4356 | Scope | Change | Gap | 6 | 1 | Excessive scope change in ERP project | 0 | Americas | Prod. Dev. | 2010 | October | 382176
4357 | Scope | Change | Gap | 13 | 8 | Translated text was too long | 0 | Americas | IT/Solution | 2010 | May | 1276080
4358 | Scope | Change | Gap | 19 | 3 | Late in long project, process rigor falls and changes are managed poorly. | 2 | Eur/ME | IT/Solution | 2006 | December | 1546467
4359 | Scope | Change | Creep | 21 | 1 | Upgrade to software required. Planning and training caused delays. | 0 | Americas | Prod. Dev. | 2007 | October | 1855161
4360 | Scope | Change | Dependency | 11 | 1 | New software release installed by IT, and inconsistencies with older version caused delay and extra work. | 0 | Americas | Prod. Dev. | 2012 | May | 744920
4361 | Resource | Money | Limitation | 15 | 2 | Details of requirements were submitted incorrectly | 0 | Americas | Prod. Dev. | 2002 | June | 820110
4362 | Schedule | Delay | Information | 5 | 4 | Patch to software required for project work; extra work required to implement. | 0 | Americas | IT/Solution | 2004 | April | 388295
4363 | Resource | People | Loss | 12 | 5 | New software installed by IT. It does not work, and causes delay to fix. | 0 | Americas | IT/Solution | 2010 | January | 902220
4364 | Resource | People | Loss | 2 | 4 | Operating system release expected slips; project forced to use prior version missing some needed functionality. | 0 | Americas | IT/Solution | 2008 | August | 113088
4365 | Resource | People | Temp loss | 23 | 4 | Metrics from many sites required. When collected, additional work required to make consistent. | 2 | Eur/ME | Prod. Dev. | 2002 | March | 1582193
4366 | Schedule | Estimates | Judgment | 1 | 4 | Mismatch in documents and expectations. Adjustments required lots of additional work. | 0 | Americas | Prod. Dev. | 2007 | March | 89941
4367 | Scope | Change | Creep | 14 | 9 | Scanning of text was estimated before it was known text was bound in volumes | 2 | Eur/ME | IT/Solution | 2004 | September | 991998
4368 | Scope | Defect | Hardware | 16 | 6 | Scope was poorly defined | 2 | Eur/ME | Prod. Dev. | 2013 | August | 917968
4369 | Resource | Money | Limitation | 24 | 5 | Online badge printing requirement completely missing from scope definition | 0 | Americas | Prod. Dev. | 2001 | June | 1388904
4370 | Resource | Outsourcing | Late or poor output | 14 | 2 | The old production machine fails. The new production machine is pressed into production ahead of schedule; takes longer than planned | 0 | Americas | Prod. Dev. | 2010 | June | 1324470
4371 | Resource | People | Late start | 6 | 1 | Missing important scope at the beginning of the project | 0 | Americas | Prod. Dev. | 2010 | November | 300936
4372 | Resource | People | Temp loss | 25 | 3 | IT staff failed to understand the user requirements | 2 | Eur/ME | Prod. Dev. | 2014 | February | 1610450
4373 | Schedule | Delay | Parts | 10 | 3 | Requirements for compiling and formatting data were not clear | 0 | Americas | IT/Solution | 2017 | December | 825120
4374 | Schedule | Delay | Parts | 6 | 8 | Scope of the project was underestimated and only detected during analysis | 2 | Eur/ME | IT/Solution | 2010 | April | 469536
4375 | Schedule | Estimates | Learning | 18 | 6 | Scope requirement discovered late in a construction project | 0 | Americas | Prod. Dev. | 2014 | October | 1384416
4376 | Scope | Change | Creep | 18 | 3 | Kitchen remodel required a seismic upgrade | 0 | Americas | IT/Solution | 2001 | January | 1367190
4377 | Scope | Change | Gap | 11 | 5 | Database of components had not been updated to current OSHA standards | 0 | Americas | IT/Solution | 2005 | September | 737825
4378 | Scope | Change | Gap | 7 | 6 | IT team did not perform a thorough investigation of the existing infrastructure | 0 | Americas | IT/Solution | 2006 | July | 532917
4379 | Resource | Outsourcing | Late or poor output | 10 | 1 | Tests not scheduled for working parts, but mandated for project. Added late. | 0 | Americas | Prod. Dev. | 2001 | November | 692580
4380 | Resource | Outsourcing | Late or poor output | 2 | 5 | Proprietary data needed, but owners unwilling to provide. After delay, partial information shared. | 2 | Eur/ME | IT/Solution | 2005 | October | 114676
4381 | Resource | People | Late start | 15 | 8 | Retrofit project discovered hidden damage that had to be fixed | 2 | Eur/ME | IT/Solution | 2010 | August | 1002765
4382 | Resource | People | Motivation | 26 | 9 | After test, additional requirements surface | 0 | Americas | Prod. Dev. | 2010 | September | 1433978
4383 | Schedule | Delay | Parts | 19 | 1 | Iadequate analysis prior to iniitating development efforts | 0 | Americas | Prod. Dev. | 2016 | January | 955263
4384 | Scope | Change | Creep | 8 | 8 | Scope was not discussed with the manufacturer before design was completed | 0 | Americas | IT/Solution | 2010 | December | 441224
4385 | Scope | Change | Dependency | 17 | 1 | Technical requirements communicated to developers too late | 0 | Americas | IT/Solution | 2015 | September | 1619250
4386 | Scope | Defect | Software | 23 | 2 | System functions well in Germany, but has no German documentation. Delay for translation. | 0 | Americas | Prod. Dev. | 2018 | October | 1223968
4387 | Resource | Money | Limitation | 14 | 8 | fittings and assemblies were not up to project standards | 0 | Americas | Prod. Dev. | 2008 | July | 1135526
4388 | Schedule | Delay | Hardware | 13 | 7 | Prototype problems excessive; more time to fix than planned. | 0 | Americas | IT/Solution | 2010 | July | 754910
4389 | Resource | Outsourcing | Late or poor output | 3 | 2 | Process reliability was too low and required a new component to work | 0 | Americas | Prod. Dev. | 2010 | November | 286980
4390 | Resource | Outsourcing | Late or poor output | 9 | 9 | Problem arose that required use of a a novel raw material not in inventory | 0 | Americas | Prod. Dev. | 2019 | December | 724374
4391 | Resource | People | Late start | 6 | 2 | Solution project integrated new, untried technology. Difficulty getting it to work. | 0 | Americas | IT/Solution | 2010 | April | 565626
4392 | Resource | People | Loss | 8 | 9 | Integrating course content that does not comply with LMS specifications | 0 | Americas | Prod. Dev. | 2004 | July | 427800
4393 | Resource | People | Loss | 25 | 3 | Software modules in system do not work together as planned. | 0 | Americas | Prod. Dev. | 2008 | April | 2276500
4394 | Resource | People | Queuing | 18 | 6 | Following recent upgrade, many bugs were found | 2 | Eur/ME | IT/Solution | 2009 | August | 1509174
4395 | Schedule | Delay | Decision | 1 | 5 | Excessive bugs detected late; delayed to fix. | 2 | Eur/ME | Prod. Dev. | 2003 | September | 87515
4396 | Schedule | Delay | Hardware | 15 | 2 | When testing reveals a performance defect which is due to a conflict between two, or more, of the components significant extra work is required | 0 | Americas | IT/Solution | 2015 | March | 1391655
4397 | Schedule | Delay | Information | 8 | 5 | Excessive bugs | 0 | Americas | IT/Solution | 2002 | October | 505064
4398 | Schedule | Delay | Parts | 3 | 5 | New software release causes problems | 0 | Americas | IT/Solution | 2015 | February | 157509
4399 | Schedule | Dependency | Legal | 19 | 3 | Bug could be fixed only by moving to a later version of software | 0 | Americas | IT/Solution | 2010 | November | 1690278
4400 | Schedule | Dependency | Project | 24 | 2 | Controlled Document rejected by Approvers | 0 | Americas | IT/Solution | 2010 | September | 1985688
4401 | Schedule | Estimates | Judgment | 25 | 9 | Approvers reject required document | 0 | Americas | Prod. Dev. | 2018 | August | 1869325
4402 | Schedule | Estimates | Learning | 10 | 4 | Late quality assurance finds additional translation work is needed | 0 | Americas | Prod. Dev. | 2010 | January | 796050
4403 | Schedule | Estimates | Learning | 15 | 4 | Translations are incomplete | 0 | Americas | IT/Solution | 2010 | April | 1497480
4404 | Schedule | Estimates | Learning | 9 | 8 | Quality problems led to late redesign, extra work and plan changes. | 0 | Americas | IT/Solution | 2015 | November | 483012
4405 | Scope | Change | Creep | 24 | 5 | Delay in patient recruitment for clinical trials | 2 | Eur/ME | IT/Solution | 2008 | January | 1948032
4406 | Scope | Change | Creep | 15 | 6 | Engineering would not stop adding “bell and whistles” to GUI | 0 | Americas | IT/Solution | 2010 | November | 753930
4407 | Scope | Change | Creep | 19 | 3 | A full bioequivalent (BE) study was unexpectedly needed even though there was only a minor difference | 0 | Americas | IT/Solution | 2010 | November | 1474305
4408 | Scope | Change | Creep | 7 | 7 | Due to poor understanding, a redesign and costing effort was neeed | 2 | Eur/ME | IT/Solution | 2008 | August | 615447
4409 | Scope | Change | Creep | 25 | 7 | Based on testing, performance was insufficient to gain approval to market | 0 | Americas | IT/Solution | 2002 | August | 1835875
4410 | Scope | Change | Creep | 5 | 2 | Requirements are misunderstood or understood differently by multiple parties | 0 | Americas | IT/Solution | 2010 | December | 466610
4411 | Scope | Change | Creep | 17 | 4 | Sudden exit of the primary developer | 0 | Americas | Prod. Dev. | 2010 | August | 997611
4412 | Scope | Change | Creep | 14 | 2 | Change requested and agreed to, but supplier ships late and it does not work. | 0 | Americas | Prod. Dev. | 2003 | February | 895986
4413 | Scope | Change | Creep | 13 | 3 | Lack of head count from a 10% company-wide lay-off. | 0 | Americas | IT/Solution | 2003 | February | 997802
4414 | Scope | Change | Creep | 5 | 8 | Neophyte project staff lacked system expertise. | 2 | Eur/ME | Prod. Dev. | 2010 | January | 458545
4415 | Scope | Change | Creep | 17 | 5 | New technology to be used failed to meet the needs | 0 | Americas | Prod. Dev. | 2015 | April | 1590418
4416 | Scope | Change | Dependency | 15 | 6 | Changes in contracts and scope not managed well | 0 | Americas | IT/Solution | 2010 | January | 1213995
4417 | Scope | Change | Gap | 19 | 8 | High turnover. ( 80%) of developer at off shore development unit left, including project lead | 2 | Eur/ME | Prod. Dev. | 2005 | August | 1848814
4418 | Scope | Change | Gap | 23 | 1 | Contributor couldn't work due to injury and back pains | 0 | Americas | IT/Solution | 2010 | May | 1926181
4419 | Scope | Change | Gap | 6 | 3 | Definition changed late in project. | 2 | Eur/ME | IT/Solution | 2011 | July | 507372
4420 | Scope | Change | Gap | 9 | 6 | Management did not plan for a requirements gathering phase | 0 | Americas | Prod. Dev. | 2010 | April | 486621
4421 | Scope | Change | Gap | 19 | 3 | 1000 hour tests required at project end. Failure half-way (or later) requires fix and restart. | 0 | Americas | Prod. Dev. | 2015 | October | 1176157
4422 | Scope | Change | Gap | 22 | 5 | Project was longer than necessary because one team insisted on doing "half" literally, even though the effort resulting was very lopsided. | 2 | Eur/ME | Prod. Dev. | 2012 | January | 1908192
4423 | Scope | Change | Gap | 22 | 7 | Partner software is incompatible with current applications. | 0 | Americas | Prod. Dev. | 2015 | November | 2180992
4424 | Scope | Change | Gap | 5 | 3 | Key person gave notice more than a month before leaving, but nothing was done | 0 | Americas | Prod. Dev. | 2015 | August | 396310
4425 | Scope | Change | Gap | 16 | 2 | Chip failed and had to be refabricated with changes | 2 | Eur/ME | Prod. Dev. | 2013 | March | 1240288
4426 | Scope | Change | Gap | 15 | 8 | Unrealistic deadline set; slips unavoidable. | 0 | Americas | IT/Solution | 2015 | September | 1351230
4427 | Scope | Change | Gap | 16 | 5 | Contractual obligations set without adequate knowledge of potential hidden issues | 2 | Eur/ME | IT/Solution | 2007 | November | 1379344
4428 | Scope | Defect | Hardware | 1 | 3 | Server expansion project dependent on delayed tape library decommissioning | 0 | Americas | IT/Solution | 2015 | October | 70008
4429 | Scope | Defect | Integration | 16 | 7 | 3 week test took 7 due to learning curve and ramp time. | 2 | Eur/ME | IT/Solution | 2012 | December | 1047552
4430 | Scope | Defect | Software | 17 | 5 | Mid project expansion to include account receivable process | 0 | Americas | Prod. Dev. | 2010 | September | 1345465
4431 | Scope | Defect | Software | 15 | 1 | Construction of subdivision was initiated using old maps | 2 | Eur/ME | Prod. Dev. | 2010 | July | 1079325
4432 | Scope | Defect | Software | 6 | 4 | System with new components fails in final tests. Getting older components difficult. | 0 | Americas | Prod. Dev. | 2010 | June | 397038
4433 | Scope | Defect | Software | 21 | 9 | Only one subject matter expert, who was also the PM | 0 | Americas | Prod. Dev. | 2005 | May | 1739598
4434 | Resource | Money | Limitation | 26 | 6 | Key analyst is scheduled to work on another project | 0 | Americas | Prod. Dev. | 2015 | November | 1809678
4435 | Resource | Money | Limitation | 19 | 6 | Architect who knew how to integrate all components fell sick and was hospitalized | 0 | Americas | Prod. Dev. | 2010 | February | 1678745
4436 | Resource | Money | Limitation | 7 | 6 | One key investigation step failed, and had to be redone | 0 | Americas | Prod. Dev. | 2016 | July | 439992
4437 | Resource | Money | Limitation | 26 | 5 | None of the developers had experience with the platform the application needed | 2 | Eur/ME | Prod. Dev. | 2009 | July | 2093078
4438 | Resource | Money | Limitation | 8 | 4 | Client made a late change the landscape design, causing overtime, expense and delay | 0 | Americas | IT/Solution | 2010 | December | 516800
4439 | Scope | Defect | Software | 3 | 6 | Didn’t explicitly define the scope, and changed part way through | 0 | Americas | IT/Solution | 2010 | February | 171021
4440 | Scope | Defect | Hardware | 5 | 1 | Late in project, the budget and staff are cut leading to delays, forced overtime, and demotivation. | 0 | Americas | IT/Solution | 2010 | November | 262635
4441 | Resource | Outsourcing | Late or poor output | 22 | 9 | Limits on headcount create work backlog | 0 | Americas | IT/Solution | 2015 | September | 1502556
4442 | Resource | People | Motivation | 10 | 9 | Required design review delayed. | 0 | Americas | Prod. Dev. | 2015 | February | 717610
4443 | Resource | People | Loss | 26 | 4 | Lack of spare parts and expertise | 2 | Eur/ME | IT/Solution | 2002 | January | 1588392
4444 | Scope | Change | Gap | 21 | 9 | Approvals held up at project completion to wait for delayed support plan. | 2 | Eur/ME | Prod. Dev. | 2002 | February | 1372245
4445 | Resource | Money | Limitation | 17 | 2 | Patch to software required for project work; extra work required to implement. | 0 | Americas | IT/Solution | 2002 | May | 885836
4446 | Resource | People | Late start | 9 | 3 | The old production machine fails. The new production machine is pressed into production ahead of schedule; takes longer than planned | 2 | Eur/ME | Prod. Dev. | 2004 | May | 707724
4447 | Scope | Defect | Software | 17 | 4 | Scope of the project was underestimated and only detected during analysis | 0 | Americas | Prod. Dev. | 2010 | June | 1334483
4448 | Schedule | Delay | Parts | 3 | 5 | Outsouced staff lacked the necessary skillset | 2 | Eur/ME | IT/Solution | 2007 | May | 225486
4449 | Resource | People | Queuing | 22 | 3 | Work at customer site had to be done by union workers; took 6 days to do what project team could do in 1. | 2 | Eur/ME | Prod. Dev. | 2002 | June | 1991176
4450 | Scope | Change | Gap | 7 | 9 | Integration testing is incomplete, causing system failures. | 0 | Americas | IT/Solution | 2010 | November | 355901
4451 | Schedule | Dependency | Infrastructure | 18 | 3 | Part of the project team ran of money three months before the project was scheduled to end | 0 | Americas | IT/Solution | 2002 | October | 987570
4452 | Schedule | Estimates | Learning | 20 | 6 | Development team had insufficient resources assigned to the project | 0 | Americas | Prod. Dev. | 2015 | August | 1806920
4453 | Scope | Change | Creep | 24 | 4 | Unexpectedly high demand requires outlisde help | 0 | Americas | Prod. Dev. | 2010 | April | 2018520
4454 | Scope | Change | Creep | 19 | 9 | Excessive challenge of initiating a project in different time zones | 0 | Americas | IT/Solution | 2010 | July | 1729589
4455 | Scope | Change | Gap | 7 | 5 | Key consultant breaks both arms 3 weeks before project end | 0 | Americas | IT/Solution | 2015 | January | 534338
4456 | Schedule | Delay | Decision | 9 | 2 | Poor planning for the transition between consultants | 2 | Eur/ME | IT/Solution | 2010 | November | 669096
4457 | Schedule | Delay | Parts | 14 | 8 | Engineering consultant firm laid off a chief structural engineer late in project | 0 | Americas | Prod. Dev. | 2015 | June | 1127336
4458 | Schedule | Estimates | Judgment | 1 | 2 | Growth pushed work to understaffed contract firms | 0 | Americas | Prod. Dev. | 2001 | February | 66567
4459 | Scope | Change | Creep | 22 | 4 | Subcontractor late with a critical component | 0 | Americas | Prod. Dev. | 2005 | October | 1245684
4460 | Scope | Change | Gap | 3 | 2 | Contractor got a bigger project moved most of his team to that | 0 | Americas | Prod. Dev. | 2015 | October | 153363
4461 | Scope | Change | Gap | 8 | 6 | Designer doesn’t have skills to finish needed work | 2 | Eur/ME | Prod. Dev. | 2013 | April | 580768
4462 | Resource | People | Queuing | 6 | 4 | Usual vendor closed its business and had to be replaced | 0 | Americas | Prod. Dev. | 2006 | July | 387192
4463 | Resource | People | Temp loss | 15 | 9 | Programming object delivered late from India delays integration tests | 0 | Americas | Prod. Dev. | 2015 | September | 1163220
4464 | Schedule | Delay | Decision | 5 | 9 | Decision to switch to contract manufacturer near end of project caused delays and cost increases. | 0 | Americas | IT/Solution | 2004 | December | 384755
4465 | Schedule | Delay | Parts | 7 | 1 | Vendor was inexperienced with relevant equipment | 2 | Eur/ME | IT/Solution | 2006 | June | 602105
4466 | Schedule | Dependency | Infrastructure | 10 | 9 | Subcontractor overbooked; not available when needed | 0 | Americas | Prod. Dev. | 2015 | July | 649840
4467 | Scope | Change | Creep | 5 | 8 | Finding instructional designers that know how to use specialized software | 0 | Americas | IT/Solution | 2010 | April | 267085
4468 | Scope | Change | Dependency | 13 | 2 | Critical person went on maternity leave | 0 | Americas | IT/Solution | 2008 | January | 762983
4469 | Resource | Outsourcing | Late or poor output | 7 | 4 | Key contriobutor quit, and there was insufficient information transfer | 0 | Americas | Prod. Dev. | 2005 | September | 471443
4470 | Schedule | Delay | Hardware | 9 | 2 | The key business user assigned to the ITS project was lost while assisting with a manufacturing problem and was no longer available to the project team | 0 | Americas | Prod. Dev. | 2010 | May | 501255
4471 | Scope | Change | Creep | 10 | 8 | Senior technical writer resigns and another takes a leave | 0 | Americas | Prod. Dev. | 2013 | October | 880230
4472 | Resource | Outsourcing | Late or poor output | 1 | 6 | A senior technical architecte quit | 2 | Eur/ME | IT/Solution | 2002 | August | 91568
4473 | Resource | Money | Limitation | 16 | 8 | The key person responsible for major marketing activities resigned | 0 | Americas | IT/Solution | 2015 | December | 1346976
4474 | Resource | Outsourcing | Delayed start | 16 | 4 | Resources committed to projects reassigned to new projects and not replaced. | 0 | Americas | Prod. Dev. | 2010 | July | 965664
4475 | Resource | Outsourcing | Late or poor output | 26 | 5 | Too little management interest and support | 0 | Americas | Prod. Dev. | 2010 | January | 1673542
4476 | Resource | Outsourcing | Late or poor output | 13 | 1 | People who require training miss classes; more classes required. | 0 | Americas | Prod. Dev. | 2015 | September | 692926
4477 | Resource | Outsourcing | Late or poor output | 22 | 7 | All students did not complete training as scheduled, so the project is completed late | 2 | Eur/ME | IT/Solution | 2019 | October | 1968626
4478 | Resource | Outsourcing | Late or poor output | 4 | 1 | Two projects depended on one resource for completion and this one had lower priority | 0 | Americas | Prod. Dev. | 2015 | December | 381120
4479 | Resource | People | Late start | 14 | 7 | There was only on one experienced consultant who knew the tool | 2 | Eur/ME | Prod. Dev. | 2016 | January | 804216
4480 | Resource | People | Loss | 26 | 7 | Only one subject matter expert, who was also the PM | 2 | Eur/ME | IT/Solution | 2015 | June | 1770652
4481 | Resource | People | Motivation | 25 | 9 | "50%" resources are not aligned, resulting in activity delays | 0 | Americas | Prod. Dev. | 2010 | June | 1777150
4482 | Resource | People | Queuing | 8 | 1 | Two of the developers were able to work on the project only 60% of their time, not full time | 2 | Eur/ME | Prod. Dev. | 2006 | July | 499792
4483 | Resource | People | Queuing | 15 | 3 | Reduction in work force affects the % commitment of team members | 0 | Americas | Prod. Dev. | 2001 | October | 1473135
4484 | Resource | People | Queuing | 7 | 9 | Expert worked on at least 4-5 projects at a time | 0 | Americas | IT/Solution | 2010 | April | 418677
4485 | Resource | People | Queuing | 15 | 6 | CMO analyzing output developed a severe backup | 0 | Americas | IT/Solution | 2010 | December | 1108875
4486 | Resource | People | Queuing | 20 | 8 | During testing phase, resource availability was indaequate due to other priorities | 0 | Americas | IT/Solution | 2009 | May | 1028640
4487 | Resource | People | Queuing | 3 | 9 | Multiple projects depend on lone expert scientist | 0 | Americas | IT/Solution | 2010 | April | 161874
4488 | Resource | People | Temp loss | 11 | 6 | 2 key team members lost for a time because of illness | 0 | Americas | IT/Solution | 2004 | January | 978252
4489 | Resource | People | Temp loss | 11 | 6 | Key analyst is scheduled to work on another project | 0 | Americas | IT/Solution | 2015 | November | 677930
4490 | Resource | People | Temp loss | 26 | 1 | Key IT resources scheduled extensive vacations | 0 | Americas | IT/Solution | 2010 | February | 1891006
4491 | Resource | People | Temp loss | 2 | 5 | Study timeline set before staff vacation dates were known | 0 | Americas | IT/Solution | 2010 | August | 105886
4492 | Resource | People | Temp loss | 3 | 1 | Loss of key members of a project team in an already constrained project. | 0 | Americas | IT/Solution | 2016 | August | 244494
4493 | Resource | People | Temp loss | 3 | 9 | Architect who knew how to integrate all components fell sick and was hospitalized | 0 | Americas | Prod. Dev. | 2015 | September | 162684
4494 | Schedule | Delay | Decision | 13 | 6 | Earthquake in Taiwan makes part of the project team unavailable for work. | 0 | Americas | Prod. Dev. | 2010 | July | 1145729
4495 | Schedule | Delay | Decision | 15 | 9 | Only 2 people understood the new system, and neither was available | 0 | Americas | Prod. Dev. | 2010 | April | 1157415
4496 | Schedule | Delay | Hardware | 6 | 8 | At year-end, engineer in Germenay had to take accrued vacation time | 2 | Eur/ME | Prod. Dev. | 2014 | April | 307182
4497 | Schedule | Delay | Hardware | 11 | 8 | Senior management approval for software licenses delayed | 0 | Americas | Prod. Dev. | 2010 | September | 923659
4498 | Schedule | Delay | Hardware | 22 | 7 | A component needed for necropsy data analysis failed | 0 | Americas | Prod. Dev. | 2015 | February | 1511730
4499 | Schedule | Delay | Hardware | 18 | 7 | One key investigation step failed, and had to be redone | 0 | Americas | IT/Solution | 2015 | April | 1609686
4500 | Schedule | Delay | Hardware | 25 | 6 | Needed system delivered to wrong building; lost for weeks. | 0 | Americas | IT/Solution | 2015 | September | 1923300
4501 | Schedule | Delay | Information | 6 | 1 | Metrics required by process improvement project collected and delivered late. | 0 | Americas | IT/Solution | 2010 | September | 336150
4502 | Schedule | Delay | Information | 23 | 9 | With 12 hour time difference and dependence on E-mail, even simple questions take 2-4 days to resolve. | 2 | Eur/ME | IT/Solution | 2015 | October | 1721320
4503 | Schedule | Delay | Information | 6 | 6 | Some tasks assigned only by function; no one actually working on them. | 2 | Eur/ME | IT/Solution | 2014 | July | 305910
4504 | Schedule | Delay | Parts | 9 | 4 | Servers stuck in customs | 2 | Eur/ME | IT/Solution | 2014 | January | 894924
4505 | Schedule | Delay | Parts | 25 | 3 | Had only 1/3 of the units needed on time | 0 | Americas | IT/Solution | 2015 | October | 1972475
4506 | Schedule | Delay | Parts | 3 | 8 | Key supplier lost in the middle of a project | 0 | Americas | IT/Solution | 2002 | October | 194244
4507 | Schedule | Delay | Parts | 12 | 3 | Parts unavailable; backordered. | 2 | Eur/ME | IT/Solution | 2006 | May | 1140288
4508 | Schedule | Delay | Parts | 5 | 2 | ASIC delays | 0 | Americas | IT/Solution | 2010 | August | 282150
4509 | Schedule | Delay | Parts | 12 | 1 | Change to US sourcing created demand and delays | 0 | Americas | IT/Solution | 2001 | February | 676512
4510 | Schedule | Delay | Parts | 8 | 5 | Manufacturing problem with key component | 0 | Americas | IT/Solution | 2011 | October | 496744
4511 | Schedule | Dependency | Project | 19 | 6 | Parts shipped by sea from Asia, not air. | 2 | Eur/ME | IT/Solution | 2010 | February | 1513255
4512 | Schedule | Dependency | Project | 5 | 9 | International shipment of parts supposed to take 6 weeks, actually averages 9. | 2 | Eur/ME | IT/Solution | 2016 | February | 320785
4513 | Schedule | Dependency | Project | 21 | 1 | Some parts are damaged in shipping and must be reordered. | 0 | Americas | IT/Solution | 2009 | August | 1794765
4514 | Schedule | Estimates | Judgment | 16 | 1 | Samples needed in Spain were late | 2 | Eur/ME | IT/Solution | 2009 | December | 1018848
4515 | Schedule | Estimates | Judgment | 18 | 3 | Needed concrete wasn’t delivered on time | 0 | Americas | IT/Solution | 2015 | July | 1686816
4516 | Scope | Change | Creep | 5 | 9 | Component delivery late. Causes ramp delays. | 2 | Eur/ME | IT/Solution | 2003 | August | 321535
4517 | Scope | Change | Creep | 20 | 9 | Needed wiring not available on time | 2 | Eur/ME | Prod. Dev. | 2002 | February | 1992660
4518 | Scope | Change | Creep | 5 | 5 | the infrastructure changes needed (network, microwave, etc) were not budgeted for the project | 0 | Americas | Prod. Dev. | 2010 | December | 462850
4519 | Scope | Change | Creep | 17 | 4 | Space unavailable; needed to implement in old space | 0 | Americas | Prod. Dev. | 2015 | August | 890970
4520 | Scope | Change | Creep | 20 | 2 | Problems due to last minute infrastructure changes | 2 | Eur/ME | Prod. Dev. | 2004 | September | 1098180
4521 | Scope | Change | Creep | 19 | 1 | Delay in approval to proceed in France and German | 0 | Americas | Prod. Dev. | 2015 | March | 1726321
4522 | Scope | Change | Creep | 8 | 4 | Commitment given, but deliverables were late. | 0 | Americas | Prod. Dev. | 2010 | January | 667576
4523 | Scope | Change | Dependency | 2 | 6 | Localization of the web contents delivery is delayed | 2 | Eur/ME | Prod. Dev. | 2001 | January | 148938
4524 | Scope | Change | Dependency | 7 | 8 | ASIC supplier (only source) was fine for low volume, but at lower cost and high volume had quality problems and created delays. | 0 | Americas | Prod. Dev. | 2001 | April | 474271
4525 | Scope | Change | Dependency | 2 | 7 | Unrealistic compressed timeline | 0 | Americas | Prod. Dev. | 2010 | March | 106068
4526 | Scope | Change | Gap | 6 | 8 | Unrealistic deadline set | 0 | Americas | Prod. Dev. | 2010 | June | 483390
4527 | Scope | Change | Gap | 13 | 8 | Recertification of updated applications took longer than hoped | 0 | Americas | IT/Solution | 2010 | April | 1213719
4528 | Scope | Change | Gap | 19 | 8 | Components that could have been purchased were developed by team, taking longer than expected. | 0 | Americas | IT/Solution | 2015 | June | 1208894
4529 | Scope | Change | Gap | 18 | 2 | The integration task was not defined and broken down to sufficiently small pieces in the project plan. | 0 | Americas | Prod. Dev. | 2011 | March | 962568
4530 | Scope | Change | Gap | 16 | 9 | Due to organizational change new person was assigned the work | 0 | Americas | IT/Solution | 2015 | October | 805248
4531 | Scope | Defect | Hardware | 1 | 8 | Team was staffed by 3 successive new hires in a six-month period | 0 | Americas | IT/Solution | 2014 | February | 61800
4532 | Scope | Defect | Hardware | 15 | 6 | None of the developers had experience with the platform the application needed | 0 | Americas | Prod. Dev. | 2010 | March | 1000860
4533 | Scope | Defect | Hardware | 2 | 9 | Oversea engineering team was inexperienced | 0 | Americas | Prod. Dev. | 2010 | December | 154942
4534 | Scope | Defect | Hardware | 8 | 6 | Lack of skills with recent university hires | 0 | Americas | Prod. Dev. | 2015 | January | 648184
4535 | Scope | Defect | Hardware | 7 | 2 | Client requested "15 minute" change accepted and led to delay and loss on project | 0 | Americas | IT/Solution | 2010 | May | 398048
4536 | Scope | Defect | Hardware | 15 | 8 | Revision to the story board is required | 0 | Americas | Prod. Dev. | 2015 | August | 1282530
4537 | Scope | Defect | Hardware | 19 | 2 | Project delayed due to recent/last minute changes to portal interface design | 0 | Americas | Prod. Dev. | 2015 | December | 1241137
4538 | Scope | Defect | Software | 3 | 8 | Client made a late change the landscape design, causing overtime, expense and delay | 0 | Americas | IT/Solution | 2002 | November | 297231
4539 | Scope | Defect | Software | 10 | 6 | Power configuration change was requested too late in the schedule | 0 | Americas | Prod. Dev. | 2015 | March | 991760
4540 | Scope | Defect | Software | 3 | 9 | 6 sister organizations with an additional 250 users added to the project late | 2 | Eur/ME | IT/Solution | 2011 | January | 263172
4541 | Scope | Defect | Software | 24 | 6 | Complex feature added that was not requested by the customer | 2 | Eur/ME | IT/Solution | 2009 | January | 1264488
4542 | Scope | Defect | Software | 16 | 2 | Additional deliverable added late | 2 | Eur/ME | IT/Solution | 2012 | December | 1198128
4543 | Scope | Defect | Software | 13 | 4 | Late design changes required manufacturing retooling at the last minute. | 0 | Americas | IT/Solution | 2018 | February | 744874
4544 | Schedule | Delay | Hardware | 1 | 2 | Didn’t explicitly define the scope, and changed part way through | 0 | Americas | Prod. Dev. | 2015 | January | 84288
4545 | Scope | Change | Gap | 23 | 1 | Escalated late changes from Sponsor | 0 | Americas | IT/Solution | 2008 | January | 2276126
4546 | Resource | Money | Limitation | 22 | 5 | Project schedule was revised user interface requirements which increased project scope | 0 | Americas | Prod. Dev. | 2010 | July | 1724844
4547 | Scope | Change | Creep | 22 | 5 | Integrating late features meant that the existing architecture had to be modified | 0 | Americas | Prod. Dev. | 2008 | June | 1333596
4548 | Scope | Change | Gap | 5 | 8 | No proper change control process resulted in unnecessary new requirements | 0 | Americas | Prod. Dev. | 2014 | March | 390025
4549 | Resource | Money | Limitation | 26 | 4 | "Minor" changes added and accepted late in project. Phase work doubled and delayed project end. | 0 | Americas | IT/Solution | 2002 | January | 2437292
4550 | Schedule | Delay | Information | 8 | 7 | Customer driven late changes | 0 | Americas | IT/Solution | 2015 | October | 692744
4551 | Resource | Outsourcing | Late or poor output | 15 | 8 | Customer requirements continually shift; lots of extra work. | 0 | Americas | IT/Solution | 2010 | August | 1133445
4552 | Resource | Money | Limitation | 26 | 7 | Server technology chage was necessitated to support application | 2 | Eur/ME | Prod. Dev. | 2015 | December | 2425748
4553 | Resource | Money | Limitation | 23 | 6 | Corporate merger delayed project | 0 | Americas | IT/Solution | 2006 | February | 1213710
4554 | Scope | Change | Gap | 6 | 5 | Lack of testing of older WWW browser versions led to custom coding being written before application could be used. | 3 | Africa | IT/Solution | 2018 | April | 415158
4555 | Resource | People | Loss | 8 | 4 | Incorrect input data provided | 3 | Africa | Prod. Dev. | 2012 | July | 783808
4556 | Resource | People | Late start | 2 | 4 | Failure to collect the details about the interfaces and links to the third party websites | 2 | Eur/ME | Prod. Dev. | 2012 | August | 126472
4557 | Resource | People | Loss | 18 | 1 | The database assigned for the client did not have sufficient free space for their growing accounts | 2 | Eur/ME | IT/Solution | 2018 | March | 1153044
4558 | Schedule | Delay | Parts | 18 | 2 | Changes were approved by the business users without proper testing | 0 | Americas | IT/Solution | 2015 | August | 1073376
4559 | Schedule | Estimates | Learning | 1 | 8 | Deliverable requirements were discovered during the execution phase | 0 | Americas | IT/Solution | 2010 | September | 61205
4560 | Scope | Change | Creep | 25 | 5 | One week’s analysis is insufficient to capture needed requirements | 0 | Americas | Prod. Dev. | 2015 | May | 1647350
4561 | Scope | Change | Creep | 12 | 4 | Legacy systems and processes were not well documented | 0 | Americas | IT/Solution | 2015 | September | 1110048
4562 | Scope | Defect | Hardware | 25 | 9 | Requireemnts sent via email were never formally documented | 0 | Americas | Prod. Dev. | 2015 | April | 1413225
4563 | Resource | Money | Limitation | 4 | 6 | Sponsor failed to communicate his requirements at the start of the project | 2 | Eur/ME | IT/Solution | 2012 | March | 318772
4564 | Scope | Change | Gap | 2 | 3 | Not enough timewas spent to identify all the requirements for the process | 0 | Americas | Prod. Dev. | 2015 | July | 114630
4565 | Schedule | Estimates | Learning | 14 | 9 | Lack of communication between the teams | 2 | Eur/ME | Prod. Dev. | 2017 | April | 821688
4566 | Scope | Change | Gap | 19 | 8 | Programmer didn’t understand what data was needed or why | 2 | Eur/ME | IT/Solution | 2015 | February | 1886491
4567 | Resource | People | Loss | 2 | 3 | Specifications incomplete and late. Delayed project start. | 2 | Eur/ME | IT/Solution | 2011 | February | 188146
4568 | Resource | People | Queuing | 25 | 5 | Insufficient initial project scope was defined when the estimate given to the client | 2 | Eur/ME | IT/Solution | 2005 | April | 2218325
4569 | Resource | People | Queuing | 13 | 5 | In testing, it is discovered that 50K words were left untranslated due to updates and changes | 0 | Americas | Prod. Dev. | 2010 | January | 1022632
4570 | Schedule | Delay | Hardware | 2 | 8 | Failure to understand the scope of the project | 2 | Eur/ME | IT/Solution | 2001 | March | 108196
4571 | Schedule | Dependency | Infrastructure | 7 | 8 | Resistance of the business stakeholders to reach consensus on the project’s scope | 0 | Americas | IT/Solution | 2010 | October | 556094
4572 | Schedule | Dependency | Legal | 3 | 9 | Lack of research and analysis on a key compoent of the deliverable | 0 | Americas | IT/Solution | 2015 | July | 289470
4573 | Scope | Change | Creep | 12 | 7 | Analysis group not involved in planning meetings | 0 | Americas | Prod. Dev. | 2010 | March | 1184544
4574 | Scope | Change | Gap | 8 | 7 | Instructions provided to the testing facility were too vague, necessitating re-tests | 0 | Americas | IT/Solution | 2010 | February | 624984
4575 | Resource | Money | Limitation | 16 | 5 | Scoping was much more complex then originally thought | 3 | Africa | IT/Solution | 2017 | January | 1405056
4576 | Resource | Outsourcing | Late or poor output | 23 | 2 | Lack of data and knowledge for the new product | 0 | Americas | IT/Solution | 2010 | May | 1875604
4577 | Resource | People | Loss | 11 | 8 | The development team in Pakistan misinterpreted a number of req'ts | 2 | Eur/ME | Prod. Dev. | 2011 | October | 971729
4578 | Resource | People | Queuing | 3 | 9 | Documentation provided in only one of two required languages. Delay for translation. | 2 | Eur/ME | IT/Solution | 2002 | December | 262839
4579 | Schedule | Delay | Decision | 21 | 1 | Documentation needed in French was entirely overlooked | 0 | Americas | IT/Solution | 2015 | July | 1906758
4580 | Schedule | Delay | Decision | 14 | 6 | Network configuration sometimes causes the backups to fail intermittently; troubleshooting is hard. | 3 | Africa | Prod. Dev. | 2017 | January | 1131396
4581 | Schedule | Delay | Hardware | 4 | 2 | Components were incorrectly measured | 3 | Africa | IT/Solution | 2003 | July | 378028
4582 | Schedule | Dependency | Legal | 13 | 1 | PC board failure requires redesign and fabrication. | 3 | Africa | IT/Solution | 2002 | September | 903422
4583 | Scope | Change | Creep | 5 | 9 | Poor quality control and record keeping on the field installation side resulted in many openings being installed incorrectly | 2 | Eur/ME | IT/Solution | 2005 | October | 469330
4584 | Scope | Change | Creep | 9 | 5 | Revisions required after review | 3 | Africa | IT/Solution | 2004 | April | 541962
4585 | Scope | Change | Dependency | 15 | 4 | There was not enough time to redo the programming to fix the errors identified | 2 | Eur/ME | IT/Solution | 2010 | September | 1005525
4586 | Scope | Change | Gap | 11 | 6 | Editing text worsened product quality and necessitated retranslation | 2 | Eur/ME | Prod. Dev. | 2013 | December | 671583
4587 | Resource | People | Queuing | 14 | 1 | Errors found in data and critrical reports | 0 | Americas | Prod. Dev. | 2010 | December | 1011052
4588 | Resource | People | Temp loss | 8 | 8 | Legacy system (COBOL) fails during system upgrade project. Extra effort required to fix. | 0 | Americas | Prod. Dev. | 2015 | March | 656592
4589 | Schedule | Delay | Information | 26 | 9 | Key supplier purchased by other company and reorganized. Forced to find new supplier. | 2 | Eur/ME | IT/Solution | 2004 | September | 1606670
4590 | Scope | Change | Dependency | 26 | 5 | Scoping for a wiring project increased substantially after awarding the business | 0 | Americas | Prod. Dev. | 2010 | June | 1842022
4591 | Resource | Money | Limitation | 14 | 4 | The software had around 20 major defects and 80 problems that prevented us from moving forward | 3 | Africa | IT/Solution | 2010 | March | 1250914
4592 | Resource | Money | Limitation | 9 | 8 | During unit testing, discovered performance issue with bulk loads | 3 | Africa | Prod. Dev. | 2016 | February | 882765
4593 | Resource | Money | Limitation | 10 | 9 | There was a very large mismatch between stakeholder expectations and given scope | 2 | Eur/ME | IT/Solution | 2015 | June | 928880
4594 | Resource | Money | Limitation | 26 | 4 | Lack of people resources (designers, requirement/business analysts, data modelers and QA/Testing) | 2 | Eur/ME | IT/Solution | 2009 | May | 1325402
4595 | Resource | Outsourcing | Delayed start | 25 | 5 | Market change due to Improvements in technology became an ‘urgent’ requirement | 0 | Americas | IT/Solution | 2015 | May | 2265925
4596 | Resource | Outsourcing | Delayed start | 13 | 6 | Due to a layoff no writer was immediately available, so approval was delayed | 3 | Africa | Prod. Dev. | 2007 | August | 888277
4597 | Resource | Outsourcing | Delayed start | 18 | 2 | New chips caused the mother board to perform poorly | 3 | Africa | Prod. Dev. | 2008 | November | 1304316
4598 | Resource | Outsourcing | Late or poor output | 25 | 6 | Product owner having unique knowledge left the company | 0 | Americas | IT/Solution | 2010 | February | 2316300
4599 | Resource | Outsourcing | Late or poor output | 25 | 1 | Poor communications resulted in never truly understanding customer needs | 0 | Americas | IT/Solution | 2010 | March | 2149800
4600 | Resource | Outsourcing | Late or poor output | 5 | 2 | High attrition in positions requiring unique technical training | 3 | Africa | Prod. Dev. | 2001 | June | 429540
4601 | Resource | Outsourcing | Late or poor output | 9 | 2 | Data for key tables not available when needed | 2 | Eur/ME | Prod. Dev. | 2009 | December | 540981
4602 | Resource | Outsourcing | Late or poor output | 17 | 2 | Manufacutring group did not have the capcity to produce a critical new enzyme | 0 | Americas | IT/Solution | 2010 | March | 1037901
4603 | Resource | Outsourcing | Late or poor output | 7 | 6 | Functionality for email added late to a document retrieval project | 2 | Eur/ME | IT/Solution | 2010 | March | 533659
4604 | Resource | Outsourcing | Late or poor output | 2 | 5 | Project delayed to work on higher profit margin work | 3 | Africa | Prod. Dev. | 2014 | January | 149744
4605 | Resource | Outsourcing | Late or poor output | 14 | 8 | The contractor half-way through the electrical job had a heart attack | 2 | Eur/ME | Prod. Dev. | 2010 | August | 1366134
4606 | Resource | Outsourcing | Late or poor output | 10 | 7 | Real-life data used did not test every scenario possible, so had to be replaced | 3 | Africa | Prod. Dev. | 2013 | April | 504040
4607 | Resource | Outsourcing | Late or poor output | 14 | 1 | Lack of communication between the customer and all vendors involved | 0 | Americas | Prod. Dev. | 2010 | May | 991046
4608 | Resource | Outsourcing | Late or poor output | 1 | 9 | Delays due to bidding issues and protests | 2 | Eur/ME | IT/Solution | 2001 | September | 85790
4609 | Resource | Outsourcing | Late or poor output | 11 | 8 | Issues discovered late in testing | 0 | Americas | IT/Solution | 2015 | November | 637373
4610 | Resource | Outsourcing | Late or poor output | 1 | 1 | Staff lost to customer Hot Site | 0 | Americas | IT/Solution | 2015 | January | 98520
4611 | Resource | Outsourcing | Late or poor output | 7 | 9 | International leased line order delayed (management approval) and then only ran at half the desired . | 3 | Africa | IT/Solution | 2008 | June | 362117
4612 | Resource | Outsourcing | Late or poor output | 13 | 4 | Other organizations are late with promised work, then deliverables do not work as expected. | 0 | Americas | IT/Solution | 2010 | February | 688688
4613 | Resource | Outsourcing | Late or poor output | 19 | 6 | Schedule set without first doing a project feasibility and capacity analysis | 0 | Americas | IT/Solution | 2015 | May | 1553896
4614 | Resource | Outsourcing | Late or poor output | 25 | 3 | A senior technical architecte quit | 0 | Americas | Prod. Dev. | 2010 | June | 1363775
4615 | Resource | People | Late start | 17 | 7 | During testing phase, resource availability was indaequate due to other priorities | 0 | Americas | Prod. Dev. | 2015 | May | 1225377
4616 | Resource | People | Late start | 23 | 1 | A key team member was replaced mid-project | 0 | Americas | IT/Solution | 2015 | November | 1590128
4617 | Resource | People | Late start | 25 | 3 | International shipment of tape was on time, but the tape was bad. | 3 | Africa | Prod. Dev. | 2018 | January | 1655850
4618 | Resource | People | Late start | 8 | 5 | Project benchmarks and requirements were never clearly defined | 2 | Eur/ME | IT/Solution | 2012 | November | 585184
4619 | Resource | People | Loss | 25 | 6 | Details of requirements were submitted incorrectly | 3 | Africa | Prod. Dev. | 2013 | February | 1555125
4620 | Resource | People | Loss | 17 | 1 | Underestimated weight of stumps to be removed | 3 | Africa | IT/Solution | 2015 | October | 889508
4621 | Resource | People | Loss | 23 | 2 | Additional enhancements requested at the last minute | 3 | Africa | IT/Solution | 2007 | September | 1882113
4622 | Resource | People | Loss | 7 | 7 | Design team failed to collect the details on what was to be displayed to users | 0 | Americas | IT/Solution | 2010 | July | 627536
4623 | Resource | People | Loss | 22 | 5 | Vibration in transit caused the loosing of the nuts and bolts of antennas, which eventually caused the collapse of the antennas | 0 | Americas | IT/Solution | 2015 | May | 1821820
4624 | Resource | People | Loss | 9 | 7 | Cable required had been left off the implementation parts list | 3 | Africa | IT/Solution | 2017 | March | 530613
4625 | Resource | People | Loss | 21 | 3 | Engineering overlooked the functional design and did not implement correctly | 2 | Eur/ME | IT/Solution | 2019 | March | 1892100
4626 | Resource | People | Loss | 21 | 4 | Key consultant was let go at a critical time for coat reasons | 0 | Americas | IT/Solution | 2015 | April | 1438332
4627 | Resource | People | Loss | 9 | 5 | Lack of funds for travel at launch | 2 | Eur/ME | Prod. Dev. | 2002 | June | 892584
4628 | Resource | People | Loss | 1 | 1 | Contract negotiations delayed by 20 days | 0 | Americas | IT/Solution | 2010 | June | 61292
4629 | Resource | People | Motivation | 18 | 5 | Vendor currently has limited capacity and could not hire quickly enough to support this product | 0 | Americas | IT/Solution | 2010 | October | 1583046
4630 | Resource | People | Motivation | 16 | 1 | For cost reasons, Asian supplier chosen. Qualification and paperwork caused delays. | 0 | Americas | IT/Solution | 2010 | May | 1314240
4631 | Resource | People | Queuing | 15 | 2 | Initial stages were outsourced to a professor who started late and lacked needed information | 0 | Americas | IT/Solution | 2015 | November | 1328055
4632 | Resource | People | Queuing | 11 | 5 | Incompetent subcontractor led to delay and unhappy clients | 2 | Eur/ME | Prod. Dev. | 2011 | March | 928664
4633 | Resource | People | Queuing | 4 | 6 | Subcontractor did not build stairs according to the drawings and had to redo them | 3 | Africa | Prod. Dev. | 2014 | September | 322368
4634 | Resource | People | Queuing | 5 | 2 | Lack of clear definition of the contractor and Lead Tech roles and responsibilities | 3 | Africa | Prod. Dev. | 2010 | March | 353030
4635 | Resource | People | Queuing | 2 | 1 | Vendor made a promise on something they could not deliver | 2 | Eur/ME | IT/Solution | 2003 | April | 199690
4636 | Resource | People | Queuing | 3 | 1 | Vendor missed validation due date delaying Clinical Trials | 0 | Americas | IT/Solution | 2010 | June | 201009
4637 | Resource | People | Queuing | 21 | 9 | Contract lab failed to inform us that they had trouble with a genotyping assay | 2 | Eur/ME | IT/Solution | 2015 | April | 1977528
4638 | Resource | People | Queuing | 15 | 7 | Contractor provided inadequate survey data | 2 | Eur/ME | IT/Solution | 2002 | February | 1334655
4639 | Resource | People | Queuing | 13 | 6 | Chinese IT company to guarantee the quality of their work | 2 | Eur/ME | Prod. Dev. | 2017 | June | 742534
4640 | Resource | People | Temp loss | 2 | 7 | Abnormally high turnover and shortage of capable developers in India | 3 | Africa | Prod. Dev. | 2008 | April | 176858
4641 | Resource | People | Temp loss | 24 | 5 | Delay in hiring more engineers due to cost cutting | 3 | Africa | IT/Solution | 2010 | June | 2286048
4642 | Resource | People | Temp loss | 3 | 8 | "Rolling Sledgehammer" Last project ties up (and exhausts) staff; next project starts late and slow. | 0 | Americas | IT/Solution | 2015 | May | 158871
4643 | Resource | People | Temp loss | 16 | 3 | Key person lost mid-project | 2 | Eur/ME | Prod. Dev. | 2006 | January | 928912
4644 | Resource | People | Temp loss | 11 | 3 | Turnover on staff 100% in year, leading to delays and training. | 2 | Eur/ME | IT/Solution | 2015 | May | 910613
4645 | Resource | People | Temp loss | 11 | 5 | The project manager was assigned to another big project part way through the project | 2 | Eur/ME | IT/Solution | 2001 | May | 1017467
4646 | Resource | People | Temp loss | 3 | 4 | Layoffs in the company | 0 | Americas | IT/Solution | 2015 | May | 163740
4647 | Resource | People | Temp loss | 24 | 2 | Loss of a key person | 0 | Americas | IT/Solution | 2010 | September | 1437960
4648 | Resource | People | Temp loss | 26 | 2 | Key resource pulled from a high priority project | 3 | Africa | Prod. Dev. | 2005 | June | 1332838
4649 | Resource | People | Temp loss | 4 | 6 | Key engineer on project leaves the company | 2 | Eur/ME | IT/Solution | 2018 | December | 221524
4650 | Resource | People | Temp loss | 21 | 9 | Project team members reassigned. Not replaced; led to overtime, quality problems, missed deadlines. | 0 | Americas | IT/Solution | 2010 | May | 1955856
4651 | Resource | People | Temp loss | 4 | 8 | Team members reassigned to other, higher priority projects. | 2 | Eur/ME | Prod. Dev. | 2006 | March | 333512
4652 | Schedule | Delay | Decision | 8 | 5 | Only one employee with other commitments had both the Cobol and relational database data conversion experience | 2 | Eur/ME | Prod. Dev. | 2014 | October | 614920
4653 | Schedule | Delay | Decision | 10 | 7 | Lack of key SME resource availability when needed | 3 | Africa | Prod. Dev. | 2005 | February | 642270
4654 | Schedule | Delay | Decision | 16 | 6 | Key contributor unavailable when needed. | 0 | Americas | Prod. Dev. | 2015 | July | 1389104
4655 | Schedule | Delay | Decision | 10 | 3 | The trained resource was tied up in other work | 3 | Africa | IT/Solution | 2008 | July | 791910
4656 | Schedule | Delay | Decision | 15 | 9 | Conflicting priorities. on-going maintenance, and loss of a person led to delay | 0 | Americas | IT/Solution | 2010 | March | 1057455
4657 | Schedule | Delay | Decision | 7 | 3 | Lone subject matter expert unavailable when needed during the initial stages | 0 | Americas | IT/Solution | 2010 | December | 638582
4658 | Schedule | Delay | Decision | 12 | 7 | Unexpected shutdown at year end delays work and rescheduling it is difficult. | 2 | Eur/ME | IT/Solution | 2001 | March | 1081236
4659 | Schedule | Delay | Decision | 20 | 2 | A valuable resource gets pulled off of project to work on a larger, higher profile project | 0 | Americas | IT/Solution | 2015 | September | 1713600
4660 | Schedule | Delay | Decision | 20 | 1 | Key resource tied to a previous project for two weeks | 0 | Americas | IT/Solution | 2015 | March | 1973680
4661 | Schedule | Delay | Decision | 23 | 6 | No vacation/time-off estimate planning was done | 2 | Eur/ME | IT/Solution | 2017 | January | 1156003
4662 | Schedule | Delay | Decision | 12 | 1 | Change Management Lead took unexpected medical leave | 0 | Americas | IT/Solution | 2010 | December | 1071996
4663 | Schedule | Delay | Hardware | 13 | 8 | Contributor has lengthy, unannounced vacation | 0 | Americas | IT/Solution | 2015 | April | 889525
4664 | Schedule | Delay | Hardware | 21 | 4 | Staff lost to customer Hot Site | 3 | Africa | IT/Solution | 2017 | March | 1585878
4665 | Schedule | Delay | Hardware | 17 | 1 | Multiple projects competing for a limited staff to do the work leads to interruptions and delays | 2 | Eur/ME | Prod. Dev. | 2006 | December | 1274065
4666 | Schedule | Delay | Hardware | 2 | 3 | Key code developer had a family emergency | 0 | Americas | Prod. Dev. | 2010 | July | 186982
4667 | Schedule | Delay | Hardware | 25 | 6 | Staff lost to customer Hot Site | 3 | Africa | IT/Solution | 2014 | March | 1255475
4668 | Schedule | Delay | Hardware | 21 | 7 | All stakeholders approve project individually, but at meeting together for final approval, disagreements changed and delayed the project. | 2 | Eur/ME | IT/Solution | 2016 | April | 1816311
4669 | Schedule | Delay | Hardware | 23 | 9 | Decisions are being delayed without apparent reason | 3 | Africa | Prod. Dev. | 2013 | June | 1964062
4670 | Schedule | Delay | Hardware | 21 | 9 | International leased line order delayed (management approval) and then only ran at half the desired . | 3 | Africa | Prod. Dev. | 2019 | September | 1698627
4671 | Schedule | Delay | Information | 10 | 2 | Systems required backordered (6 months). Forced to use competitor's system. | 0 | Americas | Prod. Dev. | 2015 | February | 995200
4672 | Schedule | Delay | Information | 2 | 2 | Multiple phase roll out paused near the end, systems temporarily out of stock. | 0 | Americas | Prod. Dev. | 2015 | March | 124242
4673 | Schedule | Delay | Information | 10 | 9 | New technology not available on time. | 3 | Africa | Prod. Dev. | 2008 | January | 716440
4674 | Schedule | Delay | Information | 3 | 4 | Equipment was unreliable and caused slips | 0 | Americas | Prod. Dev. | 2015 | December | 214179
4675 | Schedule | Delay | Information | 25 | 4 | Key parts would be delivered late | 2 | Eur/ME | IT/Solution | 2018 | September | 2206475
4676 | Schedule | Delay | Information | 6 | 2 | Key stakeholders were not identified during requirements gathering | 0 | Americas | IT/Solution | 2015 | August | 480036
4677 | Schedule | Delay | Information | 1 | 1 | The business counterparts were not in agreement with which option to choose and went back and forth on the decision | 2 | Eur/ME | IT/Solution | 2012 | January | 93493
4678 | Schedule | Delay | Information | 10 | 2 | Communications problems and misinterpretation of the requirements in India | 3 | Africa | IT/Solution | 2007 | January | 838630
4679 | Schedule | Delay | Information | 6 | 5 | Documents could not be translated promptly | 2 | Eur/ME | IT/Solution | 2001 | September | 431322
4680 | Schedule | Delay | Parts | 13 | 1 | A special peripheral used for the project deliverable was discontinued | 3 | Africa | IT/Solution | 2008 | May | 689234
4681 | Schedule | Delay | Parts | 17 | 4 | Solar panels arrived late and were not what was ordered | 3 | Africa | IT/Solution | 2017 | June | 1047591
4682 | Schedule | Delay | Parts | 26 | 3 | Supplier was unable to make a sample correctly | 2 | Eur/ME | IT/Solution | 2004 | January | 2081560
4683 | Schedule | Delay | Parts | 12 | 4 | There was a delay in the delivery of test samples | 2 | Eur/ME | IT/Solution | 2001 | March | 1008816
4684 | Schedule | Delay | Parts | 5 | 3 | Granite countertops had incorrect measurements | 3 | Africa | IT/Solution | 2012 | July | 345320
4685 | Schedule | Delay | Parts | 20 | 5 | Insufficient capacity in the cabling system for needed fiber connection | 0 | Americas | IT/Solution | 2010 | February | 1013980
4686 | Schedule | Delay | Parts | 10 | 7 | Scheduling based on small pilot installation, but full roll out backed up the help desk and project was delayed. | 2 | Eur/ME | IT/Solution | 2001 | July | 952610
4687 | Schedule | Delay | Parts | 17 | 9 | During required short visits, the network was sometimes down for an indefinite amount of time, requiring a second trip | 0 | Americas | IT/Solution | 2015 | August | 1385551
4688 | Schedule | Delay | Parts | 4 | 6 | Last minute infrastructure changes and conflict with another deployment | 3 | Africa | IT/Solution | 2004 | July | 240084
4689 | Schedule | Delay | Parts | 8 | 3 | Current processes did not scale as needed by project, requiring redesign | 2 | Eur/ME | Prod. Dev. | 2011 | February | 691792
4690 | Schedule | Delay | Parts | 10 | 1 | Infrasturcture changes made mid-project | 3 | Africa | Prod. Dev. | 2014 | August | 712100
4691 | Schedule | Delay | Parts | 6 | 4 | Compilers and open source libraries needed were not available | 0 | Americas | Prod. Dev. | 2010 | October | 568482
4692 | Schedule | Delay | Parts | 14 | 1 | Iidviduals who must to approve work are unavailable | 3 | Africa | Prod. Dev. | 2019 | February | 966910
4693 | Schedule | Delay | Parts | 23 | 2 | Other organizations are late with promised work, then deliverables do not work as expected. | 0 | Americas | Prod. Dev. | 2010 | October | 1734844
4694 | Schedule | Delay | Parts | 3 | 8 | Customer insists on deadline shorter than plan. Attempted, but not possible. | 0 | Americas | IT/Solution | 2015 | January | 169920
4695 | Schedule | Dependency | Infrastructure | 18 | 1 | Schedule set without first doing a project feasibility and capacity analysis | 2 | Eur/ME | IT/Solution | 2004 | July | 1502460
4696 | Schedule | Dependency | Infrastructure | 8 | 8 | Plans for project for new customer based on similar work for existing customer. Relationships, infrastructure, jargon and other differences took 50% more effort. | 0 | Americas | Prod. Dev. | 2010 | September | 577000
4697 | Schedule | Dependency | Infrastructure | 24 | 2 | Estimated level of effort for project was way too optimistic | 0 | Americas | Prod. Dev. | 2010 | May | 1373232
4698 | Schedule | Dependency | Infrastructure | 17 | 1 | Development scheduled in parallel leads to frequent rework. | 0 | Americas | Prod. Dev. | 2015 | June | 1143505
4699 | Schedule | Dependency | Infrastructure | 11 | 7 | Headcount required for document management was grossly underestimated | 0 | Americas | Prod. Dev. | 2010 | May | 1008326
4700 | Schedule | Dependency | Infrastructure | 14 | 3 | Unavailability of skilled resources | 0 | Americas | IT/Solution | 2015 | August | 722722
4701 | Schedule | Dependency | Legal | 16 | 7 | The team member lacked the right skills for a development job | 3 | Africa | IT/Solution | 2019 | January | 963072
4702 | Schedule | Dependency | Legal | 1 | 1 | 3 week test took 7 due to learning curve and ramp time. | 0 | Americas | IT/Solution | 2015 | September | 82992
4703 | Schedule | Dependency | Project | 15 | 1 | New hires used; time for training. | 0 | Americas | Prod. Dev. | 2010 | December | 1478895
4704 | Schedule | Dependency | Project | 6 | 6 | Field Engineers experience a long learning curve | 2 | Eur/ME | Prod. Dev. | 2007 | October | 465186
4705 | Schedule | Dependency | Project | 16 | 5 | People who would deliver training seeking perfection; required extra work and was late. | 2 | Eur/ME | Prod. Dev. | 2005 | November | 1579248
4706 | Schedule | Dependency | Project | 24 | 2 | One patch was almost completely tested when it was decided to fix another bug | 2 | Eur/ME | Prod. Dev. | 2010 | September | 1372776
4707 | Schedule | Dependency | Project | 20 | 3 | Half way through the project the client changed the scope by adding additional work | 0 | Americas | Prod. Dev. | 2010 | March | 1250500
4708 | Schedule | Dependency | Project | 24 | 8 | Several applications were changed due to change in project requirements | 3 | Africa | Prod. Dev. | 2008 | October | 1522056
4709 | Schedule | Estimates | Deadline | 12 | 1 | Mid project expansion to include account receivable process | 0 | Americas | Prod. Dev. | 2015 | September | 1111632
4710 | Schedule | Estimates | Judgment | 26 | 4 | Executives added a new requirement late | 2 | Eur/ME | Prod. Dev. | 2005 | October | 1471054
4711 | Schedule | Estimates | Judgment | 8 | 6 | Late change to motorized door led to redesign, parts delay, and conflict with other work | 2 | Eur/ME | Prod. Dev. | 2019 | May | 456296
4712 | Schedule | Estimates | Judgment | 24 | 6 | Requested scope expansion took a month to assess and was ultimately rejected | 3 | Africa | Prod. Dev. | 2017 | February | 1743432
4713 | Schedule | Estimates | Judgment | 7 | 2 | Twelve additional design and construction tasks were added late | 2 | Eur/ME | Prod. Dev. | 2006 | October | 515249
4714 | Schedule | Estimates | Judgment | 26 | 5 | Client's insisted on the use of "the latest technology | 0 | Americas | IT/Solution | 2010 | October | 1310816
4715 | Schedule | Estimates | Judgment | 6 | 4 | Project priorities and criteria are unclear through much of the project, causing lots of unneeded work. | 0 | Americas | IT/Solution | 2015 | May | 436650
4716 | Schedule | Estimates | Judgment | 21 | 4 | Changing product definition and poor estimation of effort | 0 | Americas | IT/Solution | 2015 | October | 1999221
4717 | Schedule | Estimates | Judgment | 16 | 7 | Project priorities and criteria are unclear through much of the project, causing lots of unneeded work. | 0 | Americas | IT/Solution | 2015 | October | 1500080
4718 | Schedule | Estimates | Learning | 1 | 9 | Database used for system changed in mid project; more resources used and delay. | 3 | Africa | Prod. Dev. | 2004 | April | 84722
4719 | Schedule | Estimates | Learning | 11 | 6 | Design stability poor, requiring rework and late changes for manufacturing. | 0 | Americas | Prod. Dev. | 2010 | April | 605649
4720 | Schedule | Estimates | Learning | 19 | 1 | Specifications poorly defined until late in the project. | 2 | Eur/ME | Prod. Dev. | 2001 | August | 1870056
4721 | Schedule | Estimates | Learning | 3 | 2 | Modifying requirements in the middle of a phase | 2 | Eur/ME | Prod. Dev. | 2007 | October | 257982
4722 | Scope | Change | Creep | 8 | 1 | Operating system release expected canceled; project forced to use prior version. | 0 | Americas | Prod. Dev. | 2015 | February | 629800
4723 | Scope | Change | Creep | 15 | 3 | New CPU chip to be used in product assumed same as old, but requires additional heat sink and mechanical design work. | 0 | Americas | IT/Solution | 2015 | January | 1401660
4724 | Scope | Change | Creep | 12 | 7 | As product increases, new packaging and unexpected shielding needed. | 2 | Eur/ME | Prod. Dev. | 2005 | February | 677100
4725 | Scope | Change | Creep | 23 | 9 | User specifications not defined until late in the project. | 0 | Americas | IT/Solution | 2010 | July | 2259957
4726 | Scope | Change | Creep | 16 | 7 | Work done by contractors with too little information; components require rework. | 0 | Americas | Prod. Dev. | 2010 | September | 1418032
4727 | Scope | Change | Creep | 15 | 7 | The programmer hadn’t understood how certain parts of the program date-logic worked and hadn’t asked for any assistance. | 0 | Americas | Prod. Dev. | 2010 | February | 1236225
4728 | Scope | Change | Creep | 22 | 5 | Original scope missed supply chain issues; could not be used without changes | 2 | Eur/ME | IT/Solution | 2013 | December | 1817266
4729 | Scope | Change | Creep | 11 | 7 | Scope change adding new categories and fees | 2 | Eur/ME | Prod. Dev. | 2005 | April | 717156
4730 | Scope | Change | Creep | 9 | 3 | Enterprise Portal improperly specified | 3 | Africa | Prod. Dev. | 2003 | August | 508887
4731 | Scope | Change | Creep | 5 | 1 | Major Scope change during the design phase due to the complex processes involved | 2 | Eur/ME | Prod. Dev. | 2017 | August | 480420
4732 | Scope | Change | Creep | 8 | 4 | Poor project planning and missed end-user requirements | 3 | Africa | Prod. Dev. | 2009 | July | 520280
4733 | Scope | Change | Creep | 22 | 1 | Project had aggressive timeline and due to rush details were poorly defined | 0 | Americas | Prod. Dev. | 2010 | October | 1901438
4734 | Scope | Change | Creep | 9 | 8 | Inexperience of the leader resulted in overcommitment and little planning | 3 | Africa | Prod. Dev. | 2014 | December | 630891
4735 | Scope | Change | Creep | 10 | 8 | Design documentation was signed off by users, but had fatal flaws | 0 | Americas | Prod. Dev. | 2010 | January | 591600
4736 | Scope | Change | Dependency | 18 | 5 | Substrate material was initially specified incorrectly and had to be reordered | 3 | Africa | Prod. Dev. | 2003 | February | 1302804
4737 | Scope | Change | Dependency | 12 | 6 | Customer did not describe in detail what exactly was needed | 0 | Americas | Prod. Dev. | 2010 | October | 1195440
4738 | Scope | Change | Dependency | 18 | 3 | Construction of subdivision was initiated using old maps | 0 | Americas | Prod. Dev. | 2010 | February | 1569618
4739 | Scope | Change | Dependency | 12 | 9 | Requested requirement proved impossible, but was not actually needed | 2 | Eur/ME | IT/Solution | 2007 | July | 1161024
4740 | Scope | Change | Dependency | 19 | 3 | Multiple team program with some work not clearly delegated. Assigned and added late. | 2 | Eur/ME | Prod. Dev. | 2002 | April | 1875585
4741 | Scope | Change | Dependency | 10 | 8 | Scoping set and estimated based on just one set of data from one customer | 0 | Americas | IT/Solution | 2015 | May | 845810
4742 | Scope | Change | Gap | 15 | 7 | The business analyst failed to fully understand the scientist’s requirements | 2 | Eur/ME | IT/Solution | 2001 | August | 1382685
4743 | Scope | Change | Gap | 11 | 6 | Flaw was found in the functional design | 0 | Americas | Prod. Dev. | 2010 | June | 831072
4744 | Scope | Change | Gap | 7 | 1 | System only partly specified until near the end of the project. | 3 | Africa | IT/Solution | 2005 | June | 424179
4745 | Scope | Change | Gap | 16 | 1 | Poor prework led to assumption that project would be simpler than it was | 0 | Americas | IT/Solution | 2015 | January | 975120
4746 | Scope | Change | Gap | 4 | 3 | Complexity not understood or documented. Required work added. | 0 | Americas | Prod. Dev. | 2010 | April | 390500
4747 | Scope | Change | Gap | 26 | 3 | Product developed for multiple platforms, but works only on 2. Delayed to fix some, but others dropped at project end. | 0 | Americas | Prod. Dev. | 2010 | July | 2127450
4748 | Scope | Change | Gap | 25 | 3 | Faulty market & competitive analysis information discovered late; led to changes | 3 | Africa | IT/Solution | 2017 | July | 1886200
4749 | Scope | Change | Gap | 12 | 8 | Lack of initial consensus on the scope | 0 | Americas | Prod. Dev. | 2015 | April | 770892
4750 | Scope | Change | Gap | 11 | 2 | New technology used, seeking faster results. It does not work and leads to redesign and rework. | 0 | Americas | Prod. Dev. | 2010 | July | 809600
4751 | Scope | Change | Gap | 3 | 8 | Instrument system for customer based on Intel PC. New system released; fails to work as older model did. Finally installed with salvaged older PC. | 3 | Africa | Prod. Dev. | 2018 | June | 183705
4752 | Scope | Change | Gap | 17 | 3 | Testing facilities were too low-tech to verify automated systems | 0 | Americas | IT/Solution | 2015 | December | 1555619
4753 | Scope | Change | Gap | 25 | 3 | Components do not work as documented. Replacements and software workarounds required. | 0 | Americas | IT/Solution | 2015 | September | 2285325
4754 | Scope | Change | Gap | 10 | 2 | System with new components fails in final tests. Getting older components difficult. | 2 | Eur/ME | Prod. Dev. | 2013 | May | 778720
4755 | Scope | Change | Gap | 3 | 2 | Late test results came back negative | 2 | Eur/ME | IT/Solution | 2008 | March | 207930
4756 | Scope | Change | Gap | 25 | 2 | Insufficient length of anchor bolts protruding from the concrete foundation to allow the base plate nuts to fully engage | 2 | Eur/ME | IT/Solution | 2018 | August | 2237275
4757 | Scope | Change | Gap | 6 | 1 | During the feedback/review phase it was noticed that the numbers were incorrect | 2 | Eur/ME | IT/Solution | 2009 | January | 308214
4758 | Scope | Change | Gap | 2 | 2 | After the first run was lost, a third run was added | 3 | Africa | Prod. Dev. | 2004 | August | 157506
4759 | Scope | Change | Gap | 5 | 4 | First production run problems necessitated adding a third run | 3 | Africa | Prod. Dev. | 2013 | January | 449640
4760 | Scope | Change | Gap | 1 | 3 | Deliverable fails final test; rework to fix. | 2 | Eur/ME | IT/Solution | 2007 | September | 55505
4761 | Scope | Change | Gap | 3 | 5 | All components pass tests, but assembled system fails. Rework causes delay. | 0 | Americas | Prod. Dev. | 2010 | October | 164490
4762 | Scope | Change | Gap | 15 | 3 | Failure to not carefully proofread the documents to be produced before printing | 0 | Americas | Prod. Dev. | 2015 | August | 1452570
4763 | Scope | Change | Gap | 16 | 8 | Process does not scale to production; changes required. | 0 | Americas | IT/Solution | 2010 | August | 1490640
4764 | Scope | Defect | Hardware | 15 | 7 | Problem detected in production due to transaction volume not detected in test | 3 | Africa | IT/Solution | 2016 | January | 1379715
4765 | Scope | Defect | Hardware | 26 | 1 | Bug surfaced one day after implementation | 2 | Eur/ME | IT/Solution | 2006 | October | 1653210
4766 | Scope | Defect | Hardware | 12 | 1 | Purchased software is limited and inflexible. Workarounds and additional software required. | 2 | Eur/ME | Prod. Dev. | 2014 | May | 705336
4767 | Scope | Defect | Hardware | 9 | 9 | Late testing failure | 0 | Americas | IT/Solution | 2010 | October | 630405
4768 | Scope | Defect | Hardware | 1 | 5 | Vendor was unable to control the environment: work had to be repeated | 0 | Americas | Prod. Dev. | 2010 | October | 89329
4769 | Scope | Defect | Integration | 4 | 9 | Complexity of the investigation was badly underestimated | 2 | Eur/ME | IT/Solution | 2003 | July | 264240
4770 | Scope | Defect | Integration | 25 | 7 | Inexperienced staff | 0 | Americas | IT/Solution | 2010 | January | 1877350
4771 | Scope | Defect | Integration | 7 | 2 | The team in Germany did not have the resources or expertise to do testing in key intermediate step | 3 | Africa | IT/Solution | 2015 | January | 592354
4772 | Scope | Defect | Software | 19 | 9 | Support offering requires more overhead to span several OS versions | 0 | Americas | IT/Solution | 2015 | March | 1613195
4773 | Scope | Defect | Software | 21 | 9 | Testing requierments poorly defined, so functionality deferred to phase 2 | 2 | Eur/ME | IT/Solution | 2019 | April | 1621641
4774 | Scope | Defect | Software | 6 | 3 | Contaminated specimen for cell culture had to be replaced by the contract organization | 2 | Eur/ME | IT/Solution | 2012 | July | 322554
4775 | Scope | Defect | Software | 20 | 7 | Subcontractor failed to understand technology and requirements | 0 | Americas | IT/Solution | 2015 | September | 1780340
4776 | Scope | Defect | Software | 17 | 7 | Late change required new hardware and 2 phase delivery | 0 | Americas | IT/Solution | 2015 | January | 1436483
4777 | Scope | Defect | Software | 15 | 8 | Defective component--Bugs had to be fixed | 0 | Americas | IT/Solution | 2015 | March | 1209585
4778 | Scope | Defect | Software | 2 | 3 | Project lost irreplaceable experts | 3 | Africa | IT/Solution | 2008 | November | 160694
4779 | Scope | Defect | Software | 23 | 3 | Too few disc drives, and insufficient "owned" space | 0 | Americas | Prod. Dev. | 2015 | August | 2095208
4780 | Scope | Defect | Software | 12 | 6 | There was a high fluctuation of pressure that nobody could explain | 0 | Americas | IT/Solution | 2010 | August | 1033116
4781 | Scope | Defect | Software | 5 | 3 | Contractors late and unreliable | 2 | Eur/ME | IT/Solution | 2008 | November | 445235
4782 | Schedule | Delay | Decision | 26 | 6 | Needed plants were set too far apart to fertilize initially | 0 | Americas | Prod. Dev. | 2010 | October | 1862588
4783 | Scope | Change | Creep | 2 | 6 | Workforce reduction left only 3 developers were remaining on the project | 2 | Eur/ME | Prod. Dev. | 2005 | January | 138196
4784 | Scope | Change | Dependency | 8 | 5 | Materials did not pass quality inspection | 0 | Americas | IT/Solution | 2010 | March | 526816
4785 | Scope | Change | Gap | 2 | 2 | Developer had limited experience | 3 | Africa | IT/Solution | 2016 | June | 197182
4786 | Scope | Defect | Hardware | 9 | 1 | Late requirement changes and shifting priorities | 3 | Africa | Prod. Dev. | 2001 | May | 723267
4787 | Scope | Change | Gap | 18 | 3 | New Requirement addition during the middle of the project | 2 | Eur/ME | Prod. Dev. | 2010 | February | 1790172
4788 | Resource | People | Loss | 25 | 2 | Contract lab failed to inform us that they had trouble with a genotyping assay | 3 | Africa | Prod. Dev. | 2002 | December | 2469325
4789 | Resource | Outsourcing | Late or poor output | 10 | 8 | Chinese IT company to guarantee the quality of their work | 2 | Eur/ME | Prod. Dev. | 2005 | December | 611750
4790 | Resource | People | Loss | 4 | 8 | "Rolling Sledgehammer" Last project ties up (and exhausts) staff; next project starts late and slow. | 3 | Africa | Prod. Dev. | 2014 | September | 268592
4791 | Schedule | Estimates | Learning | 3 | 1 | All stakeholders approve project individually, but at meeting together for final approval, disagreements changed and delayed the project. | 0 | Americas | IT/Solution | 2015 | August | 176751
4792 | Scope | Defect | Software | 3 | 9 | Communications problems and misinterpretation of the requirements in India | 0 | Americas | Prod. Dev. | 2010 | November | 169929
4793 | Resource | Outsourcing | Late or poor output | 26 | 1 | Supplier was unable to make a sample correctly | 0 | Americas | Prod. Dev. | 2010 | April | 1733784
4794 | Resource | Outsourcing | Late or poor output | 5 | 1 | Estimated level of effort for project was way too optimistic | 3 | Africa | Prod. Dev. | 2018 | November | 479090
4795 | Resource | People | Temp loss | 14 | 4 | Late change to motorized door led to redesign, parts delay, and conflict with other work | 3 | Africa | Prod. Dev. | 2007 | April | 1215942
4796 | Scope | Change | Creep | 2 | 3 | New CPU chip to be used in product assumed same as old, but requires additional heat sink and mechanical design work. | 3 | Africa | IT/Solution | 2015 | June | 160548
4797 | Scope | Change | Creep | 24 | 7 | Late test results came back negative | 3 | Africa | IT/Solution | 2011 | January | 2309472
4798 | Scope | Defect | Hardware | 10 | 7 | Problem detected in production due to transaction volume not detected in test | 0 | Americas | Prod. Dev. | 2015 | May | 984140
4799 | Scope | Defect | Integration | 10 | 4 | Resources committed to projects reassigned to new projects and not replaced. | 3 | Africa | IT/Solution | 2001 | August | 876760
4800 | Schedule | Dependency | Project | 13 | 9 | Manufacturing problem with key component | 0 | Americas | IT/Solution | 2015 | August | 812890
4801 | Resource | People | Loss | 20 | 4 | Lack of research and analysis on a key compoent of the deliverable | 3 | Africa | Prod. Dev. | 2019 | July | 1479720
4802 | Schedule | Delay | Parts | 9 | 6 | Components were incorrectly measured | 0 | Americas | IT/Solution | 2015 | April | 527625
4803 | Schedule | Estimates | Deadline | 8 | 5 | A single person was responsible for key reports many wait in queue | 0 | Americas | Prod. Dev. | 2015 | January | 771568
4804 | Scope | Change | Gap | 9 | 4 | Key resource was pulled off the project twice to fix bugs in a previous product | 3 | Africa | Prod. Dev. | 2006 | August | 602802
4805 | Schedule | Dependency | Project | 15 | 5 | Estimates in proposal too short. Testing takes more time and is highly variable. | 3 | Africa | Prod. Dev. | 2005 | July | 907620
4806 | Schedule | Estimates | Learning | 24 | 8 | Project end date moved; unrealistic | 0 | Americas | Prod. Dev. | 2010 | February | 1783536
4807 | Scope | Change | Creep | 1 | 4 | People were allocated to too many projects and bottlenecks developed | 3 | Africa | Prod. Dev. | 2016 | May | 57783
4808 | Scope | Change | Gap | 7 | 1 | Key person not available when needed. | 2 | Eur/ME | Prod. Dev. | 2007 | March | 528136
4809 | Scope | Defect | Hardware | 9 | 3 | Unannounced audit in mid-project caused delay to prepare and participate. | 3 | Africa | Prod. Dev. | 2016 | December | 807372
4810 | Resource | People | Queuing | 25 | 3 | Flood shuts down data center. Delay to restore power and clean up. | 0 | Americas | IT/Solution | 2010 | July | 1669725
4811 | Resource | People | Temp loss | 3 | 6 | Parts delivery delay | 0 | Americas | IT/Solution | 2010 | March | 250833
4812 | Resource | People | Temp loss | 18 | 2 | Lack of a solid plan, or any formal scoping | 2 | Eur/ME | IT/Solution | 2003 | April | 1606590
4813 | Schedule | Delay | Hardware | 21 | 3 | No problems in test, but production problems required overtime to fix | 0 | Americas | Prod. Dev. | 2010 | July | 1627248
4814 | Schedule | Estimates | Learning | 11 | 4 | Layoffs in mid-project | 0 | Americas | Prod. Dev. | 2010 | November | 568832
4815 | Scope | Change | Creep | 20 | 5 | Client slashed the original budget | 3 | Africa | Prod. Dev. | 2018 | February | 1974940
4816 | Scope | Change | Creep | 20 | 3 | Inadequate staffing | 2 | Eur/ME | Prod. Dev. | 2018 | March | 1997540
4817 | Resource | People | Loss | 5 | 8 | Delays due to bidding issues and protests | 3 | Africa | Prod. Dev. | 2006 | April | 278855
4818 | Resource | People | Queuing | 23 | 6 | Vendor failed to confirm start date, resulting in delay | 0 | Americas | Prod. Dev. | 2015 | June | 1587897
4819 | Schedule | Delay | Decision | 4 | 9 | Failed to get client sign-off for work done in India | 3 | Africa | Prod. Dev. | 2006 | November | 323052
4820 | Schedule | Delay | Parts | 8 | 1 | Consultant who worked on benefits was taken off the project | 0 | Americas | Prod. Dev. | 2010 | February | 645968
4821 | Schedule | Dependency | Project | 4 | 4 | Freelancer hired was a nutjob, and lacked the correct skills | 0 | Americas | IT/Solution | 2015 | December | 216476
4822 | Scope | Change | Dependency | 23 | 7 | Management pushed plans to outsource printing operations, causing problems | 3 | Africa | IT/Solution | 2007 | March | 1598132
4823 | Scope | Change | Gap | 7 | 9 | Contractor was uncooperative and late | 3 | Africa | IT/Solution | 2007 | November | 563290
4824 | Scope | Change | Gap | 13 | 2 | Consulting agency had not fulfilled its obligations under the terms of the contract | 0 | Americas | IT/Solution | 2015 | March | 986193
4825 | Resource | Outsourcing | Late or poor output | 23 | 9 | Outsourcing delayed the order entry process for all U.S. Based customers | 3 | Africa | IT/Solution | 2003 | July | 1566530
4826 | Resource | People | Motivation | 17 | 5 | Legacy systems not retired as planned; project team tied up in unplanned support. | 3 | Africa | IT/Solution | 2001 | December | 1444490
4827 | Scope | Defect | Software | 2 | 5 | Delay in getting a firewall PM and a firewall engineer assigned | 2 | Eur/ME | IT/Solution | 2018 | October | 163964
4828 | Resource | Money | Limitation | 19 | 4 | Resources were not available at the time the project started | 2 | Eur/ME | IT/Solution | 2003 | August | 1517093
4829 | Resource | Money | Limitation | 2 | 4 | Project has funding, but limited staff delays start. | 0 | Americas | Prod. Dev. | 2010 | December | 126734
4830 | Resource | Outsourcing | Delayed start | 14 | 2 | Critical skills unique in the head of a 62-yearl old programmer who had a heart attack | 0 | Americas | Prod. Dev. | 2010 | September | 1355816
4831 | Resource | Outsourcing | Delayed start | 15 | 6 | Lost a key programmer | 0 | Americas | IT/Solution | 2015 | March | 1191105
4832 | Resource | Outsourcing | Late or poor output | 15 | 8 | Workforce reduction left only 3 developers were remaining on the project | 0 | Americas | IT/Solution | 2015 | May | 1056900
4833 | Resource | Outsourcing | Late or poor output | 6 | 5 | Key contributor left the company | 0 | Americas | IT/Solution | 2015 | December | 336330
4834 | Resource | Outsourcing | Late or poor output | 2 | 6 | Technical lead had a “command and control" style that caused animosity | 2 | Eur/ME | Prod. Dev. | 2011 | July | 105238
4835 | Resource | Outsourcing | Late or poor output | 24 | 7 | Parallel tasks require resources beyond what is available | 2 | Eur/ME | IT/Solution | 2001 | July | 2082432
4836 | Resource | Outsourcing | Late or poor output | 12 | 1 | There were not enough study directors to conduct all the studies needed | 2 | Eur/ME | IT/Solution | 2009 | March | 999324
4837 | Resource | Outsourcing | Late or poor output | 1 | 9 | Six other projects required time and effort from our assigned engineer | 0 | Americas | IT/Solution | 2015 | July | 95792
4838 | Resource | Outsourcing | Late or poor output | 6 | 7 | Project was dependent on onekey resource and had to wait | 0 | Americas | Prod. Dev. | 2015 | February | 432270
4839 | Resource | Outsourcing | Late or poor output | 12 | 7 | Critical training had to be postponed because of a last minute emergency leave by the lead designer | 2 | Eur/ME | Prod. Dev. | 2016 | May | 1196328
4840 | Resource | Outsourcing | Late or poor output | 3 | 3 | Feedback from South Korea delayed due to a few months of sick leave by product manager | 0 | Americas | IT/Solution | 2010 | May | 247965
4841 | Resource | Outsourcing | Late or poor output | 9 | 5 | There were not enough vendors who had the capacity to manufacture specialized tools | 0 | Americas | IT/Solution | 2015 | September | 803637
4842 | Resource | Outsourcing | Late or poor output | 26 | 8 | The Project Lead did not hold the customer/business line accountable for their delay | 0 | Americas | IT/Solution | 2015 | June | 2164214
4843 | Resource | Outsourcing | Late start | 25 | 4 | Internal supplier problem; needed components delayed. | 3 | Africa | Prod. Dev. | 2013 | June | 2326750
4844 | Resource | People | Late start | 1 | 1 | Materials did not pass quality inspection | 3 | Africa | IT/Solution | 2003 | January | 79269
4845 | Resource | People | Loss | 6 | 9 | New technology was analyzed and didn’t meet the needs | 3 | Africa | Prod. Dev. | 2013 | August | 554592
4846 | Resource | People | Loss | 18 | 2 | Foundation was inadaquate and needed upgrading | 0 | Americas | Prod. Dev. | 2010 | February | 940608
4847 | Resource | People | Loss | 2 | 8 | Issues found with the SOX documents provided by the legal team | 3 | Africa | IT/Solution | 2003 | November | 193116
4848 | Resource | People | Loss | 7 | 9 | Reviews delayed on complex program, waiting for last team to finish phase work. | 2 | Eur/ME | IT/Solution | 2013 | May | 584087
4849 | Resource | People | Loss | 11 | 2 | Server expansion project dependent on delayed tape library decommissioning | 3 | Africa | Prod. Dev. | 2008 | July | 795652
4850 | Resource | People | Loss | 22 | 8 | Work was intentionally underestimatged to win the contract | 0 | Americas | IT/Solution | 2015 | May | 1689512
4851 | Resource | People | Loss | 21 | 5 | Chronic optimism on completion dates for work | 3 | Africa | IT/Solution | 2006 | May | 1205862
4852 | Resource | People | Motivation | 24 | 1 | Key staff member lacked knowledge, experience and ability | 2 | Eur/ME | IT/Solution | 2018 | June | 1781736
4853 | Resource | People | Queuing | 19 | 2 | Software engineers, not technicians skilled in the work, were used to complete product testing | 0 | Americas | IT/Solution | 2015 | May | 1224208
4854 | Resource | People | Queuing | 20 | 7 | Developer had limited experience | 0 | Americas | Prod. Dev. | 2010 | March | 1736180
4855 | Resource | People | Queuing | 17 | 4 | Big scope change in the middle of the project | 3 | Africa | IT/Solution | 2004 | October | 908888
4856 | Resource | People | Queuing | 22 | 1 | Late requirement changes and shifting priorities | 2 | Eur/ME | IT/Solution | 2019 | August | 1294942
4857 | Resource | People | Queuing | 11 | 8 | New Requirement addition during the middle of the project | 0 | Americas | IT/Solution | 2015 | March | 553047
4858 | Resource | People | Queuing | 11 | 7 | Extra release added just a month before a major upgrade go live date | 2 | Eur/ME | Prod. Dev. | 2008 | December | 977207
4859 | Resource | People | Queuing | 26 | 1 | Two new Features were introduced midway during development | 0 | Americas | IT/Solution | 2010 | June | 1335360
4860 | Resource | People | Queuing | 5 | 4 | Problems associated with confidential patient information in transit without a tracking mechanism surfaced during the project | 0 | Americas | IT/Solution | 2015 | August | 268870
4861 | Resource | People | Queuing | 17 | 5 | Late change required to meet code | 3 | Africa | IT/Solution | 2019 | April | 1085297
4862 | Resource | People | Queuing | 12 | 2 | Project required a change to the current website technology | 0 | Americas | IT/Solution | 2015 | May | 1172544
4863 | Resource | People | Queuing | 26 | 4 | Responsibilities not defined well for project | 0 | Americas | Prod. Dev. | 2010 | October | 1787630
4864 | Resource | People | Queuing | 23 | 1 | Lack of understanding by the manager of the system forced the project to replan | 2 | Eur/ME | Prod. Dev. | 2007 | April | 2157676
4865 | Resource | People | Temp loss | 14 | 8 | A critical issue was neglected resulting in a significant scope gap | 3 | Africa | IT/Solution | 2003 | June | 1353450
4866 | Resource | People | Temp loss | 4 | 9 | Scope gaps became apparent when legal department was consulted too late | 3 | Africa | Prod. Dev. | 2011 | June | 373900
4867 | Resource | People | Temp loss | 19 | 3 | Instructions to contract testing facility were too vague and tests had to be repeated | 0 | Americas | Prod. Dev. | 2015 | March | 1599420
4868 | Resource | People | Temp loss | 8 | 6 | Flaw found in functional design specifications | 0 | Americas | Prod. Dev. | 2010 | February | 589552
4869 | Resource | People | Temp loss | 25 | 5 | Some of the cross functional teams were not involved early enough | 3 | Africa | IT/Solution | 2010 | October | 2242050
4870 | Resource | People | Temp loss | 17 | 3 | Functional design was not properly done, due to limited access to users; led to changes | 0 | Americas | Prod. Dev. | 2015 | May | 1544042
4871 | Resource | People | Temp loss | 9 | 8 | Development team in France was unable to convey their requests, issues and concerns | 0 | Americas | Prod. Dev. | 2010 | March | 852849
4872 | Resource | People | Temp loss | 4 | 7 | Half way through the upgrade; the new processor failed | 0 | Americas | IT/Solution | 2015 | November | 347656
4873 | Resource | People | Temp loss | 19 | 2 | In large system conversion, new applications cannot find and work with existing data as expected. Lots of redirecting and conversion is required. | 3 | Africa | IT/Solution | 2005 | March | 1083817
4874 | Schedule | Delay | Decision | 7 | 4 | Memory problems not detected in test caused server crashes; backed out for more than a month | 0 | Americas | IT/Solution | 2010 | November | 524916
4875 | Schedule | Delay | Hardware | 25 | 9 | Issues discovered late in testing | 0 | Americas | Prod. Dev. | 2015 | May | 2257500
4876 | Schedule | Delay | Hardware | 21 | 1 | Errors were discovered in reports that had to be fixed following release | 3 | Africa | Prod. Dev. | 2016 | October | 1605492
4877 | Schedule | Delay | Hardware | 17 | 6 | Software is developed in Israel. In a week, there was less than one working day for teleconference and war made it impractical to travel. Needed info was always late. | 0 | Americas | IT/Solution | 2015 | December | 1370863
4878 | Schedule | Delay | Information | 10 | 1 | Scope definition was poor and change was rampant | 2 | Eur/ME | Prod. Dev. | 2001 | September | 753010
4879 | Schedule | Delay | Information | 20 | 4 | Research and development were outsourced, but the relationship was not managed well, and all work was ultimately redone | 2 | Eur/ME | Prod. Dev. | 2012 | March | 1733600
4880 | Schedule | Delay | Information | 10 | 7 | System for expense analysis expanded into redesign of most major internal systems | 2 | Eur/ME | IT/Solution | 2007 | September | 959500
4881 | Schedule | Delay | Parts | 25 | 2 | Deliverable received was inadequate | 2 | Eur/ME | IT/Solution | 2005 | December | 1849750
4882 | Schedule | Delay | Parts | 15 | 3 | There was a design flaw in the roof detail | 3 | Africa | Prod. Dev. | 2001 | April | 935160
4883 | Schedule | Delay | Parts | 24 | 4 | Apartments were sold before construction begins with commitments based on requests, not planning | 2 | Eur/ME | IT/Solution | 2007 | December | 2124000
4884 | Schedule | Delay | Parts | 18 | 3 | Project specifications had changed and the material needed during the design phase had to be imported from overseas | 0 | Americas | IT/Solution | 2015 | January | 1128348
4885 | Schedule | Delay | Parts | 9 | 9 | Scope initially consisted only of general objectives | 0 | Americas | Prod. Dev. | 2010 | November | 684630
4886 | Schedule | Delay | Parts | 25 | 1 | Manager quit his job because of his mother's illness | 3 | Africa | IT/Solution | 2012 | November | 1828525
4887 | Schedule | Delay | Parts | 6 | 1 | Delay due to testing requirements uncovered late and shifting priorities | 0 | Americas | IT/Solution | 2015 | December | 595134
4888 | Schedule | Delay | Parts | 5 | 6 | Project was new to the company and needed to hire people and develop a team | 3 | Africa | Prod. Dev. | 2003 | April | 372970
4889 | Schedule | Delay | Parts | 1 | 6 | Initial scoping for a minor upgrade was not sufficient | 0 | Americas | Prod. Dev. | 2010 | March | 59686
4890 | Schedule | Delay | Parts | 22 | 9 | Migration project (to NT from UNIX) saddled with increasing list of changes. | 2 | Eur/ME | Prod. Dev. | 2015 | April | 1390686
4891 | Schedule | Delay | Parts | 4 | 1 | After the upgrade was released, issues with the software were discovered | 0 | Americas | Prod. Dev. | 2015 | December | 205464
4892 | Schedule | Delay | Parts | 2 | 1 | Additional scope added; slipped project | 3 | Africa | Prod. Dev. | 2008 | August | 188244
4893 | Schedule | Delay | Parts | 19 | 2 | Product manager was out due to sick leave (a few months long) | 0 | Americas | IT/Solution | 2015 | February | 1080758
4894 | Schedule | Dependency | Infrastructure | 17 | 3 | Technical lead had a “command and control" style that caused animosity | 2 | Eur/ME | IT/Solution | 2012 | January | 1449777
4895 | Schedule | Dependency | Infrastructure | 12 | 7 | Critical training had to be postponed because of a last minute emergency leave by the lead designer | 2 | Eur/ME | Prod. Dev. | 2007 | December | 1120152
4896 | Schedule | Dependency | Infrastructure | 10 | 9 | Extra release added just a month before a major upgrade go live date | 0 | Americas | Prod. Dev. | 2015 | February | 626700
4897 | Schedule | Dependency | Infrastructure | 2 | 7 | Development team in France was unable to convey their requests, issues and concerns | 0 | Americas | IT/Solution | 2010 | February | 132774
4898 | Schedule | Dependency | Legal | 22 | 6 | Errors were discovered in reports that had to be fixed following release | 0 | Americas | Prod. Dev. | 2015 | March | 1861640
4899 | Schedule | Dependency | Project | 14 | 8 | Field Engineers experience a long learning curve | 0 | Americas | Prod. Dev. | 2015 | October | 902272
4900 | Schedule | Dependency | Project | 13 | 9 | People who would deliver training seeking perfection; required extra work and was late. | 0 | Americas | IT/Solution | 2015 | November | 995956
4901 | Schedule | Dependency | Project | 24 | 1 | Executives added a new requirement late | 2 | Eur/ME | IT/Solution | 2001 | February | 1752624
4902 | Schedule | Estimates | Deadline | 2 | 3 | Unexpectedly high demand requires outlisde help | 0 | Americas | Prod. Dev. | 2015 | March | 135968
4903 | Schedule | Estimates | Deadline | 19 | 6 | Recertification of updated applications took longer than hoped | 0 | Americas | Prod. Dev. | 2015 | March | 1490512
4904 | Schedule | Estimates | Judgment | 12 | 4 | Project schedule was revised user interface requirements which increased project scope | 2 | Eur/ME | Prod. Dev. | 2018 | July | 965640
4905 | Schedule | Estimates | Judgment | 25 | 6 | Lack of testing of older WWW browser versions led to custom coding being written before application could be used. | 0 | Americas | Prod. Dev. | 2015 | November | 2161575
4906 | Schedule | Estimates | Judgment | 19 | 8 | Incorrect input data provided | 3 | Africa | Prod. Dev. | 2004 | December | 1287478
4907 | Schedule | Estimates | Learning | 6 | 9 | The database assigned for the client did not have sufficient free space for their growing accounts | 0 | Americas | IT/Solution | 2010 | May | 571680
4908 | Schedule | Estimates | Learning | 20 | 6 | In testing, it is discovered that 50K words were left untranslated due to updates and changes | 0 | Americas | IT/Solution | 2010 | October | 1234000
4909 | Schedule | Estimates | Learning | 20 | 4 | lack of staff availability due to company down-sizing | 2 | Eur/ME | IT/Solution | 2012 | March | 1802680
4910 | Schedule | Estimates | Learning | 8 | 9 | Pricing negotiation stalls project work until resolved. | 3 | Africa | IT/Solution | 2003 | May | 452576
4911 | Schedule | Estimates | Learning | 15 | 1 | Outsourced tasks slipped, but not known until too late. | 0 | Americas | IT/Solution | 2010 | April | 1076565
4912 | Scope | Change | Creep | 22 | 4 | Equipment needed for project came from a pool of hardware partly in another country. Critical hardware delayed by customs. | 2 | Eur/ME | Prod. Dev. | 2016 | December | 1140062
4913 | Scope | Change | Creep | 17 | 9 | Parts availability and pricing volatile | 2 | Eur/ME | Prod. Dev. | 2012 | February | 985881
4914 | Scope | Change | Creep | 20 | 9 | Production problem with key component | 3 | Africa | Prod. Dev. | 2008 | August | 1371000
4915 | Scope | Change | Creep | 14 | 7 | Scope requirement discovered late in a construction project | 0 | Americas | IT/Solution | 2015 | June | 706650
4916 | Scope | Change | Creep | 16 | 8 | After test, additional requirements surface | 3 | Africa | IT/Solution | 2009 | March | 1583120
4917 | Scope | Change | Creep | 17 | 4 | Approvers reject required document | 0 | Americas | Prod. Dev. | 2015 | May | 913835
4918 | Scope | Change | Creep | 8 | 3 | A needed component was not very stable and only available from only one supplier. | 0 | Americas | Prod. Dev. | 2015 | June | 589536
4919 | Scope | Change | Creep | 17 | 4 | A batch of servers came in with the wrong configurations; had to be fixed | 0 | Americas | IT/Solution | 2015 | February | 865402
4920 | Scope | Change | Creep | 2 | 3 | Delayed start of work due to negotiation of contract. | 2 | Eur/ME | IT/Solution | 2009 | June | 163882
4921 | Scope | Change | Creep | 7 | 1 | Contractors late and unreliable | 2 | Eur/ME | IT/Solution | 2010 | January | 377909
4922 | Scope | Change | Creep | 7 | 9 | Unrelaible and incopentent contractors | 2 | Eur/ME | IT/Solution | 2007 | August | 581602
4923 | Scope | Change | Creep | 10 | 3 | Contractor installed smaller wire sizes than specified causing rework (after a fire) | 0 | Americas | IT/Solution | 2015 | January | 738730
4924 | Scope | Change | Creep | 15 | 3 | At start of project, insufficient research on the level of local expertise | 2 | Eur/ME | Prod. Dev. | 2002 | June | 1284090
4925 | Scope | Change | Creep | 25 | 2 | Outsourcing partner in Switzerland did unneeded work, delaying their inputs | 0 | Americas | Prod. Dev. | 2010 | November | 2360300
4926 | Scope | Change | Creep | 8 | 8 | Supply chain expert needed was hard to find and engage. | 0 | Americas | IT/Solution | 2010 | November | 549944
4927 | Scope | Change | Creep | 10 | 8 | Key person gave notice more than a month before leaving, but nothing was done | 3 | Africa | Prod. Dev. | 2003 | February | 747760
4928 | Scope | Change | Creep | 21 | 7 | The contractor half-way through the electrical job had a heart attack | 3 | Africa | IT/Solution | 2010 | January | 1599129
4929 | Scope | Change | Dependency | 22 | 2 | Lead Engineer’s resignation | 2 | Eur/ME | Prod. Dev. | 2014 | May | 1767964
4930 | Scope | Change | Dependency | 10 | 6 | Project leader resigns and is not replaced promptly | 0 | Americas | IT/Solution | 2015 | September | 604880
4931 | Scope | Change | Gap | 1 | 2 | The business analyst was unavailable for project work due to her backup role for a higher priority project | 0 | Americas | IT/Solution | 2015 | April | 52371
4932 | Scope | Change | Gap | 22 | 1 | Product manager was out due to sick leave (a few months long) | 3 | Africa | Prod. Dev. | 2002 | October | 1791438
4933 | Scope | Change | Gap | 25 | 1 | Negotiation and training on a new tool took more time than planned | 0 | Americas | Prod. Dev. | 2015 | September | 2292350
4934 | Scope | Change | Gap | 4 | 7 | It took a over month to get the custom designed equipment | 0 | Americas | IT/Solution | 2015 | October | 343520
4935 | Scope | Change | Gap | 17 | 6 | The vendor sent equipment to a wrong location in Michigan instead of the Bay Area | 0 | Americas | Prod. Dev. | 2015 | April | 892364
4936 | Scope | Change | Gap | 24 | 7 | Need to get input from one of the external group for specific info; late | 0 | Americas | IT/Solution | 2010 | February | 1594800
4937 | Scope | Change | Gap | 11 | 1 | Lack of communication and trust between locations | 3 | Africa | IT/Solution | 2017 | August | 623370
4938 | Scope | Change | Gap | 26 | 3 | Ship sinks with critical part; forced to replace with remanufactured old component | 0 | Americas | Prod. Dev. | 2010 | February | 2533232
4939 | Scope | Change | Gap | 19 | 3 | Delay in getting material when a fermentation run crashes | 2 | Eur/ME | Prod. Dev. | 2015 | August | 1475692
4940 | Scope | Change | Gap | 26 | 8 | Chip failed and had to be refabricated with changes | 2 | Eur/ME | IT/Solution | 2018 | January | 2548442
4941 | Scope | Change | Gap | 3 | 9 | Inadequate water supply available to complete project, needed to be trucked in | 3 | Africa | IT/Solution | 2014 | November | 195690
4942 | Scope | Change | Gap | 9 | 3 | Lack of communication with the project team in Germany | 3 | Africa | IT/Solution | 2012 | July | 542718
4943 | Scope | Change | Gap | 16 | 7 | Unrealistic deadline set; slips unavoidable. | 0 | Americas | IT/Solution | 2015 | September | 1068240
4944 | Scope | Change | Gap | 18 | 6 | Company underestimated the scope of the project | 2 | Eur/ME | IT/Solution | 2012 | May | 959616
4945 | Scope | Change | Gap | 12 | 6 | Expert opinion was 2 weeks; work took 8. | 0 | Americas | IT/Solution | 2015 | March | 977196
4946 | Scope | Change | Gap | 5 | 4 | Problems using trainers and training materials from Germany | 3 | Africa | IT/Solution | 2018 | September | 361790
4947 | Scope | Change | Gap | 23 | 4 | Inexperienced staff | 0 | Americas | Prod. Dev. | 2015 | April | 2088676
4948 | Scope | Change | Gap | 12 | 8 | Entry level employees lacked needed skill and experience | 0 | Americas | IT/Solution | 2015 | October | 967776
4949 | Scope | Change | Gap | 26 | 5 | No cross training within the team to make more knowledgeable resources available | 2 | Eur/ME | IT/Solution | 2013 | July | 1374854
4950 | Scope | Change | Gap | 17 | 5 | Late features were added | 0 | Americas | Prod. Dev. | 2015 | September | 903924
4951 | Scope | Change | Gap | 16 | 6 | Late stakeholders redefine requiremnts | 2 | Eur/ME | IT/Solution | 2007 | August | 984624
4952 | Scope | Change | Gap | 18 | 8 | Conflicting design attributes and an unfocused process resulted in confusion and changes | 0 | Americas | Prod. Dev. | 2010 | October | 1471374
4953 | Scope | Change | Gap | 6 | 9 | Late addition of a USB port to a recharging adapter | 2 | Eur/ME | IT/Solution | 2004 | June | 525084
4954 | Scope | Change | Gap | 24 | 8 | Sponsor agreed to specifications on door, loading docks, structural supports etc that impeded efficient work flows | 0 | Americas | Prod. Dev. | 2015 | February | 1513656
4955 | Scope | Change | Gap | 1 | 7 | Constant design changes occurred and parts had to be scrapped and replaced | 2 | Eur/ME | IT/Solution | 2001 | February | 65817
4956 | Scope | Change | Gap | 26 | 6 | The scope of the project was poorly defined | 0 | Americas | IT/Solution | 2010 | September | 2535416
4957 | Scope | Defect | Hardware | 10 | 7 | Client added new web pages to showcase the European site | 0 | Americas | IT/Solution | 2015 | December | 782570
4958 | Scope | Defect | Hardware | 25 | 4 | Old hardware became unavailable and product had to be tested on the new series | 3 | Africa | IT/Solution | 2009 | February | 1643125
4959 | Scope | Defect | Hardware | 3 | 2 | The statement of work did not indicate clearly the responsibilities of the outsourced programmers | 2 | Eur/ME | Prod. Dev. | 2003 | January | 209961
4960 | Scope | Defect | Hardware | 17 | 4 | The statement of work was not as specific as the authors thought and the deliverable from the vendor did not function as expected | 2 | Eur/ME | Prod. Dev. | 2019 | March | 1368364
4961 | Scope | Defect | Hardware | 4 | 7 | Contractual obligations set without adequate knowledge of potential hidden issues | 2 | Eur/ME | IT/Solution | 2007 | September | 277408
4962 | Scope | Defect | Software | 16 | 9 | The delivery of the content started without the content being finalized | 0 | Americas | IT/Solution | 2010 | September | 1524864
4963 | Scope | Defect | Software | 11 | 5 | Manufacturing process was not scalable and had to be redesigned | 0 | Americas | IT/Solution | 2010 | April | 658141
4964 | Scope | Defect | Software | 11 | 8 | Real-life data used did not test every scenario possible, so had to be replaced | 3 | Africa | IT/Solution | 2006 | May | 603636
4965 | Scope | Defect | Software | 14 | 3 | Lack of communication between the customer and all vendors involved | 2 | Eur/ME | IT/Solution | 2001 | May | 1261022
4966 | Resource | Outsourcing | Late or poor output | 10 | 2 | Management never talked to the test department when creating proposals | 0 | Americas | IT/Solution | 2010 | April | 531140
4967 | Scope | Change | Creep | 26 | 1 | Needed plants were set too far apart to fertilize initially | 0 | Americas | IT/Solution | 2010 | April | 1684228
4968 | Scope | Defect | Software | 7 | 9 | Chp failed due to a hardware design issue and had to be redesigned and refabricated | 0 | Americas | IT/Solution | 2015 | October | 679763
4969 | Scope | Defect | Software | 17 | 5 | New application works, but data collected is not accessible. | 3 | Africa | IT/Solution | 2006 | November | 1520718
4970 | Scope | Change | Gap | 23 | 2 | Defects discovered in late testing | 0 | Americas | IT/Solution | 2010 | February | 2227527
4971 | Resource | People | Loss | 23 | 7 | Application required its own server, delay for installation | 0 | Americas | Prod. Dev. | 2010 | March | 1325099
4972 | Scope | Change | Dependency | 6 | 5 | Excessive defects in Web Page translations | 0 | Americas | IT/Solution | 2015 | August | 511416
4973 | Resource | Money | Limitation | 13 | 8 | Understaffing causes overtime and leads to loss of staff | 2 | Eur/ME | IT/Solution | 2019 | August | 1046214
4974 | Scope | Defect | Hardware | 18 | 7 | Money for needed software was not in the budget; project was delayed to push expense into next quarter | 0 | Americas | IT/Solution | 2010 | July | 1689804
4975 | Resource | People | Loss | 14 | 3 | Project manager thought the solution was only one task, but there were four | 0 | Americas | Prod. Dev. | 2015 | January | 1125712
4976 | Scope | Change | Gap | 2 | 7 | Lack of consensus on the spec resulted in modifications during the second phase of the project | 3 | Africa | IT/Solution | 2012 | January | 170160
4977 | Schedule | Estimates | Learning | 12 | 7 | Critical application delivery late | 2 | Eur/ME | IT/Solution | 2019 | January | 1060872
4978 | Schedule | Delay | Information | 11 | 3 | Prior work was completed late | 3 | Africa | Prod. Dev. | 2007 | April | 919985
4979 | Schedule | Delay | Parts | 19 | 5 | Insufficient resources and little change control | 0 | Americas | Prod. Dev. | 2015 | March | 1505541
4980 | Scope | Change | Creep | 6 | 3 | Unique and specific requirements were poorly understood | 0 | Americas | IT/Solution | 2010 | February | 304122
4981 | Schedule | Dependency | Project | 5 | 9 | Subcontracted work failed to meet client's criteria | 2 | Eur/ME | Prod. Dev. | 2002 | August | 447655
4982 | Resource | People | Loss | 25 | 8 | Planning the terms of the agreement and negotiating the contracts took time, making the project begin late | 3 | Africa | Prod. Dev. | 2013 | January | 1468050
4983 | Scope | Change | Gap | 23 | 6 | Old application to be modified for Y2K had no documentation, and finding original code took weeks. | 2 | Eur/ME | Prod. Dev. | 2012 | September | 1778383
4984 | Scope | Change | Gap | 17 | 4 | Peak season begun earlier than expected and Higher Freight Volume than usual | 2 | Eur/ME | IT/Solution | 2009 | March | 945404
4985 | Resource | Outsourcing | Delayed start | 5 | 6 | Key requirements were uncovered late | 0 | Americas | IT/Solution | 2010 | July | 438545
4986 | Scope | Defect | Software | 25 | 6 | Initial code release was a major failure | 0 | Americas | IT/Solution | 2010 | July | 2085275
4987 | Resource | People | Temp loss | 1 | 2 | High turnover led to training and low productivity throughout project. | 3 | Africa | IT/Solution | 2010 | March | 50171
4988 | Schedule | Delay | Decision | 18 | 6 | Initial ubjects for tests did not meet project requirements | 0 | Americas | Prod. Dev. | 2010 | June | 1329948
4989 | Schedule | Dependency | Project | 16 | 7 | Subcontractor goes out of business and it took 2 months to replace them. | 0 | Americas | Prod. Dev. | 2010 | May | 1544976
4990 | Schedule | Estimates | Deadline | 1 | 9 | Key contributor on jury duty | 0 | Americas | IT/Solution | 2010 | March | 61338
4991 | Resource | People | Loss | 26 | 2 | To expand business, unrealistic commitments were made to win the project | 3 | Africa | Prod. Dev. | 2004 | May | 2504268
4992 | Resource | People | Queuing | 2 | 8 | Completion criteria were not documented well | 3 | Africa | IT/Solution | 2015 | June | 155844
4993 | Resource | People | Loss | 22 | 1 | Complex system designed in pieces, and integration fails. Redesign is required. | 2 | Eur/ME | Prod. Dev. | 2001 | October | 1286648
4994 | Schedule | Delay | Parts | 24 | 7 | Freelancer hired was a nutjob, and lacked the correct skills | 0 | Americas | IT/Solution | 2015 | September | 1952040
4995 | Scope | Change | Creep | 8 | 2 | Resources were not available at the time the project started | 0 | Americas | IT/Solution | 2015 | May | 758136
4996 | Scope | Change | Dependency | 3 | 5 | Unexpected shutdown at year end delays work and rescheduling it is difficult. | 2 | Eur/ME | IT/Solution | 2013 | July | 254283
4997 | Schedule | Estimates | Judgment | 12 | 2 | Infrasturcture changes made mid-project | 0 | Americas | IT/Solution | 2009 | April | 968424
4998 | Scope | Change | Creep | 18 | 1 | Plans for project for new customer based on similar work for existing customer. Relationships, infrastructure, jargon and other differences took 50% more effort. | 0 | Americas | Prod. Dev. | 2019 | October | 1123974
4999 | Scope | Change | Creep | 5 | 2 | One patch was almost completely tested when it was decided to fix another bug | 2 | Eur/ME | Prod. Dev. | 2005 | October | 478375